## personalist
Name | Position | labor$/day
Alexander H | Manager/senior Engineer | 671 | position | labor $/day
Amanda S | Remote senior | 671 | Technician I | 295
Andy R | Engineer/supervisor | 536 | Technician II | 456
Angie G | Technician II | 456 | Welder | 469
Ashton F | Technician II | 456 | Engineer/supervisor | 536
Brian K | Manager/senior Engineer | 671 | Manager/senior Engineer | 671
Brian M | Engineer/supervisor | 536 | Remote mid engineer | 536
Brian V | Technician II | 456 | Remote senior | 671
Carol W | Remote senior | 671
Chris H | Engineer/supervisor | 536
Christopher M | Technician II | 456
Cole M | Technician II | 456
Eric C | Remote mid engineer | 536
Gordon D | Remote senior | 671
Greg S | Technician II | 456
Howard H | Technician II | 456
Iain C | Remote senior | 671
Jason C | Remote senior | 671
Joe F | Technician II | 456
Jonathan R | Engineer/supervisor | 536
Levi W | Welder | 469
Luis Z | Remote mid engineer | 536
Luke G | Welder | 469
Michael H | Technician II | 456
Mike C | Technician II | 456
Robert W | Technician II | 456
Roy Z | Remote mid engineer | 536
Ryan O | Welder | 469
Sepehr G | Remote senior | 671
Shane M | Technician II | 456
Vace V | Technician II | 456
Vu T | Engineer/supervisor | 536
Wyatt S | Welder | 469

## weekly hours
position |  |  | Remote senior | Remote senior | Remote senior | Remote senior | Remote mid engineer | Remote mid engineer | Remote mid engineer | Remote senior | Manager/senior Engineer | Engineer/supervisor | Engineer/supervisor | Engineer/supervisor | Engineer/supervisor | Technician II | Welder | Technician II | Technician II | Welder | Welder | Welder
Salary $/day |  |  | 671 | 671 | 671 | 671 | 536 | 536 | 536 | 671 | 671 | 536 | 536 | 536 | 536 | 456 | 469 | 456 | 456 | 469 | 469 | 469
Week # | Start Date | End Date | Carol W | Iain C | Gordon D | Jason C | Eric C | Luis Z | Roy Z | Amanda S | Brian K | Jonathan R | Brian M | Brian M | Andy R | Mike C | Luke G | Robert W | Angie G | Wyatt S | Ryan O | Levi W
1 | 2025-04-07 | 2025-04-13 |  |  |  | 60 | 80 |  | 40
2 | 2025-04-14 | 2025-04-20 |  |  |  |  | 20
3 | 2025-04-21 | 2025-04-27
4 | 2025-04-28 | 2025-05-04
5 | 2025-05-05 | 2025-05-11
6 | 2025-05-12 | 2025-05-18
7 | 2025-05-19 | 2025-05-25 |  |  |  | 10 | 30 |  | 8
8 | 2025-05-26 | 2025-06-01
9 | 2025-06-02 | 2025-06-08
10 | 2025-06-09 | 2025-06-15
11 | 2025-06-16 | 2025-06-22
12 | 2025-06-23 | 2025-06-29
13 | 2025-06-30 | 2025-07-06 | [12 empty] | 32
14 | 2025-07-07 | 2025-07-13 | [12 empty] | 40 | 8 | 8
15 | 2025-07-14 | 2025-07-20 |  |  |  |  | 16 | [7 empty] | 40 | 40 | 40
16 | 2025-07-21 | 2025-07-27 | [9 empty] | 16 |  |  | 40 | 40 | 40
17 | 2025-07-28 | 2025-08-03 | [9 empty] | 32 |  |  | 40 | 40 | 40
18 | 2025-08-04 | 2025-08-10 | [12 empty] | 40 | 40 | 40 | 40
19 | 2025-08-11 | 2025-08-17 | [9 empty] | 40 |  |  | 40 | 40 | 40 | 40
20 | 2025-08-18 | 2025-08-24 | [9 empty] | 40 |  |  | 40 | 40 | 40 | 40
21 | 2025-08-25 | 2025-08-31 |  |  |  | 8 | 16 | 8 |  |  |  | 24 |  |  |  | 40 | 32 | 40
22 | 2025-09-01 | 2025-09-07 |  |  |  | 16 | 16 | 8 | [9 empty] | 40
23 | 2025-09-08 | 2025-09-14 |  |  |  | 8 | 30 | 6 |  |  |  | 40 |  |  | 32 |  |  | 40
24 | 2025-09-15 | 2025-09-21
25 | 2025-09-22 | 2025-09-28
26 | 2025-09-29 | 2025-10-05
27 | 2025-10-06 | 2025-10-12
28 | 2025-10-13 | 2025-10-19
29 | 2025-10-20 | 2025-10-26
30 | 2025-10-27 | 2025-11-02
31 | 2025-11-03 | 2025-11-09
32 | 2025-11-10 | 2025-11-16
33 | 2025-11-17 | 2025-11-23
34 | 2025-11-24 | 2025-11-30
35 | 2025-12-01 | 2025-12-07
36 | 2025-12-08 | 2025-12-14
37 | 2025-12-15 | 2025-12-21
38 | 2025-12-22 | 2025-12-28
39 | 2025-12-29 | 2026-01-04
40 | 2026-01-05 | 2026-01-11
41 | 2026-01-12 | 2026-01-18
42 | 2026-01-19 | 2026-01-25
43 | 2026-01-26 | 2026-02-01
44 | 2026-02-02 | 2026-02-08
45 | 2026-02-09 | 2026-02-15
46 | 2026-02-16 | 2026-02-22
47 | 2026-02-23 | 2026-03-01
48 | 2026-03-02 | 2026-03-08
49 | 2026-03-09 | 2026-03-15
50 | 2026-03-16 | 2026-03-22
51 | 2026-03-23 | 2026-03-29
52 | 2026-03-30 | 2026-04-05
53 | 2026-04-06 | 2026-04-12
54 | 2026-04-13 | 2026-04-19
55 | 2026-04-20 | 2026-04-26
56 | 2026-04-27 | 2026-05-03
57 | 2026-05-04 | 2026-05-10
58 | 2026-05-11 | 2026-05-17
59 | 2026-05-18 | 2026-05-24
60 | 2026-05-25 | 2026-05-31
61 | 2026-06-01 | 2026-06-07
62 | 2026-06-08 | 2026-06-14
63 | 2026-06-15 | 2026-06-21
64 | 2026-06-22 | 2026-06-28
65 | 2026-06-29 | 2026-07-05
66 | 2026-07-06 | 2026-07-12
67 | 2026-07-13 | 2026-07-19
68 | 2026-07-20 | 2026-07-26
Formulas:
End Date = [Start Date]+6
Start Date = [Start Date, row above]+7

## labor Cost (hidden)
position |  |  | Remote senior | Remote senior | Remote senior | Remote senior | Remote mid engineer | Remote mid engineer | Remote mid engineer | Remote senior | Manager/senior Engineer | Engineer/supervisor | Engineer/supervisor | Engineer/supervisor | Engineer/supervisor | Technician II | Welder | Technician II | Welder | Welder | Welder | Technician II
Salary $/day |  |  | 671 | 671 | 671 | 671 | 536 | 536 | 536 | 671 | 671 | 536 | 536 | 536 | 536 | 456 | 469 | 456 | 469 | 469 | 469 | 456
Week # | Start Date | End Date | Carol W | Iain C | Gordon D | Jason C | Eric C | Luis Z | Roy Z | Amanda S | Brian K | Jonathan R | Brian M | Brian M | Andy R | Mike C | Luke G | Angie G | Wyatt S | Ryan O | Levi W | Robert W
1 | 2025-04-07 | 2025-04-13 |  |  |  | 5032.5 | 5360 |  | 2680
2 | 2025-04-14 | 2025-04-20 |  |  |  |  | 1340
3 | 2025-04-21 | 2025-04-27
4 | 2025-04-28 | 2025-05-04
5 | 2025-05-05 | 2025-05-11
6 | 2025-05-12 | 2025-05-18
7 | 2025-05-19 | 2025-05-25 |  |  |  | 838.75 | 2010 |  | 536
8 | 2025-05-26 | 2025-06-01
9 | 2025-06-02 | 2025-06-08
10 | 2025-06-09 | 2025-06-15
11 | 2025-06-16 | 2025-06-22
12 | 2025-06-23 | 2025-06-29
13 | 2025-06-30 | 2025-07-06 | [12 empty] | 2144
14 | 2025-07-07 | 2025-07-13 | [12 empty] | 2680 | 456 | 469
15 | 2025-07-14 | 2025-07-20 |  |  |  |  | 1072 | [7 empty] | 2680 | 2280 | 2345
16 | 2025-07-21 | 2025-07-27 | [9 empty] | 1072 |  |  | 2680 | 2280 | 2345
17 | 2025-07-28 | 2025-08-03 | [9 empty] | 2144 |  |  | 2680 | 2280 | 2345
18 | 2025-08-04 | 2025-08-10 | [12 empty] | 2680 | 2280 | 2345 |  |  |  |  | 2280
19 | 2025-08-11 | 2025-08-17 | [9 empty] | 2680 |  |  | 2680 | 2280 | 2345 |  |  |  |  | 2280
20 | 2025-08-18 | 2025-08-24 | [9 empty] | 2680 |  |  | 2680 | 2280 | 2345 |  |  |  |  | 2280
21 | 2025-08-25 | 2025-08-31 |  |  |  | 671 | 1072 | 536 |  |  |  | 1608 |  |  |  | 2280 | 1876 |  |  |  |  | 2280
22 | 2025-09-01 | 2025-09-07 |  |  |  | 1342 | 1072 | 536 | [13 empty] | 2280
23 | 2025-09-08 | 2025-09-14 |  |  |  | 671 | 2010 | 402 |  |  |  | 2680 |  |  | 2144 | [6 empty] | 2280
24 | 2025-09-15 | 2025-09-21
25 | 2025-09-22 | 2025-09-28
26 | 2025-09-29 | 2025-10-05
27 | 2025-10-06 | 2025-10-12
28 | 2025-10-13 | 2025-10-19
29 | 2025-10-20 | 2025-10-26
30 | 2025-10-27 | 2025-11-02
31 | 2025-11-03 | 2025-11-09
32 | 2025-11-10 | 2025-11-16
33 | 2025-11-17 | 2025-11-23
34 | 2025-11-24 | 2025-11-30
35 | 2025-12-01 | 2025-12-07
36 | 2025-12-08 | 2025-12-14
37 | 2025-12-15 | 2025-12-21
38 | 2025-12-22 | 2025-12-28
39 | 2025-12-29 | 2026-01-04
40 | 2026-01-05 | 2026-01-11
41 | 2026-01-12 | 2026-01-18
42 | 2026-01-19 | 2026-01-25
43 | 2026-01-26 | 2026-02-01
44 | 2026-02-02 | 2026-02-08
45 | 2026-02-09 | 2026-02-15
46 | 2026-02-16 | 2026-02-22
47 | 2026-02-23 | 2026-03-01
48 | 2026-03-02 | 2026-03-08
49 | 2026-03-09 | 2026-03-15
50 | 2026-03-16 | 2026-03-22
51 | 2026-03-23 | 2026-03-29
52 | 2026-03-30 | 2026-04-05
53 | 2026-04-06 | 2026-04-12
54 | 2026-04-13 | 2026-04-19
55 | 2026-04-20 | 2026-04-26
56 | 2026-04-27 | 2026-05-03
57 | 2026-05-04 | 2026-05-10
58 | 2026-05-11 | 2026-05-17
59 | 2026-05-18 | 2026-05-24
60 | 2026-05-25 | 2026-05-31
61 | 2026-06-01 | 2026-06-07
62 | 2026-06-08 | 2026-06-14
63 | 2026-06-15 | 2026-06-21
64 | 2026-06-22 | 2026-06-28
65 | 2026-06-29 | 2026-07-05
66 | 2026-07-06 | 2026-07-12
67 | 2026-07-13 | 2026-07-19
68 | 2026-07-20 | 2026-07-26