## Cost Tracking
Project Cost Analysis - Cost Tracking
Date | Planned Sum | Planned Material-Equipment | Planned Direct Cost Sum | Planned Work Sum | Actual Sum | Actual Material-Equipment | Actual Direct Cost Sum | Actual Work Sum
2025-04-01 | 1273.3773 | 0 | 0 | 1273.3773 | 0 | 0 | 0 | 0
2025-04-02 | 2546.7545 | 0 | 0 | 2546.7545 | 0 | 0 | 0 | 0
2025-04-03 | 3820.1318 | 0 | 0 | 3820.1318 | 0 | 0 | 0 | 0
2025-04-04 | 5093.5091 | 0 | 0 | 5093.5091 | 0 | 0 | 0 | 0
2025-04-05 | 6366.8864 | 0 | 0 | 6366.8864 | 0 | 0 | 0 | 0
2025-04-06 | 7640.2636 | 0 | 0 | 7640.2636 | 0 | 0 | 0 | 0
2025-04-07 | 8913.6409 | 0 | 0 | 8913.6409 | 0 | 0 | 0 | 0
2025-04-08 | 10187.0182 | 0 | 0 | 10187.0182 | 0 | 0 | 0 | 0
2025-04-09 | 11460.3955 | 0 | 0 | 11460.3955 | 0 | 0 | 0 | 0
2025-04-10 | 12733.7727 | 0 | 0 | 12733.7727 | 0 | 0 | 0 | 0
2025-04-11 | 14007.15 | 0 | 0 | 14007.15 | 0 | 0 | 0 | 0
2025-04-12 | 15280.5273 | 0 | 0 | 15280.5273 | 0 | 0 | 0 | 0
2025-04-13 | 16553.9045 | 0 | 0 | 16553.9045 | 0 | 0 | 0 | 0
2025-04-14 | 17827.2818 | 0 | 0 | 17827.2818 | 0 | 0 | 0 | 0
2025-04-15 | 19100.6591 | 0 | 0 | 19100.6591 | 0 | 0 | 0 | 0
2025-04-16 | 20374.0364 | 0 | 0 | 20374.0364 | 33.72 | 0 | 33.72 | 0
2025-04-17 | 21647.4136 | 0 | 0 | 21647.4136 | 33.72 | 0 | 33.72 | 0
2025-04-18 | 22920.7909 | 0 | 0 | 22920.7909 | 33.72 | 0 | 33.72 | 0
2025-04-19 | 24194.1682 | 0 | 0 | 24194.1682 | 33.72 | 0 | 33.72 | 0
2025-04-20 | 25467.5455 | 0 | 0 | 25467.5455 | 33.72 | 0 | 33.72 | 0
2025-04-21 | 26740.9227 | 0 | 0 | 26740.9227 | 33.72 | 0 | 33.72 | 0
2025-04-22 | 28014.3 | 0 | 0 | 28014.3 | 33.72 | 0 | 33.72 | 0
2025-04-23 | 29287.6773 | 0 | 0 | 29287.6773 | 33.72 | 0 | 33.72 | 0
2025-04-24 | 30561.0545 | 0 | 0 | 30561.0545 | 33.72 | 0 | 33.72 | 0
2025-04-25 | 31834.4318 | 0 | 0 | 31834.4318 | 33.72 | 0 | 33.72 | 0
2025-04-26 | 33107.8091 | 0 | 0 | 33107.8091 | 33.72 | 0 | 33.72 | 0
2025-04-27 | 34381.1864 | 0 | 0 | 34381.1864 | 33.72 | 0 | 33.72 | 0
2025-04-28 | 35654.5636 | 0 | 0 | 35654.5636 | 33.72 | 0 | 33.72 | 0
2025-04-29 | 36927.9409 | 0 | 0 | 36927.9409 | 33.72 | 0 | 33.72 | 0
2025-04-30 | 38201.3182 | 0 | 0 | 38201.3182 | 33.72 | 0 | 33.72 | 0
2025-05-01 | 39474.6955 | 0 | 0 | 39474.6955 | 33.72 | 0 | 33.72 | 0
2025-05-02 | 40748.0727 | 0 | 0 | 40748.0727 | 33.72 | 0 | 33.72 | 0
2025-05-03 | 42021.45 | 0 | 0 | 42021.45 | 33.72 | 0 | 33.72 | 0
2025-05-04 | 43294.8273 | 0 | 0 | 43294.8273 | 33.72 | 0 | 33.72 | 0
2025-05-05 | 44568.2045 | 0 | 0 | 44568.2045 | 33.72 | 0 | 33.72 | 0
2025-05-06 | 45841.5818 | 0 | 0 | 45841.5818 | 33.72 | 0 | 33.72 | 0
2025-05-07 | 47114.9591 | 0 | 0 | 47114.9591 | 33.72 | 0 | 33.72 | 0
2025-05-08 | 48388.3364 | 0 | 0 | 48388.3364 | 33.72 | 0 | 33.72 | 0
2025-05-09 | 49661.7136 | 0 | 0 | 49661.7136 | 33.72 | 0 | 33.72 | 0
2025-05-10 | 50935.0909 | 0 | 0 | 50935.0909 | 33.72 | 0 | 33.72 | 0
2025-05-11 | 52208.4682 | 0 | 0 | 52208.4682 | 33.72 | 0 | 33.72 | 0
2025-05-12 | 53481.8455 | 0 | 0 | 53481.8455 | 33.72 | 0 | 33.72 | 0
2025-05-13 | 54755.2227 | 0 | 0 | 54755.2227 | 33.72 | 0 | 33.72 | 0
2025-05-14 | 56028.6 | 0 | 0 | 56028.6 | 33.72 | 0 | 33.72 | 0
2025-05-15 | 57301.9773 | 0 | 0 | 57301.9773 | 33.72 | 0 | 33.72 | 0
2025-05-16 | 58575.3545 | 0 | 0 | 58575.3545 | 33.72 | 0 | 33.72 | 0
2025-05-17 | 59848.7318 | 0 | 0 | 59848.7318 | 33.72 | 0 | 33.72 | 0
2025-05-18 | 61122.1091 | 0 | 0 | 61122.1091 | 33.72 | 0 | 33.72 | 0
2025-05-19 | 62395.4864 | 0 | 0 | 62395.4864 | 33.72 | 0 | 33.72 | 0
2025-05-20 | 63668.8636 | 0 | 0 | 63668.8636 | 33.72 | 0 | 33.72 | 0
2025-05-21 | 64942.2409 | 0 | 0 | 64942.2409 | 33.72 | 0 | 33.72 | 0
2025-05-22 | 66215.6182 | 0 | 0 | 66215.6182 | 33.72 | 0 | 33.72 | 0
2025-05-23 | 67488.9955 | 0 | 0 | 67488.9955 | 33.72 | 0 | 33.72 | 0
2025-05-24 | 68762.3727 | 0 | 0 | 68762.3727 | 33.72 | 0 | 33.72 | 0
2025-05-25 | 70035.75 | 0 | 0 | 70035.75 | 33.72 | 0 | 33.72 | 0
2025-05-26 | 71309.1273 | 0 | 0 | 71309.1273 | 33.72 | 0 | 33.72 | 0
2025-05-27 | 72582.5045 | 0 | 0 | 72582.5045 | 33.72 | 0 | 33.72 | 0
2025-05-28 | 73855.8818 | 0 | 0 | 73855.8818 | 33.72 | 0 | 33.72 | 0
2025-05-29 | 75129.2591 | 0 | 0 | 75129.2591 | 33.72 | 0 | 33.72 | 0
2025-05-30 | 76402.6364 | 0 | 0 | 76402.6364 | 33.72 | 0 | 33.72 | 0
2025-05-31 | 77676.0136 | 0 | 0 | 77676.0136 | 33.72 | 0 | 33.72 | 0
2025-06-01 | 83269.3981 | 1441.4843 | 2747.7518 | 79080.162 | 33.72 | 0 | 33.72 | 0
2025-06-02 | 88862.7826 | 2882.9687 | 5495.5036 | 80484.3104 | 33.72 | 0 | 33.72 | 0
2025-06-03 | 94456.1671 | 4324.453 | 8243.2554 | 81888.4587 | 33.72 | 0 | 33.72 | 0
2025-06-04 | 100049.5516 | 5765.9373 | 10991.0072 | 83292.6071 | 53.64 | 0 | 53.64 | 0
2025-06-05 | 105642.9361 | 7207.4217 | 13738.759 | 84696.7554 | 25692.32 | 0 | 25692.32 | 0
2025-06-06 | 109962.9434 | 8648.906 | 16486.5108 | 84827.5265 | 25692.32 | 0 | 25692.32 | 0
2025-06-07 | 114282.9506 | 10090.3904 | 19234.2627 | 84958.2976 | 25692.32 | 0 | 25692.32 | 0
2025-06-08 | 118602.9578 | 11531.8747 | 21982.0145 | 85089.0687 | 25692.32 | 0 | 25692.32 | 0
2025-06-09 | 122922.9651 | 12973.359 | 24729.7663 | 85219.8398 | 25692.32 | 0 | 25692.32 | 0
2025-06-10 | 127242.9723 | 14414.8434 | 27477.5181 | 85350.6108 | 25692.32 | 0 | 25692.32 | 0
2025-06-11 | 131562.9795 | 15856.3277 | 30225.2699 | 85481.3819 | 25692.32 | 0 | 25692.32 | 0
2025-06-12 | 135882.9867 | 17297.812 | 32973.0217 | 85612.153 | 25692.32 | 0 | 25692.32 | 0
2025-06-13 | 140202.994 | 18739.2964 | 35720.7735 | 85742.9241 | 25692.32 | 0 | 25692.32 | 0
2025-06-14 | 144523.0012 | 20180.7807 | 38468.5253 | 85873.6952 | 25692.32 | 0 | 25692.32 | 0
2025-06-15 | 148843.0084 | 21622.2651 | 41216.2771 | 86004.4663 | 25692.32 | 0 | 25692.32 | 0
2025-06-16 | 153163.0157 | 23063.7494 | 43964.0289 | 86135.2373 | 25692.32 | 0 | 25692.32 | 0
2025-06-17 | 157483.0229 | 24505.2337 | 46711.7807 | 86266.0084 | 25692.32 | 0 | 25692.32 | 0
2025-06-18 | 161803.0301 | 25946.7181 | 49459.5325 | 86396.7795 | 25692.32 | 0 | 25692.32 | 0
2025-06-19 | 166123.0373 | 27388.2024 | 52207.2843 | 86527.5506 | 25692.32 | 0 | 25692.32 | 0
2025-06-20 | 170443.0446 | 28829.6867 | 54955.0361 | 86658.3217 | 26274.82 | 0 | 26274.82 | 0
2025-06-21 | 174763.0518 | 30271.1711 | 57702.788 | 86789.0928 | 26274.82 | 0 | 26274.82 | 0
2025-06-22 | 179083.059 | 31712.6554 | 60450.5398 | 86919.8639 | 26274.82 | 0 | 26274.82 | 0
2025-06-23 | 183403.0663 | 33154.1398 | 63198.2916 | 87050.6349 | 26274.82 | 0 | 26274.82 | 0
2025-06-24 | 187723.0735 | 34595.6241 | 65946.0434 | 87181.406 | 27201.68 | 0 | 27201.68 | 0
2025-06-25 | 192043.0807 | 36037.1084 | 68693.7952 | 87312.1771 | 27590.08 | 0 | 27590.08 | 0
2025-06-26 | 196363.088 | 37478.5928 | 71441.547 | 87442.9482 | 27590.08 | 0 | 27590.08 | 0
2025-06-27 | 200683.0952 | 38920.0771 | 74189.2988 | 87573.7193 | 27590.08 | 0 | 27590.08 | 0
2025-06-28 | 205003.1024 | 40361.5614 | 76937.0506 | 87704.4904 | 27702.35 | 0 | 27702.35 | 0
2025-06-29 | 209323.1096 | 41803.0458 | 79684.8024 | 87835.2614 | 27851.1 | 0 | 27851.1 | 0
2025-06-30 | 213643.1169 | 43244.5301 | 82432.5542 | 87966.0325 | 27851.1 | 0 | 27851.1 | 0
2025-07-01 | 217963.1241 | 44686.0145 | 85180.306 | 88096.8036 | 66561.92 | 0 | 66561.92 | 0
2025-07-02 | 222283.1313 | 46127.4988 | 87928.0578 | 88227.5747 | 66671.07 | 109.15 | 66671.07 | 0
2025-07-03 | 226603.1386 | 47568.9831 | 90675.8096 | 88358.3458 | 66753.65 | 109.15 | 66753.65 | 0
2025-07-04 | 230923.1458 | 49010.4675 | 93423.5614 | 88489.1169 | 67490.27 | 559.15 | 67490.27 | 0
2025-07-05 | 235243.153 | 50451.9518 | 96171.3133 | 88619.888 | 67540.52 | 559.15 | 67540.52 | 0
2025-07-06 | 239563.1602 | 51893.4361 | 98919.0651 | 88750.659 | 67540.52 | 559.15 | 67540.52 | 0
2025-07-07 | 243883.1675 | 53334.9205 | 101666.8169 | 88881.4301 | 67721.62 | 559.15 | 67721.62 | 0
2025-07-08 | 248203.1747 | 54776.4048 | 104414.5687 | 89012.2012 | 68848.47 | 559.15 | 68848.47 | 0
2025-07-09 | 252523.1819 | 56217.8892 | 107162.3205 | 89142.9723 | 68941.17 | 651.85 | 68941.17 | 0
2025-07-10 | 256843.1892 | 57659.3735 | 109910.0723 | 89273.7434 | 68999.06 | 651.85 | 68999.06 | 0
2025-07-11 | 261163.1964 | 59100.8578 | 112657.8241 | 89404.5145 | 70888.29 | 651.85 | 70888.29 | 0
2025-07-12 | 265483.2036 | 60542.3422 | 115405.5759 | 89535.2855 | 71322.41 | 651.85 | 71322.41 | 0
2025-07-13 | 269803.2108 | 61983.8265 | 118153.3277 | 89666.0566 | 71677.06 | 818.03 | 71677.06 | 0
2025-07-14 | 274123.2181 | 63425.3108 | 120901.0795 | 89796.8277 | 77127.38 | 818.03 | 77127.38 | 0
2025-07-15 | 288693.5873 | 64866.7952 | 132875.4304 | 90951.3617 | 79070.09 | 818.03 | 79070.09 | 0
2025-07-16 | 303263.9564 | 66308.2795 | 144849.7813 | 92105.8956 | 86537.64 | 818.03 | 86537.64 | 0
2025-07-17 | 317834.3256 | 67749.7639 | 156824.1322 | 93260.4295 | 87190.87 | 818.03 | 87190.87 | 0
2025-07-18 | 332404.6948 | 69191.2482 | 168798.4831 | 94414.9635 | 95773.69 | 818.03 | 95773.69 | 0
2025-07-19 | 346975.064 | 70632.7325 | 180772.834 | 95569.4974 | 96608.68 | 818.03 | 96608.68 | 0
2025-07-20 | 361545.4332 | 72074.2169 | 192747.185 | 96724.0314 | 96608.68 | 818.03 | 96608.68 | 0
2025-07-21 | 376115.8024 | 73515.7012 | 204721.5359 | 97878.5653 | 96648.68 | 818.03 | 96648.68 | 0
2025-07-22 | 390686.1715 | 74957.1855 | 216695.8868 | 99033.0992 | 112102.86 | 818.03 | 112102.86 | 0
2025-07-23 | 405256.5407 | 76398.6699 | 228670.2377 | 100187.6332 | 114795.78 | 818.03 | 114795.78 | 0
2025-07-24 | 419826.9099 | 77840.1542 | 240644.5886 | 101342.1671 | 115170.16 | 818.03 | 115170.16 | 0
2025-07-25 | 434397.2791 | 79281.6386 | 252618.9395 | 102496.7011 | 116684.93 | 818.03 | 116684.93 | 0
2025-07-26 | 448967.6483 | 80723.1229 | 264593.2904 | 103651.235 | 116715.68 | 818.03 | 116715.68 | 0
2025-07-27 | 463538.0175 | 82164.6072 | 276567.6413 | 104805.769 | 116808.12 | 818.03 | 116808.12 | 0
2025-07-28 | 478108.3867 | 83606.0916 | 288541.9922 | 105960.3029 | 116808.12 | 818.03 | 116808.12 | 0
2025-07-29 | 492678.7558 | 85047.5759 | 300516.3431 | 107114.8368 | 116868.12 | 818.03 | 116868.12 | 0
2025-07-30 | 507249.125 | 86489.0602 | 312490.694 | 108269.3708 | 123960.36 | 818.03 | 123960.36 | 0
2025-07-31 | 521819.4942 | 87930.5446 | 324465.0449 | 109423.9047 | 149901.18 | 818.03 | 149901.18 | 0
2025-08-01 | 536389.8634 | 89372.0289 | 336439.3958 | 110578.4387 | 151328.68 | 818.03 | 151328.68 | 0
2025-08-02 | 550960.2326 | 90813.5133 | 348413.7467 | 111732.9726 | 151328.68 | 818.03 | 151328.68 | 0
2025-08-03 | 565530.6018 | 92254.9976 | 360388.0976 | 112887.5065 | 151328.68 | 818.03 | 151328.68 | 0
2025-08-04 | 580100.9709 | 93696.4819 | 372362.4485 | 114042.0405 | 151411.03 | 818.03 | 151411.03 | 0
2025-08-05 | 594671.3401 | 95137.9663 | 384336.7994 | 115196.5744 | 154515.26 | 818.03 | 154515.26 | 0
2025-08-06 | 609241.7093 | 96579.4506 | 396311.1503 | 116351.1084 | 159422.7 | 818.03 | 159422.7 | 0
2025-08-07 | 623812.0785 | 98020.9349 | 408285.5013 | 117505.6423 | 159422.7 | 818.03 | 159422.7 | 0
2025-08-08 | 638382.4477 | 99462.4193 | 420259.8522 | 118660.1762 | 161172.7 | 818.03 | 161172.7 | 0
2025-08-09 | 652952.8169 | 100903.9036 | 432234.2031 | 119814.7102 | 161172.7 | 818.03 | 161172.7 | 0
2025-08-10 | 667523.186 | 102345.388 | 444208.554 | 120969.2441 | 161172.7 | 818.03 | 161172.7 | 0
2025-08-11 | 682093.5552 | 103786.8723 | 456182.9049 | 122123.7781 | 161172.7 | 818.03 | 161172.7 | 0
2025-08-12 | 696663.9244 | 105228.3566 | 468157.2558 | 123278.312 | 162880.32 | 818.03 | 162880.32 | 0
2025-08-13 | 711234.2936 | 106669.841 | 480131.6067 | 124432.846 | 162880.32 | 818.03 | 162880.32 | 0
2025-08-14 | 725804.6628 | 108111.3253 | 492105.9576 | 125587.3799 | 164292.27 | 818.03 | 164292.27 | 0
2025-08-15 | 740375.032 | 109552.8096 | 504080.3085 | 126741.9138 | 167221.18 | 818.03 | 167221.18 | 0
2025-08-16 | 754945.4012 | 110994.294 | 516054.6594 | 127896.4478 | 167221.18 | 818.03 | 167221.18 | 0
2025-08-17 | 769515.7703 | 112435.7783 | 528029.0103 | 129050.9817 | 167221.18 | 818.03 | 167221.18 | 0
2025-08-18 | 784086.1395 | 113877.2627 | 540003.3612 | 130205.5157 | 167221.18 | 818.03 | 167221.18 | 0
2025-08-19 | 798656.5087 | 115318.747 | 551977.7121 | 131360.0496 | 169780.24 | 818.03 | 169780.24 | 0
2025-08-20 | 813226.8779 | 116760.2313 | 563952.063 | 132514.5835 | 173586.53 | 818.03 | 173586.53 | 0
2025-08-21 | 827797.2471 | 118201.7157 | 575926.4139 | 133669.1175 | 173586.53 | 818.03 | 173586.53 | 0
2025-08-22 | 842367.6163 | 119643.2 | 587900.7648 | 134823.6514 | 187369.72 | 818.03 | 187369.72 | 0
2025-08-23 | 852617.9782 | 119643.2 | 597127.3639 | 135847.4143 | 187369.72 | 818.03 | 187369.72 | 0
2025-08-24 | 862868.3402 | 119643.2 | 606353.963 | 136871.1771 | 187369.72 | 818.03 | 187369.72 | 0
2025-08-25 | 873118.7021 | 119643.2 | 615580.5621 | 137894.94 | 241312.22 | 818.03 | 241312.22 | 0
2025-08-26 | 883369.0641 | 119643.2 | 624807.1612 | 138918.7029 | 246671.06 | 818.03 | 246671.06 | 0
2025-08-27 | 893619.426 | 119643.2 | 634033.7603 | 139942.4657 | 249942.89 | 818.03 | 249942.89 | 0
2025-08-28 | 903869.788 | 119643.2 | 643260.3594 | 140966.2286 | 249942.89 | 818.03 | 249942.89 | 0
2025-08-29 | 914120.1499 | 119643.2 | 652486.9585 | 141989.9914 | 250292.89 | 818.03 | 250292.89 | 0
2025-08-30 | 924370.5119 | 119643.2 | 661713.5576 | 143013.7543 | 250292.89 | 818.03 | 250292.89 | 0
2025-08-31 | 934620.8739 | 119643.2 | 670940.1567 | 144037.5171 | 260467.62 | 818.03 | 260467.62 | 0
2025-09-01 | 944871.2358 | 119643.2 | 680166.7558 | 145061.28 | 0 | 0 | 0 | 0
2025-09-02 | 948899.5625 | 119643.2 | 682368.5325 | 146887.83 | 0 | 0 | 0 | 0
2025-09-03 | 952927.8892 | 119643.2 | 684570.3092 | 148714.38 | 0 | 0 | 0 | 0
2025-09-04 | 956956.216 | 119643.2 | 686772.086 | 150540.93 | 0 | 0 | 0 | 0
2025-09-05 | 960984.5427 | 119643.2 | 688973.8627 | 152367.48 | 0 | 0 | 0 | 0
2025-09-06 | 965012.8694 | 119643.2 | 691175.6394 | 154194.03 | 0 | 0 | 0 | 0
2025-09-07 | 969041.1961 | 119643.2 | 693377.4161 | 156020.58 | 0 | 0 | 0 | 0
2025-09-08 | 973069.5228 | 119643.2 | 695579.1928 | 157847.13 | 0 | 0 | 0 | 0
2025-09-09 | 977097.8496 | 119643.2 | 697780.9696 | 159673.68 | 0 | 0 | 0 | 0
2025-09-10 | 981126.1763 | 119643.2 | 699982.7463 | 161500.23 | 0 | 0 | 0 | 0
2025-09-11 | 985154.503 | 119643.2 | 702184.523 | 163326.78 | 0 | 0 | 0 | 0
2025-09-12 | 989182.8297 | 119643.2 | 704386.2997 | 165153.33 | 0 | 0 | 0 | 0
2025-09-13 | 993211.1564 | 119643.2 | 706588.0764 | 166979.88 | 0 | 0 | 0 | 0
2025-09-14 | 997239.4831 | 119643.2 | 708789.8531 | 168806.43 | 0 | 0 | 0 | 0
2025-09-15 | 1001267.8099 | 119643.2 | 710991.6299 | 170632.98 | 0 | 0 | 0 | 0
2025-09-16 | 1005296.1366 | 119643.2 | 713193.4066 | 172459.53 | 0 | 0 | 0 | 0
2025-09-17 | 1009324.4633 | 119643.2 | 715395.1833 | 174286.08 | 0 | 0 | 0 | 0
2025-09-18 | 1013352.79 | 119643.2 | 717596.96 | 176112.63 | 0 | 0 | 0 | 0
2025-09-19 | 1017381.1167 | 119643.2 | 719798.7367 | 177939.18 | 0 | 0 | 0 | 0
2025-09-20 | 1021409.4434 | 119643.2 | 722000.5134 | 179765.73 | 0 | 0 | 0 | 0
2025-09-21 | 1025437.7702 | 119643.2 | 724202.2902 | 181592.28 | 0 | 0 | 0 | 0
2025-09-22 | 1029466.0969 | 119643.2 | 726404.0669 | 183418.83 | 0 | 0 | 0 | 0
2025-09-23 | 1033494.4236 | 119643.2 | 728605.8436 | 185245.38 | 0 | 0 | 0 | 0
2025-09-24 | 1037522.7503 | 119643.2 | 730807.6203 | 187071.93 | 0 | 0 | 0 | 0
2025-09-25 | 1041551.077 | 119643.2 | 733009.397 | 188898.48 | 0 | 0 | 0 | 0
2025-09-26 | 1045579.4037 | 119643.2 | 735211.1737 | 190725.03 | 0 | 0 | 0 | 0
2025-09-27 | 1049607.7305 | 119643.2 | 737412.9505 | 192551.58 | 0 | 0 | 0 | 0
2025-09-28 | 1053636.0572 | 119643.2 | 739614.7272 | 194378.13 | 0 | 0 | 0 | 0
2025-09-29 | 1057664.3839 | 119643.2 | 741816.5039 | 196204.68 | 0 | 0 | 0 | 0
2025-09-30 | 1061692.7106 | 119643.2 | 744018.2806 | 198031.23 | 0 | 0 | 0 | 0
2025-10-01 | 1065721.0373 | 119643.2 | 746220.0573 | 199857.78 | 0 | 0 | 0 | 0
2025-10-02 | 1069749.364 | 119643.2 | 748421.834 | 201684.33 | 0 | 0 | 0 | 0
2025-10-03 | 1073777.6908 | 119643.2 | 750623.6108 | 203510.88 | 0 | 0 | 0 | 0
2025-10-04 | 1077806.0175 | 119643.2 | 752825.3875 | 205337.43 | 0 | 0 | 0 | 0
2025-10-05 | 1081834.3442 | 119643.2 | 755027.1642 | 207163.98 | 0 | 0 | 0 | 0
2025-10-06 | 1085862.6709 | 119643.2 | 757228.9409 | 208990.53 | 0 | 0 | 0 | 0
2025-10-07 | 1089890.9976 | 119643.2 | 759430.7176 | 210817.08 | 0 | 0 | 0 | 0
2025-10-08 | 1093919.3243 | 119643.2 | 761632.4943 | 212643.63 | 0 | 0 | 0 | 0
2025-10-09 | 1097947.6511 | 119643.2 | 763834.2711 | 214470.18 | 0 | 0 | 0 | 0
2025-10-10 | 1101975.9778 | 119643.2 | 766036.0478 | 216296.73 | 0 | 0 | 0 | 0
2025-10-11 | 1106004.3045 | 119643.2 | 768237.8245 | 218123.28 | 0 | 0 | 0 | 0
2025-10-12 | 1110032.6312 | 119643.2 | 770439.6012 | 219949.83 | 0 | 0 | 0 | 0
2025-10-13 | 1114060.9579 | 119643.2 | 772641.3779 | 221776.38 | 0 | 0 | 0 | 0
2025-10-14 | 1118089.2846 | 119643.2 | 774843.1546 | 223602.93 | 0 | 0 | 0 | 0
2025-10-15 | 1122117.6114 | 119643.2 | 777044.9314 | 225429.48 | 0 | 0 | 0 | 0
2025-10-16 | 1126145.9381 | 119643.2 | 779246.7081 | 227256.03 | 0 | 0 | 0 | 0
2025-10-17 | 1130174.2648 | 119643.2 | 781448.4848 | 229082.58 | 0 | 0 | 0 | 0
2025-10-18 | 1134202.5915 | 119643.2 | 783650.2615 | 230909.13 | 0 | 0 | 0 | 0
2025-10-19 | 1138230.9182 | 119643.2 | 785852.0382 | 232735.68 | 0 | 0 | 0 | 0
2025-10-20 | 1142259.2449 | 119643.2 | 788053.8149 | 234562.23 | 0 | 0 | 0 | 0
2025-10-21 | 1146287.5717 | 119643.2 | 790255.5917 | 236388.78 | 0 | 0 | 0 | 0
2025-10-22 | 1150315.8984 | 119643.2 | 792457.3684 | 238215.33 | 0 | 0 | 0 | 0
2025-10-23 | 1154344.2251 | 119643.2 | 794659.1451 | 240041.88 | 0 | 0 | 0 | 0
2025-10-24 | 1158372.5518 | 119643.2 | 796860.9218 | 241868.43 | 0 | 0 | 0 | 0
2025-10-25 | 1162400.8785 | 119643.2 | 799062.6985 | 243694.98 | 0 | 0 | 0 | 0
2025-10-26 | 1166429.2053 | 119643.2 | 801264.4753 | 245521.53 | 0 | 0 | 0 | 0
2025-10-27 | 1170457.532 | 119643.2 | 803466.252 | 247348.08 | 0 | 0 | 0 | 0
2025-10-28 | 1172749.038 | 119643.2 | 804351.0734 | 248754.7646 | 0 | 0 | 0 | 0
2025-10-29 | 1175040.5439 | 119643.2 | 805235.8948 | 250161.4491 | 0 | 0 | 0 | 0
2025-10-30 | 1177332.0499 | 119643.2 | 806120.7162 | 251568.1337 | 0 | 0 | 0 | 0
2025-10-31 | 1179623.5559 | 119643.2 | 807005.5377 | 252974.8182 | 0 | 0 | 0 | 0
2025-11-01 | 1181915.0619 | 119643.2 | 807890.3591 | 254381.5028 | 0 | 0 | 0 | 0
2025-11-02 | 1184206.5679 | 119643.2 | 808775.1805 | 255788.1873 | 0 | 0 | 0 | 0
2025-11-03 | 1186498.0738 | 119643.2 | 809660.002 | 257194.8719 | 0 | 0 | 0 | 0
2025-11-04 | 1188789.5798 | 119643.2 | 810544.8234 | 258601.5564 | 0 | 0 | 0 | 0
2025-11-05 | 1191081.0858 | 119643.2 | 811429.6448 | 260008.241 | 0 | 0 | 0 | 0
2025-11-06 | 1193372.5918 | 119643.2 | 812314.4662 | 261414.9256 | 0 | 0 | 0 | 0
2025-11-07 | 1195664.0978 | 119643.2 | 813199.2877 | 262821.6101 | 0 | 0 | 0 | 0
2025-11-08 | 1197955.6038 | 119643.2 | 814084.1091 | 264228.2947 | 0 | 0 | 0 | 0
2025-11-09 | 1200247.1097 | 119643.2 | 814968.9305 | 265634.9792 | 0 | 0 | 0 | 0
2025-11-10 | 1202538.6157 | 119643.2 | 815853.7519 | 267041.6638 | 0 | 0 | 0 | 0
2025-11-11 | 1204830.1217 | 119643.2 | 816738.5734 | 268448.3483 | 0 | 0 | 0 | 0
2025-11-12 | 1207121.6277 | 119643.2 | 817623.3948 | 269855.0329 | 0 | 0 | 0 | 0
2025-11-13 | 1209413.1337 | 119643.2 | 818508.2162 | 271261.7175 | 0 | 0 | 0 | 0
2025-11-14 | 1211704.6397 | 119643.2 | 819393.0376 | 272668.402 | 0 | 0 | 0 | 0
2025-11-15 | 1213996.1456 | 119643.2 | 820277.8591 | 274075.0866 | 0 | 0 | 0 | 0
2025-11-16 | 1216287.6516 | 119643.2 | 821162.6805 | 275481.7711 | 0 | 0 | 0 | 0
2025-11-17 | 1218579.1576 | 119643.2 | 822047.5019 | 276888.4557 | 0 | 0 | 0 | 0
2025-11-18 | 1220870.6636 | 119643.2 | 822932.3234 | 278295.1402 | 0 | 0 | 0 | 0
2025-11-19 | 1223162.1696 | 119643.2 | 823817.1448 | 279701.8248 | 0 | 0 | 0 | 0
2025-11-20 | 1225453.6756 | 119643.2 | 824701.9662 | 281108.5093 | 0 | 0 | 0 | 0
2025-11-21 | 1227745.1815 | 119643.2 | 825586.7876 | 282515.1939 | 0 | 0 | 0 | 0
2025-11-22 | 1230036.6875 | 119643.2 | 826471.6091 | 283921.8785 | 0 | 0 | 0 | 0
2025-11-23 | 1232328.1935 | 119643.2 | 827356.4305 | 285328.563 | 0 | 0 | 0 | 0
2025-11-24 | 1234619.6995 | 119643.2 | 828241.2519 | 286735.2476 | 0 | 0 | 0 | 0
2025-11-25 | 1236911.2055 | 119643.2 | 829126.0733 | 288141.9321 | 0 | 0 | 0 | 0
2025-11-26 | 1239202.7114 | 119643.2 | 830010.8948 | 289548.6167 | 0 | 0 | 0 | 0
2025-11-27 | 1241494.2174 | 119643.2 | 830895.7162 | 290955.3012 | 0 | 0 | 0 | 0
2025-11-28 | 1243785.7234 | 119643.2 | 831780.5376 | 292361.9858 | 0 | 0 | 0 | 0
2025-11-29 | 1246077.2294 | 119643.2 | 832665.359 | 293768.6703 | 0 | 0 | 0 | 0
2025-11-30 | 1248368.7354 | 119643.2 | 833550.1805 | 295175.3549 | 0 | 0 | 0 | 0
2025-12-01 | 1250660.2414 | 119643.2 | 834435.0019 | 296582.0395 | 0 | 0 | 0 | 0
2025-12-02 | 1252951.7473 | 119643.2 | 835319.8233 | 297988.724 | 0 | 0 | 0 | 0
2025-12-03 | 1255243.2533 | 119643.2 | 836204.6448 | 299395.4086 | 0 | 0 | 0 | 0
2025-12-04 | 1257534.7593 | 119643.2 | 837089.4662 | 300802.0931 | 0 | 0 | 0 | 0
2025-12-05 | 1259826.2653 | 119643.2 | 837974.2876 | 302208.7777 | 0 | 0 | 0 | 0
2025-12-06 | 1262117.7713 | 119643.2 | 838859.109 | 303615.4622 | 0 | 0 | 0 | 0
2025-12-07 | 1264409.2773 | 119643.2 | 839743.9305 | 305022.1468 | 0 | 0 | 0 | 0
2025-12-08 | 1266700.7832 | 119643.2 | 840628.7519 | 306428.8314 | 0 | 0 | 0 | 0
2025-12-09 | 1268992.2892 | 119643.2 | 841513.5733 | 307835.5159 | 0 | 0 | 0 | 0
2025-12-10 | 1271283.7952 | 119643.2 | 842398.3947 | 309242.2005 | 0 | 0 | 0 | 0
2025-12-11 | 1273575.3012 | 119643.2 | 843283.2162 | 310648.885 | 0 | 0 | 0 | 0
2025-12-12 | 1275866.8072 | 119643.2 | 844168.0376 | 312055.5696 | 0 | 0 | 0 | 0
2025-12-13 | 1278158.3132 | 119643.2 | 845052.859 | 313462.2541 | 0 | 0 | 0 | 0
2025-12-14 | 1280449.8191 | 119643.2 | 845937.6804 | 314868.9387 | 0 | 0 | 0 | 0
2025-12-15 | 1282741.3251 | 119643.2 | 846822.5019 | 316275.6232 | 0 | 0 | 0 | 0
2025-12-16 | 1285032.8311 | 119643.2 | 847707.3233 | 317682.3078 | 0 | 0 | 0 | 0
2025-12-17 | 1287324.3371 | 119643.2 | 848592.1447 | 319088.9924 | 0 | 0 | 0 | 0
2025-12-18 | 1289615.8431 | 119643.2 | 849476.9662 | 320495.6769 | 0 | 0 | 0 | 0
2025-12-19 | 1291907.3491 | 119643.2 | 850361.7876 | 321902.3615 | 0 | 0 | 0 | 0
2025-12-20 | 1294198.855 | 119643.2 | 851246.609 | 323309.046 | 0 | 0 | 0 | 0
2025-12-21 | 1296490.361 | 119643.2 | 852131.4304 | 324715.7306 | 0 | 0 | 0 | 0
2025-12-22 | 1298781.867 | 119643.2 | 853016.2519 | 326122.4151 | 0 | 0 | 0 | 0
2025-12-23 | 1301073.373 | 119643.2 | 853901.0733 | 327529.0997 | 0 | 0 | 0 | 0
2025-12-24 | 1303364.879 | 119643.2 | 854785.8947 | 328935.7842 | 0 | 0 | 0 | 0
2025-12-25 | 1305656.3849 | 119643.2 | 855670.7161 | 330342.4688 | 0 | 0 | 0 | 0
2025-12-26 | 1307947.8909 | 119643.2 | 856555.5376 | 331749.1534 | 0 | 0 | 0 | 0
2025-12-27 | 1310239.3969 | 119643.2 | 857440.359 | 333155.8379 | 0 | 0 | 0 | 0
2025-12-28 | 1312530.9029 | 119643.2 | 858325.1804 | 334562.5225 | 0 | 0 | 0 | 0
2025-12-29 | 1314822.4089 | 119643.2 | 859210.0018 | 335969.207 | 0 | 0 | 0 | 0
2025-12-30 | 1317113.9149 | 119643.2 | 860094.8233 | 337375.8916 | 0 | 0 | 0 | 0
2025-12-31 | 1319405.4208 | 119643.2 | 860979.6447 | 338782.5761 | 0 | 0 | 0 | 0
2026-01-01 | 1321696.9268 | 119643.2 | 861864.4661 | 340189.2607 | 0 | 0 | 0 | 0
2026-01-02 | 1323988.4328 | 119643.2 | 862749.2876 | 341595.9453 | 0 | 0 | 0 | 0
2026-01-03 | 1326279.9388 | 119643.2 | 863634.109 | 343002.6298 | 0 | 0 | 0 | 0
2026-01-04 | 1328571.4448 | 119643.2 | 864518.9304 | 344409.3144 | 0 | 0 | 0 | 0
2026-01-05 | 1330862.9508 | 119643.2 | 865403.7518 | 345815.9989 | 0 | 0 | 0 | 0
2026-01-06 | 1333154.4567 | 119643.2 | 866288.5733 | 347222.6835 | 0 | 0 | 0 | 0
2026-01-07 | 1335445.9627 | 119643.2 | 867173.3947 | 348629.368 | 0 | 0 | 0 | 0
2026-01-08 | 1337737.4687 | 119643.2 | 868058.2161 | 350036.0526 | 0 | 0 | 0 | 0
2026-01-09 | 1340028.9747 | 119643.2 | 868943.0375 | 351442.7371 | 0 | 0 | 0 | 0
2026-01-10 | 1342320.4807 | 119643.2 | 869827.859 | 352849.4217 | 0 | 0 | 0 | 0
2026-01-11 | 1344611.9867 | 119643.2 | 870712.6804 | 354256.1063 | 0 | 0 | 0 | 0
2026-01-12 | 1346903.4926 | 119643.2 | 871597.5018 | 355662.7908 | 0 | 0 | 0 | 0
2026-01-13 | 1349194.9986 | 119643.2 | 872482.3232 | 357069.4754 | 0 | 0 | 0 | 0
2026-01-14 | 1351486.5046 | 119643.2 | 873367.1447 | 358476.1599 | 0 | 0 | 0 | 0
2026-01-15 | 1353778.0106 | 119643.2 | 874251.9661 | 359882.8445 | 0 | 0 | 0 | 0
2026-01-16 | 1356069.5166 | 119643.2 | 875136.7875 | 361289.529 | 0 | 0 | 0 | 0
2026-01-17 | 1358361.0225 | 119643.2 | 876021.609 | 362696.2136 | 0 | 0 | 0 | 0
2026-01-18 | 1360652.5285 | 119643.2 | 876906.4304 | 364102.8981 | 0 | 0 | 0 | 0
2026-01-19 | 1362944.0345 | 119643.2 | 877791.2518 | 365509.5827 | 0 | 0 | 0 | 0
2026-01-20 | 1365235.5405 | 119643.2 | 878676.0732 | 366916.2673 | 0 | 0 | 0 | 0
2026-01-21 | 1367527.0465 | 119643.2 | 879560.8947 | 368322.9518 | 0 | 0 | 0 | 0
2026-01-22 | 1369818.5525 | 119643.2 | 880445.7161 | 369729.6364 | 0 | 0 | 0 | 0
2026-01-23 | 1372110.0584 | 119643.2 | 881330.5375 | 371136.3209 | 0 | 0 | 0 | 0
2026-01-24 | 1374401.5644 | 119643.2 | 882215.3589 | 372543.0055 | 0 | 0 | 0 | 0
2026-01-25 | 1376693.0704 | 119643.2 | 883100.1804 | 373949.69 | 0 | 0 | 0 | 0
2026-01-26 | 1378984.5764 | 119643.2 | 883985.0018 | 375356.3746 | 0 | 0 | 0 | 0
2026-01-27 | 1381276.0824 | 119643.2 | 884869.8232 | 376763.0592 | 0 | 0 | 0 | 0
2026-01-28 | 1383567.5884 | 119643.2 | 885754.6446 | 378169.7437 | 0 | 0 | 0 | 0
2026-01-29 | 1385859.0943 | 119643.2 | 886639.4661 | 379576.4283 | 0 | 0 | 0 | 0
2026-01-30 | 1388150.6003 | 119643.2 | 887524.2875 | 380983.1128 | 0 | 0 | 0 | 0
2026-01-31 | 1390442.1063 | 119643.2 | 888409.1089 | 382389.7974 | 0 | 0 | 0 | 0
2026-02-01 | 1392733.6123 | 119643.2 | 889293.9304 | 383796.4819 | 0 | 0 | 0 | 0
2026-02-02 | 1395025.1183 | 119643.2 | 890178.7518 | 385203.1665 | 0 | 0 | 0 | 0
2026-02-03 | 1397316.6243 | 119643.2 | 891063.5732 | 386609.851 | 0 | 0 | 0 | 0
2026-02-04 | 1399608.1302 | 119643.2 | 891948.3946 | 388016.5356 | 0 | 0 | 0 | 0
2026-02-05 | 1401899.6362 | 119643.2 | 892833.2161 | 389423.2202 | 0 | 0 | 0 | 0
2026-02-06 | 1404191.1422 | 119643.2 | 893718.0375 | 390829.9047 | 0 | 0 | 0 | 0
2026-02-07 | 1406482.6482 | 119643.2 | 894602.8589 | 392236.5893 | 0 | 0 | 0 | 0
2026-02-08 | 1408774.1542 | 119643.2 | 895487.6803 | 393643.2738 | 0 | 0 | 0 | 0
2026-02-09 | 1411065.6601 | 119643.2 | 896372.5018 | 395049.9584 | 0 | 0 | 0 | 0
2026-02-10 | 1413357.1661 | 119643.2 | 897257.3232 | 396456.6429 | 0 | 0 | 0 | 0
2026-02-11 | 1415648.6721 | 119643.2 | 898142.1446 | 397863.3275 | 0 | 0 | 0 | 0
2026-02-12 | 1417940.1781 | 119643.2 | 899026.966 | 399270.012 | 0 | 0 | 0 | 0
2026-02-13 | 1420231.6841 | 119643.2 | 899911.7875 | 400676.6966 | 0 | 0 | 0 | 0
2026-02-14 | 1422523.1901 | 119643.2 | 900796.6089 | 402083.3812 | 0 | 0 | 0 | 0
2026-02-15 | 1424814.696 | 119643.2 | 901681.4303 | 403490.0657 | 0 | 0 | 0 | 0
2026-02-16 | 1427106.202 | 119643.2 | 902566.2518 | 404896.7503 | 0 | 0 | 0 | 0
2026-02-17 | 1429397.708 | 119643.2 | 903451.0732 | 406303.4348 | 0 | 0 | 0 | 0
2026-02-18 | 1431689.214 | 119643.2 | 904335.8946 | 407710.1194 | 0 | 0 | 0 | 0
2026-02-19 | 1433980.72 | 119643.2 | 905220.716 | 409116.8039 | 0 | 0 | 0 | 0
2026-02-20 | 1436272.226 | 119643.2 | 906105.5375 | 410523.4885 | 0 | 0 | 0 | 0
2026-02-21 | 1438563.7319 | 119643.2 | 906990.3589 | 411930.1731 | 0 | 0 | 0 | 0
2026-02-22 | 1440855.2379 | 119643.2 | 907875.1803 | 413336.8576 | 0 | 0 | 0 | 0
2026-02-23 | 1443146.7439 | 119643.2 | 908760.0017 | 414743.5422 | 0 | 0 | 0 | 0
2026-02-24 | 1445438.2499 | 119643.2 | 909644.8232 | 416150.2267 | 0 | 0 | 0 | 0
2026-02-25 | 1447729.7559 | 119643.2 | 910529.6446 | 417556.9113 | 0 | 0 | 0 | 0
2026-02-26 | 1450021.2619 | 119643.2 | 911414.466 | 418963.5958 | 0 | 0 | 0 | 0
2026-02-27 | 1452312.7678 | 119643.2 | 912299.2874 | 420370.2804 | 0 | 0 | 0 | 0
2026-02-28 | 1454604.2738 | 119643.2 | 913184.1089 | 421776.9649 | 0 | 0 | 0 | 0
2026-03-01 | 1456895.7798 | 119643.2 | 914068.9303 | 423183.6495 | 0 | 0 | 0 | 0
2026-03-02 | 1459187.2858 | 119643.2 | 914953.7517 | 424590.3341 | 0 | 0 | 0 | 0
2026-03-03 | 1461478.7918 | 119643.2 | 915838.5732 | 425997.0186 | 0 | 0 | 0 | 0
2026-03-04 | 1463770.2978 | 119643.2 | 916723.3946 | 427403.7032 | 0 | 0 | 0 | 0
2026-03-05 | 1466061.8037 | 119643.2 | 917608.216 | 428810.3877 | 0 | 0 | 0 | 0
2026-03-06 | 1468353.3097 | 119643.2 | 918493.0374 | 430217.0723 | 0 | 0 | 0 | 0
2026-03-07 | 1470644.8157 | 119643.2 | 919377.8589 | 431623.7568 | 0 | 0 | 0 | 0
2026-03-08 | 1472936.3217 | 119643.2 | 920262.6803 | 433030.4414 | 0 | 0 | 0 | 0
2026-03-09 | 1475227.8277 | 119643.2 | 921147.5017 | 434437.1259 | 0 | 0 | 0 | 0
2026-03-10 | 1477519.3336 | 119643.2 | 922032.3231 | 435843.8105 | 0 | 0 | 0 | 0
2026-03-11 | 1479810.8396 | 119643.2 | 922917.1446 | 437250.4951 | 0 | 0 | 0 | 0
2026-03-12 | 1482102.3456 | 119643.2 | 923801.966 | 438657.1796 | 0 | 0 | 0 | 0
2026-03-13 | 1484393.8516 | 119643.2 | 924686.7874 | 440063.8642 | 0 | 0 | 0 | 0
2026-03-14 | 1486685.3576 | 119643.2 | 925571.6088 | 441470.5487 | 0 | 0 | 0 | 0
2026-03-15 | 1488976.8636 | 119643.2 | 926456.4303 | 442877.2333 | 0 | 0 | 0 | 0
2026-03-16 | 1491268.3695 | 119643.2 | 927341.2517 | 444283.9178 | 0 | 0 | 0 | 0
2026-03-17 | 1493559.8755 | 119643.2 | 928226.0731 | 445690.6024 | 0 | 0 | 0 | 0
2026-03-18 | 1495851.3815 | 119643.2 | 929110.8946 | 447097.287 | 0 | 0 | 0 | 0
2026-03-19 | 1498142.8875 | 119643.2 | 929995.716 | 448503.9715 | 0 | 0 | 0 | 0
2026-03-20 | 1500434.3935 | 119643.2 | 930880.5374 | 449910.6561 | 0 | 0 | 0 | 0
2026-03-21 | 1502725.8995 | 119643.2 | 931765.3588 | 451317.3406 | 0 | 0 | 0 | 0
2026-03-22 | 1505017.4054 | 119643.2 | 932650.1803 | 452724.0252 | 0 | 0 | 0 | 0
2026-03-23 | 1507308.9114 | 119643.2 | 933535.0017 | 454130.7097 | 0 | 0 | 0 | 0
2026-03-24 | 1509600.4174 | 119643.2 | 934419.8231 | 455537.3943 | 0 | 0 | 0 | 0
2026-03-25 | 1511891.9234 | 119643.2 | 935304.6445 | 456944.0788 | 0 | 0 | 0 | 0
2026-03-26 | 1514183.4294 | 119643.2 | 936189.466 | 458350.7634 | 0 | 0 | 0 | 0
2026-03-27 | 1516474.9354 | 119643.2 | 937074.2874 | 459757.448 | 0 | 0 | 0 | 0
2026-03-28 | 1518766.4413 | 119643.2 | 937959.1088 | 461164.1325 | 0 | 0 | 0 | 0
2026-03-29 | 1521057.9473 | 119643.2 | 938843.9302 | 462570.8171 | 0 | 0 | 0 | 0
2026-03-30 | 1523349.4533 | 119643.2 | 939728.7517 | 463977.5016 | 0 | 0 | 0 | 0
2026-03-31 | 1525640.9593 | 119643.2 | 940613.5731 | 465384.1862 | 0 | 0 | 0 | 0
2026-04-01 | 1527932.4653 | 119643.2 | 941498.3945 | 466790.8707 | 0 | 0 | 0 | 0
2026-04-02 | 1530223.9712 | 119643.2 | 942383.216 | 468197.5553 | 0 | 0 | 0 | 0
2026-04-03 | 1532515.4772 | 119643.2 | 943268.0374 | 469604.2398 | 0 | 0 | 0 | 0
2026-04-04 | 1534806.9832 | 119643.2 | 944152.8588 | 471010.9244 | 0 | 0 | 0 | 0
2026-04-05 | 1537098.4892 | 119643.2 | 945037.6802 | 472417.609 | 0 | 0 | 0 | 0
2026-04-06 | 1539389.9952 | 119643.2 | 945922.5017 | 473824.2935 | 0 | 0 | 0 | 0
2026-04-07 | 1541681.5012 | 119643.2 | 946807.3231 | 475230.9781 | 0 | 0 | 0 | 0
2026-04-08 | 1543973.0071 | 119643.2 | 947692.1445 | 476637.6626 | 0 | 0 | 0 | 0
2026-04-09 | 1546264.5131 | 119643.2 | 948576.9659 | 478044.3472 | 0 | 0 | 0 | 0
2026-04-10 | 1548556.0191 | 119643.2 | 949461.7874 | 479451.0317 | 0 | 0 | 0 | 0
2026-04-11 | 1550847.5251 | 119643.2 | 950346.6088 | 480857.7163 | 0 | 0 | 0 | 0
2026-04-12 | 1553139.0311 | 119643.2 | 951231.4302 | 482264.4009 | 0 | 0 | 0 | 0
2026-04-13 | 1555430.5371 | 119643.2 | 952116.2516 | 483671.0854 | 0 | 0 | 0 | 0
2026-04-14 | 1557722.043 | 119643.2 | 953001.0731 | 485077.77 | 0 | 0 | 0 | 0
2026-04-15 | 1560013.549 | 119643.2 | 953885.8945 | 486484.4545 | 0 | 0 | 0 | 0
2026-04-16 | 1562305.055 | 119643.2 | 954770.7159 | 487891.1391 | 0 | 0 | 0 | 0
2026-04-17 | 1564596.561 | 119643.2 | 955655.5374 | 489297.8236 | 0 | 0 | 0 | 0
2026-04-18 | 1566888.067 | 119643.2 | 956540.3588 | 490704.5082 | 0 | 0 | 0 | 0
2026-04-19 | 1569179.573 | 119643.2 | 957425.1802 | 492111.1927 | 0 | 0 | 0 | 0
2026-04-20 | 1571471.0789 | 119643.2 | 958310.0016 | 493517.8773 | 0 | 0 | 0 | 0
2026-04-21 | 1573762.5849 | 119643.2 | 959194.8231 | 494924.5619 | 0 | 0 | 0 | 0
2026-04-22 | 1576054.0909 | 119643.2 | 960079.6445 | 496331.2464 | 0 | 0 | 0 | 0
2026-04-23 | 1578345.5969 | 119643.2 | 960964.4659 | 497737.931 | 0 | 0 | 0 | 0
2026-04-24 | 1580637.1029 | 119643.2 | 961849.2873 | 499144.6155 | 0 | 0 | 0 | 0
2026-04-25 | 1582928.6088 | 119643.2 | 962734.1088 | 500551.3001 | 0 | 0 | 0 | 0
2026-04-26 | 1585220.1148 | 119643.2 | 963618.9302 | 501957.9846 | 0 | 0 | 0 | 0
2026-04-27 | 1587511.6208 | 119643.2 | 964503.7516 | 503364.6692 | 0 | 0 | 0 | 0
2026-04-28 | 1589803.1268 | 119643.2 | 965388.573 | 504771.3537 | 0 | 0 | 0 | 0
2026-04-29 | 1592094.6328 | 119643.2 | 966273.3945 | 506178.0383 | 0 | 0 | 0 | 0
2026-04-30 | 1594386.1388 | 119643.2 | 967158.2159 | 507584.7229 | 0 | 0 | 0 | 0
2026-05-01 | 1596677.6447 | 119643.2 | 968043.0373 | 508991.4074 | 0 | 0 | 0 | 0
2026-05-02 | 1598969.1507 | 119643.2 | 968927.8588 | 510398.092 | 0 | 0 | 0 | 0
2026-05-03 | 1601260.6567 | 119643.2 | 969812.6802 | 511804.7765 | 0 | 0 | 0 | 0
2026-05-04 | 1603552.1627 | 119643.2 | 970697.5016 | 513211.4611 | 0 | 0 | 0 | 0
2026-05-05 | 1605843.6687 | 119643.2 | 971582.323 | 514618.1456 | 0 | 0 | 0 | 0
2026-05-06 | 1608135.1747 | 119643.2 | 972467.1445 | 516024.8302 | 0 | 0 | 0 | 0
2026-05-07 | 1610426.6806 | 119643.2 | 973351.9659 | 517431.5148 | 0 | 0 | 0 | 0
2026-05-08 | 1612718.1866 | 119643.2 | 974236.7873 | 518838.1993 | 0 | 0 | 0 | 0
2026-05-09 | 1615009.6926 | 119643.2 | 975121.6087 | 520244.8839 | 0 | 0 | 0 | 0
2026-05-10 | 1617301.1986 | 119643.2 | 976006.4302 | 521651.5684 | 0 | 0 | 0 | 0
2026-05-11 | 1619592.7046 | 119643.2 | 976891.2516 | 523058.253 | 0 | 0 | 0 | 0
2026-05-12 | 1621884.2106 | 119643.2 | 977776.073 | 524464.9375 | 0 | 0 | 0 | 0
2026-05-13 | 1624175.7165 | 119643.2 | 978660.8944 | 525871.6221 | 0 | 0 | 0 | 0
2026-05-14 | 1626467.2225 | 119643.2 | 979545.7159 | 527278.3066 | 0 | 0 | 0 | 0
2026-05-15 | 1628758.7285 | 119643.2 | 980430.5373 | 528684.9912 | 0 | 0 | 0 | 0
2026-05-16 | 1628758.7285 | 119643.2 | 980430.5373 | 528684.9912 | 0 | 0 | 0 | 0
2026-05-17 | 1628758.7285 | 119643.2 | 980430.5373 | 528684.9912 | 0 | 0 | 0 | 0
2026-05-18 | 1638251.7088 | 119643.2 | 986565.0307 | 532043.4781 | 0 | 0 | 0 | 0
2026-05-19 | 1647744.6891 | 119643.2 | 992699.5241 | 535401.965 | 0 | 0 | 0 | 0
2026-05-20 | 1657237.6694 | 119643.2 | 998834.0175 | 538760.4519 | 0 | 0 | 0 | 0
2026-05-21 | 1666730.6497 | 119643.2 | 1004968.5109 | 542118.9388 | 0 | 0 | 0 | 0
2026-05-22 | 1676223.6301 | 119643.2 | 1011103.0043 | 545477.4257 | 0 | 0 | 0 | 0
2026-05-23 | 1685716.6104 | 119643.2 | 1017237.4977 | 548835.9127 | 0 | 0 | 0 | 0
2026-05-24 | 1695209.5907 | 119643.2 | 1023371.9911 | 552194.3996 | 0 | 0 | 0 | 0
2026-05-25 | 1704702.571 | 119643.2 | 1029506.4845 | 555552.8865 | 0 | 0 | 0 | 0
2026-05-26 | 1714195.5513 | 119643.2 | 1035640.9779 | 558911.3734 | 0 | 0 | 0 | 0
2026-05-27 | 1723688.5316 | 119643.2 | 1041775.4713 | 562269.8603 | 0 | 0 | 0 | 0
2026-05-28 | 1733181.5119 | 119643.2 | 1047909.9647 | 565628.3472 | 0 | 0 | 0 | 0
2026-05-29 | 1742674.4922 | 119643.2 | 1054044.4581 | 568986.8341 | 0 | 0 | 0 | 0
2026-05-30 | 1752167.4725 | 119643.2 | 1060178.9515 | 572345.321 | 0 | 0 | 0 | 0
2026-05-31 | 1761660.4529 | 119643.2 | 1066313.4449 | 575703.8079 | 0 | 0 | 0 | 0
2026-06-01 | 1771153.4332 | 119643.2 | 1072447.9383 | 579062.2948 | 0 | 0 | 0 | 0
2026-06-02 | 1780646.4135 | 119643.2 | 1078582.4317 | 582420.7817 | 0 | 0 | 0 | 0
2026-06-03 | 1790139.3938 | 119643.2 | 1084716.9251 | 585779.2687 | 0 | 0 | 0 | 0
2026-06-04 | 1799632.3741 | 119643.2 | 1090851.4185 | 589137.7556 | 0 | 0 | 0 | 0
2026-06-05 | 1809125.3544 | 119643.2 | 1096985.9119 | 592496.2425 | 0 | 0 | 0 | 0
2026-06-06 | 1818618.3347 | 119643.2 | 1103120.4053 | 595854.7294 | 0 | 0 | 0 | 0
2026-06-07 | 1828111.315 | 119643.2 | 1109254.8987 | 599213.2163 | 0 | 0 | 0 | 0
2026-06-08 | 1837604.2953 | 119643.2 | 1115389.3921 | 602571.7032 | 0 | 0 | 0 | 0
2026-06-09 | 1838287.9953 | 119643.2 | 1115389.3921 | 603255.4032 | 0 | 0 | 0 | 0
2026-06-10 | 1838971.6953 | 119643.2 | 1115389.3921 | 603939.1032 | 0 | 0 | 0 | 0
2026-06-11 | 1839655.3953 | 119643.2 | 1115389.3921 | 604622.8032 | 0 | 0 | 0 | 0
2026-06-12 | 1840339.0953 | 119643.2 | 1115389.3921 | 605306.5032 | 0 | 0 | 0 | 0
2026-06-13 | 1841022.7953 | 119643.2 | 1115389.3921 | 605990.2032 | 0 | 0 | 0 | 0
2026-06-14 | 1841706.4953 | 119643.2 | 1115389.3921 | 606673.9032 | 0 | 0 | 0 | 0
2026-06-15 | 1842390.1953 | 119643.2 | 1115389.3921 | 607357.6032 | 0 | 0 | 0 | 0
2026-06-16 | 1843073.8953 | 119643.2 | 1115389.3921 | 608041.3032 | 0 | 0 | 0 | 0
2026-06-17 | 1843757.5953 | 119643.2 | 1115389.3921 | 608725.0032 | 0 | 0 | 0 | 0
2026-06-18 | 1844441.2953 | 119643.2 | 1115389.3921 | 609408.7032 | 0 | 0 | 0 | 0
2026-06-19 | 1845124.9953 | 119643.2 | 1115389.3921 | 610092.4032 | 0 | 0 | 0 | 0
2026-06-20 | 1845808.6953 | 119643.2 | 1115389.3921 | 610776.1032 | 0 | 0 | 0 | 0
2026-06-21 | 1846492.3953 | 119643.2 | 1115389.3921 | 611459.8032 | 0 | 0 | 0 | 0
2026-06-22 | 1847176.0953 | 119643.2 | 1115389.3921 | 612143.5032 | 0 | 0 | 0 | 0
2026-06-23 | 1847859.7953 | 119643.2 | 1115389.3921 | 612827.2032 | 0 | 0 | 0 | 0
2026-06-24 | 1848543.4953 | 119643.2 | 1115389.3921 | 613510.9032 | 0 | 0 | 0 | 0
2026-06-25 | 1849227.1953 | 119643.2 | 1115389.3921 | 614194.6032 | 0 | 0 | 0 | 0
2026-06-26 | 1849910.8953 | 119643.2 | 1115389.3921 | 614878.3032 | 0 | 0 | 0 | 0
2026-06-27 | 1850594.5953 | 119643.2 | 1115389.3921 | 615562.0032 | 0 | 0 | 0 | 0
2026-06-28 | 1851278.2953 | 119643.2 | 1115389.3921 | 616245.7032 | 0 | 0 | 0 | 0
2026-06-29 | 1851961.9953 | 119643.2 | 1115389.3921 | 616929.4032 | 0 | 0 | 0 | 0
2026-06-30 | 1852645.6953 | 119643.2 | 1115389.3921 | 617613.1032 | 0 | 0 | 0 | 0
2026-07-01 | 1853329.3953 | 119643.2 | 1115389.3921 | 618296.8032 | 0 | 0 | 0 | 0
2026-07-02 | 1854013.0953 | 119643.2 | 1115389.3921 | 618980.5032 | 0 | 0 | 0 | 0
2026-07-03 | 1854696.7953 | 119643.2 | 1115389.3921 | 619664.2032 | 0 | 0 | 0 | 0
2026-07-04 | 1855380.4953 | 119643.2 | 1115389.3921 | 620347.9032 | 0 | 0 | 0 | 0
2026-07-05 | 1856064.1953 | 119643.2 | 1115389.3921 | 621031.6032 | 0 | 0 | 0 | 0
2026-07-06 | 1856747.8953 | 119643.2 | 1115389.3921 | 621715.3032 | 0 | 0 | 0 | 0
2026-07-07 | 1857431.5953 | 119643.2 | 1115389.3921 | 622399.0032 | 0 | 0 | 0 | 0
2026-07-08 | 1858115.2953 | 119643.2 | 1115389.3921 | 623082.7032 | 0 | 0 | 0 | 0
2026-07-09 | 1858798.9953 | 119643.2 | 1115389.3921 | 623766.4032 | 0 | 0 | 0 | 0
2026-07-10 | 1859482.6953 | 119643.2 | 1115389.3921 | 624450.1032 | 0 | 0 | 0 | 0

## Invoice Tracking
Date | Planned Invoice Sum | Actual Invoice Sum
2025-04-01 | 1591.7216 | 0
2025-04-02 | 3183.4432 | 0
2025-04-03 | 4775.1648 | 0
2025-04-04 | 6366.8864 | 0
2025-04-05 | 7958.608 | 0
2025-04-06 | 9550.3295 | 0
2025-04-07 | 11142.0511 | 0
2025-04-08 | 12733.7727 | 0
2025-04-09 | 14325.4943 | 0
2025-04-10 | 15917.2159 | 0
2025-04-11 | 17508.9375 | 0
2025-04-12 | 19100.6591 | 0
2025-04-13 | 20692.3807 | 0
2025-04-14 | 22284.1023 | 0
2025-04-15 | 23875.8239 | 0
2025-04-16 | 25467.5455 | 0
2025-04-17 | 27059.267 | 0
2025-04-18 | 28650.9886 | 0
2025-04-19 | 30242.7102 | 0
2025-04-20 | 31834.4318 | 0
2025-04-21 | 33426.1534 | 0
2025-04-22 | 35017.875 | 0
2025-04-23 | 36609.5966 | 0
2025-04-24 | 38201.3182 | 0
2025-04-25 | 39793.0398 | 0
2025-04-26 | 41384.7614 | 0
2025-04-27 | 42976.483 | 0
2025-04-28 | 44568.2045 | 0
2025-04-29 | 46159.9261 | 0
2025-04-30 | 47751.6477 | 0
2025-05-01 | 49343.3693 | 0
2025-05-02 | 50935.0909 | 0
2025-05-03 | 52526.8125 | 0
2025-05-04 | 54118.5341 | 0
2025-05-05 | 55710.2557 | 0
2025-05-06 | 57301.9773 | 0
2025-05-07 | 58893.6989 | 0
2025-05-08 | 60485.4205 | 0
2025-05-09 | 62077.142 | 0
2025-05-10 | 63668.8636 | 0
2025-05-11 | 65260.5852 | 0
2025-05-12 | 66852.3068 | 0
2025-05-13 | 68444.0284 | 0
2025-05-14 | 70035.75 | 0
2025-05-15 | 71627.4716 | 0
2025-05-16 | 73219.1932 | 0
2025-05-17 | 74810.9148 | 0
2025-05-18 | 76402.6364 | 0
2025-05-19 | 77994.358 | 0
2025-05-20 | 79586.0795 | 0
2025-05-21 | 81177.8011 | 0
2025-05-22 | 82769.5227 | 0
2025-05-23 | 84361.2443 | 0
2025-05-24 | 85952.9659 | 0
2025-05-25 | 87544.6875 | 0
2025-05-26 | 89136.4091 | 0
2025-05-27 | 90728.1307 | 0
2025-05-28 | 92319.8523 | 0
2025-05-29 | 93911.5739 | 0
2025-05-30 | 95503.2955 | 0
2025-05-31 | 97095.017 | 0
2025-06-01 | 104207.1854 | 0
2025-06-02 | 111319.3537 | 0
2025-06-03 | 118431.5221 | 0
2025-06-04 | 125543.6904 | 0
2025-06-05 | 132655.8587 | 0
2025-06-06 | 138176.3055 | 0
2025-06-07 | 143696.7522 | 0
2025-06-08 | 149217.199 | 0
2025-06-09 | 154737.6457 | 0
2025-06-10 | 160258.0925 | 0
2025-06-11 | 165778.5392 | 0
2025-06-12 | 171298.986 | 0
2025-06-13 | 176819.4327 | 0
2025-06-14 | 182339.8795 | 0
2025-06-15 | 187860.3262 | 0
2025-06-16 | 193380.773 | 0
2025-06-17 | 198901.2197 | 0
2025-06-18 | 204421.6664 | 0
2025-06-19 | 209942.1132 | 0
2025-06-20 | 215462.5599 | 0
2025-06-21 | 220983.0067 | 0
2025-06-22 | 226503.4534 | 0
2025-06-23 | 232023.9002 | 0
2025-06-24 | 237544.3469 | 0
2025-06-25 | 243064.7937 | 0
2025-06-26 | 248585.2404 | 0
2025-06-27 | 254105.6872 | 0
2025-06-28 | 259626.1339 | 0
2025-06-29 | 265146.5807 | 0
2025-06-30 | 270667.0274 | 0
2025-07-01 | 276187.4742 | 0
2025-07-02 | 281707.9209 | 0
2025-07-03 | 287228.3677 | 0
2025-07-04 | 292748.8144 | 0
2025-07-05 | 298269.2611 | 0
2025-07-06 | 303789.7079 | 0
2025-07-07 | 309310.1546 | 0
2025-07-08 | 314830.6014 | 0
2025-07-09 | 320351.0481 | 0
2025-07-10 | 325871.4949 | 0
2025-07-11 | 331391.9416 | 0
2025-07-12 | 336912.3884 | 0
2025-07-13 | 342432.8351 | 0
2025-07-14 | 347953.2819 | 0
2025-07-15 | 365565.8355 | 0
2025-07-16 | 383178.389 | 0
2025-07-17 | 400790.9426 | 0
2025-07-18 | 418403.4962 | 0
2025-07-19 | 436016.0498 | 0
2025-07-20 | 453628.6034 | 0
2025-07-21 | 471241.157 | 0
2025-07-22 | 488853.7105 | 0
2025-07-23 | 506466.2641 | 0
2025-07-24 | 524078.8177 | 0
2025-07-25 | 541691.3713 | 0
2025-07-26 | 559303.9249 | 0
2025-07-27 | 576916.4785 | 0
2025-07-28 | 594529.032 | 0
2025-07-29 | 612141.5856 | 0
2025-07-30 | 629754.1392 | 0
2025-07-31 | 647366.6928 | 484608.92
2025-08-01 | 664979.2464 | 484608.92
2025-08-02 | 682591.8 | 484608.92
2025-08-03 | 700204.3535 | 484608.92
2025-08-04 | 717816.9071 | 484608.92
2025-08-05 | 735429.4607 | 484608.92
2025-08-06 | 753042.0143 | 484608.92
2025-08-07 | 770654.5679 | 484608.92
2025-08-08 | 788267.1215 | 484608.92
2025-08-09 | 805879.675 | 484608.92
2025-08-10 | 823492.2286 | 484608.92
2025-08-11 | 841104.7822 | 484608.92
2025-08-12 | 858717.3358 | 484608.92
2025-08-13 | 876329.8894 | 484608.92
2025-08-14 | 893942.443 | 484608.92
2025-08-15 | 911554.9965 | 484608.92
2025-08-16 | 929167.5501 | 484608.92
2025-08-17 | 946780.1037 | 484608.92
2025-08-18 | 964392.6573 | 484608.92
2025-08-19 | 982005.2109 | 484608.92
2025-08-20 | 999617.7645 | 484608.92
2025-08-21 | 1017230.3181 | 484608.92
2025-08-22 | 1034842.8716 | 484608.92
2025-08-23 | 1046934.9785 | 484608.92
2025-08-24 | 1059027.0853 | 484608.92
2025-08-25 | 1071119.1921 | 484608.92
2025-08-26 | 1083211.299 | 484608.92
2025-08-27 | 1095303.4058 | 484608.92
2025-08-28 | 1107395.5127 | 484608.92
2025-08-29 | 1119487.6195 | 484608.92
2025-08-30 | 1131579.7263 | 484608.92
2025-08-31 | 1143671.8332 | 662202.05
2025-09-01 | 1155763.94 | 0
2025-09-02 | 1160749.5372 | 0
2025-09-03 | 1165735.1345 | 0
2025-09-04 | 1170720.7317 | 0
2025-09-05 | 1175706.329 | 0
2025-09-06 | 1180691.9262 | 0
2025-09-07 | 1185677.5235 | 0
2025-09-08 | 1190663.1207 | 0
2025-09-09 | 1195648.7179 | 0
2025-09-10 | 1200634.3152 | 0
2025-09-11 | 1205619.9124 | 0
2025-09-12 | 1210605.5097 | 0
2025-09-13 | 1215591.1069 | 0
2025-09-14 | 1220576.7042 | 0
2025-09-15 | 1225562.3014 | 0
2025-09-16 | 1230547.8986 | 0
2025-09-17 | 1235533.4959 | 0
2025-09-18 | 1240519.0931 | 0
2025-09-19 | 1245504.6904 | 0
2025-09-20 | 1250490.2876 | 0
2025-09-21 | 1255475.8849 | 0
2025-09-22 | 1260461.4821 | 0
2025-09-23 | 1265447.0793 | 0
2025-09-24 | 1270432.6766 | 0
2025-09-25 | 1275418.2738 | 0
2025-09-26 | 1280403.8711 | 0
2025-09-27 | 1285389.4683 | 0
2025-09-28 | 1290375.0655 | 0
2025-09-29 | 1295360.6628 | 0
2025-09-30 | 1300346.26 | 0
2025-10-01 | 1305331.8573 | 0
2025-10-02 | 1310317.4545 | 0
2025-10-03 | 1315303.0518 | 0
2025-10-04 | 1320288.649 | 0
2025-10-05 | 1325274.2462 | 0
2025-10-06 | 1330259.8435 | 0
2025-10-07 | 1335245.4407 | 0
2025-10-08 | 1340231.038 | 0
2025-10-09 | 1345216.6352 | 0
2025-10-10 | 1350202.2325 | 0
2025-10-11 | 1355187.8297 | 0
2025-10-12 | 1360173.4269 | 0
2025-10-13 | 1365159.0242 | 0
2025-10-14 | 1370144.6214 | 0
2025-10-15 | 1375130.2187 | 0
2025-10-16 | 1380115.8159 | 0
2025-10-17 | 1385101.4132 | 0
2025-10-18 | 1390087.0104 | 0
2025-10-19 | 1395072.6076 | 0
2025-10-20 | 1400058.2049 | 0
2025-10-21 | 1405043.8021 | 0
2025-10-22 | 1410029.3994 | 0
2025-10-23 | 1415014.9966 | 0
2025-10-24 | 1420000.5939 | 0
2025-10-25 | 1424986.1911 | 0
2025-10-26 | 1429971.7883 | 0
2025-10-27 | 1434957.3856 | 0
2025-10-28 | 1437810.0776 | 0
2025-10-29 | 1440662.7697 | 0
2025-10-30 | 1443515.4618 | 0
2025-10-31 | 1446368.1538 | 0
2025-11-01 | 1449220.8459 | 0
2025-11-02 | 1452073.538 | 0
2025-11-03 | 1454926.23 | 0
2025-11-04 | 1457778.9221 | 0
2025-11-05 | 1460631.6141 | 0
2025-11-06 | 1463484.3062 | 0
2025-11-07 | 1466336.9983 | 0
2025-11-08 | 1469189.6903 | 0
2025-11-09 | 1472042.3824 | 0
2025-11-10 | 1474895.0744 | 0
2025-11-11 | 1477747.7665 | 0
2025-11-12 | 1480600.4586 | 0
2025-11-13 | 1483453.1506 | 0
2025-11-14 | 1486305.8427 | 0
2025-11-15 | 1489158.5348 | 0
2025-11-16 | 1492011.2268 | 0
2025-11-17 | 1494863.9189 | 0
2025-11-18 | 1497716.6109 | 0
2025-11-19 | 1500569.303 | 0
2025-11-20 | 1503421.9951 | 0
2025-11-21 | 1506274.6871 | 0
2025-11-22 | 1509127.3792 | 0
2025-11-23 | 1511980.0712 | 0
2025-11-24 | 1514832.7633 | 0
2025-11-25 | 1517685.4554 | 0
2025-11-26 | 1520538.1474 | 0
2025-11-27 | 1523390.8395 | 0
2025-11-28 | 1526243.5316 | 0
2025-11-29 | 1529096.2236 | 0
2025-11-30 | 1531948.9157 | 0
2025-12-01 | 1534801.6077 | 0
2025-12-02 | 1537654.2998 | 0
2025-12-03 | 1540506.9919 | 0
2025-12-04 | 1543359.6839 | 0
2025-12-05 | 1546212.376 | 0
2025-12-06 | 1549065.068 | 0
2025-12-07 | 1551917.7601 | 0
2025-12-08 | 1554770.4522 | 0
2025-12-09 | 1557623.1442 | 0
2025-12-10 | 1560475.8363 | 0
2025-12-11 | 1563328.5284 | 0
2025-12-12 | 1566181.2204 | 0
2025-12-13 | 1569033.9125 | 0
2025-12-14 | 1571886.6045 | 0
2025-12-15 | 1574739.2966 | 0
2025-12-16 | 1577591.9887 | 0
2025-12-17 | 1580444.6807 | 0
2025-12-18 | 1583297.3728 | 0
2025-12-19 | 1586150.0648 | 0
2025-12-20 | 1589002.7569 | 0
2025-12-21 | 1591855.449 | 0
2025-12-22 | 1594708.141 | 0
2025-12-23 | 1597560.8331 | 0
2025-12-24 | 1600413.5252 | 0
2025-12-25 | 1603266.2172 | 0
2025-12-26 | 1606118.9093 | 0
2025-12-27 | 1608971.6013 | 0
2025-12-28 | 1611824.2934 | 0
2025-12-29 | 1614676.9855 | 0
2025-12-30 | 1617529.6775 | 0
2025-12-31 | 1620382.3696 | 0
2026-01-01 | 1623235.0617 | 0
2026-01-02 | 1626087.7537 | 0
2026-01-03 | 1628940.4458 | 0
2026-01-04 | 1631793.1378 | 0
2026-01-05 | 1634645.8299 | 0
2026-01-06 | 1637498.522 | 0
2026-01-07 | 1640351.214 | 0
2026-01-08 | 1643203.9061 | 0
2026-01-09 | 1646056.5981 | 0
2026-01-10 | 1648909.2902 | 0
2026-01-11 | 1651761.9823 | 0
2026-01-12 | 1654614.6743 | 0
2026-01-13 | 1657467.3664 | 0
2026-01-14 | 1660320.0585 | 0
2026-01-15 | 1663172.7505 | 0
2026-01-16 | 1666025.4426 | 0
2026-01-17 | 1668878.1346 | 0
2026-01-18 | 1671730.8267 | 0
2026-01-19 | 1674583.5188 | 0
2026-01-20 | 1677436.2108 | 0
2026-01-21 | 1680288.9029 | 0
2026-01-22 | 1683141.5949 | 0
2026-01-23 | 1685994.287 | 0
2026-01-24 | 1688846.9791 | 0
2026-01-25 | 1691699.6711 | 0
2026-01-26 | 1694552.3632 | 0
2026-01-27 | 1697405.0553 | 0
2026-01-28 | 1700257.7473 | 0
2026-01-29 | 1703110.4394 | 0
2026-01-30 | 1705963.1314 | 0
2026-01-31 | 1708815.8235 | 0
2026-02-01 | 1711668.5156 | 0
2026-02-02 | 1714521.2076 | 0
2026-02-03 | 1717373.8997 | 0
2026-02-04 | 1720226.5917 | 0
2026-02-05 | 1723079.2838 | 0
2026-02-06 | 1725931.9759 | 0
2026-02-07 | 1728784.6679 | 0
2026-02-08 | 1731637.36 | 0
2026-02-09 | 1734490.0521 | 0
2026-02-10 | 1737342.7441 | 0
2026-02-11 | 1740195.4362 | 0
2026-02-12 | 1743048.1282 | 0
2026-02-13 | 1745900.8203 | 0
2026-02-14 | 1748753.5124 | 0
2026-02-15 | 1751606.2044 | 0
2026-02-16 | 1754458.8965 | 0
2026-02-17 | 1757311.5885 | 0
2026-02-18 | 1760164.2806 | 0
2026-02-19 | 1763016.9727 | 0
2026-02-20 | 1765869.6647 | 0
2026-02-21 | 1768722.3568 | 0
2026-02-22 | 1771575.0489 | 0
2026-02-23 | 1774427.7409 | 0
2026-02-24 | 1777280.433 | 0
2026-02-25 | 1780133.125 | 0
2026-02-26 | 1782985.8171 | 0
2026-02-27 | 1785838.5092 | 0
2026-02-28 | 1788691.2012 | 0
2026-03-01 | 1791543.8933 | 0
2026-03-02 | 1794396.5854 | 0
2026-03-03 | 1797249.2774 | 0
2026-03-04 | 1800101.9695 | 0
2026-03-05 | 1802954.6615 | 0
2026-03-06 | 1805807.3536 | 0
2026-03-07 | 1808660.0457 | 0
2026-03-08 | 1811512.7377 | 0
2026-03-09 | 1814365.4298 | 0
2026-03-10 | 1817218.1218 | 0
2026-03-11 | 1820070.8139 | 0
2026-03-12 | 1822923.506 | 0
2026-03-13 | 1825776.198 | 0
2026-03-14 | 1828628.8901 | 0
2026-03-15 | 1831481.5822 | 0
2026-03-16 | 1834334.2742 | 0
2026-03-17 | 1837186.9663 | 0
2026-03-18 | 1840039.6583 | 0
2026-03-19 | 1842892.3504 | 0
2026-03-20 | 1845745.0425 | 0
2026-03-21 | 1848597.7345 | 0
2026-03-22 | 1851450.4266 | 0
2026-03-23 | 1854303.1186 | 0
2026-03-24 | 1857155.8107 | 0
2026-03-25 | 1860008.5028 | 0
2026-03-26 | 1862861.1948 | 0
2026-03-27 | 1865713.8869 | 0
2026-03-28 | 1868566.579 | 0
2026-03-29 | 1871419.271 | 0
2026-03-30 | 1874271.9631 | 0
2026-03-31 | 1877124.6551 | 0
2026-04-01 | 1879977.3472 | 0
2026-04-02 | 1882830.0393 | 0
2026-04-03 | 1885682.7313 | 0
2026-04-04 | 1888535.4234 | 0
2026-04-05 | 1891388.1154 | 0
2026-04-06 | 1894240.8075 | 0
2026-04-07 | 1897093.4996 | 0
2026-04-08 | 1899946.1916 | 0
2026-04-09 | 1902798.8837 | 0
2026-04-10 | 1905651.5758 | 0
2026-04-11 | 1908504.2678 | 0
2026-04-12 | 1911356.9599 | 0
2026-04-13 | 1914209.6519 | 0
2026-04-14 | 1917062.344 | 0
2026-04-15 | 1919915.0361 | 0
2026-04-16 | 1922767.7281 | 0
2026-04-17 | 1925620.4202 | 0
2026-04-18 | 1928473.1122 | 0
2026-04-19 | 1931325.8043 | 0
2026-04-20 | 1934178.4964 | 0
2026-04-21 | 1937031.1884 | 0
2026-04-22 | 1939883.8805 | 0
2026-04-23 | 1942736.5726 | 0
2026-04-24 | 1945589.2646 | 0
2026-04-25 | 1948441.9567 | 0
2026-04-26 | 1951294.6487 | 0
2026-04-27 | 1954147.3408 | 0
2026-04-28 | 1957000.0329 | 0
2026-04-29 | 1959852.7249 | 0
2026-04-30 | 1962705.417 | 0
2026-05-01 | 1965558.1091 | 0
2026-05-02 | 1968410.8011 | 0
2026-05-03 | 1971263.4932 | 0
2026-05-04 | 1974116.1852 | 0
2026-05-05 | 1976968.8773 | 0
2026-05-06 | 1979821.5694 | 0
2026-05-07 | 1982674.2614 | 0
2026-05-08 | 1985526.9535 | 0
2026-05-09 | 1988379.6455 | 0
2026-05-10 | 1991232.3376 | 0
2026-05-11 | 1994085.0297 | 0
2026-05-12 | 1996937.7217 | 0
2026-05-13 | 1999790.4138 | 0
2026-05-14 | 2002643.1059 | 0
2026-05-15 | 2005495.7979 | 0
2026-05-16 | 2005495.7979 | 0
2026-05-17 | 2005495.7979 | 0
2026-05-18 | 2017383.2543 | 0
2026-05-19 | 2029270.7108 | 0
2026-05-20 | 2041158.1672 | 0
2026-05-21 | 2053045.6236 | 0
2026-05-22 | 2064933.08 | 0
2026-05-23 | 2076820.5364 | 0
2026-05-24 | 2088707.9929 | 0
2026-05-25 | 2100595.4493 | 0
2026-05-26 | 2112482.9057 | 0
2026-05-27 | 2124370.3621 | 0
2026-05-28 | 2136257.8186 | 0
2026-05-29 | 2148145.275 | 0
2026-05-30 | 2160032.7314 | 0
2026-05-31 | 2171920.1878 | 0
2026-06-01 | 2183807.6442 | 0
2026-06-02 | 2195695.1007 | 0
2026-06-03 | 2207582.5571 | 0
2026-06-04 | 2219470.0135 | 0
2026-06-05 | 2231357.4699 | 0
2026-06-06 | 2243244.9264 | 0
2026-06-07 | 2255132.3828 | 0
2026-06-08 | 2267019.8392 | 0
2026-06-09 | 2267874.4642 | 0
2026-06-10 | 2268729.0892 | 0
2026-06-11 | 2269583.7142 | 0
2026-06-12 | 2270438.3392 | 0
2026-06-13 | 2271292.9642 | 0
2026-06-14 | 2272147.5892 | 0
2026-06-15 | 2273002.2142 | 0
2026-06-16 | 2273856.8392 | 0
2026-06-17 | 2274711.4642 | 0
2026-06-18 | 2275566.0892 | 0
2026-06-19 | 2276420.7142 | 0
2026-06-20 | 2277275.3392 | 0
2026-06-21 | 2278129.9642 | 0
2026-06-22 | 2278984.5892 | 0
2026-06-23 | 2279839.2142 | 0
2026-06-24 | 2280693.8392 | 0
2026-06-25 | 2281548.4642 | 0
2026-06-26 | 2282403.0892 | 0
2026-06-27 | 2283257.7142 | 0
2026-06-28 | 2284112.3392 | 0
2026-06-29 | 2284966.9642 | 0
2026-06-30 | 2285821.5892 | 0
2026-07-01 | 2286676.2142 | 0
2026-07-02 | 2287530.8392 | 0
2026-07-03 | 2288385.4642 | 0
2026-07-04 | 2289240.0892 | 0
2026-07-05 | 2290094.7142 | 0
2026-07-06 | 2290949.3392 | 0
2026-07-07 | 2291803.9642 | 0
2026-07-08 | 2292658.5892 | 0
2026-07-09 | 2293513.2142 | 0
2026-07-10 | 2294367.8392 | 0

## Travel and Per Diem Tracking
Date | Planned Travel Sum | Planned Air Cost | Planned Hotel Cost | Planned Other Travel Cost | Planned Meal Cost | Actual Travel Sum | Actual Air Cost | Actual Hotel Cost | Actual Other Travel Cost | Actual Meal Cost
2025-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 80.6747 | 7.8072 | 47.3639 | 7.2867 | 18.2169 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 161.3494 | 15.6145 | 94.7277 | 14.5735 | 36.4337 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 242.0241 | 23.4217 | 142.0916 | 21.8602 | 54.6506 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 322.6988 | 31.2289 | 189.4554 | 29.147 | 72.8675 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 403.3735 | 39.0361 | 236.8193 | 36.4337 | 91.0843 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 484.0482 | 46.8434 | 284.1831 | 43.7205 | 109.3012 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 564.7229 | 54.6506 | 331.547 | 51.0072 | 127.5181 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 645.3976 | 62.4578 | 378.9108 | 58.294 | 145.7349 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 726.0723 | 70.2651 | 426.2747 | 65.5807 | 163.9518 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 806.747 | 78.0723 | 473.6386 | 72.8675 | 182.1687 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 887.4217 | 85.8795 | 521.0024 | 80.1542 | 200.3855 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 968.0964 | 93.6867 | 568.3663 | 87.441 | 218.6024 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 1048.7711 | 101.494 | 615.7301 | 94.7277 | 236.8193 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 1129.4458 | 109.3012 | 663.094 | 102.0145 | 255.0361 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 1210.1205 | 117.1084 | 710.4578 | 109.3012 | 273.253 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 1290.7952 | 124.9157 | 757.8217 | 116.588 | 291.4699 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 1371.4699 | 132.7229 | 805.1855 | 123.8747 | 309.6867 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 1452.1446 | 140.5301 | 852.5494 | 131.1614 | 327.9036 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 1532.8193 | 148.3373 | 899.9133 | 138.4482 | 346.1205 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 1613.494 | 156.1446 | 947.2771 | 145.7349 | 364.3373 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 1694.1687 | 163.9518 | 994.641 | 153.0217 | 382.5542 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 1774.8434 | 171.759 | 1042.0048 | 160.3084 | 400.7711 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 1855.5181 | 179.5663 | 1089.3687 | 167.5952 | 418.988 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 1936.1928 | 187.3735 | 1136.7325 | 174.8819 | 437.2048 | 679.86 | 0 | 0 | 679.86 | 0
2025-06-25 | 2016.8675 | 195.1807 | 1184.0964 | 182.1687 | 455.4217 | 679.86 | 0 | 0 | 679.86 | 0
2025-06-26 | 2097.5422 | 202.988 | 1231.4602 | 189.4554 | 473.6386 | 679.86 | 0 | 0 | 679.86 | 0
2025-06-27 | 2178.2169 | 210.7952 | 1278.8241 | 196.7422 | 491.8554 | 679.86 | 0 | 0 | 679.86 | 0
2025-06-28 | 2258.8916 | 218.6024 | 1326.188 | 204.0289 | 510.0723 | 792.13 | 0 | 0 | 792.13 | 0
2025-06-29 | 2339.5663 | 226.4096 | 1373.5518 | 211.3157 | 528.2892 | 940.88 | 0 | 148.75 | 792.13 | 0
2025-06-30 | 2420.241 | 234.2169 | 1420.9157 | 218.6024 | 546.506 | 940.88 | 0 | 148.75 | 792.13 | 0
2025-07-01 | 2500.9157 | 242.0241 | 1468.2795 | 225.8892 | 564.7229 | 940.88 | 0 | 148.75 | 792.13 | 0
2025-07-02 | 2581.5904 | 249.8313 | 1515.6434 | 233.1759 | 582.9398 | 940.88 | 0 | 148.75 | 792.13 | 0
2025-07-03 | 2662.2651 | 257.6386 | 1563.0072 | 240.4627 | 601.1566 | 940.88 | 0 | 148.75 | 792.13 | 0
2025-07-04 | 2742.9398 | 265.4458 | 1610.3711 | 247.7494 | 619.3735 | 940.88 | 0 | 148.75 | 792.13 | 0
2025-07-05 | 2823.6145 | 273.253 | 1657.7349 | 255.0361 | 637.5904 | 940.88 | 0 | 148.75 | 792.13 | 0
2025-07-06 | 2904.2892 | 281.0602 | 1705.0988 | 262.3229 | 655.8072 | 940.88 | 0 | 148.75 | 792.13 | 0
2025-07-07 | 2984.9639 | 288.8675 | 1752.4627 | 269.6096 | 674.0241 | 1121.98 | 0 | 148.75 | 973.23 | 0
2025-07-08 | 3065.6386 | 296.6747 | 1799.8265 | 276.8964 | 692.241 | 1621.98 | 0 | 148.75 | 973.23 | 500
2025-07-09 | 3146.3133 | 304.4819 | 1847.1904 | 284.1831 | 710.4578 | 1621.98 | 0 | 148.75 | 973.23 | 500
2025-07-10 | 3226.988 | 312.2892 | 1894.5542 | 291.4699 | 728.6747 | 1679.87 | 0 | 148.75 | 1031.12 | 500
2025-07-11 | 3307.6627 | 320.0964 | 1941.9181 | 298.7566 | 746.8916 | 1980.99 | 0 | 449.87 | 1031.12 | 500
2025-07-12 | 3388.3373 | 327.9036 | 1989.2819 | 306.0434 | 765.1084 | 2415.11 | 0 | 654.71 | 1260.4 | 500
2025-07-13 | 3469.012 | 335.7108 | 2036.6458 | 313.3301 | 783.3253 | 2603.58 | 0 | 843.18 | 1260.4 | 500
2025-07-14 | 3549.6867 | 343.5181 | 2084.0096 | 320.6169 | 801.5422 | 2800.62 | 0 | 970.08 | 1330.54 | 500
2025-07-15 | 4108.6472 | 397.611 | 2412.1735 | 371.1036 | 927.759 | 3199.12 | 0 | 1368.58 | 1330.54 | 500
2025-07-16 | 4667.6076 | 451.704 | 2740.3373 | 421.5904 | 1053.9759 | 3549.12 | 0 | 1368.58 | 1330.54 | 850
2025-07-17 | 5226.568 | 505.7969 | 3068.5012 | 472.0771 | 1180.1928 | 3638.74 | 0 | 1368.58 | 1420.16 | 850
2025-07-18 | 5785.5284 | 559.8898 | 3396.6651 | 522.5639 | 1306.4096 | 5798.74 | 0 | 1728.58 | 1420.16 | 2650
2025-07-19 | 6344.4888 | 613.9828 | 3724.8289 | 573.0506 | 1432.6265 | 5842.04 | 43.3 | 1728.58 | 1420.16 | 2650
2025-07-20 | 6903.4492 | 668.0757 | 4052.9928 | 623.5373 | 1558.8434 | 5842.04 | 43.3 | 1728.58 | 1420.16 | 2650
2025-07-21 | 7462.4096 | 722.1687 | 4381.1566 | 674.0241 | 1685.0602 | 5882.04 | 43.3 | 1728.58 | 1460.16 | 2650
2025-07-22 | 8021.3701 | 776.2616 | 4709.3205 | 724.5108 | 1811.2771 | 5933.29 | 43.3 | 1678.58 | 1561.41 | 2650
2025-07-23 | 8580.3305 | 830.3546 | 5037.4843 | 774.9976 | 1937.494 | 5753.29 | 43.3 | 1498.58 | 1561.41 | 2650
2025-07-24 | 9139.2909 | 884.4475 | 5365.6482 | 825.4843 | 2063.7108 | 5873.18 | 43.3 | 1498.58 | 1681.3 | 2650
2025-07-25 | 9698.2513 | 938.5404 | 5693.812 | 875.9711 | 2189.9277 | 7023.18 | 43.3 | 1498.58 | 1681.3 | 3800
2025-07-26 | 10257.2117 | 992.6334 | 6021.9759 | 926.4578 | 2316.1446 | 7023.18 | 43.3 | 1498.58 | 1681.3 | 3800
2025-07-27 | 10816.1721 | 1046.7263 | 6350.1398 | 976.9446 | 2442.3614 | 7115.62 | 43.3 | 1498.58 | 1773.74 | 3800
2025-07-28 | 11375.1325 | 1100.8193 | 6678.3036 | 1027.4313 | 2568.5783 | 7115.62 | 43.3 | 1498.58 | 1773.74 | 3800
2025-07-29 | 11934.0929 | 1154.9122 | 7006.4675 | 1077.9181 | 2694.7952 | 7175.62 | 43.3 | 1498.58 | 1833.74 | 3800
2025-07-30 | 12493.0534 | 1209.0052 | 7334.6313 | 1128.4048 | 2821.012 | 7175.62 | 43.3 | 1498.58 | 1833.74 | 3800
2025-07-31 | 13052.0138 | 1263.0981 | 7662.7952 | 1178.8916 | 2947.2289 | 7175.62 | 43.3 | 1498.58 | 1833.74 | 3800
2025-08-01 | 13610.9742 | 1317.191 | 7990.959 | 1229.3783 | 3073.4458 | 8538.49 | 43.3 | 1498.58 | 2146.61 | 4850
2025-08-02 | 14169.9346 | 1371.284 | 8319.1229 | 1279.8651 | 3199.6627 | 8538.49 | 43.3 | 1498.58 | 2146.61 | 4850
2025-08-03 | 14728.895 | 1425.3769 | 8647.2867 | 1330.3518 | 3325.8795 | 8538.49 | 43.3 | 1498.58 | 2146.61 | 4850
2025-08-04 | 15287.8554 | 1479.4699 | 8975.4506 | 1380.8386 | 3452.0964 | 8538.49 | 43.3 | 1498.58 | 2146.61 | 4850
2025-08-05 | 15846.8158 | 1533.5628 | 9303.6145 | 1431.3253 | 3578.3133 | 8538.49 | 43.3 | 1498.58 | 2146.61 | 4850
2025-08-06 | 16405.7762 | 1587.6558 | 9631.7783 | 1481.812 | 3704.5301 | 8538.49 | 43.3 | 1498.58 | 2146.61 | 4850
2025-08-07 | 16964.7367 | 1641.7487 | 9959.9422 | 1532.2988 | 3830.747 | 8538.49 | 43.3 | 1498.58 | 2146.61 | 4850
2025-08-08 | 17523.6971 | 1695.8417 | 10288.106 | 1582.7855 | 3956.9639 | 10288.49 | 43.3 | 1498.58 | 2146.61 | 6600
2025-08-09 | 18082.6575 | 1749.9346 | 10616.2699 | 1633.2723 | 4083.1807 | 10288.49 | 43.3 | 1498.58 | 2146.61 | 6600
2025-08-10 | 18641.6179 | 1804.0275 | 10944.4337 | 1683.759 | 4209.3976 | 10288.49 | 43.3 | 1498.58 | 2146.61 | 6600
2025-08-11 | 19200.5783 | 1858.1205 | 11272.5976 | 1734.2458 | 4335.6145 | 10288.49 | 43.3 | 1498.58 | 2146.61 | 6600
2025-08-12 | 19759.5387 | 1912.2134 | 11600.7614 | 1784.7325 | 4461.8313 | 10288.49 | 43.3 | 1498.58 | 2146.61 | 6600
2025-08-13 | 20318.4991 | 1966.3064 | 11928.9253 | 1835.2193 | 4588.0482 | 10288.49 | 43.3 | 1498.58 | 2146.61 | 6600
2025-08-14 | 20877.4596 | 2020.3993 | 12257.0892 | 1885.706 | 4714.2651 | 10288.49 | 43.3 | 1498.58 | 2146.61 | 6600
2025-08-15 | 21436.42 | 2074.4923 | 12585.253 | 1936.1928 | 4840.4819 | 12038.49 | 43.3 | 1498.58 | 2146.61 | 8350
2025-08-16 | 21995.3804 | 2128.5852 | 12913.4169 | 1986.6795 | 4966.6988 | 12038.49 | 43.3 | 1498.58 | 2146.61 | 8350
2025-08-17 | 22554.3408 | 2182.6781 | 13241.5807 | 2037.1663 | 5092.9157 | 12038.49 | 43.3 | 1498.58 | 2146.61 | 8350
2025-08-18 | 23113.3012 | 2236.7711 | 13569.7446 | 2087.653 | 5219.1325 | 12038.49 | 43.3 | 1498.58 | 2146.61 | 8350
2025-08-19 | 23672.2616 | 2290.864 | 13897.9084 | 2138.1398 | 5345.3494 | 12038.49 | 43.3 | 1498.58 | 2146.61 | 8350
2025-08-20 | 24231.222 | 2344.957 | 14226.0723 | 2188.6265 | 5471.5663 | 12038.49 | 43.3 | 1498.58 | 2146.61 | 8350
2025-08-21 | 24790.1824 | 2399.0499 | 14554.2361 | 2239.1133 | 5597.7831 | 12038.49 | 43.3 | 1498.58 | 2146.61 | 8350
2025-08-22 | 25349.1429 | 2453.1429 | 14882.4 | 2289.6 | 5724 | 12888.49 | 43.3 | 1498.58 | 2146.61 | 9200
2025-08-23 | 25827.4286 | 2499.4286 | 15163.2 | 2332.8 | 5832 | 12888.49 | 43.3 | 1498.58 | 2146.61 | 9200
2025-08-24 | 26305.7143 | 2545.7143 | 15444 | 2376 | 5940 | 12888.49 | 43.3 | 1498.58 | 2146.61 | 9200
2025-08-25 | 26784 | 2592 | 15724.8 | 2419.2 | 6048 | 12888.49 | 43.3 | 1498.58 | 2146.61 | 9200
2025-08-26 | 27262.2857 | 2638.2857 | 16005.6 | 2462.4 | 6156 | 12888.49 | 43.3 | 1498.58 | 2146.61 | 9200
2025-08-27 | 27740.5714 | 2684.5714 | 16286.4 | 2505.6 | 6264 | 12888.49 | 43.3 | 1498.58 | 2146.61 | 9200
2025-08-28 | 28218.8571 | 2730.8571 | 16567.2 | 2548.8 | 6372 | 12888.49 | 43.3 | 1498.58 | 2146.61 | 9200
2025-08-29 | 28697.1429 | 2777.1429 | 16848 | 2592 | 6480 | 13238.49 | 43.3 | 1498.58 | 2146.61 | 9550
2025-08-30 | 29175.4286 | 2823.4286 | 17128.8 | 2635.2 | 6588 | 13238.49 | 43.3 | 1498.58 | 2146.61 | 9550
2025-08-31 | 29653.7143 | 2869.7143 | 17409.6 | 2678.4 | 6696 | 13238.49 | 43.3 | 1498.58 | 2146.61 | 9550
2025-09-01 | 30132 | 2916 | 17690.4 | 2721.6 | 6804 | 0 | 0 | 0 | 0 | 0
2025-09-02 | 31118.4643 | 3011.4643 | 18269.55 | 2810.7 | 7026.75 | 0 | 0 | 0 | 0 | 0
2025-09-03 | 32104.9286 | 3106.9286 | 18848.7 | 2899.8 | 7249.5 | 0 | 0 | 0 | 0 | 0
2025-09-04 | 33091.3929 | 3202.3929 | 19427.85 | 2988.9 | 7472.25 | 0 | 0 | 0 | 0 | 0
2025-09-05 | 34077.8571 | 3297.8571 | 20007 | 3078 | 7695 | 0 | 0 | 0 | 0 | 0
2025-09-06 | 35064.3214 | 3393.3214 | 20586.15 | 3167.1 | 7917.75 | 0 | 0 | 0 | 0 | 0
2025-09-07 | 36050.7857 | 3488.7857 | 21165.3 | 3256.2 | 8140.5 | 0 | 0 | 0 | 0 | 0
2025-09-08 | 37037.25 | 3584.25 | 21744.45 | 3345.3 | 8363.25 | 0 | 0 | 0 | 0 | 0
2025-09-09 | 38023.7143 | 3679.7143 | 22323.6 | 3434.4 | 8586 | 0 | 0 | 0 | 0 | 0
2025-09-10 | 39010.1786 | 3775.1786 | 22902.75 | 3523.5 | 8808.75 | 0 | 0 | 0 | 0 | 0
2025-09-11 | 39996.6429 | 3870.6429 | 23481.9 | 3612.6 | 9031.5 | 0 | 0 | 0 | 0 | 0
2025-09-12 | 40983.1071 | 3966.1071 | 24061.05 | 3701.7 | 9254.25 | 0 | 0 | 0 | 0 | 0
2025-09-13 | 41969.5714 | 4061.5714 | 24640.2 | 3790.8 | 9477 | 0 | 0 | 0 | 0 | 0
2025-09-14 | 42956.0357 | 4157.0357 | 25219.35 | 3879.9 | 9699.75 | 0 | 0 | 0 | 0 | 0
2025-09-15 | 43942.5 | 4252.5 | 25798.5 | 3969 | 9922.5 | 0 | 0 | 0 | 0 | 0
2025-09-16 | 44928.9643 | 4347.9643 | 26377.65 | 4058.1 | 10145.25 | 0 | 0 | 0 | 0 | 0
2025-09-17 | 45915.4286 | 4443.4286 | 26956.8 | 4147.2 | 10368 | 0 | 0 | 0 | 0 | 0
2025-09-18 | 46901.8929 | 4538.8929 | 27535.95 | 4236.3 | 10590.75 | 0 | 0 | 0 | 0 | 0
2025-09-19 | 47888.3571 | 4634.3571 | 28115.1 | 4325.4 | 10813.5 | 0 | 0 | 0 | 0 | 0
2025-09-20 | 48874.8214 | 4729.8214 | 28694.25 | 4414.5 | 11036.25 | 0 | 0 | 0 | 0 | 0
2025-09-21 | 49861.2857 | 4825.2857 | 29273.4 | 4503.6 | 11259 | 0 | 0 | 0 | 0 | 0
2025-09-22 | 50847.75 | 4920.75 | 29852.55 | 4592.7 | 11481.75 | 0 | 0 | 0 | 0 | 0
2025-09-23 | 51834.2143 | 5016.2143 | 30431.7 | 4681.8 | 11704.5 | 0 | 0 | 0 | 0 | 0
2025-09-24 | 52820.6786 | 5111.6786 | 31010.85 | 4770.9 | 11927.25 | 0 | 0 | 0 | 0 | 0
2025-09-25 | 53807.1429 | 5207.1429 | 31590 | 4860 | 12150 | 0 | 0 | 0 | 0 | 0
2025-09-26 | 54793.6071 | 5302.6071 | 32169.15 | 4949.1 | 12372.75 | 0 | 0 | 0 | 0 | 0
2025-09-27 | 55780.0714 | 5398.0714 | 32748.3 | 5038.2 | 12595.5 | 0 | 0 | 0 | 0 | 0
2025-09-28 | 56766.5357 | 5493.5357 | 33327.45 | 5127.3 | 12818.25 | 0 | 0 | 0 | 0 | 0
2025-09-29 | 57753 | 5589 | 33906.6 | 5216.4 | 13041 | 0 | 0 | 0 | 0 | 0
2025-09-30 | 58739.4643 | 5684.4643 | 34485.75 | 5305.5 | 13263.75 | 0 | 0 | 0 | 0 | 0
2025-10-01 | 59725.9286 | 5779.9286 | 35064.9 | 5394.6 | 13486.5 | 0 | 0 | 0 | 0 | 0
2025-10-02 | 60712.3929 | 5875.3929 | 35644.05 | 5483.7 | 13709.25 | 0 | 0 | 0 | 0 | 0
2025-10-03 | 61698.8571 | 5970.8571 | 36223.2 | 5572.8 | 13932 | 0 | 0 | 0 | 0 | 0
2025-10-04 | 62685.3214 | 6066.3214 | 36802.35 | 5661.9 | 14154.75 | 0 | 0 | 0 | 0 | 0
2025-10-05 | 63671.7857 | 6161.7857 | 37381.5 | 5751 | 14377.5 | 0 | 0 | 0 | 0 | 0
2025-10-06 | 64658.25 | 6257.25 | 37960.65 | 5840.1 | 14600.25 | 0 | 0 | 0 | 0 | 0
2025-10-07 | 65644.7143 | 6352.7143 | 38539.8 | 5929.2 | 14823 | 0 | 0 | 0 | 0 | 0
2025-10-08 | 66631.1786 | 6448.1786 | 39118.95 | 6018.3 | 15045.75 | 0 | 0 | 0 | 0 | 0
2025-10-09 | 67617.6429 | 6543.6429 | 39698.1 | 6107.4 | 15268.5 | 0 | 0 | 0 | 0 | 0
2025-10-10 | 68604.1071 | 6639.1071 | 40277.25 | 6196.5 | 15491.25 | 0 | 0 | 0 | 0 | 0
2025-10-11 | 69590.5714 | 6734.5714 | 40856.4 | 6285.6 | 15714 | 0 | 0 | 0 | 0 | 0
2025-10-12 | 70577.0357 | 6830.0357 | 41435.55 | 6374.7 | 15936.75 | 0 | 0 | 0 | 0 | 0
2025-10-13 | 71563.5 | 6925.5 | 42014.7 | 6463.8 | 16159.5 | 0 | 0 | 0 | 0 | 0
2025-10-14 | 72549.9643 | 7020.9643 | 42593.85 | 6552.9 | 16382.25 | 0 | 0 | 0 | 0 | 0
2025-10-15 | 73536.4286 | 7116.4286 | 43173 | 6642 | 16605 | 0 | 0 | 0 | 0 | 0
2025-10-16 | 74522.8929 | 7211.8929 | 43752.15 | 6731.1 | 16827.75 | 0 | 0 | 0 | 0 | 0
2025-10-17 | 75509.3571 | 7307.3571 | 44331.3 | 6820.2 | 17050.5 | 0 | 0 | 0 | 0 | 0
2025-10-18 | 76495.8214 | 7402.8214 | 44910.45 | 6909.3 | 17273.25 | 0 | 0 | 0 | 0 | 0
2025-10-19 | 77482.2857 | 7498.2857 | 45489.6 | 6998.4 | 17496 | 0 | 0 | 0 | 0 | 0
2025-10-20 | 78468.75 | 7593.75 | 46068.75 | 7087.5 | 17718.75 | 0 | 0 | 0 | 0 | 0
2025-10-21 | 79455.2143 | 7689.2143 | 46647.9 | 7176.6 | 17941.5 | 0 | 0 | 0 | 0 | 0
2025-10-22 | 80441.6786 | 7784.6786 | 47227.05 | 7265.7 | 18164.25 | 0 | 0 | 0 | 0 | 0
2025-10-23 | 81428.1429 | 7880.1429 | 47806.2 | 7354.8 | 18387 | 0 | 0 | 0 | 0 | 0
2025-10-24 | 82414.6071 | 7975.6071 | 48385.35 | 7443.9 | 18609.75 | 0 | 0 | 0 | 0 | 0
2025-10-25 | 83401.0714 | 8071.0714 | 48964.5 | 7533 | 18832.5 | 0 | 0 | 0 | 0 | 0
2025-10-26 | 84387.5357 | 8166.5357 | 49543.65 | 7622.1 | 19055.25 | 0 | 0 | 0 | 0 | 0
2025-10-27 | 85374 | 8262 | 50122.8 | 7711.2 | 19278 | 0 | 0 | 0 | 0 | 0
2025-10-28 | 86038.9798 | 8326.3529 | 50513.2075 | 7771.2627 | 19428.1567 | 0 | 0 | 0 | 0 | 0
2025-10-29 | 86703.9595 | 8390.7058 | 50903.6149 | 7831.3254 | 19578.3134 | 0 | 0 | 0 | 0 | 0
2025-10-30 | 87368.9393 | 8455.0586 | 51294.0224 | 7891.3881 | 19728.4702 | 0 | 0 | 0 | 0 | 0
2025-10-31 | 88033.919 | 8519.4115 | 51684.4299 | 7951.4508 | 19878.6269 | 0 | 0 | 0 | 0 | 0
2025-11-01 | 88698.8988 | 8583.7644 | 52074.8374 | 8011.5134 | 20028.7836 | 0 | 0 | 0 | 0 | 0
2025-11-02 | 89363.8786 | 8648.1173 | 52465.2448 | 8071.5761 | 20178.9403 | 0 | 0 | 0 | 0 | 0
2025-11-03 | 90028.8583 | 8712.4702 | 52855.6523 | 8131.6388 | 20329.097 | 0 | 0 | 0 | 0 | 0
2025-11-04 | 90693.8381 | 8776.823 | 53246.0598 | 8191.7015 | 20479.2538 | 0 | 0 | 0 | 0 | 0
2025-11-05 | 91358.8178 | 8841.1759 | 53636.4672 | 8251.7642 | 20629.4105 | 0 | 0 | 0 | 0 | 0
2025-11-06 | 92023.7976 | 8905.5288 | 54026.8747 | 8311.8269 | 20779.5672 | 0 | 0 | 0 | 0 | 0
2025-11-07 | 92688.7774 | 8969.8817 | 54417.2822 | 8371.8896 | 20929.7239 | 0 | 0 | 0 | 0 | 0
2025-11-08 | 93353.7571 | 9034.2346 | 54807.6897 | 8431.9523 | 21079.8806 | 0 | 0 | 0 | 0 | 0
2025-11-09 | 94018.7369 | 9098.5874 | 55198.0971 | 8492.0149 | 21230.0374 | 0 | 0 | 0 | 0 | 0
2025-11-10 | 94683.7166 | 9162.9403 | 55588.5046 | 8552.0776 | 21380.1941 | 0 | 0 | 0 | 0 | 0
2025-11-11 | 95348.6964 | 9227.2932 | 55978.9121 | 8612.1403 | 21530.3508 | 0 | 0 | 0 | 0 | 0
2025-11-12 | 96013.6762 | 9291.6461 | 56369.3196 | 8672.203 | 21680.5075 | 0 | 0 | 0 | 0 | 0
2025-11-13 | 96678.6559 | 9355.999 | 56759.727 | 8732.2657 | 21830.6642 | 0 | 0 | 0 | 0 | 0
2025-11-14 | 97343.6357 | 9420.3518 | 57150.1345 | 8792.3284 | 21980.821 | 0 | 0 | 0 | 0 | 0
2025-11-15 | 98008.6154 | 9484.7047 | 57540.542 | 8852.3911 | 22130.9777 | 0 | 0 | 0 | 0 | 0
2025-11-16 | 98673.5952 | 9549.0576 | 57930.9494 | 8912.4538 | 22281.1344 | 0 | 0 | 0 | 0 | 0
2025-11-17 | 99338.575 | 9613.4105 | 58321.3569 | 8972.5164 | 22431.2911 | 0 | 0 | 0 | 0 | 0
2025-11-18 | 100003.5547 | 9677.7634 | 58711.7644 | 9032.5791 | 22581.4478 | 0 | 0 | 0 | 0 | 0
2025-11-19 | 100668.5345 | 9742.1162 | 59102.1719 | 9092.6418 | 22731.6046 | 0 | 0 | 0 | 0 | 0
2025-11-20 | 101333.5142 | 9806.4691 | 59492.5793 | 9152.7045 | 22881.7613 | 0 | 0 | 0 | 0 | 0
2025-11-21 | 101998.494 | 9870.822 | 59882.9868 | 9212.7672 | 23031.918 | 0 | 0 | 0 | 0 | 0
2025-11-22 | 102663.4738 | 9935.1749 | 60273.3943 | 9272.8299 | 23182.0747 | 0 | 0 | 0 | 0 | 0
2025-11-23 | 103328.4535 | 9999.5278 | 60663.8017 | 9332.8926 | 23332.2314 | 0 | 0 | 0 | 0 | 0
2025-11-24 | 103993.4333 | 10063.8806 | 61054.2092 | 9392.9553 | 23482.3882 | 0 | 0 | 0 | 0 | 0
2025-11-25 | 104658.413 | 10128.2335 | 61444.6167 | 9453.018 | 23632.5449 | 0 | 0 | 0 | 0 | 0
2025-11-26 | 105323.3928 | 10192.5864 | 61835.0242 | 9513.0806 | 23782.7016 | 0 | 0 | 0 | 0 | 0
2025-11-27 | 105988.3726 | 10256.9393 | 62225.4316 | 9573.1433 | 23932.8583 | 0 | 0 | 0 | 0 | 0
2025-11-28 | 106653.3523 | 10321.2922 | 62615.8391 | 9633.206 | 24083.015 | 0 | 0 | 0 | 0 | 0
2025-11-29 | 107318.3321 | 10385.645 | 63006.2466 | 9693.2687 | 24233.1718 | 0 | 0 | 0 | 0 | 0
2025-11-30 | 107983.3118 | 10449.9979 | 63396.654 | 9753.3314 | 24383.3285 | 0 | 0 | 0 | 0 | 0
2025-12-01 | 108648.2916 | 10514.3508 | 63787.0615 | 9813.3941 | 24533.4852 | 0 | 0 | 0 | 0 | 0
2025-12-02 | 109313.2714 | 10578.7037 | 64177.469 | 9873.4568 | 24683.6419 | 0 | 0 | 0 | 0 | 0
2025-12-03 | 109978.2511 | 10643.0566 | 64567.8765 | 9933.5195 | 24833.7986 | 0 | 0 | 0 | 0 | 0
2025-12-04 | 110643.2309 | 10707.4094 | 64958.2839 | 9993.5821 | 24983.9554 | 0 | 0 | 0 | 0 | 0
2025-12-05 | 111308.2106 | 10771.7623 | 65348.6914 | 10053.6448 | 25134.1121 | 0 | 0 | 0 | 0 | 0
2025-12-06 | 111973.1904 | 10836.1152 | 65739.0989 | 10113.7075 | 25284.2688 | 0 | 0 | 0 | 0 | 0
2025-12-07 | 112638.1702 | 10900.4681 | 66129.5064 | 10173.7702 | 25434.4255 | 0 | 0 | 0 | 0 | 0
2025-12-08 | 113303.1499 | 10964.821 | 66519.9138 | 10233.8329 | 25584.5822 | 0 | 0 | 0 | 0 | 0
2025-12-09 | 113968.1297 | 11029.1738 | 66910.3213 | 10293.8956 | 25734.739 | 0 | 0 | 0 | 0 | 0
2025-12-10 | 114633.1094 | 11093.5267 | 67300.7288 | 10353.9583 | 25884.8957 | 0 | 0 | 0 | 0 | 0
2025-12-11 | 115298.0892 | 11157.8796 | 67691.1362 | 10414.021 | 26035.0524 | 0 | 0 | 0 | 0 | 0
2025-12-12 | 115963.069 | 11222.2325 | 68081.5437 | 10474.0836 | 26185.2091 | 0 | 0 | 0 | 0 | 0
2025-12-13 | 116628.0487 | 11286.5854 | 68471.9512 | 10534.1463 | 26335.3658 | 0 | 0 | 0 | 0 | 0
2025-12-14 | 117293.0285 | 11350.9382 | 68862.3587 | 10594.209 | 26485.5226 | 0 | 0 | 0 | 0 | 0
2025-12-15 | 117958.0082 | 11415.2911 | 69252.7661 | 10654.2717 | 26635.6793 | 0 | 0 | 0 | 0 | 0
2025-12-16 | 118622.988 | 11479.644 | 69643.1736 | 10714.3344 | 26785.836 | 0 | 0 | 0 | 0 | 0
2025-12-17 | 119287.9678 | 11543.9969 | 70033.5811 | 10774.3971 | 26935.9927 | 0 | 0 | 0 | 0 | 0
2025-12-18 | 119952.9475 | 11608.3498 | 70423.9885 | 10834.4598 | 27086.1494 | 0 | 0 | 0 | 0 | 0
2025-12-19 | 120617.9273 | 11672.7026 | 70814.396 | 10894.5225 | 27236.3062 | 0 | 0 | 0 | 0 | 0
2025-12-20 | 121282.907 | 11737.0555 | 71204.8035 | 10954.5852 | 27386.4629 | 0 | 0 | 0 | 0 | 0
2025-12-21 | 121947.8868 | 11801.4084 | 71595.211 | 11014.6478 | 27536.6196 | 0 | 0 | 0 | 0 | 0
2025-12-22 | 122612.8666 | 11865.7613 | 71985.6184 | 11074.7105 | 27686.7763 | 0 | 0 | 0 | 0 | 0
2025-12-23 | 123277.8463 | 11930.1142 | 72376.0259 | 11134.7732 | 27836.933 | 0 | 0 | 0 | 0 | 0
2025-12-24 | 123942.8261 | 11994.467 | 72766.4334 | 11194.8359 | 27987.0898 | 0 | 0 | 0 | 0 | 0
2025-12-25 | 124607.8058 | 12058.8199 | 73156.8408 | 11254.8986 | 28137.2465 | 0 | 0 | 0 | 0 | 0
2025-12-26 | 125272.7856 | 12123.1728 | 73547.2483 | 11314.9613 | 28287.4032 | 0 | 0 | 0 | 0 | 0
2025-12-27 | 125937.7654 | 12187.5257 | 73937.6558 | 11375.024 | 28437.5599 | 0 | 0 | 0 | 0 | 0
2025-12-28 | 126602.7451 | 12251.8786 | 74328.0633 | 11435.0867 | 28587.7166 | 0 | 0 | 0 | 0 | 0
2025-12-29 | 127267.7249 | 12316.2314 | 74718.4707 | 11495.1493 | 28737.8734 | 0 | 0 | 0 | 0 | 0
2025-12-30 | 127932.7046 | 12380.5843 | 75108.8782 | 11555.212 | 28888.0301 | 0 | 0 | 0 | 0 | 0
2025-12-31 | 128597.6844 | 12444.9372 | 75499.2857 | 11615.2747 | 29038.1868 | 0 | 0 | 0 | 0 | 0
2026-01-01 | 129262.6642 | 12509.2901 | 75889.6932 | 11675.3374 | 29188.3435 | 0 | 0 | 0 | 0 | 0
2026-01-02 | 129927.6439 | 12573.643 | 76280.1006 | 11735.4001 | 29338.5002 | 0 | 0 | 0 | 0 | 0
2026-01-03 | 130592.6237 | 12637.9958 | 76670.5081 | 11795.4628 | 29488.657 | 0 | 0 | 0 | 0 | 0
2026-01-04 | 131257.6034 | 12702.3487 | 77060.9156 | 11855.5255 | 29638.8137 | 0 | 0 | 0 | 0 | 0
2026-01-05 | 131922.5832 | 12766.7016 | 77451.323 | 11915.5882 | 29788.9704 | 0 | 0 | 0 | 0 | 0
2026-01-06 | 132587.563 | 12831.0545 | 77841.7305 | 11975.6508 | 29939.1271 | 0 | 0 | 0 | 0 | 0
2026-01-07 | 133252.5427 | 12895.4074 | 78232.138 | 12035.7135 | 30089.2838 | 0 | 0 | 0 | 0 | 0
2026-01-08 | 133917.5225 | 12959.7602 | 78622.5455 | 12095.7762 | 30239.4406 | 0 | 0 | 0 | 0 | 0
2026-01-09 | 134582.5022 | 13024.1131 | 79012.9529 | 12155.8389 | 30389.5973 | 0 | 0 | 0 | 0 | 0
2026-01-10 | 135247.482 | 13088.466 | 79403.3604 | 12215.9016 | 30539.754 | 0 | 0 | 0 | 0 | 0
2026-01-11 | 135912.4618 | 13152.8189 | 79793.7679 | 12275.9643 | 30689.9107 | 0 | 0 | 0 | 0 | 0
2026-01-12 | 136577.4415 | 13217.1718 | 80184.1753 | 12336.027 | 30840.0674 | 0 | 0 | 0 | 0 | 0
2026-01-13 | 137242.4213 | 13281.5246 | 80574.5828 | 12396.0897 | 30990.2242 | 0 | 0 | 0 | 0 | 0
2026-01-14 | 137907.401 | 13345.8775 | 80964.9903 | 12456.1524 | 31140.3809 | 0 | 0 | 0 | 0 | 0
2026-01-15 | 138572.3808 | 13410.2304 | 81355.3978 | 12516.215 | 31290.5376 | 0 | 0 | 0 | 0 | 0
2026-01-16 | 139237.3606 | 13474.5833 | 81745.8052 | 12576.2777 | 31440.6943 | 0 | 0 | 0 | 0 | 0
2026-01-17 | 139902.3403 | 13538.9362 | 82136.2127 | 12636.3404 | 31590.851 | 0 | 0 | 0 | 0 | 0
2026-01-18 | 140567.3201 | 13603.289 | 82526.6202 | 12696.4031 | 31741.0078 | 0 | 0 | 0 | 0 | 0
2026-01-19 | 141232.2998 | 13667.6419 | 82917.0276 | 12756.4658 | 31891.1645 | 0 | 0 | 0 | 0 | 0
2026-01-20 | 141897.2796 | 13731.9948 | 83307.4351 | 12816.5285 | 32041.3212 | 0 | 0 | 0 | 0 | 0
2026-01-21 | 142562.2594 | 13796.3477 | 83697.8426 | 12876.5912 | 32191.4779 | 0 | 0 | 0 | 0 | 0
2026-01-22 | 143227.2391 | 13860.7006 | 84088.2501 | 12936.6539 | 32341.6346 | 0 | 0 | 0 | 0 | 0
2026-01-23 | 143892.2189 | 13925.0534 | 84478.6575 | 12996.7165 | 32491.7914 | 0 | 0 | 0 | 0 | 0
2026-01-24 | 144557.1986 | 13989.4063 | 84869.065 | 13056.7792 | 32641.9481 | 0 | 0 | 0 | 0 | 0
2026-01-25 | 145222.1784 | 14053.7592 | 85259.4725 | 13116.8419 | 32792.1048 | 0 | 0 | 0 | 0 | 0
2026-01-26 | 145887.1582 | 14118.1121 | 85649.88 | 13176.9046 | 32942.2615 | 0 | 0 | 0 | 0 | 0
2026-01-27 | 146552.1379 | 14182.465 | 86040.2874 | 13236.9673 | 33092.4182 | 0 | 0 | 0 | 0 | 0
2026-01-28 | 147217.1177 | 14246.8178 | 86430.6949 | 13297.03 | 33242.575 | 0 | 0 | 0 | 0 | 0
2026-01-29 | 147882.0974 | 14311.1707 | 86821.1024 | 13357.0927 | 33392.7317 | 0 | 0 | 0 | 0 | 0
2026-01-30 | 148547.0772 | 14375.5236 | 87211.5098 | 13417.1554 | 33542.8884 | 0 | 0 | 0 | 0 | 0
2026-01-31 | 149212.057 | 14439.8765 | 87601.9173 | 13477.218 | 33693.0451 | 0 | 0 | 0 | 0 | 0
2026-02-01 | 149877.0367 | 14504.2294 | 87992.3248 | 13537.2807 | 33843.2018 | 0 | 0 | 0 | 0 | 0
2026-02-02 | 150542.0165 | 14568.5822 | 88382.7323 | 13597.3434 | 33993.3586 | 0 | 0 | 0 | 0 | 0
2026-02-03 | 151206.9962 | 14632.9351 | 88773.1397 | 13657.4061 | 34143.5153 | 0 | 0 | 0 | 0 | 0
2026-02-04 | 151871.976 | 14697.288 | 89163.5472 | 13717.4688 | 34293.672 | 0 | 0 | 0 | 0 | 0
2026-02-05 | 152536.9558 | 14761.6409 | 89553.9547 | 13777.5315 | 34443.8287 | 0 | 0 | 0 | 0 | 0
2026-02-06 | 153201.9355 | 14825.9938 | 89944.3621 | 13837.5942 | 34593.9854 | 0 | 0 | 0 | 0 | 0
2026-02-07 | 153866.9153 | 14890.3466 | 90334.7696 | 13897.6569 | 34744.1422 | 0 | 0 | 0 | 0 | 0
2026-02-08 | 154531.895 | 14954.6995 | 90725.1771 | 13957.7196 | 34894.2989 | 0 | 0 | 0 | 0 | 0
2026-02-09 | 155196.8748 | 15019.0524 | 91115.5846 | 14017.7822 | 35044.4556 | 0 | 0 | 0 | 0 | 0
2026-02-10 | 155861.8546 | 15083.4053 | 91505.992 | 14077.8449 | 35194.6123 | 0 | 0 | 0 | 0 | 0
2026-02-11 | 156526.8343 | 15147.7582 | 91896.3995 | 14137.9076 | 35344.769 | 0 | 0 | 0 | 0 | 0
2026-02-12 | 157191.8141 | 15212.111 | 92286.807 | 14197.9703 | 35494.9258 | 0 | 0 | 0 | 0 | 0
2026-02-13 | 157856.7938 | 15276.4639 | 92677.2144 | 14258.033 | 35645.0825 | 0 | 0 | 0 | 0 | 0
2026-02-14 | 158521.7736 | 15340.8168 | 93067.6219 | 14318.0957 | 35795.2392 | 0 | 0 | 0 | 0 | 0
2026-02-15 | 159186.7534 | 15405.1697 | 93458.0294 | 14378.1584 | 35945.3959 | 0 | 0 | 0 | 0 | 0
2026-02-16 | 159851.7331 | 15469.5226 | 93848.4369 | 14438.2211 | 36095.5526 | 0 | 0 | 0 | 0 | 0
2026-02-17 | 160516.7129 | 15533.8754 | 94238.8443 | 14498.2837 | 36245.7094 | 0 | 0 | 0 | 0 | 0
2026-02-18 | 161181.6926 | 15598.2283 | 94629.2518 | 14558.3464 | 36395.8661 | 0 | 0 | 0 | 0 | 0
2026-02-19 | 161846.6724 | 15662.5812 | 95019.6593 | 14618.4091 | 36546.0228 | 0 | 0 | 0 | 0 | 0
2026-02-20 | 162511.6522 | 15726.9341 | 95410.0668 | 14678.4718 | 36696.1795 | 0 | 0 | 0 | 0 | 0
2026-02-21 | 163176.6319 | 15791.287 | 95800.4742 | 14738.5345 | 36846.3362 | 0 | 0 | 0 | 0 | 0
2026-02-22 | 163841.6117 | 15855.6398 | 96190.8817 | 14798.5972 | 36996.493 | 0 | 0 | 0 | 0 | 0
2026-02-23 | 164506.5914 | 15919.9927 | 96581.2892 | 14858.6599 | 37146.6497 | 0 | 0 | 0 | 0 | 0
2026-02-24 | 165171.5712 | 15984.3456 | 96971.6966 | 14918.7226 | 37296.8064 | 0 | 0 | 0 | 0 | 0
2026-02-25 | 165836.551 | 16048.6985 | 97362.1041 | 14978.7852 | 37446.9631 | 0 | 0 | 0 | 0 | 0
2026-02-26 | 166501.5307 | 16113.0514 | 97752.5116 | 15038.8479 | 37597.1198 | 0 | 0 | 0 | 0 | 0
2026-02-27 | 167166.5105 | 16177.4042 | 98142.9191 | 15098.9106 | 37747.2766 | 0 | 0 | 0 | 0 | 0
2026-02-28 | 167831.4902 | 16241.7571 | 98533.3265 | 15158.9733 | 37897.4333 | 0 | 0 | 0 | 0 | 0
2026-03-01 | 168496.47 | 16306.11 | 98923.734 | 15219.036 | 38047.59 | 0 | 0 | 0 | 0 | 0
2026-03-02 | 169161.4498 | 16370.4629 | 99314.1415 | 15279.0987 | 38197.7467 | 0 | 0 | 0 | 0 | 0
2026-03-03 | 169826.4295 | 16434.8158 | 99704.5489 | 15339.1614 | 38347.9034 | 0 | 0 | 0 | 0 | 0
2026-03-04 | 170491.4093 | 16499.1686 | 100094.9564 | 15399.2241 | 38498.0602 | 0 | 0 | 0 | 0 | 0
2026-03-05 | 171156.389 | 16563.5215 | 100485.3639 | 15459.2868 | 38648.2169 | 0 | 0 | 0 | 0 | 0
2026-03-06 | 171821.3688 | 16627.8744 | 100875.7714 | 15519.3494 | 38798.3736 | 0 | 0 | 0 | 0 | 0
2026-03-07 | 172486.3486 | 16692.2273 | 101266.1788 | 15579.4121 | 38948.5303 | 0 | 0 | 0 | 0 | 0
2026-03-08 | 173151.3283 | 16756.5802 | 101656.5863 | 15639.4748 | 39098.687 | 0 | 0 | 0 | 0 | 0
2026-03-09 | 173816.3081 | 16820.933 | 102046.9938 | 15699.5375 | 39248.8438 | 0 | 0 | 0 | 0 | 0
2026-03-10 | 174481.2878 | 16885.2859 | 102437.4012 | 15759.6002 | 39399.0005 | 0 | 0 | 0 | 0 | 0
2026-03-11 | 175146.2676 | 16949.6388 | 102827.8087 | 15819.6629 | 39549.1572 | 0 | 0 | 0 | 0 | 0
2026-03-12 | 175811.2474 | 17013.9917 | 103218.2162 | 15879.7256 | 39699.3139 | 0 | 0 | 0 | 0 | 0
2026-03-13 | 176476.2271 | 17078.3446 | 103608.6237 | 15939.7883 | 39849.4706 | 0 | 0 | 0 | 0 | 0
2026-03-14 | 177141.2069 | 17142.6974 | 103999.0311 | 15999.8509 | 39999.6274 | 0 | 0 | 0 | 0 | 0
2026-03-15 | 177806.1866 | 17207.0503 | 104389.4386 | 16059.9136 | 40149.7841 | 0 | 0 | 0 | 0 | 0
2026-03-16 | 178471.1664 | 17271.4032 | 104779.8461 | 16119.9763 | 40299.9408 | 0 | 0 | 0 | 0 | 0
2026-03-17 | 179136.1462 | 17335.7561 | 105170.2536 | 16180.039 | 40450.0975 | 0 | 0 | 0 | 0 | 0
2026-03-18 | 179801.1259 | 17400.109 | 105560.661 | 16240.1017 | 40600.2542 | 0 | 0 | 0 | 0 | 0
2026-03-19 | 180466.1057 | 17464.4618 | 105951.0685 | 16300.1644 | 40750.411 | 0 | 0 | 0 | 0 | 0
2026-03-20 | 181131.0854 | 17528.8147 | 106341.476 | 16360.2271 | 40900.5677 | 0 | 0 | 0 | 0 | 0
2026-03-21 | 181796.0652 | 17593.1676 | 106731.8834 | 16420.2898 | 41050.7244 | 0 | 0 | 0 | 0 | 0
2026-03-22 | 182461.045 | 17657.5205 | 107122.2909 | 16480.3524 | 41200.8811 | 0 | 0 | 0 | 0 | 0
2026-03-23 | 183126.0247 | 17721.8734 | 107512.6984 | 16540.4151 | 41351.0378 | 0 | 0 | 0 | 0 | 0
2026-03-24 | 183791.0045 | 17786.2262 | 107903.1059 | 16600.4778 | 41501.1946 | 0 | 0 | 0 | 0 | 0
2026-03-25 | 184455.9842 | 17850.5791 | 108293.5133 | 16660.5405 | 41651.3513 | 0 | 0 | 0 | 0 | 0
2026-03-26 | 185120.964 | 17914.932 | 108683.9208 | 16720.6032 | 41801.508 | 0 | 0 | 0 | 0 | 0
2026-03-27 | 185785.9438 | 17979.2849 | 109074.3283 | 16780.6659 | 41951.6647 | 0 | 0 | 0 | 0 | 0
2026-03-28 | 186450.9235 | 18043.6378 | 109464.7357 | 16840.7286 | 42101.8214 | 0 | 0 | 0 | 0 | 0
2026-03-29 | 187115.9033 | 18107.9906 | 109855.1432 | 16900.7913 | 42251.9782 | 0 | 0 | 0 | 0 | 0
2026-03-30 | 187780.883 | 18172.3435 | 110245.5507 | 16960.854 | 42402.1349 | 0 | 0 | 0 | 0 | 0
2026-03-31 | 188445.8628 | 18236.6964 | 110635.9582 | 17020.9166 | 42552.2916 | 0 | 0 | 0 | 0 | 0
2026-04-01 | 189110.8426 | 18301.0493 | 111026.3656 | 17080.9793 | 42702.4483 | 0 | 0 | 0 | 0 | 0
2026-04-02 | 189775.8223 | 18365.4022 | 111416.7731 | 17141.042 | 42852.605 | 0 | 0 | 0 | 0 | 0
2026-04-03 | 190440.8021 | 18429.755 | 111807.1806 | 17201.1047 | 43002.7618 | 0 | 0 | 0 | 0 | 0
2026-04-04 | 191105.7818 | 18494.1079 | 112197.588 | 17261.1674 | 43152.9185 | 0 | 0 | 0 | 0 | 0
2026-04-05 | 191770.7616 | 18558.4608 | 112587.9955 | 17321.2301 | 43303.0752 | 0 | 0 | 0 | 0 | 0
2026-04-06 | 192435.7414 | 18622.8137 | 112978.403 | 17381.2928 | 43453.2319 | 0 | 0 | 0 | 0 | 0
2026-04-07 | 193100.7211 | 18687.1666 | 113368.8105 | 17441.3555 | 43603.3886 | 0 | 0 | 0 | 0 | 0
2026-04-08 | 193765.7009 | 18751.5194 | 113759.2179 | 17501.4181 | 43753.5454 | 0 | 0 | 0 | 0 | 0
2026-04-09 | 194430.6806 | 18815.8723 | 114149.6254 | 17561.4808 | 43903.7021 | 0 | 0 | 0 | 0 | 0
2026-04-10 | 195095.6604 | 18880.2252 | 114540.0329 | 17621.5435 | 44053.8588 | 0 | 0 | 0 | 0 | 0
2026-04-11 | 195760.6402 | 18944.5781 | 114930.4404 | 17681.6062 | 44204.0155 | 0 | 0 | 0 | 0 | 0
2026-04-12 | 196425.6199 | 19008.931 | 115320.8478 | 17741.6689 | 44354.1722 | 0 | 0 | 0 | 0 | 0
2026-04-13 | 197090.5997 | 19073.2838 | 115711.2553 | 17801.7316 | 44504.329 | 0 | 0 | 0 | 0 | 0
2026-04-14 | 197755.5794 | 19137.6367 | 116101.6628 | 17861.7943 | 44654.4857 | 0 | 0 | 0 | 0 | 0
2026-04-15 | 198420.5592 | 19201.9896 | 116492.0702 | 17921.857 | 44804.6424 | 0 | 0 | 0 | 0 | 0
2026-04-16 | 199085.539 | 19266.3425 | 116882.4777 | 17981.9196 | 44954.7991 | 0 | 0 | 0 | 0 | 0
2026-04-17 | 199750.5187 | 19330.6954 | 117272.8852 | 18041.9823 | 45104.9558 | 0 | 0 | 0 | 0 | 0
2026-04-18 | 200415.4985 | 19395.0482 | 117663.2927 | 18102.045 | 45255.1126 | 0 | 0 | 0 | 0 | 0
2026-04-19 | 201080.4782 | 19459.4011 | 118053.7001 | 18162.1077 | 45405.2693 | 0 | 0 | 0 | 0 | 0
2026-04-20 | 201745.458 | 19523.754 | 118444.1076 | 18222.1704 | 45555.426 | 0 | 0 | 0 | 0 | 0
2026-04-21 | 202410.4378 | 19588.1069 | 118834.5151 | 18282.2331 | 45705.5827 | 0 | 0 | 0 | 0 | 0
2026-04-22 | 203075.4175 | 19652.4598 | 119224.9225 | 18342.2958 | 45855.7394 | 0 | 0 | 0 | 0 | 0
2026-04-23 | 203740.3973 | 19716.8126 | 119615.33 | 18402.3585 | 46005.8962 | 0 | 0 | 0 | 0 | 0
2026-04-24 | 204405.377 | 19781.1655 | 120005.7375 | 18462.4212 | 46156.0529 | 0 | 0 | 0 | 0 | 0
2026-04-25 | 205070.3568 | 19845.5184 | 120396.145 | 18522.4838 | 46306.2096 | 0 | 0 | 0 | 0 | 0
2026-04-26 | 205735.3366 | 19909.8713 | 120786.5524 | 18582.5465 | 46456.3663 | 0 | 0 | 0 | 0 | 0
2026-04-27 | 206400.3163 | 19974.2242 | 121176.9599 | 18642.6092 | 46606.523 | 0 | 0 | 0 | 0 | 0
2026-04-28 | 207065.2961 | 20038.577 | 121567.3674 | 18702.6719 | 46756.6798 | 0 | 0 | 0 | 0 | 0
2026-04-29 | 207730.2758 | 20102.9299 | 121957.7748 | 18762.7346 | 46906.8365 | 0 | 0 | 0 | 0 | 0
2026-04-30 | 208395.2556 | 20167.2828 | 122348.1823 | 18822.7973 | 47056.9932 | 0 | 0 | 0 | 0 | 0
2026-05-01 | 209060.2354 | 20231.6357 | 122738.5898 | 18882.86 | 47207.1499 | 0 | 0 | 0 | 0 | 0
2026-05-02 | 209725.2151 | 20295.9886 | 123128.9973 | 18942.9227 | 47357.3066 | 0 | 0 | 0 | 0 | 0
2026-05-03 | 210390.1949 | 20360.3414 | 123519.4047 | 19002.9853 | 47507.4634 | 0 | 0 | 0 | 0 | 0
2026-05-04 | 211055.1746 | 20424.6943 | 123909.8122 | 19063.048 | 47657.6201 | 0 | 0 | 0 | 0 | 0
2026-05-05 | 211720.1544 | 20489.0472 | 124300.2197 | 19123.1107 | 47807.7768 | 0 | 0 | 0 | 0 | 0
2026-05-06 | 212385.1342 | 20553.4001 | 124690.6272 | 19183.1734 | 47957.9335 | 0 | 0 | 0 | 0 | 0
2026-05-07 | 213050.1139 | 20617.753 | 125081.0346 | 19243.2361 | 48108.0902 | 0 | 0 | 0 | 0 | 0
2026-05-08 | 213715.0937 | 20682.1058 | 125471.4421 | 19303.2988 | 48258.247 | 0 | 0 | 0 | 0 | 0
2026-05-09 | 214380.0734 | 20746.4587 | 125861.8496 | 19363.3615 | 48408.4037 | 0 | 0 | 0 | 0 | 0
2026-05-10 | 215045.0532 | 20810.8116 | 126252.257 | 19423.4242 | 48558.5604 | 0 | 0 | 0 | 0 | 0
2026-05-11 | 215710.033 | 20875.1645 | 126642.6645 | 19483.4868 | 48708.7171 | 0 | 0 | 0 | 0 | 0
2026-05-12 | 216375.0127 | 20939.5174 | 127033.072 | 19543.5495 | 48858.8738 | 0 | 0 | 0 | 0 | 0
2026-05-13 | 217039.9925 | 21003.8702 | 127423.4795 | 19603.6122 | 49009.0306 | 0 | 0 | 0 | 0 | 0
2026-05-14 | 217704.9722 | 21068.2231 | 127813.8869 | 19663.6749 | 49159.1873 | 0 | 0 | 0 | 0 | 0
2026-05-15 | 218369.952 | 21132.576 | 128204.2944 | 19723.7376 | 49309.344 | 0 | 0 | 0 | 0 | 0
2026-05-16 | 218369.952 | 21132.576 | 128204.2944 | 19723.7376 | 49309.344 | 0 | 0 | 0 | 0 | 0
2026-05-17 | 218369.952 | 21132.576 | 128204.2944 | 19723.7376 | 49309.344 | 0 | 0 | 0 | 0 | 0
2026-05-18 | 220104.8247 | 21300.4669 | 129222.8326 | 19880.4358 | 49701.0895 | 0 | 0 | 0 | 0 | 0
2026-05-19 | 221839.6975 | 21468.3578 | 130241.3708 | 20037.134 | 50092.8349 | 0 | 0 | 0 | 0 | 0
2026-05-20 | 223574.5702 | 21636.2487 | 131259.9089 | 20193.8321 | 50484.5804 | 0 | 0 | 0 | 0 | 0
2026-05-21 | 225309.4429 | 21804.1396 | 132278.4471 | 20350.5303 | 50876.3258 | 0 | 0 | 0 | 0 | 0
2026-05-22 | 227044.3156 | 21972.0305 | 133296.9853 | 20507.2285 | 51268.0713 | 0 | 0 | 0 | 0 | 0
2026-05-23 | 228779.1884 | 22139.9215 | 134315.5235 | 20663.9267 | 51659.8167 | 0 | 0 | 0 | 0 | 0
2026-05-24 | 230514.0611 | 22307.8124 | 135334.0617 | 20820.6249 | 52051.5622 | 0 | 0 | 0 | 0 | 0
2026-05-25 | 232248.9338 | 22475.7033 | 136352.5999 | 20977.3231 | 52443.3076 | 0 | 0 | 0 | 0 | 0
2026-05-26 | 233983.8065 | 22643.5942 | 137371.138 | 21134.0212 | 52835.0531 | 0 | 0 | 0 | 0 | 0
2026-05-27 | 235718.6793 | 22811.4851 | 138389.6762 | 21290.7194 | 53226.7985 | 0 | 0 | 0 | 0 | 0
2026-05-28 | 237453.552 | 22979.376 | 139408.2144 | 21447.4176 | 53618.544 | 0 | 0 | 0 | 0 | 0
2026-05-29 | 239188.4247 | 23147.2669 | 140426.7526 | 21604.1158 | 54010.2895 | 0 | 0 | 0 | 0 | 0
2026-05-30 | 240923.2975 | 23315.1578 | 141445.2908 | 21760.814 | 54402.0349 | 0 | 0 | 0 | 0 | 0
2026-05-31 | 242658.1702 | 23483.0487 | 142463.8289 | 21917.5121 | 54793.7804 | 0 | 0 | 0 | 0 | 0
2026-06-01 | 244393.0429 | 23650.9396 | 143482.3671 | 22074.2103 | 55185.5258 | 0 | 0 | 0 | 0 | 0
2026-06-02 | 246127.9156 | 23818.8305 | 144500.9053 | 22230.9085 | 55577.2713 | 0 | 0 | 0 | 0 | 0
2026-06-03 | 247862.7884 | 23986.7215 | 145519.4435 | 22387.6067 | 55969.0167 | 0 | 0 | 0 | 0 | 0
2026-06-04 | 249597.6611 | 24154.6124 | 146537.9817 | 22544.3049 | 56360.7622 | 0 | 0 | 0 | 0 | 0
2026-06-05 | 251332.5338 | 24322.5033 | 147556.5199 | 22701.0031 | 56752.5076 | 0 | 0 | 0 | 0 | 0
2026-06-06 | 253067.4065 | 24490.3942 | 148575.058 | 22857.7012 | 57144.2531 | 0 | 0 | 0 | 0 | 0
2026-06-07 | 254802.2793 | 24658.2851 | 149593.5962 | 23014.3994 | 57535.9985 | 0 | 0 | 0 | 0 | 0
2026-06-08 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-09 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-10 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-11 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-12 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-13 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-14 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-15 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-16 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-17 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-18 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-19 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-20 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-21 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-22 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-23 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-24 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-25 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-26 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-27 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-28 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-29 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-06-30 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-07-01 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-07-02 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-07-03 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-07-04 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-07-05 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-07-06 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-07-07 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-07-08 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-07-09 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0
2026-07-10 | 256537.152 | 24826.176 | 150612.1344 | 23171.0976 | 57927.744 | 0 | 0 | 0 | 0 | 0

## Outsource Tracking
Date | Planned Drilling Cost | Planned Outside Services Cost | Planned Temporary Labor Cost | Planned License Cost | Planned Internet Cost | Planned Outsource Sum | Actual Drilling Cost | Actual Outside Services Cost | Actual Temporary Labor Cost | Actual License Cost | Actual Internet Cost | Actual Outsource Sum
2025-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 0 | 566.6024 | 0 | 0 | 48.1928 | 614.7952 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 0 | 1133.2048 | 0 | 0 | 96.3855 | 1229.5904 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 0 | 1699.8072 | 0 | 0 | 144.5783 | 1844.3855 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 0 | 2266.4096 | 0 | 0 | 192.7711 | 2459.1807 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 0 | 2833.012 | 0 | 0 | 240.9639 | 3073.9759 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 0 | 3399.6145 | 0 | 0 | 289.1566 | 3688.7711 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 0 | 3966.2169 | 0 | 0 | 337.3494 | 4303.5663 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 0 | 4532.8193 | 0 | 0 | 385.5422 | 4918.3614 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 0 | 5099.4217 | 0 | 0 | 433.7349 | 5533.1566 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 0 | 5666.0241 | 0 | 0 | 481.9277 | 6147.9518 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 0 | 6232.6265 | 0 | 0 | 530.1205 | 6762.747 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 0 | 6799.2289 | 0 | 0 | 578.3133 | 7377.5422 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 0 | 7365.8313 | 0 | 0 | 626.506 | 7992.3373 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 0 | 7932.4337 | 0 | 0 | 674.6988 | 8607.1325 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 0 | 8499.0361 | 0 | 0 | 722.8916 | 9221.9277 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 0 | 9065.6386 | 0 | 0 | 771.0843 | 9836.7229 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 0 | 9632.241 | 0 | 0 | 819.2771 | 10451.5181 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 0 | 10198.8434 | 0 | 0 | 867.4699 | 11066.3133 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 0 | 10765.4458 | 0 | 0 | 915.6627 | 11681.1084 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 0 | 11332.0482 | 0 | 0 | 963.8554 | 12295.9036 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 0 | 11898.6506 | 0 | 0 | 1012.0482 | 12910.6988 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 0 | 12465.253 | 0 | 0 | 1060.241 | 13525.494 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 0 | 13031.8554 | 0 | 0 | 1108.4337 | 14140.2892 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 0 | 13598.4578 | 0 | 0 | 1156.6265 | 14755.0843 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 0 | 14165.0602 | 0 | 0 | 1204.8193 | 15369.8795 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-26 | 0 | 14731.6627 | 0 | 0 | 1253.012 | 15984.6747 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-27 | 0 | 15298.2651 | 0 | 0 | 1301.2048 | 16599.4699 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-28 | 0 | 15864.8675 | 0 | 0 | 1349.3976 | 17214.2651 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-29 | 0 | 16431.4699 | 0 | 0 | 1397.5904 | 17829.0602 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-30 | 0 | 16998.0723 | 0 | 0 | 1445.7831 | 18443.8554 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-01 | 0 | 17564.6747 | 0 | 0 | 1493.9759 | 19058.6506 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-02 | 0 | 18131.2771 | 0 | 0 | 1542.1687 | 19673.4458 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-03 | 0 | 18697.8795 | 0 | 0 | 1590.3614 | 20288.241 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-04 | 0 | 19264.4819 | 0 | 0 | 1638.5542 | 20903.0361 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-05 | 0 | 19831.0843 | 0 | 0 | 1686.747 | 21517.8313 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-06 | 0 | 20397.6867 | 0 | 0 | 1734.9398 | 22132.6265 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-07 | 0 | 20964.2892 | 0 | 0 | 1783.1325 | 22747.4217 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-08 | 0 | 21530.8916 | 0 | 0 | 1831.3253 | 23362.2169 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-09 | 0 | 22097.494 | 0 | 0 | 1879.5181 | 23977.012 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-10 | 0 | 22664.0964 | 0 | 0 | 1927.7108 | 24591.8072 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-11 | 0 | 23230.6988 | 0 | 0 | 1975.9036 | 25206.6024 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-12 | 0 | 23797.3012 | 0 | 0 | 2024.0964 | 25821.3976 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-13 | 0 | 24363.9036 | 0 | 0 | 2072.2892 | 26436.1928 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-14 | 0 | 24930.506 | 0 | 0 | 2120.4819 | 27050.988 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-15 | 5413.0714 | 27805.7788 | 0 | 0 | 2168.6747 | 35387.525 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-16 | 10826.1429 | 30681.0517 | 0 | 0 | 2216.8675 | 43724.062 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-17 | 16239.2143 | 33556.3245 | 0 | 0 | 2265.0602 | 52060.599 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-18 | 21652.2857 | 36431.5973 | 0 | 0 | 2313.253 | 60397.1361 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-19 | 27065.3571 | 39306.8702 | 0 | 0 | 2361.4458 | 68733.6731 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-20 | 32478.4286 | 42182.143 | 0 | 0 | 2409.6386 | 77070.2101 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-21 | 37891.5 | 45057.4158 | 0 | 0 | 2457.8313 | 85406.7471 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-22 | 43304.5714 | 47932.6886 | 0 | 0 | 2506.0241 | 93743.2842 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-23 | 48717.6429 | 50807.9615 | 0 | 0 | 2554.2169 | 102079.8212 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-24 | 54130.7143 | 53683.2343 | 0 | 0 | 2602.4096 | 110416.3582 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-25 | 59543.7857 | 56558.5071 | 0 | 0 | 2650.6024 | 118752.8952 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-26 | 64956.8571 | 59433.7799 | 0 | 0 | 2698.7952 | 127089.4323 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-27 | 70369.9286 | 62309.0528 | 0 | 0 | 2746.988 | 135425.9693 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-28 | 75783 | 65184.3256 | 0 | 0 | 2795.1807 | 143762.5063 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-29 | 81196.0714 | 68059.5984 | 0 | 0 | 2843.3735 | 152099.0433 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-30 | 86609.1429 | 70934.8712 | 0 | 0 | 2891.5663 | 160435.5804 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-31 | 92022.2143 | 73810.1441 | 0 | 0 | 2939.759 | 168772.1174 | 23367.75 | 2277.67 | 0 | 0 | 0 | 25645.42
2025-08-01 | 97435.2857 | 76685.4169 | 0 | 0 | 2987.9518 | 177108.6544 | 23367.75 | 2277.67 | 0 | 0 | 0 | 25645.42
2025-08-02 | 102848.3571 | 79560.6897 | 0 | 0 | 3036.1446 | 185445.1914 | 23367.75 | 2277.67 | 0 | 0 | 0 | 25645.42
2025-08-03 | 108261.4286 | 82435.9625 | 0 | 0 | 3084.3373 | 193781.7285 | 23367.75 | 2277.67 | 0 | 0 | 0 | 25645.42
2025-08-04 | 113674.5 | 85311.2354 | 0 | 0 | 3132.5301 | 202118.2655 | 23367.75 | 2277.67 | 0 | 0 | 0 | 25645.42
2025-08-05 | 119087.5714 | 88186.5082 | 0 | 0 | 3180.7229 | 210454.8025 | 23367.75 | 2277.67 | 0 | 0 | 0 | 25645.42
2025-08-06 | 124500.6429 | 91061.781 | 0 | 0 | 3228.9157 | 218791.3395 | 23367.75 | 7185.11 | 0 | 0 | 0 | 30552.86
2025-08-07 | 129913.7143 | 93937.0538 | 0 | 0 | 3277.1084 | 227127.8766 | 23367.75 | 7185.11 | 0 | 0 | 0 | 30552.86
2025-08-08 | 135326.7857 | 96812.3267 | 0 | 0 | 3325.3012 | 235464.4136 | 23367.75 | 7185.11 | 0 | 0 | 0 | 30552.86
2025-08-09 | 140739.8571 | 99687.5995 | 0 | 0 | 3373.494 | 243800.9506 | 23367.75 | 7185.11 | 0 | 0 | 0 | 30552.86
2025-08-10 | 146152.9286 | 102562.8723 | 0 | 0 | 3421.6867 | 252137.4876 | 23367.75 | 7185.11 | 0 | 0 | 0 | 30552.86
2025-08-11 | 151566 | 105438.1451 | 0 | 0 | 3469.8795 | 260474.0247 | 23367.75 | 7185.11 | 0 | 0 | 0 | 30552.86
2025-08-12 | 156979.0714 | 108313.418 | 0 | 0 | 3518.0723 | 268810.5617 | 23367.75 | 8892.73 | 0 | 0 | 0 | 32260.48
2025-08-13 | 162392.1429 | 111188.6908 | 0 | 0 | 3566.2651 | 277147.0987 | 23367.75 | 8892.73 | 0 | 0 | 0 | 32260.48
2025-08-14 | 167805.2143 | 114063.9636 | 0 | 0 | 3614.4578 | 285483.6357 | 23367.75 | 8892.73 | 0 | 0 | 0 | 32260.48
2025-08-15 | 173218.2857 | 116939.2364 | 0 | 0 | 3662.6506 | 293820.1728 | 23367.75 | 8892.73 | 0 | 0 | 0 | 32260.48
2025-08-16 | 178631.3571 | 119814.5093 | 0 | 0 | 3710.8434 | 302156.7098 | 23367.75 | 8892.73 | 0 | 0 | 0 | 32260.48
2025-08-17 | 184044.4286 | 122689.7821 | 0 | 0 | 3759.0361 | 310493.2468 | 23367.75 | 8892.73 | 0 | 0 | 0 | 32260.48
2025-08-18 | 189457.5 | 125565.0549 | 0 | 0 | 3807.2289 | 318829.7838 | 23367.75 | 8892.73 | 0 | 0 | 0 | 32260.48
2025-08-19 | 194870.5714 | 128440.3277 | 0 | 0 | 3855.4217 | 327166.3209 | 23367.75 | 8892.73 | 0 | 0 | 0 | 32260.48
2025-08-20 | 200283.6429 | 131315.6006 | 0 | 0 | 3903.6145 | 335502.8579 | 23367.75 | 12699.02 | 0 | 0 | 0 | 36066.77
2025-08-21 | 205696.7143 | 134190.8734 | 0 | 0 | 3951.8072 | 343839.3949 | 23367.75 | 12699.02 | 0 | 0 | 0 | 36066.77
2025-08-22 | 211109.7857 | 137066.1462 | 0 | 0 | 4000 | 352175.9319 | 23367.75 | 12699.02 | 0 | 0 | 0 | 36066.77
2025-08-23 | 216522.8571 | 139374.8166 | 0 | 0 | 4000 | 359897.6738 | 23367.75 | 12699.02 | 0 | 0 | 0 | 36066.77
2025-08-24 | 221935.9286 | 141683.487 | 0 | 0 | 4000 | 367619.4156 | 23367.75 | 12699.02 | 0 | 0 | 0 | 36066.77
2025-08-25 | 227349 | 143992.1575 | 0 | 0 | 4000 | 375341.1575 | 77310.25 | 12699.02 | 0 | 0 | 0 | 90009.27
2025-08-26 | 232762.0714 | 146300.8279 | 0 | 0 | 4000 | 383062.8993 | 77310.25 | 12699.02 | 0 | 0 | 0 | 90009.27
2025-08-27 | 238175.1429 | 148609.4983 | 0 | 0 | 4000 | 390784.6412 | 77310.25 | 15277.7 | 0 | 0 | 0 | 92587.95
2025-08-28 | 243588.2143 | 150918.1687 | 0 | 0 | 4000 | 398506.383 | 77310.25 | 15277.7 | 0 | 0 | 0 | 92587.95
2025-08-29 | 249001.2857 | 153226.8391 | 0 | 0 | 4000 | 406228.1248 | 77310.25 | 15277.7 | 0 | 0 | 0 | 92587.95
2025-08-30 | 254414.3571 | 155535.5095 | 0 | 0 | 4000 | 413949.8667 | 77310.25 | 15277.7 | 0 | 0 | 0 | 92587.95
2025-08-31 | 259827.4286 | 157844.18 | 0 | 0 | 4000 | 421671.6085 | 77310.25 | 24170.43 | 0 | 0 | 0 | 101480.68
2025-09-01 | 265240.5 | 160152.8504 | 0 | 0 | 4000 | 429393.3504 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-02 | 265240.5 | 160890.0289 | 0 | 0 | 4000 | 430130.5289 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-03 | 265240.5 | 161627.2074 | 0 | 0 | 4000 | 430867.7074 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-04 | 265240.5 | 162364.3859 | 0 | 0 | 4000 | 431604.8859 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-05 | 265240.5 | 163101.5644 | 0 | 0 | 4000 | 432342.0644 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-06 | 265240.5 | 163838.7429 | 0 | 0 | 4000 | 433079.2429 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-07 | 265240.5 | 164575.9214 | 0 | 0 | 4000 | 433816.4214 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-08 | 265240.5 | 165313.0999 | 0 | 0 | 4000 | 434553.5999 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-09 | 265240.5 | 166050.2784 | 0 | 0 | 4000 | 435290.7784 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-10 | 265240.5 | 166787.4569 | 0 | 0 | 4000 | 436027.9569 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-11 | 265240.5 | 167524.6354 | 0 | 0 | 4000 | 436765.1354 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-12 | 265240.5 | 168261.8139 | 0 | 0 | 4000 | 437502.3139 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-13 | 265240.5 | 168998.9924 | 0 | 0 | 4000 | 438239.4924 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-14 | 265240.5 | 169736.1709 | 0 | 0 | 4000 | 438976.6709 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-15 | 265240.5 | 170473.3494 | 0 | 0 | 4000 | 439713.8494 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-16 | 265240.5 | 171210.5279 | 0 | 0 | 4000 | 440451.0279 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-17 | 265240.5 | 171947.7064 | 0 | 0 | 4000 | 441188.2064 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-18 | 265240.5 | 172684.8849 | 0 | 0 | 4000 | 441925.3849 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-19 | 265240.5 | 173422.0634 | 0 | 0 | 4000 | 442662.5634 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-20 | 265240.5 | 174159.2419 | 0 | 0 | 4000 | 443399.7419 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-21 | 265240.5 | 174896.4204 | 0 | 0 | 4000 | 444136.9204 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-22 | 265240.5 | 175633.5989 | 0 | 0 | 4000 | 444874.0989 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-23 | 265240.5 | 176370.7774 | 0 | 0 | 4000 | 445611.2774 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-24 | 265240.5 | 177107.9559 | 0 | 0 | 4000 | 446348.4559 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-25 | 265240.5 | 177845.1344 | 0 | 0 | 4000 | 447085.6344 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-26 | 265240.5 | 178582.3129 | 0 | 0 | 4000 | 447822.8129 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-27 | 265240.5 | 179319.4914 | 0 | 0 | 4000 | 448559.9914 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-28 | 265240.5 | 180056.67 | 0 | 0 | 4000 | 449297.17 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-29 | 265240.5 | 180793.8485 | 0 | 0 | 4000 | 450034.3485 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-30 | 265240.5 | 181531.027 | 0 | 0 | 4000 | 450771.527 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-01 | 265240.5 | 182268.2055 | 0 | 0 | 4000 | 451508.7055 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-02 | 265240.5 | 183005.384 | 0 | 0 | 4000 | 452245.884 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-03 | 265240.5 | 183742.5625 | 0 | 0 | 4000 | 452983.0625 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-04 | 265240.5 | 184479.741 | 0 | 0 | 4000 | 453720.241 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-05 | 265240.5 | 185216.9195 | 0 | 0 | 4000 | 454457.4195 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-06 | 265240.5 | 185954.098 | 0 | 0 | 4000 | 455194.598 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-07 | 265240.5 | 186691.2765 | 0 | 0 | 4000 | 455931.7765 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-08 | 265240.5 | 187428.455 | 0 | 0 | 4000 | 456668.955 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-09 | 265240.5 | 188165.6335 | 0 | 0 | 4000 | 457406.1335 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-10 | 265240.5 | 188902.812 | 0 | 0 | 4000 | 458143.312 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-11 | 265240.5 | 189639.9905 | 0 | 0 | 4000 | 458880.4905 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-12 | 265240.5 | 190377.169 | 0 | 0 | 4000 | 459617.669 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-13 | 265240.5 | 191114.3475 | 0 | 0 | 4000 | 460354.8475 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-14 | 265240.5 | 191851.526 | 0 | 0 | 4000 | 461092.026 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-15 | 265240.5 | 192588.7045 | 0 | 0 | 4000 | 461829.2045 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-16 | 265240.5 | 193325.883 | 0 | 0 | 4000 | 462566.383 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-17 | 265240.5 | 194063.0615 | 0 | 0 | 4000 | 463303.5615 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-18 | 265240.5 | 194800.24 | 0 | 0 | 4000 | 464040.74 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-19 | 265240.5 | 195537.4185 | 0 | 0 | 4000 | 464777.9185 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-20 | 265240.5 | 196274.597 | 0 | 0 | 4000 | 465515.097 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-21 | 265240.5 | 197011.7755 | 0 | 0 | 4000 | 466252.2755 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-22 | 265240.5 | 197748.954 | 0 | 0 | 4000 | 466989.454 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-23 | 265240.5 | 198486.1325 | 0 | 0 | 4000 | 467726.6325 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-24 | 265240.5 | 199223.311 | 0 | 0 | 4000 | 468463.811 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-25 | 265240.5 | 199960.4895 | 0 | 0 | 4000 | 469200.9895 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-26 | 265240.5 | 200697.668 | 0 | 0 | 4000 | 469938.168 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-27 | 265240.5 | 201434.8465 | 0 | 0 | 4000 | 470675.3465 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-28 | 265240.5 | 201586.0632 | 0 | 0 | 4000 | 470826.5632 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-29 | 265240.5 | 201737.2799 | 0 | 0 | 4000 | 470977.7799 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-30 | 265240.5 | 201888.4965 | 0 | 0 | 4000 | 471128.9965 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-31 | 265240.5 | 202039.7132 | 0 | 0 | 4000 | 471280.2132 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-01 | 265240.5 | 202190.9299 | 0 | 0 | 4000 | 471431.4299 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-02 | 265240.5 | 202342.1465 | 0 | 0 | 4000 | 471582.6465 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-03 | 265240.5 | 202493.3632 | 0 | 0 | 4000 | 471733.8632 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-04 | 265240.5 | 202644.5799 | 0 | 0 | 4000 | 471885.0799 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-05 | 265240.5 | 202795.7965 | 0 | 0 | 4000 | 472036.2965 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-06 | 265240.5 | 202947.0132 | 0 | 0 | 4000 | 472187.5132 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-07 | 265240.5 | 203098.2299 | 0 | 0 | 4000 | 472338.7299 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-08 | 265240.5 | 203249.4465 | 0 | 0 | 4000 | 472489.9465 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-09 | 265240.5 | 203400.6632 | 0 | 0 | 4000 | 472641.1632 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-10 | 265240.5 | 203551.8799 | 0 | 0 | 4000 | 472792.3799 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-11 | 265240.5 | 203703.0965 | 0 | 0 | 4000 | 472943.5965 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-12 | 265240.5 | 203854.3132 | 0 | 0 | 4000 | 473094.8132 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-13 | 265240.5 | 204005.5299 | 0 | 0 | 4000 | 473246.0299 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-14 | 265240.5 | 204156.7465 | 0 | 0 | 4000 | 473397.2465 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-15 | 265240.5 | 204307.9632 | 0 | 0 | 4000 | 473548.4632 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-16 | 265240.5 | 204459.1799 | 0 | 0 | 4000 | 473699.6799 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-17 | 265240.5 | 204610.3965 | 0 | 0 | 4000 | 473850.8965 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-18 | 265240.5 | 204761.6132 | 0 | 0 | 4000 | 474002.1132 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-19 | 265240.5 | 204912.8299 | 0 | 0 | 4000 | 474153.3299 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-20 | 265240.5 | 205064.0465 | 0 | 0 | 4000 | 474304.5465 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-21 | 265240.5 | 205215.2632 | 0 | 0 | 4000 | 474455.7632 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-22 | 265240.5 | 205366.4799 | 0 | 0 | 4000 | 474606.9799 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-23 | 265240.5 | 205517.6965 | 0 | 0 | 4000 | 474758.1965 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-24 | 265240.5 | 205668.9132 | 0 | 0 | 4000 | 474909.4132 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-25 | 265240.5 | 205820.1299 | 0 | 0 | 4000 | 475060.6299 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-26 | 265240.5 | 205971.3465 | 0 | 0 | 4000 | 475211.8465 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-27 | 265240.5 | 206122.5632 | 0 | 0 | 4000 | 475363.0632 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-28 | 265240.5 | 206273.7799 | 0 | 0 | 4000 | 475514.2799 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-29 | 265240.5 | 206424.9965 | 0 | 0 | 4000 | 475665.4965 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-30 | 265240.5 | 206576.2132 | 0 | 0 | 4000 | 475816.7132 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-01 | 265240.5 | 206727.4299 | 0 | 0 | 4000 | 475967.9299 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-02 | 265240.5 | 206878.6465 | 0 | 0 | 4000 | 476119.1465 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-03 | 265240.5 | 207029.8632 | 0 | 0 | 4000 | 476270.3632 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-04 | 265240.5 | 207181.0799 | 0 | 0 | 4000 | 476421.5799 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-05 | 265240.5 | 207332.2965 | 0 | 0 | 4000 | 476572.7965 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-06 | 265240.5 | 207483.5132 | 0 | 0 | 4000 | 476724.0132 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-07 | 265240.5 | 207634.7299 | 0 | 0 | 4000 | 476875.2299 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-08 | 265240.5 | 207785.9465 | 0 | 0 | 4000 | 477026.4465 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-09 | 265240.5 | 207937.1632 | 0 | 0 | 4000 | 477177.6632 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-10 | 265240.5 | 208088.3799 | 0 | 0 | 4000 | 477328.8799 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-11 | 265240.5 | 208239.5965 | 0 | 0 | 4000 | 477480.0965 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-12 | 265240.5 | 208390.8132 | 0 | 0 | 4000 | 477631.3132 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-13 | 265240.5 | 208542.0299 | 0 | 0 | 4000 | 477782.5299 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-14 | 265240.5 | 208693.2465 | 0 | 0 | 4000 | 477933.7465 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-15 | 265240.5 | 208844.4632 | 0 | 0 | 4000 | 478084.9632 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-16 | 265240.5 | 208995.6799 | 0 | 0 | 4000 | 478236.1799 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-17 | 265240.5 | 209146.8965 | 0 | 0 | 4000 | 478387.3965 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-18 | 265240.5 | 209298.1132 | 0 | 0 | 4000 | 478538.6132 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-19 | 265240.5 | 209449.3299 | 0 | 0 | 4000 | 478689.8299 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-20 | 265240.5 | 209600.5465 | 0 | 0 | 4000 | 478841.0465 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-21 | 265240.5 | 209751.7632 | 0 | 0 | 4000 | 478992.2632 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-22 | 265240.5 | 209902.9799 | 0 | 0 | 4000 | 479143.4799 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-23 | 265240.5 | 210054.1965 | 0 | 0 | 4000 | 479294.6965 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-24 | 265240.5 | 210205.4132 | 0 | 0 | 4000 | 479445.9132 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-25 | 265240.5 | 210356.6299 | 0 | 0 | 4000 | 479597.1299 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-26 | 265240.5 | 210507.8465 | 0 | 0 | 4000 | 479748.3465 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-27 | 265240.5 | 210659.0632 | 0 | 0 | 4000 | 479899.5632 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-28 | 265240.5 | 210810.2799 | 0 | 0 | 4000 | 480050.7799 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-29 | 265240.5 | 210961.4965 | 0 | 0 | 4000 | 480201.9965 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-30 | 265240.5 | 211112.7132 | 0 | 0 | 4000 | 480353.2132 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-31 | 265240.5 | 211263.9299 | 0 | 0 | 4000 | 480504.4299 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-01 | 265240.5 | 211415.1465 | 0 | 0 | 4000 | 480655.6465 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-02 | 265240.5 | 211566.3632 | 0 | 0 | 4000 | 480806.8632 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-03 | 265240.5 | 211717.5799 | 0 | 0 | 4000 | 480958.0799 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-04 | 265240.5 | 211868.7965 | 0 | 0 | 4000 | 481109.2965 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-05 | 265240.5 | 212020.0132 | 0 | 0 | 4000 | 481260.5132 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-06 | 265240.5 | 212171.2299 | 0 | 0 | 4000 | 481411.7299 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-07 | 265240.5 | 212322.4465 | 0 | 0 | 4000 | 481562.9465 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-08 | 265240.5 | 212473.6632 | 0 | 0 | 4000 | 481714.1632 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-09 | 265240.5 | 212624.8799 | 0 | 0 | 4000 | 481865.3799 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-10 | 265240.5 | 212776.0965 | 0 | 0 | 4000 | 482016.5965 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-11 | 265240.5 | 212927.3132 | 0 | 0 | 4000 | 482167.8132 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-12 | 265240.5 | 213078.5299 | 0 | 0 | 4000 | 482319.0299 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-13 | 265240.5 | 213229.7465 | 0 | 0 | 4000 | 482470.2465 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-14 | 265240.5 | 213380.9632 | 0 | 0 | 4000 | 482621.4632 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-15 | 265240.5 | 213532.1799 | 0 | 0 | 4000 | 482772.6799 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-16 | 265240.5 | 213683.3965 | 0 | 0 | 4000 | 482923.8965 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-17 | 265240.5 | 213834.6132 | 0 | 0 | 4000 | 483075.1132 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-18 | 265240.5 | 213985.8299 | 0 | 0 | 4000 | 483226.3299 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-19 | 265240.5 | 214137.0465 | 0 | 0 | 4000 | 483377.5465 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-20 | 265240.5 | 214288.2632 | 0 | 0 | 4000 | 483528.7632 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-21 | 265240.5 | 214439.4799 | 0 | 0 | 4000 | 483679.9799 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-22 | 265240.5 | 214590.6965 | 0 | 0 | 4000 | 483831.1965 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-23 | 265240.5 | 214741.9132 | 0 | 0 | 4000 | 483982.4132 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-24 | 265240.5 | 214893.1299 | 0 | 0 | 4000 | 484133.6299 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-25 | 265240.5 | 215044.3465 | 0 | 0 | 4000 | 484284.8465 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-26 | 265240.5 | 215195.5632 | 0 | 0 | 4000 | 484436.0632 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-27 | 265240.5 | 215346.7799 | 0 | 0 | 4000 | 484587.2799 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-28 | 265240.5 | 215497.9965 | 0 | 0 | 4000 | 484738.4965 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-29 | 265240.5 | 215649.2132 | 0 | 0 | 4000 | 484889.7132 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-30 | 265240.5 | 215800.4299 | 0 | 0 | 4000 | 485040.9299 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-31 | 265240.5 | 215951.6465 | 0 | 0 | 4000 | 485192.1465 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-01 | 265240.5 | 216102.8632 | 0 | 0 | 4000 | 485343.3632 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-02 | 265240.5 | 216254.0799 | 0 | 0 | 4000 | 485494.5799 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-03 | 265240.5 | 216405.2965 | 0 | 0 | 4000 | 485645.7965 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-04 | 265240.5 | 216556.5132 | 0 | 0 | 4000 | 485797.0132 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-05 | 265240.5 | 216707.7299 | 0 | 0 | 4000 | 485948.2299 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-06 | 265240.5 | 216858.9465 | 0 | 0 | 4000 | 486099.4465 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-07 | 265240.5 | 217010.1632 | 0 | 0 | 4000 | 486250.6632 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-08 | 265240.5 | 217161.3799 | 0 | 0 | 4000 | 486401.8799 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-09 | 265240.5 | 217312.5965 | 0 | 0 | 4000 | 486553.0965 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-10 | 265240.5 | 217463.8132 | 0 | 0 | 4000 | 486704.3132 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-11 | 265240.5 | 217615.0299 | 0 | 0 | 4000 | 486855.5299 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-12 | 265240.5 | 217766.2465 | 0 | 0 | 4000 | 487006.7465 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-13 | 265240.5 | 217917.4632 | 0 | 0 | 4000 | 487157.9632 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-14 | 265240.5 | 218068.6799 | 0 | 0 | 4000 | 487309.1799 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-15 | 265240.5 | 218219.8965 | 0 | 0 | 4000 | 487460.3965 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-16 | 265240.5 | 218371.1132 | 0 | 0 | 4000 | 487611.6132 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-17 | 265240.5 | 218522.3299 | 0 | 0 | 4000 | 487762.8299 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-18 | 265240.5 | 218673.5465 | 0 | 0 | 4000 | 487914.0465 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-19 | 265240.5 | 218824.7632 | 0 | 0 | 4000 | 488065.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-20 | 265240.5 | 218975.9799 | 0 | 0 | 4000 | 488216.4799 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-21 | 265240.5 | 219127.1965 | 0 | 0 | 4000 | 488367.6965 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-22 | 265240.5 | 219278.4132 | 0 | 0 | 4000 | 488518.9132 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-23 | 265240.5 | 219429.6299 | 0 | 0 | 4000 | 488670.1299 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-24 | 265240.5 | 219580.8465 | 0 | 0 | 4000 | 488821.3465 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-25 | 265240.5 | 219732.0632 | 0 | 0 | 4000 | 488972.5632 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-26 | 265240.5 | 219883.2799 | 0 | 0 | 4000 | 489123.7799 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-27 | 265240.5 | 220034.4965 | 0 | 0 | 4000 | 489274.9965 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-28 | 265240.5 | 220185.7132 | 0 | 0 | 4000 | 489426.2132 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-01 | 265240.5 | 220336.9299 | 0 | 0 | 4000 | 489577.4299 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-02 | 265240.5 | 220488.1465 | 0 | 0 | 4000 | 489728.6465 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-03 | 265240.5 | 220639.3632 | 0 | 0 | 4000 | 489879.8632 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-04 | 265240.5 | 220790.5799 | 0 | 0 | 4000 | 490031.0799 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-05 | 265240.5 | 220941.7965 | 0 | 0 | 4000 | 490182.2965 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-06 | 265240.5 | 221093.0132 | 0 | 0 | 4000 | 490333.5132 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-07 | 265240.5 | 221244.2299 | 0 | 0 | 4000 | 490484.7299 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-08 | 265240.5 | 221395.4465 | 0 | 0 | 4000 | 490635.9465 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-09 | 265240.5 | 221546.6632 | 0 | 0 | 4000 | 490787.1632 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-10 | 265240.5 | 221697.8799 | 0 | 0 | 4000 | 490938.3799 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-11 | 265240.5 | 221849.0965 | 0 | 0 | 4000 | 491089.5965 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-12 | 265240.5 | 222000.3132 | 0 | 0 | 4000 | 491240.8132 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-13 | 265240.5 | 222151.5299 | 0 | 0 | 4000 | 491392.0299 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-14 | 265240.5 | 222302.7465 | 0 | 0 | 4000 | 491543.2465 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-15 | 265240.5 | 222453.9632 | 0 | 0 | 4000 | 491694.4632 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-16 | 265240.5 | 222605.1799 | 0 | 0 | 4000 | 491845.6799 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-17 | 265240.5 | 222756.3965 | 0 | 0 | 4000 | 491996.8965 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-18 | 265240.5 | 222907.6132 | 0 | 0 | 4000 | 492148.1132 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-19 | 265240.5 | 223058.8299 | 0 | 0 | 4000 | 492299.3299 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-20 | 265240.5 | 223210.0465 | 0 | 0 | 4000 | 492450.5465 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-21 | 265240.5 | 223361.2632 | 0 | 0 | 4000 | 492601.7632 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-22 | 265240.5 | 223512.4799 | 0 | 0 | 4000 | 492752.9799 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-23 | 265240.5 | 223663.6965 | 0 | 0 | 4000 | 492904.1965 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-24 | 265240.5 | 223814.9132 | 0 | 0 | 4000 | 493055.4132 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-25 | 265240.5 | 223966.1299 | 0 | 0 | 4000 | 493206.6299 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-26 | 265240.5 | 224117.3465 | 0 | 0 | 4000 | 493357.8465 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-27 | 265240.5 | 224268.5632 | 0 | 0 | 4000 | 493509.0632 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-28 | 265240.5 | 224419.7799 | 0 | 0 | 4000 | 493660.2799 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-29 | 265240.5 | 224570.9965 | 0 | 0 | 4000 | 493811.4965 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-30 | 265240.5 | 224722.2132 | 0 | 0 | 4000 | 493962.7132 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-31 | 265240.5 | 224873.4299 | 0 | 0 | 4000 | 494113.9299 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-01 | 265240.5 | 225024.6465 | 0 | 0 | 4000 | 494265.1465 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-02 | 265240.5 | 225175.8632 | 0 | 0 | 4000 | 494416.3632 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-03 | 265240.5 | 225327.0799 | 0 | 0 | 4000 | 494567.5799 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-04 | 265240.5 | 225478.2965 | 0 | 0 | 4000 | 494718.7965 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-05 | 265240.5 | 225629.5132 | 0 | 0 | 4000 | 494870.0132 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-06 | 265240.5 | 225780.7299 | 0 | 0 | 4000 | 495021.2299 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-07 | 265240.5 | 225931.9465 | 0 | 0 | 4000 | 495172.4465 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-08 | 265240.5 | 226083.1632 | 0 | 0 | 4000 | 495323.6632 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-09 | 265240.5 | 226234.3799 | 0 | 0 | 4000 | 495474.8799 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-10 | 265240.5 | 226385.5965 | 0 | 0 | 4000 | 495626.0965 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-11 | 265240.5 | 226536.8132 | 0 | 0 | 4000 | 495777.3132 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-12 | 265240.5 | 226688.0299 | 0 | 0 | 4000 | 495928.5299 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-13 | 265240.5 | 226839.2465 | 0 | 0 | 4000 | 496079.7465 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-14 | 265240.5 | 226990.4632 | 0 | 0 | 4000 | 496230.9632 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-15 | 265240.5 | 227141.6799 | 0 | 0 | 4000 | 496382.1799 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-16 | 265240.5 | 227292.8965 | 0 | 0 | 4000 | 496533.3965 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-17 | 265240.5 | 227444.1132 | 0 | 0 | 4000 | 496684.6132 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-18 | 265240.5 | 227595.3299 | 0 | 0 | 4000 | 496835.8299 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-19 | 265240.5 | 227746.5465 | 0 | 0 | 4000 | 496987.0465 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-20 | 265240.5 | 227897.7632 | 0 | 0 | 4000 | 497138.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-21 | 265240.5 | 228048.9799 | 0 | 0 | 4000 | 497289.4799 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-22 | 265240.5 | 228200.1965 | 0 | 0 | 4000 | 497440.6965 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-23 | 265240.5 | 228351.4132 | 0 | 0 | 4000 | 497591.9132 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-24 | 265240.5 | 228502.6299 | 0 | 0 | 4000 | 497743.1299 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-25 | 265240.5 | 228653.8465 | 0 | 0 | 4000 | 497894.3465 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-26 | 265240.5 | 228805.0632 | 0 | 0 | 4000 | 498045.5632 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-27 | 265240.5 | 228956.2799 | 0 | 0 | 4000 | 498196.7799 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-28 | 265240.5 | 229107.4965 | 0 | 0 | 4000 | 498347.9965 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-29 | 265240.5 | 229258.7132 | 0 | 0 | 4000 | 498499.2132 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-30 | 265240.5 | 229409.9299 | 0 | 0 | 4000 | 498650.4299 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-01 | 265240.5 | 229561.1465 | 0 | 0 | 4000 | 498801.6465 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-02 | 265240.5 | 229712.3632 | 0 | 0 | 4000 | 498952.8632 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-03 | 265240.5 | 229863.5799 | 0 | 0 | 4000 | 499104.0799 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-04 | 265240.5 | 230014.7965 | 0 | 0 | 4000 | 499255.2965 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-05 | 265240.5 | 230166.0132 | 0 | 0 | 4000 | 499406.5132 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-06 | 265240.5 | 230317.2299 | 0 | 0 | 4000 | 499557.7299 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-07 | 265240.5 | 230468.4465 | 0 | 0 | 4000 | 499708.9465 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-08 | 265240.5 | 230619.6632 | 0 | 0 | 4000 | 499860.1632 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-09 | 265240.5 | 230770.8799 | 0 | 0 | 4000 | 500011.3799 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-10 | 265240.5 | 230922.0965 | 0 | 0 | 4000 | 500162.5965 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-11 | 265240.5 | 231073.3132 | 0 | 0 | 4000 | 500313.8132 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-12 | 265240.5 | 231224.5299 | 0 | 0 | 4000 | 500465.0299 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-13 | 265240.5 | 231375.7465 | 0 | 0 | 4000 | 500616.2465 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-14 | 265240.5 | 231526.9632 | 0 | 0 | 4000 | 500767.4632 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-15 | 265240.5 | 231678.1799 | 0 | 0 | 4000 | 500918.6799 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-16 | 265240.5 | 231678.1799 | 0 | 0 | 4000 | 500918.6799 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-17 | 265240.5 | 231678.1799 | 0 | 0 | 4000 | 500918.6799 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-18 | 265240.5 | 233003.1799 | 2351.7083 | 0 | 4000 | 504595.3882 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-19 | 265240.5 | 234328.1799 | 4703.4167 | 0 | 4000 | 508272.0965 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-20 | 265240.5 | 235653.1799 | 7055.125 | 0 | 4000 | 511948.8049 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-21 | 265240.5 | 236978.1799 | 9406.8333 | 0 | 4000 | 515625.5132 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-22 | 265240.5 | 238303.1799 | 11758.5417 | 0 | 4000 | 519302.2215 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-23 | 265240.5 | 239628.1799 | 14110.25 | 0 | 4000 | 522978.9299 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-24 | 265240.5 | 240953.1799 | 16461.9583 | 0 | 4000 | 526655.6382 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-25 | 265240.5 | 242278.1799 | 18813.6667 | 0 | 4000 | 530332.3465 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-26 | 265240.5 | 243603.1799 | 21165.375 | 0 | 4000 | 534009.0549 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-27 | 265240.5 | 244928.1799 | 23517.0833 | 0 | 4000 | 537685.7632 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-28 | 265240.5 | 246253.1799 | 25868.7917 | 0 | 4000 | 541362.4715 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-29 | 265240.5 | 247578.1799 | 28220.5 | 0 | 4000 | 545039.1799 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-30 | 265240.5 | 248903.1799 | 30572.2083 | 0 | 4000 | 548715.8882 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-31 | 265240.5 | 250228.1799 | 32923.9167 | 0 | 4000 | 552392.5965 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-01 | 265240.5 | 251553.1799 | 35275.625 | 0 | 4000 | 556069.3049 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-02 | 265240.5 | 252878.1799 | 37627.3333 | 0 | 4000 | 559746.0132 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-03 | 265240.5 | 254203.1799 | 39979.0417 | 0 | 4000 | 563422.7215 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-04 | 265240.5 | 255528.1799 | 42330.75 | 0 | 4000 | 567099.4299 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-05 | 265240.5 | 256853.1799 | 44682.4583 | 0 | 4000 | 570776.1382 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-06 | 265240.5 | 258178.1799 | 47034.1667 | 0 | 4000 | 574452.8465 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-07 | 265240.5 | 259503.1799 | 49385.875 | 0 | 4000 | 578129.5549 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-08 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-09 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-10 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-11 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-12 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-13 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-14 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-15 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-16 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-17 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-18 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-19 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-20 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-21 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-22 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-23 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-24 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-25 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-26 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-27 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-28 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-29 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-30 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-01 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-02 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-03 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-04 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-05 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-06 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-07 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-08 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-09 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-10 | 265240.5 | 260828.1799 | 51737.5833 | 0 | 4000 | 581806.2632 | 0 | 0 | 0 | 0 | 0 | 0

## Parts Tracking
Date | Planned GTR Parts | Planned Parts & Materials | Planned Carbon & Lab | Planned Building Rent | Planned Equipment Rent | Planned Freight & Shipping | Planned Health & Safety | Planned Misc Expenses | Planned Parts Sum | Actual GTR Parts | Actual Parts & Materials | Actual Carbon & Lab | Actual Building Rent | Actual Equipment Rent | Actual Freight & Shipping | Actual Health & Safety | Actual Misc Expenses | Actual Parts Sum
2025-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-04-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-04-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-04-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-04-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-04-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-04-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-06-01 | 0 | 1261.7398 | 0 | 0 | 670.0602 | 120.4819 | 0 | 0 | 2052.2819 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-06-02 | 0 | 2523.4795 | 0 | 0 | 1340.1205 | 240.9639 | 0 | 0 | 4104.5639 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-06-03 | 0 | 3785.2193 | 0 | 0 | 2010.1807 | 361.4458 | 0 | 0 | 6156.8458 | 0 | 33.72 | 0 | 0 | 0 | 0 | 0 | 0 | 33.72
2025-06-04 | 0 | 5046.959 | 0 | 0 | 2680.241 | 481.9277 | 0 | 0 | 8209.1277 | 0 | 53.64 | 0 | 0 | 0 | 0 | 0 | 0 | 53.64
2025-06-05 | 0 | 6308.6988 | 0 | 0 | 3350.3012 | 602.4096 | 0 | 0 | 10261.4096 | 0 | 25692.32 | 0 | 0 | 0 | 0 | 0 | 0 | 25692.32
2025-06-06 | 0 | 7570.4386 | 0 | 0 | 4020.3614 | 722.8916 | 0 | 0 | 12313.6916 | 0 | 25692.32 | 0 | 0 | 0 | 0 | 0 | 0 | 25692.32
2025-06-07 | 0 | 8832.1783 | 0 | 0 | 4690.4217 | 843.3735 | 0 | 0 | 14365.9735 | 0 | 25692.32 | 0 | 0 | 0 | 0 | 0 | 0 | 25692.32
2025-06-08 | 0 | 10093.9181 | 0 | 0 | 5360.4819 | 963.8554 | 0 | 0 | 16418.2554 | 0 | 25692.32 | 0 | 0 | 0 | 0 | 0 | 0 | 25692.32
2025-06-09 | 0 | 11355.6578 | 0 | 0 | 6030.5422 | 1084.3373 | 0 | 0 | 18470.5373 | 0 | 25692.32 | 0 | 0 | 0 | 0 | 0 | 0 | 25692.32
2025-06-10 | 0 | 12617.3976 | 0 | 0 | 6700.6024 | 1204.8193 | 0 | 0 | 20522.8193 | 0 | 25692.32 | 0 | 0 | 0 | 0 | 0 | 0 | 25692.32
2025-06-11 | 0 | 13879.1373 | 0 | 0 | 7370.6627 | 1325.3012 | 0 | 0 | 22575.1012 | 0 | 25692.32 | 0 | 0 | 0 | 0 | 0 | 0 | 25692.32
2025-06-12 | 0 | 15140.8771 | 0 | 0 | 8040.7229 | 1445.7831 | 0 | 0 | 24627.3831 | 0 | 25692.32 | 0 | 0 | 0 | 0 | 0 | 0 | 25692.32
2025-06-13 | 0 | 16402.6169 | 0 | 0 | 8710.7831 | 1566.2651 | 0 | 0 | 26679.6651 | 0 | 25692.32 | 0 | 0 | 0 | 0 | 0 | 0 | 25692.32
2025-06-14 | 0 | 17664.3566 | 0 | 0 | 9380.8434 | 1686.747 | 0 | 0 | 28731.947 | 0 | 25692.32 | 0 | 0 | 0 | 0 | 0 | 0 | 25692.32
2025-06-15 | 0 | 18926.0964 | 0 | 0 | 10050.9036 | 1807.2289 | 0 | 0 | 30784.2289 | 0 | 25692.32 | 0 | 0 | 0 | 0 | 0 | 0 | 25692.32
2025-06-16 | 0 | 20187.8361 | 0 | 0 | 10720.9639 | 1927.7108 | 0 | 0 | 32836.5108 | 0 | 25692.32 | 0 | 0 | 0 | 0 | 0 | 0 | 25692.32
2025-06-17 | 0 | 21449.5759 | 0 | 0 | 11391.0241 | 2048.1928 | 0 | 0 | 34888.7928 | 0 | 25692.32 | 0 | 0 | 0 | 0 | 0 | 0 | 25692.32
2025-06-18 | 0 | 22711.3157 | 0 | 0 | 12061.0843 | 2168.6747 | 0 | 0 | 36941.0747 | 0 | 25692.32 | 0 | 0 | 0 | 0 | 0 | 0 | 25692.32
2025-06-19 | 0 | 23973.0554 | 0 | 0 | 12731.1446 | 2289.1566 | 0 | 0 | 38993.3566 | 0 | 25692.32 | 0 | 0 | 0 | 0 | 0 | 0 | 25692.32
2025-06-20 | 0 | 25234.7952 | 0 | 0 | 13401.2048 | 2409.6386 | 0 | 0 | 41045.6386 | 0 | 25692.32 | 0 | 0 | 0 | 0 | 0 | 582.5 | 26274.82
2025-06-21 | 0 | 26496.5349 | 0 | 0 | 14071.2651 | 2530.1205 | 0 | 0 | 43097.9205 | 0 | 25692.32 | 0 | 0 | 0 | 0 | 0 | 582.5 | 26274.82
2025-06-22 | 0 | 27758.2747 | 0 | 0 | 14741.3253 | 2650.6024 | 0 | 0 | 45150.2024 | 0 | 25692.32 | 0 | 0 | 0 | 0 | 0 | 582.5 | 26274.82
2025-06-23 | 0 | 29020.0145 | 0 | 0 | 15411.3855 | 2771.0843 | 0 | 0 | 47202.4843 | 0 | 25692.32 | 0 | 0 | 0 | 0 | 0 | 582.5 | 26274.82
2025-06-24 | 0 | 30281.7542 | 0 | 0 | 16081.4458 | 2891.5663 | 0 | 0 | 49254.7663 | 0 | 25939.32 | 0 | 0 | 0 | 0 | 0 | 582.5 | 26521.82
2025-06-25 | 0 | 31543.494 | 0 | 0 | 16751.506 | 3012.0482 | 0 | 0 | 51307.0482 | 0 | 26327.72 | 0 | 0 | 0 | 0 | 0 | 582.5 | 26910.22
2025-06-26 | 0 | 32805.2337 | 0 | 0 | 17421.5663 | 3132.5301 | 0 | 0 | 53359.3301 | 0 | 26327.72 | 0 | 0 | 0 | 0 | 0 | 582.5 | 26910.22
2025-06-27 | 0 | 34066.9735 | 0 | 0 | 18091.6265 | 3253.012 | 0 | 0 | 55411.612 | 0 | 26327.72 | 0 | 0 | 0 | 0 | 0 | 582.5 | 26910.22
2025-06-28 | 0 | 35328.7133 | 0 | 0 | 18761.6867 | 3373.494 | 0 | 0 | 57463.894 | 0 | 26327.72 | 0 | 0 | 0 | 0 | 0 | 582.5 | 26910.22
2025-06-29 | 0 | 36590.453 | 0 | 0 | 19431.747 | 3493.9759 | 0 | 0 | 59516.1759 | 0 | 26327.72 | 0 | 0 | 0 | 0 | 0 | 582.5 | 26910.22
2025-06-30 | 0 | 37852.1928 | 0 | 0 | 20101.8072 | 3614.4578 | 0 | 0 | 61568.4578 | 0 | 26327.72 | 0 | 0 | 0 | 0 | 0 | 582.5 | 26910.22
2025-07-01 | 0 | 39113.9325 | 0 | 0 | 20771.8675 | 3734.9398 | 0 | 0 | 63620.7398 | 37227.57 | 27810.97 | 0 | 0 | 0 | 0 | 0 | 582.5 | 65621.04
2025-07-02 | 0 | 40375.6723 | 0 | 0 | 21441.9277 | 3855.4217 | 0 | 0 | 65673.0217 | 37227.57 | 27810.97 | 0 | 0 | 0 | 0 | 0 | 582.5 | 65621.04
2025-07-03 | 0 | 41637.412 | 0 | 0 | 22111.988 | 3975.9036 | 0 | 0 | 67725.3036 | 37227.57 | 27893.55 | 0 | 0 | 0 | 0 | 0 | 582.5 | 65703.62
2025-07-04 | 0 | 42899.1518 | 0 | 0 | 22782.0482 | 4096.3855 | 0 | 0 | 69777.5855 | 37227.57 | 28180.17 | 0 | 0 | 0 | 0 | 0 | 582.5 | 65990.24
2025-07-05 | 0 | 44160.8916 | 0 | 0 | 23452.1084 | 4216.8675 | 0 | 0 | 71829.8675 | 37227.57 | 28230.42 | 0 | 0 | 0 | 0 | 0 | 582.5 | 66040.49
2025-07-06 | 0 | 45422.6313 | 0 | 0 | 24122.1687 | 4337.3494 | 0 | 0 | 73882.1494 | 37227.57 | 28230.42 | 0 | 0 | 0 | 0 | 0 | 582.5 | 66040.49
2025-07-07 | 0 | 46684.3711 | 0 | 0 | 24792.2289 | 4457.8313 | 0 | 0 | 75934.4313 | 37227.57 | 28230.42 | 0 | 0 | 0 | 0 | 0 | 582.5 | 66040.49
2025-07-08 | 0 | 47946.1108 | 0 | 0 | 25462.2892 | 4578.3133 | 0 | 0 | 77986.7133 | 37227.57 | 28857.27 | 0 | 0 | 0 | 0 | 0 | 582.5 | 66667.34
2025-07-09 | 0 | 49207.8506 | 0 | 0 | 26132.3494 | 4698.7952 | 0 | 0 | 80038.9952 | 37227.57 | 28857.27 | 0 | 0 | 0 | 0 | 0 | 582.5 | 66667.34
2025-07-10 | 0 | 50469.5904 | 0 | 0 | 26802.4096 | 4819.2771 | 0 | 0 | 82091.2771 | 37227.57 | 28857.27 | 0 | 0 | 0 | 0 | 0 | 582.5 | 66667.34
2025-07-11 | 0 | 51731.3301 | 0 | 0 | 27472.4699 | 4939.759 | 0 | 0 | 84143.559 | 37227.57 | 30187.08 | 0 | 0 | 0 | 258.3 | 0 | 582.5 | 68255.45
2025-07-12 | 0 | 52993.0699 | 0 | 0 | 28142.5301 | 5060.241 | 0 | 0 | 86195.841 | 37227.57 | 30187.08 | 0 | 0 | 0 | 258.3 | 0 | 582.5 | 68255.45
2025-07-13 | 0 | 54254.8096 | 0 | 0 | 28812.5904 | 5180.7229 | 0 | 0 | 88248.1229 | 37227.57 | 30187.08 | 0 | 0 | 0 | 258.3 | 0 | 582.5 | 68255.45
2025-07-14 | 0 | 55516.5494 | 0 | 0 | 29482.6506 | 5301.2048 | 0 | 0 | 90300.4048 | 37227.57 | 35440.36 | 0 | 0 | 0 | 258.3 | 0 | 582.5 | 73508.73
2025-07-15 | 0 | 57724.0444 | 0 | 0 | 30233.5272 | 5421.6867 | 0 | 0 | 93379.2583 | 37227.57 | 36862.62 | 0 | 0 | 121.95 | 258.3 | 0 | 582.5 | 75052.94
2025-07-16 | 0 | 59931.5393 | 0 | 0 | 30984.4037 | 5542.1687 | 0 | 0 | 96458.1118 | 37227.57 | 37680.17 | 0 | 0 | 121.95 | 6558.3 | 0 | 582.5 | 82170.49
2025-07-17 | 0 | 62139.0343 | 0 | 0 | 31735.2803 | 5662.6506 | 0 | 0 | 99536.9652 | 37227.57 | 37981.29 | 0 | 0 | 121.95 | 6558.3 | 0 | 582.5 | 82471.61
2025-07-18 | 0 | 64346.5293 | 0 | 0 | 32486.1569 | 5783.1325 | 0 | 0 | 102615.8187 | 37227.57 | 43913.02 | 0 | 0 | 121.95 | 7008.3 | 0 | 582.5 | 88853.34
2025-07-19 | 0 | 66554.0243 | 0 | 0 | 33237.0334 | 5903.6145 | 0 | 0 | 105694.6722 | 37227.57 | 44704.71 | 0 | 0 | 121.95 | 7008.3 | 0 | 582.5 | 89645.03
2025-07-20 | 0 | 68761.5192 | 0 | 0 | 33987.91 | 6024.0964 | 0 | 0 | 108773.5256 | 37227.57 | 44704.71 | 0 | 0 | 121.95 | 7008.3 | 0 | 582.5 | 89645.03
2025-07-21 | 0 | 70969.0142 | 0 | 0 | 34738.7866 | 6144.5783 | 0 | 0 | 111852.3791 | 37227.57 | 44704.71 | 0 | 0 | 121.95 | 7008.3 | 0 | 582.5 | 89645.03
2025-07-22 | 0 | 73176.5092 | 0 | 0 | 35489.6631 | 6265.0602 | 0 | 0 | 114931.2326 | 37227.57 | 60107.64 | 0 | 0 | 121.95 | 7008.3 | 0 | 582.5 | 105047.96
2025-07-23 | 0 | 75384.0041 | 0 | 0 | 36240.5397 | 6385.5422 | 0 | 0 | 118010.086 | 37227.57 | 62980.56 | 0 | 0 | 121.95 | 7008.3 | 0 | 582.5 | 107920.88
2025-07-24 | 0 | 77591.4991 | 0 | 0 | 36991.4163 | 6506.0241 | 0 | 0 | 121088.9395 | 37227.57 | 63175.05 | 0 | 0 | 121.95 | 7008.3 | 0 | 582.5 | 108115.37
2025-07-25 | 0 | 79798.9941 | 0 | 0 | 37742.2928 | 6626.506 | 0 | 0 | 124167.793 | 37227.57 | 63539.82 | 0 | 0 | 121.95 | 7008.3 | 0 | 582.5 | 108480.14
2025-07-26 | 0 | 82006.4891 | 0 | 0 | 38493.1694 | 6746.988 | 0 | 0 | 127246.6464 | 37227.57 | 63555.95 | 0 | 0 | 121.95 | 7008.3 | 0 | 582.5 | 108496.27
2025-07-27 | 0 | 84213.984 | 0 | 0 | 39244.046 | 6867.4699 | 0 | 0 | 130325.4999 | 37227.57 | 63555.95 | 0 | 0 | 121.95 | 7008.3 | 0 | 582.5 | 108496.27
2025-07-28 | 0 | 86421.479 | 0 | 0 | 39994.9225 | 6987.9518 | 0 | 0 | 133404.3534 | 37227.57 | 63555.95 | 0 | 0 | 121.95 | 7008.3 | 0 | 582.5 | 108496.27
2025-07-29 | 0 | 88628.974 | 0 | 0 | 40745.7991 | 7108.4337 | 0 | 0 | 136483.2068 | 37227.57 | 63555.95 | 0 | 0 | 121.95 | 7008.3 | 0 | 582.5 | 108496.27
2025-07-30 | 0 | 90836.469 | 0 | 0 | 41496.6757 | 7228.9157 | 0 | 0 | 139562.0603 | 37227.57 | 64977.01 | 0 | 0 | 5793.13 | 7008.3 | 0 | 582.5 | 115588.51
2025-07-31 | 0 | 93043.9639 | 0 | 0 | 42247.5522 | 7349.3976 | 0 | 0 | 142640.9138 | 37227.57 | 64977.01 | 0 | 0 | 5793.13 | 7008.3 | 295.4 | 582.5 | 115883.91
2025-08-01 | 0 | 95251.4589 | 0 | 0 | 42998.4288 | 7469.8795 | 0 | 0 | 145719.7672 | 37227.57 | 65041.64 | 0 | 0 | 5793.13 | 7008.3 | 295.4 | 582.5 | 115948.54
2025-08-02 | 0 | 97458.9539 | 0 | 0 | 43749.3054 | 7590.3614 | 0 | 0 | 148798.6207 | 37227.57 | 65041.64 | 0 | 0 | 5793.13 | 7008.3 | 295.4 | 582.5 | 115948.54
2025-08-03 | 0 | 99666.4488 | 0 | 0 | 44500.182 | 7710.8434 | 0 | 0 | 151877.4742 | 37227.57 | 65041.64 | 0 | 0 | 5793.13 | 7008.3 | 295.4 | 582.5 | 115948.54
2025-08-04 | 0 | 101873.9438 | 0 | 0 | 45251.0585 | 7831.3253 | 0 | 0 | 154956.3276 | 37227.57 | 65123.99 | 0 | 0 | 5793.13 | 7008.3 | 295.4 | 582.5 | 116030.89
2025-08-05 | 0 | 104081.4388 | 0 | 0 | 46001.9351 | 7951.8072 | 0 | 0 | 158035.1811 | 37227.57 | 65123.99 | 0 | 0 | 8897.36 | 7008.3 | 295.4 | 582.5 | 119135.12
2025-08-06 | 0 | 106288.9338 | 0 | 0 | 46752.8117 | 8072.2892 | 0 | 0 | 161114.0346 | 37227.57 | 65123.99 | 0 | 0 | 8897.36 | 7008.3 | 295.4 | 582.5 | 119135.12
2025-08-07 | 0 | 108496.4287 | 0 | 0 | 47503.6882 | 8192.7711 | 0 | 0 | 164192.888 | 37227.57 | 65123.99 | 0 | 0 | 8897.36 | 7008.3 | 295.4 | 582.5 | 119135.12
2025-08-08 | 0 | 110703.9237 | 0 | 0 | 48254.5648 | 8313.253 | 0 | 0 | 167271.7415 | 37227.57 | 65123.99 | 0 | 0 | 8897.36 | 7008.3 | 295.4 | 582.5 | 119135.12
2025-08-09 | 0 | 112911.4187 | 0 | 0 | 49005.4414 | 8433.7349 | 0 | 0 | 170350.595 | 37227.57 | 65123.99 | 0 | 0 | 8897.36 | 7008.3 | 295.4 | 582.5 | 119135.12
2025-08-10 | 0 | 115118.9136 | 0 | 0 | 49756.3179 | 8554.2169 | 0 | 0 | 173429.4484 | 37227.57 | 65123.99 | 0 | 0 | 8897.36 | 7008.3 | 295.4 | 582.5 | 119135.12
2025-08-11 | 0 | 117326.4086 | 0 | 0 | 50507.1945 | 8674.6988 | 0 | 0 | 176508.3019 | 37227.57 | 65123.99 | 0 | 0 | 8897.36 | 7008.3 | 295.4 | 582.5 | 119135.12
2025-08-12 | 0 | 119533.9036 | 0 | 0 | 51258.0711 | 8795.1807 | 0 | 0 | 179587.1554 | 37227.57 | 65123.99 | 0 | 0 | 8897.36 | 7008.3 | 295.4 | 582.5 | 119135.12
2025-08-13 | 0 | 121741.3986 | 0 | 0 | 52008.9476 | 8915.6627 | 0 | 0 | 182666.0088 | 37227.57 | 65123.99 | 0 | 0 | 8897.36 | 7008.3 | 295.4 | 582.5 | 119135.12
2025-08-14 | 0 | 123948.8935 | 0 | 0 | 52759.8242 | 9036.1446 | 0 | 0 | 185744.8623 | 37227.57 | 65235.94 | 0 | 0 | 8897.36 | 8308.3 | 295.4 | 582.5 | 120547.07
2025-08-15 | 0 | 126156.3885 | 0 | 0 | 53510.7008 | 9156.6265 | 0 | 0 | 188823.7158 | 37227.57 | 65318.93 | 0 | 0 | 9961.36 | 8340.22 | 295.4 | 582.5 | 121725.98
2025-08-16 | 0 | 128363.8835 | 0 | 0 | 54261.5773 | 9277.1084 | 0 | 0 | 191902.5692 | 37227.57 | 65318.93 | 0 | 0 | 9961.36 | 8340.22 | 295.4 | 582.5 | 121725.98
2025-08-17 | 0 | 130571.3784 | 0 | 0 | 55012.4539 | 9397.5904 | 0 | 0 | 194981.4227 | 37227.57 | 65318.93 | 0 | 0 | 9961.36 | 8340.22 | 295.4 | 582.5 | 121725.98
2025-08-18 | 0 | 132778.8734 | 0 | 0 | 55763.3305 | 9518.0723 | 0 | 0 | 198060.2762 | 37227.57 | 65318.93 | 0 | 0 | 9961.36 | 8340.22 | 295.4 | 582.5 | 121725.98
2025-08-19 | 0 | 134986.3684 | 0 | 0 | 56514.207 | 9638.5542 | 0 | 0 | 201139.1296 | 37227.57 | 67877.99 | 0 | 0 | 9961.36 | 8340.22 | 295.4 | 582.5 | 124285.04
2025-08-20 | 0 | 137193.8634 | 0 | 0 | 57265.0836 | 9759.0361 | 0 | 0 | 204217.9831 | 37227.57 | 67877.99 | 0 | 0 | 9961.36 | 8340.22 | 295.4 | 582.5 | 124285.04
2025-08-21 | 0 | 139401.3583 | 0 | 0 | 58015.9602 | 9879.5181 | 0 | 0 | 207296.8366 | 37227.57 | 67877.99 | 0 | 0 | 9961.36 | 8340.22 | 295.4 | 582.5 | 124285.04
2025-08-22 | 0 | 141608.8533 | 0 | 0 | 58766.8367 | 10000 | 0 | 0 | 210375.69 | 37227.57 | 80811.18 | 0 | 0 | 9961.36 | 8340.22 | 295.4 | 582.5 | 137218.23
2025-08-23 | 0 | 142554.6085 | 0 | 0 | 58847.6531 | 10000 | 0 | 0 | 211402.2616 | 37227.57 | 80811.18 | 0 | 0 | 9961.36 | 8340.22 | 295.4 | 582.5 | 137218.23
2025-08-24 | 0 | 143500.3637 | 0 | 0 | 58928.4694 | 10000 | 0 | 0 | 212428.8331 | 37227.57 | 80811.18 | 0 | 0 | 9961.36 | 8340.22 | 295.4 | 582.5 | 137218.23
2025-08-25 | 0 | 144446.1189 | 0 | 0 | 59009.2857 | 10000 | 0 | 0 | 213455.4047 | 37227.57 | 80811.18 | 0 | 0 | 9961.36 | 8340.22 | 295.4 | 582.5 | 137218.23
2025-08-26 | 0 | 145391.8742 | 0 | 0 | 59090.102 | 10000 | 0 | 0 | 214481.9762 | 37227.57 | 86170.02 | 0 | 0 | 9961.36 | 8340.22 | 295.4 | 582.5 | 142577.07
2025-08-27 | 0 | 146337.6294 | 0 | 0 | 59170.9184 | 10000 | 0 | 0 | 215508.5477 | 37227.57 | 86863.17 | 0 | 0 | 9961.36 | 8340.22 | 295.4 | 582.5 | 143270.22
2025-08-28 | 0 | 147283.3846 | 0 | 0 | 59251.7347 | 10000 | 0 | 0 | 216535.1193 | 37227.57 | 86863.17 | 0 | 0 | 9961.36 | 8340.22 | 295.4 | 582.5 | 143270.22
2025-08-29 | 0 | 148229.1398 | 0 | 0 | 59332.551 | 10000 | 0 | 0 | 217561.6908 | 37227.57 | 86863.17 | 0 | 0 | 9961.36 | 8340.22 | 295.4 | 582.5 | 143270.22
2025-08-30 | 0 | 149174.895 | 0 | 0 | 59413.3673 | 10000 | 0 | 0 | 218588.2624 | 37227.57 | 86863.17 | 0 | 0 | 9961.36 | 8340.22 | 295.4 | 582.5 | 143270.22
2025-08-31 | 0 | 150120.6502 | 0 | 0 | 59494.1837 | 10000 | 0 | 0 | 219614.8339 | 37227.57 | 88145.17 | 0 | 0 | 9961.36 | 8340.22 | 295.4 | 582.5 | 144552.22
2025-09-01 | 0 | 151066.4054 | 0 | 0 | 59575 | 10000 | 0 | 0 | 220641.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-02 | 0 | 151544.5394 | 0 | 0 | 59575 | 10000 | 0 | 0 | 221119.5394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-03 | 0 | 152022.6733 | 0 | 0 | 59575 | 10000 | 0 | 0 | 221597.6733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-04 | 0 | 152500.8072 | 0 | 0 | 59575 | 10000 | 0 | 0 | 222075.8072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-05 | 0 | 152978.9412 | 0 | 0 | 59575 | 10000 | 0 | 0 | 222553.9412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-06 | 0 | 153457.0751 | 0 | 0 | 59575 | 10000 | 0 | 0 | 223032.0751 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-07 | 0 | 153935.209 | 0 | 0 | 59575 | 10000 | 0 | 0 | 223510.209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-08 | 0 | 154413.3429 | 0 | 0 | 59575 | 10000 | 0 | 0 | 223988.3429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-09 | 0 | 154891.4769 | 0 | 0 | 59575 | 10000 | 0 | 0 | 224466.4769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-10 | 0 | 155369.6108 | 0 | 0 | 59575 | 10000 | 0 | 0 | 224944.6108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-11 | 0 | 155847.7447 | 0 | 0 | 59575 | 10000 | 0 | 0 | 225422.7447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-12 | 0 | 156325.8787 | 0 | 0 | 59575 | 10000 | 0 | 0 | 225900.8787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-13 | 0 | 156804.0126 | 0 | 0 | 59575 | 10000 | 0 | 0 | 226379.0126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-14 | 0 | 157282.1465 | 0 | 0 | 59575 | 10000 | 0 | 0 | 226857.1465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-15 | 0 | 157760.2804 | 0 | 0 | 59575 | 10000 | 0 | 0 | 227335.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-16 | 0 | 158238.4144 | 0 | 0 | 59575 | 10000 | 0 | 0 | 227813.4144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-17 | 0 | 158716.5483 | 0 | 0 | 59575 | 10000 | 0 | 0 | 228291.5483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-18 | 0 | 159194.6822 | 0 | 0 | 59575 | 10000 | 0 | 0 | 228769.6822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-19 | 0 | 159672.8162 | 0 | 0 | 59575 | 10000 | 0 | 0 | 229247.8162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-20 | 0 | 160150.9501 | 0 | 0 | 59575 | 10000 | 0 | 0 | 229725.9501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-21 | 0 | 160629.084 | 0 | 0 | 59575 | 10000 | 0 | 0 | 230204.084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-22 | 0 | 161107.2179 | 0 | 0 | 59575 | 10000 | 0 | 0 | 230682.2179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-23 | 0 | 161585.3519 | 0 | 0 | 59575 | 10000 | 0 | 0 | 231160.3519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-24 | 0 | 162063.4858 | 0 | 0 | 59575 | 10000 | 0 | 0 | 231638.4858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-25 | 0 | 162541.6197 | 0 | 0 | 59575 | 10000 | 0 | 0 | 232116.6197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-26 | 0 | 163019.7537 | 0 | 0 | 59575 | 10000 | 0 | 0 | 232594.7537 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-27 | 0 | 163497.8876 | 0 | 0 | 59575 | 10000 | 0 | 0 | 233072.8876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-28 | 0 | 163976.0215 | 0 | 0 | 59575 | 10000 | 0 | 0 | 233551.0215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-29 | 0 | 164454.1554 | 0 | 0 | 59575 | 10000 | 0 | 0 | 234029.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-30 | 0 | 164932.2894 | 0 | 0 | 59575 | 10000 | 0 | 0 | 234507.2894 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-01 | 0 | 165410.4233 | 0 | 0 | 59575 | 10000 | 0 | 0 | 234985.4233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-02 | 0 | 165888.5572 | 0 | 0 | 59575 | 10000 | 0 | 0 | 235463.5572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-03 | 0 | 166366.6912 | 0 | 0 | 59575 | 10000 | 0 | 0 | 235941.6912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-04 | 0 | 166844.8251 | 0 | 0 | 59575 | 10000 | 0 | 0 | 236419.8251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-05 | 0 | 167322.959 | 0 | 0 | 59575 | 10000 | 0 | 0 | 236897.959 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-06 | 0 | 167801.0929 | 0 | 0 | 59575 | 10000 | 0 | 0 | 237376.0929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-07 | 0 | 168279.2269 | 0 | 0 | 59575 | 10000 | 0 | 0 | 237854.2269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-08 | 0 | 168757.3608 | 0 | 0 | 59575 | 10000 | 0 | 0 | 238332.3608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-09 | 0 | 169235.4947 | 0 | 0 | 59575 | 10000 | 0 | 0 | 238810.4947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-10 | 0 | 169713.6287 | 0 | 0 | 59575 | 10000 | 0 | 0 | 239288.6287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-11 | 0 | 170191.7626 | 0 | 0 | 59575 | 10000 | 0 | 0 | 239766.7626 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-12 | 0 | 170669.8965 | 0 | 0 | 59575 | 10000 | 0 | 0 | 240244.8965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-13 | 0 | 171148.0304 | 0 | 0 | 59575 | 10000 | 0 | 0 | 240723.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-14 | 0 | 171626.1644 | 0 | 0 | 59575 | 10000 | 0 | 0 | 241201.1644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-15 | 0 | 172104.2983 | 0 | 0 | 59575 | 10000 | 0 | 0 | 241679.2983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-16 | 0 | 172582.4322 | 0 | 0 | 59575 | 10000 | 0 | 0 | 242157.4322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-17 | 0 | 173060.5662 | 0 | 0 | 59575 | 10000 | 0 | 0 | 242635.5662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-18 | 0 | 173538.7001 | 0 | 0 | 59575 | 10000 | 0 | 0 | 243113.7001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-19 | 0 | 174016.834 | 0 | 0 | 59575 | 10000 | 0 | 0 | 243591.834 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-20 | 0 | 174494.9679 | 0 | 0 | 59575 | 10000 | 0 | 0 | 244069.9679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-21 | 0 | 174973.1019 | 0 | 0 | 59575 | 10000 | 0 | 0 | 244548.1019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-22 | 0 | 175451.2358 | 0 | 0 | 59575 | 10000 | 0 | 0 | 245026.2358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-23 | 0 | 175929.3697 | 0 | 0 | 59575 | 10000 | 0 | 0 | 245504.3697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-24 | 0 | 176407.5037 | 0 | 0 | 59575 | 10000 | 0 | 0 | 245982.5037 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-25 | 0 | 176885.6376 | 0 | 0 | 59575 | 10000 | 0 | 0 | 246460.6376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-26 | 0 | 177363.7715 | 0 | 0 | 59575 | 10000 | 0 | 0 | 246938.7715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-27 | 0 | 177841.9054 | 0 | 0 | 59575 | 10000 | 0 | 0 | 247416.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-28 | 0 | 177841.9054 | 68.625 | 0 | 59575 | 10000 | 0 | 0 | 247485.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-29 | 0 | 177841.9054 | 137.25 | 0 | 59575 | 10000 | 0 | 0 | 247554.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-30 | 0 | 177841.9054 | 205.875 | 0 | 59575 | 10000 | 0 | 0 | 247622.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-31 | 0 | 177841.9054 | 274.5 | 0 | 59575 | 10000 | 0 | 0 | 247691.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-01 | 0 | 177841.9054 | 343.125 | 0 | 59575 | 10000 | 0 | 0 | 247760.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-02 | 0 | 177841.9054 | 411.75 | 0 | 59575 | 10000 | 0 | 0 | 247828.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-03 | 0 | 177841.9054 | 480.375 | 0 | 59575 | 10000 | 0 | 0 | 247897.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-04 | 0 | 177841.9054 | 549 | 0 | 59575 | 10000 | 0 | 0 | 247965.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-05 | 0 | 177841.9054 | 617.625 | 0 | 59575 | 10000 | 0 | 0 | 248034.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-06 | 0 | 177841.9054 | 686.25 | 0 | 59575 | 10000 | 0 | 0 | 248103.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-07 | 0 | 177841.9054 | 754.875 | 0 | 59575 | 10000 | 0 | 0 | 248171.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-08 | 0 | 177841.9054 | 823.5 | 0 | 59575 | 10000 | 0 | 0 | 248240.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-09 | 0 | 177841.9054 | 892.125 | 0 | 59575 | 10000 | 0 | 0 | 248309.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-10 | 0 | 177841.9054 | 960.75 | 0 | 59575 | 10000 | 0 | 0 | 248377.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-11 | 0 | 177841.9054 | 1029.375 | 0 | 59575 | 10000 | 0 | 0 | 248446.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-12 | 0 | 177841.9054 | 1098 | 0 | 59575 | 10000 | 0 | 0 | 248514.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-13 | 0 | 177841.9054 | 1166.625 | 0 | 59575 | 10000 | 0 | 0 | 248583.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-14 | 0 | 177841.9054 | 1235.25 | 0 | 59575 | 10000 | 0 | 0 | 248652.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-15 | 0 | 177841.9054 | 1303.875 | 0 | 59575 | 10000 | 0 | 0 | 248720.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-16 | 0 | 177841.9054 | 1372.5 | 0 | 59575 | 10000 | 0 | 0 | 248789.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-17 | 0 | 177841.9054 | 1441.125 | 0 | 59575 | 10000 | 0 | 0 | 248858.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-18 | 0 | 177841.9054 | 1509.75 | 0 | 59575 | 10000 | 0 | 0 | 248926.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-19 | 0 | 177841.9054 | 1578.375 | 0 | 59575 | 10000 | 0 | 0 | 248995.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-20 | 0 | 177841.9054 | 1647 | 0 | 59575 | 10000 | 0 | 0 | 249063.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-21 | 0 | 177841.9054 | 1715.625 | 0 | 59575 | 10000 | 0 | 0 | 249132.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-22 | 0 | 177841.9054 | 1784.25 | 0 | 59575 | 10000 | 0 | 0 | 249201.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-23 | 0 | 177841.9054 | 1852.875 | 0 | 59575 | 10000 | 0 | 0 | 249269.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-24 | 0 | 177841.9054 | 1921.5 | 0 | 59575 | 10000 | 0 | 0 | 249338.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-25 | 0 | 177841.9054 | 1990.125 | 0 | 59575 | 10000 | 0 | 0 | 249407.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-26 | 0 | 177841.9054 | 2058.75 | 0 | 59575 | 10000 | 0 | 0 | 249475.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-27 | 0 | 177841.9054 | 2127.375 | 0 | 59575 | 10000 | 0 | 0 | 249544.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-28 | 0 | 177841.9054 | 2196 | 0 | 59575 | 10000 | 0 | 0 | 249612.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-29 | 0 | 177841.9054 | 2264.625 | 0 | 59575 | 10000 | 0 | 0 | 249681.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-30 | 0 | 177841.9054 | 2333.25 | 0 | 59575 | 10000 | 0 | 0 | 249750.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-01 | 0 | 177841.9054 | 2401.875 | 0 | 59575 | 10000 | 0 | 0 | 249818.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-02 | 0 | 177841.9054 | 2470.5 | 0 | 59575 | 10000 | 0 | 0 | 249887.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-03 | 0 | 177841.9054 | 2539.125 | 0 | 59575 | 10000 | 0 | 0 | 249956.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-04 | 0 | 177841.9054 | 2607.75 | 0 | 59575 | 10000 | 0 | 0 | 250024.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-05 | 0 | 177841.9054 | 2676.375 | 0 | 59575 | 10000 | 0 | 0 | 250093.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-06 | 0 | 177841.9054 | 2745 | 0 | 59575 | 10000 | 0 | 0 | 250161.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-07 | 0 | 177841.9054 | 2813.625 | 0 | 59575 | 10000 | 0 | 0 | 250230.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-08 | 0 | 177841.9054 | 2882.25 | 0 | 59575 | 10000 | 0 | 0 | 250299.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-09 | 0 | 177841.9054 | 2950.875 | 0 | 59575 | 10000 | 0 | 0 | 250367.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-10 | 0 | 177841.9054 | 3019.5 | 0 | 59575 | 10000 | 0 | 0 | 250436.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-11 | 0 | 177841.9054 | 3088.125 | 0 | 59575 | 10000 | 0 | 0 | 250505.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-12 | 0 | 177841.9054 | 3156.75 | 0 | 59575 | 10000 | 0 | 0 | 250573.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-13 | 0 | 177841.9054 | 3225.375 | 0 | 59575 | 10000 | 0 | 0 | 250642.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-14 | 0 | 177841.9054 | 3294 | 0 | 59575 | 10000 | 0 | 0 | 250710.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-15 | 0 | 177841.9054 | 3362.625 | 0 | 59575 | 10000 | 0 | 0 | 250779.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-16 | 0 | 177841.9054 | 3431.25 | 0 | 59575 | 10000 | 0 | 0 | 250848.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-17 | 0 | 177841.9054 | 3499.875 | 0 | 59575 | 10000 | 0 | 0 | 250916.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-18 | 0 | 177841.9054 | 3568.5 | 0 | 59575 | 10000 | 0 | 0 | 250985.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-19 | 0 | 177841.9054 | 3637.125 | 0 | 59575 | 10000 | 0 | 0 | 251054.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-20 | 0 | 177841.9054 | 3705.75 | 0 | 59575 | 10000 | 0 | 0 | 251122.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-21 | 0 | 177841.9054 | 3774.375 | 0 | 59575 | 10000 | 0 | 0 | 251191.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-22 | 0 | 177841.9054 | 3843 | 0 | 59575 | 10000 | 0 | 0 | 251259.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-23 | 0 | 177841.9054 | 3911.625 | 0 | 59575 | 10000 | 0 | 0 | 251328.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-24 | 0 | 177841.9054 | 3980.25 | 0 | 59575 | 10000 | 0 | 0 | 251397.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-25 | 0 | 177841.9054 | 4048.875 | 0 | 59575 | 10000 | 0 | 0 | 251465.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-26 | 0 | 177841.9054 | 4117.5 | 0 | 59575 | 10000 | 0 | 0 | 251534.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-27 | 0 | 177841.9054 | 4186.125 | 0 | 59575 | 10000 | 0 | 0 | 251603.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-28 | 0 | 177841.9054 | 4254.75 | 0 | 59575 | 10000 | 0 | 0 | 251671.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-29 | 0 | 177841.9054 | 4323.375 | 0 | 59575 | 10000 | 0 | 0 | 251740.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-30 | 0 | 177841.9054 | 4392 | 0 | 59575 | 10000 | 0 | 0 | 251808.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-31 | 0 | 177841.9054 | 4460.625 | 0 | 59575 | 10000 | 0 | 0 | 251877.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-01 | 0 | 177841.9054 | 4529.25 | 0 | 59575 | 10000 | 0 | 0 | 251946.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-02 | 0 | 177841.9054 | 4597.875 | 0 | 59575 | 10000 | 0 | 0 | 252014.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-03 | 0 | 177841.9054 | 4666.5 | 0 | 59575 | 10000 | 0 | 0 | 252083.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-04 | 0 | 177841.9054 | 4735.125 | 0 | 59575 | 10000 | 0 | 0 | 252152.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-05 | 0 | 177841.9054 | 4803.75 | 0 | 59575 | 10000 | 0 | 0 | 252220.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-06 | 0 | 177841.9054 | 4872.375 | 0 | 59575 | 10000 | 0 | 0 | 252289.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-07 | 0 | 177841.9054 | 4941 | 0 | 59575 | 10000 | 0 | 0 | 252357.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-08 | 0 | 177841.9054 | 5009.625 | 0 | 59575 | 10000 | 0 | 0 | 252426.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-09 | 0 | 177841.9054 | 5078.25 | 0 | 59575 | 10000 | 0 | 0 | 252495.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-10 | 0 | 177841.9054 | 5146.875 | 0 | 59575 | 10000 | 0 | 0 | 252563.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-11 | 0 | 177841.9054 | 5215.5 | 0 | 59575 | 10000 | 0 | 0 | 252632.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-12 | 0 | 177841.9054 | 5284.125 | 0 | 59575 | 10000 | 0 | 0 | 252701.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-13 | 0 | 177841.9054 | 5352.75 | 0 | 59575 | 10000 | 0 | 0 | 252769.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-14 | 0 | 177841.9054 | 5421.375 | 0 | 59575 | 10000 | 0 | 0 | 252838.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-15 | 0 | 177841.9054 | 5490 | 0 | 59575 | 10000 | 0 | 0 | 252906.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-16 | 0 | 177841.9054 | 5558.625 | 0 | 59575 | 10000 | 0 | 0 | 252975.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-17 | 0 | 177841.9054 | 5627.25 | 0 | 59575 | 10000 | 0 | 0 | 253044.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-18 | 0 | 177841.9054 | 5695.875 | 0 | 59575 | 10000 | 0 | 0 | 253112.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-19 | 0 | 177841.9054 | 5764.5 | 0 | 59575 | 10000 | 0 | 0 | 253181.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-20 | 0 | 177841.9054 | 5833.125 | 0 | 59575 | 10000 | 0 | 0 | 253250.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-21 | 0 | 177841.9054 | 5901.75 | 0 | 59575 | 10000 | 0 | 0 | 253318.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-22 | 0 | 177841.9054 | 5970.375 | 0 | 59575 | 10000 | 0 | 0 | 253387.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-23 | 0 | 177841.9054 | 6039 | 0 | 59575 | 10000 | 0 | 0 | 253455.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-24 | 0 | 177841.9054 | 6107.625 | 0 | 59575 | 10000 | 0 | 0 | 253524.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-25 | 0 | 177841.9054 | 6176.25 | 0 | 59575 | 10000 | 0 | 0 | 253593.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-26 | 0 | 177841.9054 | 6244.875 | 0 | 59575 | 10000 | 0 | 0 | 253661.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-27 | 0 | 177841.9054 | 6313.5 | 0 | 59575 | 10000 | 0 | 0 | 253730.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-28 | 0 | 177841.9054 | 6382.125 | 0 | 59575 | 10000 | 0 | 0 | 253799.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-29 | 0 | 177841.9054 | 6450.75 | 0 | 59575 | 10000 | 0 | 0 | 253867.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-30 | 0 | 177841.9054 | 6519.375 | 0 | 59575 | 10000 | 0 | 0 | 253936.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-31 | 0 | 177841.9054 | 6588 | 0 | 59575 | 10000 | 0 | 0 | 254004.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-01 | 0 | 177841.9054 | 6656.625 | 0 | 59575 | 10000 | 0 | 0 | 254073.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-02 | 0 | 177841.9054 | 6725.25 | 0 | 59575 | 10000 | 0 | 0 | 254142.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-03 | 0 | 177841.9054 | 6793.875 | 0 | 59575 | 10000 | 0 | 0 | 254210.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-04 | 0 | 177841.9054 | 6862.5 | 0 | 59575 | 10000 | 0 | 0 | 254279.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-05 | 0 | 177841.9054 | 6931.125 | 0 | 59575 | 10000 | 0 | 0 | 254348.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-06 | 0 | 177841.9054 | 6999.75 | 0 | 59575 | 10000 | 0 | 0 | 254416.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-07 | 0 | 177841.9054 | 7068.375 | 0 | 59575 | 10000 | 0 | 0 | 254485.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-08 | 0 | 177841.9054 | 7137 | 0 | 59575 | 10000 | 0 | 0 | 254553.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-09 | 0 | 177841.9054 | 7205.625 | 0 | 59575 | 10000 | 0 | 0 | 254622.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-10 | 0 | 177841.9054 | 7274.25 | 0 | 59575 | 10000 | 0 | 0 | 254691.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-11 | 0 | 177841.9054 | 7342.875 | 0 | 59575 | 10000 | 0 | 0 | 254759.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-12 | 0 | 177841.9054 | 7411.5 | 0 | 59575 | 10000 | 0 | 0 | 254828.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-13 | 0 | 177841.9054 | 7480.125 | 0 | 59575 | 10000 | 0 | 0 | 254897.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-14 | 0 | 177841.9054 | 7548.75 | 0 | 59575 | 10000 | 0 | 0 | 254965.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-15 | 0 | 177841.9054 | 7617.375 | 0 | 59575 | 10000 | 0 | 0 | 255034.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-16 | 0 | 177841.9054 | 7686 | 0 | 59575 | 10000 | 0 | 0 | 255102.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-17 | 0 | 177841.9054 | 7754.625 | 0 | 59575 | 10000 | 0 | 0 | 255171.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-18 | 0 | 177841.9054 | 7823.25 | 0 | 59575 | 10000 | 0 | 0 | 255240.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-19 | 0 | 177841.9054 | 7891.875 | 0 | 59575 | 10000 | 0 | 0 | 255308.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-20 | 0 | 177841.9054 | 7960.5 | 0 | 59575 | 10000 | 0 | 0 | 255377.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-21 | 0 | 177841.9054 | 8029.125 | 0 | 59575 | 10000 | 0 | 0 | 255446.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-22 | 0 | 177841.9054 | 8097.75 | 0 | 59575 | 10000 | 0 | 0 | 255514.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-23 | 0 | 177841.9054 | 8166.375 | 0 | 59575 | 10000 | 0 | 0 | 255583.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-24 | 0 | 177841.9054 | 8235 | 0 | 59575 | 10000 | 0 | 0 | 255651.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-25 | 0 | 177841.9054 | 8303.625 | 0 | 59575 | 10000 | 0 | 0 | 255720.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-26 | 0 | 177841.9054 | 8372.25 | 0 | 59575 | 10000 | 0 | 0 | 255789.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-27 | 0 | 177841.9054 | 8440.875 | 0 | 59575 | 10000 | 0 | 0 | 255857.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-28 | 0 | 177841.9054 | 8509.5 | 0 | 59575 | 10000 | 0 | 0 | 255926.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-01 | 0 | 177841.9054 | 8578.125 | 0 | 59575 | 10000 | 0 | 0 | 255995.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-02 | 0 | 177841.9054 | 8646.75 | 0 | 59575 | 10000 | 0 | 0 | 256063.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-03 | 0 | 177841.9054 | 8715.375 | 0 | 59575 | 10000 | 0 | 0 | 256132.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-04 | 0 | 177841.9054 | 8784 | 0 | 59575 | 10000 | 0 | 0 | 256200.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-05 | 0 | 177841.9054 | 8852.625 | 0 | 59575 | 10000 | 0 | 0 | 256269.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-06 | 0 | 177841.9054 | 8921.25 | 0 | 59575 | 10000 | 0 | 0 | 256338.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-07 | 0 | 177841.9054 | 8989.875 | 0 | 59575 | 10000 | 0 | 0 | 256406.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-08 | 0 | 177841.9054 | 9058.5 | 0 | 59575 | 10000 | 0 | 0 | 256475.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-09 | 0 | 177841.9054 | 9127.125 | 0 | 59575 | 10000 | 0 | 0 | 256544.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-10 | 0 | 177841.9054 | 9195.75 | 0 | 59575 | 10000 | 0 | 0 | 256612.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-11 | 0 | 177841.9054 | 9264.375 | 0 | 59575 | 10000 | 0 | 0 | 256681.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-12 | 0 | 177841.9054 | 9333 | 0 | 59575 | 10000 | 0 | 0 | 256749.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-13 | 0 | 177841.9054 | 9401.625 | 0 | 59575 | 10000 | 0 | 0 | 256818.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-14 | 0 | 177841.9054 | 9470.25 | 0 | 59575 | 10000 | 0 | 0 | 256887.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-15 | 0 | 177841.9054 | 9538.875 | 0 | 59575 | 10000 | 0 | 0 | 256955.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-16 | 0 | 177841.9054 | 9607.5 | 0 | 59575 | 10000 | 0 | 0 | 257024.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-17 | 0 | 177841.9054 | 9676.125 | 0 | 59575 | 10000 | 0 | 0 | 257093.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-18 | 0 | 177841.9054 | 9744.75 | 0 | 59575 | 10000 | 0 | 0 | 257161.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-19 | 0 | 177841.9054 | 9813.375 | 0 | 59575 | 10000 | 0 | 0 | 257230.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-20 | 0 | 177841.9054 | 9882 | 0 | 59575 | 10000 | 0 | 0 | 257298.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-21 | 0 | 177841.9054 | 9950.625 | 0 | 59575 | 10000 | 0 | 0 | 257367.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-22 | 0 | 177841.9054 | 10019.25 | 0 | 59575 | 10000 | 0 | 0 | 257436.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-23 | 0 | 177841.9054 | 10087.875 | 0 | 59575 | 10000 | 0 | 0 | 257504.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-24 | 0 | 177841.9054 | 10156.5 | 0 | 59575 | 10000 | 0 | 0 | 257573.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-25 | 0 | 177841.9054 | 10225.125 | 0 | 59575 | 10000 | 0 | 0 | 257642.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-26 | 0 | 177841.9054 | 10293.75 | 0 | 59575 | 10000 | 0 | 0 | 257710.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-27 | 0 | 177841.9054 | 10362.375 | 0 | 59575 | 10000 | 0 | 0 | 257779.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-28 | 0 | 177841.9054 | 10431 | 0 | 59575 | 10000 | 0 | 0 | 257847.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-29 | 0 | 177841.9054 | 10499.625 | 0 | 59575 | 10000 | 0 | 0 | 257916.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-30 | 0 | 177841.9054 | 10568.25 | 0 | 59575 | 10000 | 0 | 0 | 257985.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-31 | 0 | 177841.9054 | 10636.875 | 0 | 59575 | 10000 | 0 | 0 | 258053.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-01 | 0 | 177841.9054 | 10705.5 | 0 | 59575 | 10000 | 0 | 0 | 258122.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-02 | 0 | 177841.9054 | 10774.125 | 0 | 59575 | 10000 | 0 | 0 | 258191.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-03 | 0 | 177841.9054 | 10842.75 | 0 | 59575 | 10000 | 0 | 0 | 258259.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-04 | 0 | 177841.9054 | 10911.375 | 0 | 59575 | 10000 | 0 | 0 | 258328.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-05 | 0 | 177841.9054 | 10980 | 0 | 59575 | 10000 | 0 | 0 | 258396.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-06 | 0 | 177841.9054 | 11048.625 | 0 | 59575 | 10000 | 0 | 0 | 258465.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-07 | 0 | 177841.9054 | 11117.25 | 0 | 59575 | 10000 | 0 | 0 | 258534.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-08 | 0 | 177841.9054 | 11185.875 | 0 | 59575 | 10000 | 0 | 0 | 258602.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-09 | 0 | 177841.9054 | 11254.5 | 0 | 59575 | 10000 | 0 | 0 | 258671.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-10 | 0 | 177841.9054 | 11323.125 | 0 | 59575 | 10000 | 0 | 0 | 258740.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-11 | 0 | 177841.9054 | 11391.75 | 0 | 59575 | 10000 | 0 | 0 | 258808.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-12 | 0 | 177841.9054 | 11460.375 | 0 | 59575 | 10000 | 0 | 0 | 258877.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-13 | 0 | 177841.9054 | 11529 | 0 | 59575 | 10000 | 0 | 0 | 258945.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-14 | 0 | 177841.9054 | 11597.625 | 0 | 59575 | 10000 | 0 | 0 | 259014.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-15 | 0 | 177841.9054 | 11666.25 | 0 | 59575 | 10000 | 0 | 0 | 259083.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-16 | 0 | 177841.9054 | 11734.875 | 0 | 59575 | 10000 | 0 | 0 | 259151.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-17 | 0 | 177841.9054 | 11803.5 | 0 | 59575 | 10000 | 0 | 0 | 259220.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-18 | 0 | 177841.9054 | 11872.125 | 0 | 59575 | 10000 | 0 | 0 | 259289.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-19 | 0 | 177841.9054 | 11940.75 | 0 | 59575 | 10000 | 0 | 0 | 259357.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-20 | 0 | 177841.9054 | 12009.375 | 0 | 59575 | 10000 | 0 | 0 | 259426.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-21 | 0 | 177841.9054 | 12078 | 0 | 59575 | 10000 | 0 | 0 | 259494.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-22 | 0 | 177841.9054 | 12146.625 | 0 | 59575 | 10000 | 0 | 0 | 259563.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-23 | 0 | 177841.9054 | 12215.25 | 0 | 59575 | 10000 | 0 | 0 | 259632.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-24 | 0 | 177841.9054 | 12283.875 | 0 | 59575 | 10000 | 0 | 0 | 259700.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-25 | 0 | 177841.9054 | 12352.5 | 0 | 59575 | 10000 | 0 | 0 | 259769.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-26 | 0 | 177841.9054 | 12421.125 | 0 | 59575 | 10000 | 0 | 0 | 259838.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-27 | 0 | 177841.9054 | 12489.75 | 0 | 59575 | 10000 | 0 | 0 | 259906.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-28 | 0 | 177841.9054 | 12558.375 | 0 | 59575 | 10000 | 0 | 0 | 259975.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-29 | 0 | 177841.9054 | 12627 | 0 | 59575 | 10000 | 0 | 0 | 260043.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-30 | 0 | 177841.9054 | 12695.625 | 0 | 59575 | 10000 | 0 | 0 | 260112.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-01 | 0 | 177841.9054 | 12764.25 | 0 | 59575 | 10000 | 0 | 0 | 260181.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-02 | 0 | 177841.9054 | 12832.875 | 0 | 59575 | 10000 | 0 | 0 | 260249.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-03 | 0 | 177841.9054 | 12901.5 | 0 | 59575 | 10000 | 0 | 0 | 260318.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-04 | 0 | 177841.9054 | 12970.125 | 0 | 59575 | 10000 | 0 | 0 | 260387.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-05 | 0 | 177841.9054 | 13038.75 | 0 | 59575 | 10000 | 0 | 0 | 260455.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-06 | 0 | 177841.9054 | 13107.375 | 0 | 59575 | 10000 | 0 | 0 | 260524.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-07 | 0 | 177841.9054 | 13176 | 0 | 59575 | 10000 | 0 | 0 | 260592.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-08 | 0 | 177841.9054 | 13244.625 | 0 | 59575 | 10000 | 0 | 0 | 260661.5304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-09 | 0 | 177841.9054 | 13313.25 | 0 | 59575 | 10000 | 0 | 0 | 260730.1554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-10 | 0 | 177841.9054 | 13381.875 | 0 | 59575 | 10000 | 0 | 0 | 260798.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-11 | 0 | 177841.9054 | 13450.5 | 0 | 59575 | 10000 | 0 | 0 | 260867.4054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-12 | 0 | 177841.9054 | 13519.125 | 0 | 59575 | 10000 | 0 | 0 | 260936.0304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-13 | 0 | 177841.9054 | 13587.75 | 0 | 59575 | 10000 | 0 | 0 | 261004.6554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-14 | 0 | 177841.9054 | 13656.375 | 0 | 59575 | 10000 | 0 | 0 | 261073.2804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-15 | 0 | 177841.9054 | 13725 | 0 | 59575 | 10000 | 0 | 0 | 261141.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-16 | 0 | 177841.9054 | 13725 | 0 | 59575 | 10000 | 0 | 0 | 261141.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-17 | 0 | 177841.9054 | 13725 | 0 | 59575 | 10000 | 0 | 0 | 261141.9054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-18 | 0 | 178064.8178 | 13725 | 0 | 59711.3636 | 10363.6364 | 0 | 0 | 261864.8178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-19 | 0 | 178287.7301 | 13725 | 0 | 59847.7273 | 10727.2727 | 0 | 0 | 262587.7301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-20 | 0 | 178510.6425 | 13725 | 0 | 59984.0909 | 11090.9091 | 0 | 0 | 263310.6425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-21 | 0 | 178733.5548 | 13725 | 0 | 60120.4545 | 11454.5455 | 0 | 0 | 264033.5548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-22 | 0 | 178956.4671 | 13725 | 0 | 60256.8182 | 11818.1818 | 0 | 0 | 264756.4671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-23 | 0 | 179179.3795 | 13725 | 0 | 60393.1818 | 12181.8182 | 0 | 0 | 265479.3795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-24 | 0 | 179402.2918 | 13725 | 0 | 60529.5455 | 12545.4545 | 0 | 0 | 266202.2918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-25 | 0 | 179625.2042 | 13725 | 0 | 60665.9091 | 12909.0909 | 0 | 0 | 266925.2042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-26 | 0 | 179848.1165 | 13725 | 0 | 60802.2727 | 13272.7273 | 0 | 0 | 267648.1165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-27 | 0 | 180071.0288 | 13725 | 0 | 60938.6364 | 13636.3636 | 0 | 0 | 268371.0288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-28 | 0 | 180293.9412 | 13725 | 0 | 61075 | 14000 | 0 | 0 | 269093.9412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-29 | 0 | 180516.8535 | 13725 | 0 | 61211.3636 | 14363.6364 | 0 | 0 | 269816.8535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-30 | 0 | 180739.7659 | 13725 | 0 | 61347.7273 | 14727.2727 | 0 | 0 | 270539.7659 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-31 | 0 | 180962.6782 | 13725 | 0 | 61484.0909 | 15090.9091 | 0 | 0 | 271262.6782 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-01 | 0 | 181185.5906 | 13725 | 0 | 61620.4545 | 15454.5455 | 0 | 0 | 271985.5906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-02 | 0 | 181408.5029 | 13725 | 0 | 61756.8182 | 15818.1818 | 0 | 0 | 272708.5029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-03 | 0 | 181631.4152 | 13725 | 0 | 61893.1818 | 16181.8182 | 0 | 0 | 273431.4152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-04 | 0 | 181854.3276 | 13725 | 0 | 62029.5455 | 16545.4545 | 0 | 0 | 274154.3276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-05 | 0 | 182077.2399 | 13725 | 0 | 62165.9091 | 16909.0909 | 0 | 0 | 274877.2399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-06 | 0 | 182300.1523 | 13725 | 0 | 62302.2727 | 17272.7273 | 0 | 0 | 275600.1523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-07 | 0 | 182523.0646 | 13725 | 0 | 62438.6364 | 17636.3636 | 0 | 0 | 276323.0646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-08 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-09 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-10 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-11 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-12 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-13 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-14 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-15 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-16 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-17 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-18 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-19 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-20 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-21 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-22 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-23 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-24 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-25 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-26 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-27 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-28 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-29 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-30 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-01 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-02 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-03 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-04 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-05 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-06 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-07 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-08 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-09 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-10 | 0 | 182745.9769 | 13725 | 0 | 62575 | 18000 | 0 | 0 | 277045.9769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0