## Summary
Task ID | Task Name | Status | Schedule | Planned Duration | Actual Duration | Duration % | Invoice | Income Received | Income % | Planned Spend | Actual Spend | Spent Cost % | Profit % | Planned Labor Days | Actual Labor Days | Applied Labor %
100 | Design and Plans For Thermal Remediation | Completed | 04/01/25 - 05/30/25 | 48 | 44 | 92% | 105053.625 | 105053.63 | 100% | 77817.5 | 17830.97 | 23% | 489% | 137.5 | 31 | 23%
200 | Site Preparation & Mobilization Prep | Completed | 06/01/25 - 08/22/25 | 50 | 60 | 120% | 344279.25 | 352897.05 | 103% | 357756.6 | 239400.88 | 67% | 47% | 20 | 14 | 70%
300 | Drilling and Well Installation | Completed | 07/21/25 - 09/01/25 | 35 | 31 | 89% | 592513.235 | 504930.08 | 85% | 498551.8558 | 426267.76 | 86% | 18% | 91 | 132 | 145%
400 | Construction and Installation | Completed | 09/02/25 - 01/28/26 | 30 | 107 | 357% | 279193.4456 | 246716.79 | 88% | 218009.4962 | 593132.8 | 272% | -58% | 195 | 315.75 | 162%
500 | Operation and Maintenance | In Progress | 01/29/26 - 08/16/26 | 200 | 49 | 24% | 648306.4923 | 92438.79 | 14% | 437461.4253 | 79612.35 | 18% | 16% | 537.24 | 135.375 | 25%
600 | Demobilization | Future | 08/18/26 - 09/08/26 | 16 |  |  | 278872.0413 | 0 |  | 189445.2548 | 0 |  |  | 114 | 0
700 | Reporting | Future | 08/18/26 - 10/12/26 | 40 |  |  | 46149.75 | 0 |  | 34185 | 0 |  |  | 66.4 | 0
| TOTAL |  | 04/01/25 - 10/12/26 | 559 | 352 | 63% | 2294367.8392 | 1302036.34 | 57% | 1813227.1321 | 1356244.76 | 75% | -4% | 1161.14 | 628.125 | 54%

## Invoice Sum
Date | Planned Income (Cumulative) | Actual Income (Daily) | Actual Income (Cumulative) | Planned Labor Sum (Cumulative) | Planned Travel&perdiem (Direct Cost) Sum (Cumulative) | Planned Parts&materials (Direct Cost) Sum (Cumulative) | Planned Outsource (Direct Cost) Sum (Cumulative) | Planned Equipment (Cumulative) | Planned 1805 · EQUIPMENT - FORKLIFT (Cumulative) | Planned 1818 · EQUIPMENT - BCU (Cumulative) | Planned 1819 · EQUIPMENT - TPMB (Cumulative) | Planned 1820 · EQUIPMENT & TOOLS (Cumulative) | Planned 1821 · EQUIPMENT - C3 (Cumulative) | Planned 1822 · EQUIPMENT - C2 (Cumulative) | Planned 1823 · EQUIPMENT - TCU BASIC (Cumulative) | Planned 1824 · EQUIPMENT - TCU PLC (Cumulative) | Planned 1825 · EQUIPMENT - BLOWER SKIDS (Cumulative) | Planned 1826 · EQUIPMENT - WELL HEADS (Cumulative) | Planned 1827 · EQUIPMENT - THERMAL WELLS (Cumulative) | Planned 1829 · EQUIPMENT - WATER TREATMENT SYS (Cumulative) | Planned 1830 · EQUIPMENT - VAPOR EXTRACTION (Cumulative) | Planned 1831 · EQUIPMENT - GTR/C3 COMPONENTS (Cumulative) | Planned 1832 · EQUIP - CONTROL/DIST PANELS (Cumulative) | Planned 1833 · EQUIPMENT - OFFICE & COMPUTER (Cumulative) | Planned 5004 · GTR COST OF SALES - PARTS (Cumulative) | Planned 5006 · DRILLING EXPENSE (Cumulative) | Planned 5101 · SALARY AND WAGES (DIRECT) (Cumulative) | Planned 5102 · PAYROLL TAXES (DIRECT) (Cumulative) | Planned 5105 · TRAVEL - AIRFARE (DIRECT) (Cumulative) | Planned 5106 · TRAVEL - HOTEL (DIRECT) (Cumulative) | Planned 5107 · TRAVEL - OTHER (DIRECT) (Cumulative) | Planned 5108 · MEALS & ENTERTAINMENT (DIRECT) (Cumulative) | Planned 5110 · TEMPORARY LABOR (DIRECT) (Cumulative) | Planned 5111 · PARTS & MATERIAL COSTS (DIRECT) (Cumulative) | Planned 5112 · CARBON & LAB SAMPLIES (DRIECT) (Cumulative) | Planned 5113 · REPAIRS & MAINT (DIRECT) (Cumulative) | Planned 5114 · RENT - BUILDING (DIRECT) (Cumulative) | Planned 5115 · RENT - EQUIPMENT (DIRECT) (Cumulative) | Planned 5120 · OUTSIDE SERVICES (DIRECT) (Cumulative) | Planned 5121 · FREIGHT & SHIPPING (DIRECT) (Cumulative) | Planned 5122 · MOTOR VEHICLE EXP (DIRECT) (Cumulative) | Planned 5123 · AUTO FUEL (DIRECT) (Cumulative) | Planned 5124 · LICENSE AND PERMITS (DIRECT) (Cumulative) | Planned 5128 · HEALTH & SAFETY EQUIP (DIRECT) (Cumulative) | Planned 5129 · MISC EXPENSES (DIRECT) (Cumulative) | Planned 5132 · INTERNET FEE (DIRECT) (Cumulative) | Planned 6999 · UNCATEGORIZED EXPENSES (Cumulative) | Planned 4001 · SERVICE INCOME (Cumulative) | Planned 4002 · EQUIPMENT RENTAL INCOME (Cumulative) | Planned 4003 · MOBILIZATION INCOME (Cumulative) | Planned 4004 · DEMOBILIZATION INCOME (Cumulative) | Planned 4005 · PERDIEM INCOME (Cumulative) | Planned 4006 · DRILLING INCOME (Cumulative) | Planned 4011 · - SERVICE INCOME - (Cumulative) | Planned 4012 · GTR- UNITS SOLD (Cumulative) | Planned 4100 · ACCOUNTS RECEIVABLE (Cumulative) | Planned 4110 · MARK UP ACCOUNT (Cumulative)
2025-04-01 | 1750.8937 | 0 | 0 | 1750.8937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750.8937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-02 | 3501.7875 | 0 | 0 | 3501.7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3501.7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 5252.6812 | 0 | 0 | 5252.6812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5252.6812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 7003.575 | 0 | 0 | 7003.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7003.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 8754.4688 | 0 | 0 | 8754.4688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8754.4688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 10505.3625 | 0 | 0 | 10505.3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10505.3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 12256.2563 | 0 | 0 | 12256.2563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12256.2563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 14007.15 | 0 | 0 | 14007.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14007.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 15758.0438 | 0 | 0 | 15758.0438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15758.0438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 17508.9375 | 0 | 0 | 17508.9375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17508.9375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 19259.8312 | 0 | 0 | 19259.8312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19259.8312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 21010.725 | 0 | 0 | 21010.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21010.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 22761.6187 | 0 | 0 | 22761.6187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22761.6187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 24512.5125 | 0 | 0 | 24512.5125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24512.5125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 26263.4062 | 0 | 0 | 26263.4062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26263.4062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 28014.3 | 0 | 0 | 28014.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28014.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 29765.1937 | 0 | 0 | 29765.1937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29765.1937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 31516.0875 | 0 | 0 | 31516.0875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31516.0875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 33266.9812 | 0 | 0 | 33266.9812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33266.9812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 35017.875 | 0 | 0 | 35017.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35017.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 36768.7688 | 0 | 0 | 36768.7688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36768.7688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 38519.6625 | 0 | 0 | 38519.6625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38519.6625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 40270.5563 | 0 | 0 | 40270.5563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40270.5563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 42021.45 | 0 | 0 | 42021.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42021.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 43772.3438 | 0 | 0 | 43772.3438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43772.3438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 45523.2375 | 0 | 0 | 45523.2375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45523.2375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 47274.1313 | 0 | 0 | 47274.1313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47274.1313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 49025.025 | 0 | 0 | 49025.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49025.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 50775.9188 | 0 | 0 | 50775.9188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50775.9188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 52526.8125 | 0 | 0 | 52526.8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52526.8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 54277.7063 | 0 | 0 | 54277.7063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54277.7063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 56028.6 | 0 | 0 | 56028.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56028.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 57779.4938 | 0 | 0 | 57779.4938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57779.4938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 59530.3875 | 0 | 0 | 59530.3875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59530.3875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 61281.2813 | 0 | 0 | 61281.2813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61281.2813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 63032.175 | 0 | 0 | 63032.175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63032.175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 64783.0688 | 0 | 0 | 64783.0688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64783.0688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 66533.9625 | 0 | 0 | 66533.9625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66533.9625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 68284.8563 | 0 | 0 | 68284.8563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68284.8563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 70035.75 | 0 | 0 | 70035.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70035.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 71786.6438 | 0 | 0 | 71786.6438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71786.6438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 73537.5375 | 0 | 0 | 73537.5375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73537.5375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 75288.4313 | 0 | 0 | 75288.4313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75288.4313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 77039.325 | 0 | 0 | 77039.325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77039.325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 78790.2188 | 0 | 0 | 78790.2188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78790.2188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 80541.1125 | 0 | 0 | 80541.1125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80541.1125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 82292.0063 | 0 | 0 | 82292.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82292.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 84042.9 | 0 | 0 | 84042.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84042.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 85793.7938 | 0 | 0 | 85793.7938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85793.7938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 87544.6875 | 0 | 0 | 87544.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87544.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 89295.5813 | 0 | 0 | 89295.5813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89295.5813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 91046.475 | 0 | 0 | 91046.475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91046.475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 92797.3688 | 0 | 0 | 92797.3688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92797.3688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 94548.2625 | 0 | 0 | 94548.2625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94548.2625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 96299.1563 | 0 | 0 | 96299.1563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96299.1563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 98050.05 | 0 | 0 | 98050.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98050.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 99800.9438 | 0 | 0 | 99800.9438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99800.9438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 101551.8375 | 0 | 0 | 101551.8375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101551.8375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 103302.7313 | 0 | 0 | 103302.7313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103302.7313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 105053.625 | 0 | 0 | 105053.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105053.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 109201.5678 | 0 | 0 | 105217.0889 | 100.8434 | 1640.2617 | 1306.409 | 936.9648 | 0 | 96.4819 | 15.6627 | 0 | 0 | 462.2863 | 159.759 | 0 | 0 | 0 | 0 | 0 | 77.4737 | 50.1205 | 75.1807 | 0 | 0 | 0 | 105217.0889 | 0 | 9.759 | 59.2048 | 9.1084 | 22.7711 | 0 | 1640.2617 | 0 | 0 | 0 | 435.5392 | 651.5928 | 156.6265 | 0 | 0 | 0 | 0 | 0 | 62.6506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 113349.5105 | 0 | 0 | 105380.5527 | 201.6867 | 3280.5234 | 2612.8181 | 1873.9296 | 0 | 192.9639 | 31.3253 | 0 | 0 | 924.5725 | 319.5181 | 0 | 0 | 0 | 0 | 0 | 154.9475 | 100.241 | 150.3614 | 0 | 0 | 0 | 105380.5527 | 0 | 19.5181 | 118.4096 | 18.2169 | 45.5422 | 0 | 3280.5234 | 0 | 0 | 0 | 871.0783 | 1303.1855 | 313.253 | 0 | 0 | 0 | 0 | 0 | 125.3012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 117497.4533 | 0 | 0 | 105544.0166 | 302.5301 | 4920.7851 | 3919.2271 | 2810.8945 | 0 | 289.4458 | 46.988 | 0 | 0 | 1386.8588 | 479.2771 | 0 | 0 | 0 | 0 | 0 | 232.4212 | 150.3614 | 225.5422 | 0 | 0 | 0 | 105544.0166 | 0 | 29.2771 | 177.6145 | 27.3253 | 68.3133 | 0 | 4920.7851 | 0 | 0 | 0 | 1306.6175 | 1954.7783 | 469.8795 | 0 | 0 | 0 | 0 | 0 | 187.9518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 121645.3961 | 0 | 0 | 105707.4804 | 403.3735 | 6561.0467 | 5225.6361 | 3747.8593 | 0 | 385.9277 | 62.6506 | 0 | 0 | 1849.1451 | 639.0361 | 0 | 0 | 0 | 0 | 0 | 309.8949 | 200.4819 | 300.7229 | 0 | 0 | 0 | 105707.4804 | 0 | 39.0361 | 236.8193 | 36.4337 | 91.0843 | 0 | 6561.0467 | 0 | 0 | 0 | 1742.1566 | 2606.3711 | 626.506 | 0 | 0 | 0 | 0 | 0 | 250.6024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 125793.3389 | 0 | 0 | 105870.9443 | 504.2169 | 8201.3084 | 6532.0452 | 4684.8241 | 0 | 482.4096 | 78.3133 | 0 | 0 | 2311.4313 | 798.7952 | 0 | 0 | 0 | 0 | 0 | 387.3687 | 250.6024 | 375.9036 | 0 | 0 | 0 | 105870.9443 | 0 | 48.7952 | 296.0241 | 45.5422 | 113.8554 | 0 | 8201.3084 | 0 | 0 | 0 | 2177.6958 | 3257.9639 | 783.1325 | 0 | 0 | 0 | 0 | 0 | 313.253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 129941.2816 | 0 | 0 | 106034.4081 | 605.0602 | 9841.5701 | 7838.4542 | 5621.7889 | 0 | 578.8916 | 93.9759 | 0 | 0 | 2773.7176 | 958.5542 | 0 | 0 | 0 | 0 | 0 | 464.8424 | 300.7229 | 451.0843 | 0 | 0 | 0 | 106034.4081 | 0 | 58.5542 | 355.2289 | 54.6506 | 136.6265 | 0 | 9841.5701 | 0 | 0 | 0 | 2613.2349 | 3909.5566 | 939.759 | 0 | 0 | 0 | 0 | 0 | 375.9036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 134089.2244 | 0 | 0 | 106197.872 | 705.9036 | 11481.8318 | 9144.8633 | 6558.7537 | 0 | 675.3735 | 109.6386 | 0 | 0 | 3236.0039 | 1118.3133 | 0 | 0 | 0 | 0 | 0 | 542.3161 | 350.8434 | 526.2651 | 0 | 0 | 0 | 106197.872 | 0 | 68.3133 | 414.4337 | 63.759 | 159.3976 | 0 | 11481.8318 | 0 | 0 | 0 | 3048.7741 | 4561.1494 | 1096.3855 | 0 | 0 | 0 | 0 | 0 | 438.5542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 138237.1672 | 0 | 0 | 106361.3358 | 806.747 | 13122.0935 | 10451.2723 | 7495.7186 | 0 | 771.8554 | 125.3012 | 0 | 0 | 3698.2901 | 1278.0723 | 0 | 0 | 0 | 0 | 0 | 619.7899 | 400.9639 | 601.4458 | 0 | 0 | 0 | 106361.3358 | 0 | 78.0723 | 473.6386 | 72.8675 | 182.1687 | 0 | 13122.0935 | 0 | 0 | 0 | 3484.3133 | 5212.7422 | 1253.012 | 0 | 0 | 0 | 0 | 0 | 501.2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 142385.1099 | 0 | 0 | 106524.7997 | 907.5904 | 14762.3552 | 11757.6813 | 8432.6834 | 0 | 868.3373 | 140.9639 | 0 | 0 | 4160.5764 | 1437.8313 | 0 | 0 | 0 | 0 | 0 | 697.2636 | 451.0843 | 676.6265 | 0 | 0 | 0 | 106524.7997 | 0 | 87.8313 | 532.8434 | 81.9759 | 204.9398 | 0 | 14762.3552 | 0 | 0 | 0 | 3919.8524 | 5864.3349 | 1409.6386 | 0 | 0 | 0 | 0 | 0 | 563.8554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 146533.0527 | 0 | 0 | 106688.2636 | 1008.4337 | 16402.6169 | 13064.0904 | 9369.6482 | 0 | 964.8193 | 156.6265 | 0 | 0 | 4622.8627 | 1597.5904 | 0 | 0 | 0 | 0 | 0 | 774.7373 | 501.2048 | 751.8072 | 0 | 0 | 0 | 106688.2636 | 0 | 97.5904 | 592.0482 | 91.0843 | 227.7108 | 0 | 16402.6169 | 0 | 0 | 0 | 4355.3916 | 6515.9277 | 1566.2651 | 0 | 0 | 0 | 0 | 0 | 626.506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 150680.9955 | 0 | 0 | 106851.7274 | 1109.2771 | 18042.8786 | 14370.4994 | 10306.613 | 0 | 1061.3012 | 172.2892 | 0 | 0 | 5085.1489 | 1757.3494 | 0 | 0 | 0 | 0 | 0 | 852.2111 | 551.3253 | 826.988 | 0 | 0 | 0 | 106851.7274 | 0 | 107.3494 | 651.253 | 100.1928 | 250.4819 | 0 | 18042.8786 | 0 | 0 | 0 | 4790.9307 | 7167.5205 | 1722.8916 | 0 | 0 | 0 | 0 | 0 | 689.1566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 154828.9383 | 0 | 0 | 107015.1913 | 1210.1205 | 19683.1402 | 15676.9084 | 11243.5778 | 0 | 1157.7831 | 187.9518 | 0 | 0 | 5547.4352 | 1917.1084 | 0 | 0 | 0 | 0 | 0 | 929.6848 | 601.4458 | 902.1687 | 0 | 0 | 0 | 107015.1913 | 0 | 117.1084 | 710.4578 | 109.3012 | 273.253 | 0 | 19683.1402 | 0 | 0 | 0 | 5226.4699 | 7819.1133 | 1879.5181 | 0 | 0 | 0 | 0 | 0 | 751.8072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 158976.881 | 0 | 0 | 107178.6551 | 1310.9639 | 21323.4019 | 16983.3175 | 12180.5427 | 0 | 1254.2651 | 203.6145 | 0 | 0 | 6009.7214 | 2076.8675 | 0 | 0 | 0 | 0 | 0 | 1007.1586 | 651.5663 | 977.3494 | 0 | 0 | 0 | 107178.6551 | 0 | 126.8675 | 769.6627 | 118.4096 | 296.0241 | 0 | 21323.4019 | 0 | 0 | 0 | 5662.009 | 8470.706 | 2036.1446 | 0 | 0 | 0 | 0 | 0 | 814.4578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 163124.8238 | 0 | 0 | 107342.119 | 1411.8072 | 22963.6636 | 18289.7265 | 13117.5075 | 0 | 1350.747 | 219.2771 | 0 | 0 | 6472.0077 | 2236.6265 | 0 | 0 | 0 | 0 | 0 | 1084.6323 | 701.6867 | 1052.5301 | 0 | 0 | 0 | 107342.119 | 0 | 136.6265 | 828.8675 | 127.5181 | 318.7952 | 0 | 22963.6636 | 0 | 0 | 0 | 6097.5482 | 9122.2988 | 2192.7711 | 0 | 0 | 0 | 0 | 0 | 877.1084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 167272.7666 | 0 | 0 | 107505.5828 | 1512.6506 | 24603.9253 | 19596.1355 | 14054.4723 | 0 | 1447.2289 | 234.9398 | 0 | 0 | 6934.294 | 2396.3855 | 0 | 0 | 0 | 0 | 0 | 1162.106 | 751.8072 | 1127.7108 | 0 | 0 | 0 | 107505.5828 | 0 | 146.3855 | 888.0723 | 136.6265 | 341.5663 | 0 | 24603.9253 | 0 | 0 | 0 | 6533.0873 | 9773.8916 | 2349.3976 | 0 | 0 | 0 | 0 | 0 | 939.759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 171420.7093 | 0 | 0 | 107669.0467 | 1613.494 | 26244.187 | 20902.5446 | 14991.4371 | 0 | 1543.7108 | 250.6024 | 0 | 0 | 7396.5802 | 2556.1446 | 0 | 0 | 0 | 0 | 0 | 1239.5798 | 801.9277 | 1202.8916 | 0 | 0 | 0 | 107669.0467 | 0 | 156.1446 | 947.2771 | 145.7349 | 364.3373 | 0 | 26244.187 | 0 | 0 | 0 | 6968.6265 | 10425.4843 | 2506.0241 | 0 | 0 | 0 | 0 | 0 | 1002.4096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 175568.6521 | 0 | 0 | 107832.5105 | 1714.3373 | 27884.4487 | 22208.9536 | 15928.4019 | 0 | 1640.1928 | 266.2651 | 0 | 0 | 7858.8665 | 2715.9036 | 0 | 0 | 0 | 0 | 0 | 1317.0535 | 852.0482 | 1278.0723 | 0 | 0 | 0 | 107832.5105 | 0 | 165.9036 | 1006.4819 | 154.8434 | 387.1084 | 0 | 27884.4487 | 0 | 0 | 0 | 7404.1657 | 11077.0771 | 2662.6506 | 0 | 0 | 0 | 0 | 0 | 1065.0602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 179716.5949 | 0 | 0 | 107995.9744 | 1815.1807 | 29524.7104 | 23515.3627 | 16865.3667 | 0 | 1736.6747 | 281.9277 | 0 | 0 | 8321.1528 | 2875.6627 | 0 | 0 | 0 | 0 | 0 | 1394.5272 | 902.1687 | 1353.253 | 0 | 0 | 0 | 107995.9744 | 0 | 175.6627 | 1065.6867 | 163.9518 | 409.8795 | 0 | 29524.7104 | 0 | 0 | 0 | 7839.7048 | 11728.6699 | 2819.2771 | 0 | 0 | 0 | 0 | 0 | 1127.7108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 183864.5377 | 0 | 0 | 108159.4383 | 1916.0241 | 31164.972 | 24821.7717 | 17802.3316 | 0 | 1833.1566 | 297.5904 | 0 | 0 | 8783.439 | 3035.4217 | 0 | 0 | 0 | 0 | 0 | 1472.001 | 952.2892 | 1428.4337 | 0 | 0 | 0 | 108159.4383 | 0 | 185.4217 | 1124.8916 | 173.0602 | 432.6506 | 0 | 31164.972 | 0 | 0 | 0 | 8275.244 | 12380.2627 | 2975.9036 | 0 | 0 | 0 | 0 | 0 | 1190.3614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 188012.4804 | 0 | 0 | 108322.9021 | 2016.8675 | 32805.2337 | 26128.1807 | 18739.2964 | 0 | 1929.6386 | 313.253 | 0 | 0 | 9245.7253 | 3195.1807 | 0 | 0 | 0 | 0 | 0 | 1549.4747 | 1002.4096 | 1503.6145 | 0 | 0 | 0 | 108322.9021 | 0 | 195.1807 | 1184.0964 | 182.1687 | 455.4217 | 0 | 32805.2337 | 0 | 0 | 0 | 8710.7831 | 13031.8554 | 3132.5301 | 0 | 0 | 0 | 0 | 0 | 1253.012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 192160.4232 | 0 | 0 | 108486.366 | 2117.7108 | 34445.4954 | 27434.5898 | 19676.2612 | 0 | 2026.1205 | 328.9157 | 0 | 0 | 9708.0116 | 3354.9398 | 0 | 0 | 0 | 0 | 0 | 1626.9484 | 1052.5301 | 1578.7952 | 0 | 0 | 0 | 108486.366 | 0 | 204.9398 | 1243.3012 | 191.2771 | 478.1928 | 0 | 34445.4954 | 0 | 0 | 0 | 9146.3223 | 13683.4482 | 3289.1566 | 0 | 0 | 0 | 0 | 0 | 1315.6627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 196308.366 | 0 | 0 | 108649.8298 | 2218.5542 | 36085.7571 | 28740.9988 | 20613.226 | 0 | 2122.6024 | 344.5783 | 0 | 0 | 10170.2978 | 3514.6988 | 0 | 0 | 0 | 0 | 0 | 1704.4222 | 1102.6506 | 1653.9759 | 0 | 0 | 0 | 108649.8298 | 0 | 214.6988 | 1302.506 | 200.3855 | 500.9639 | 0 | 36085.7571 | 0 | 0 | 0 | 9581.8614 | 14335.041 | 3445.7831 | 0 | 0 | 0 | 0 | 0 | 1378.3133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 200456.3087 | 0 | 0 | 108813.2937 | 2319.3976 | 37726.0188 | 30047.4078 | 21550.1908 | 0 | 2219.0843 | 360.241 | 0 | 0 | 10632.5841 | 3674.4578 | 0 | 0 | 0 | 0 | 0 | 1781.8959 | 1152.7711 | 1729.1566 | 0 | 0 | 0 | 108813.2937 | 0 | 224.4578 | 1361.7108 | 209.494 | 523.7349 | 0 | 37726.0188 | 0 | 0 | 0 | 10017.4006 | 14986.6337 | 3602.4096 | 0 | 0 | 0 | 0 | 0 | 1440.9639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 204604.2515 | 0 | 0 | 108976.7575 | 2420.241 | 39366.2805 | 31353.8169 | 22487.1557 | 0 | 2315.5663 | 375.9036 | 0 | 0 | 11094.8704 | 3834.2169 | 0 | 0 | 0 | 0 | 0 | 1859.3696 | 1202.8916 | 1804.3373 | 0 | 0 | 0 | 108976.7575 | 0 | 234.2169 | 1420.9157 | 218.6024 | 546.506 | 0 | 39366.2805 | 0 | 0 | 0 | 10452.9398 | 15638.2265 | 3759.0361 | 0 | 0 | 0 | 0 | 0 | 1503.6145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 208752.1943 | 0 | 0 | 109140.2214 | 2521.0843 | 41006.5422 | 32660.2259 | 23424.1205 | 0 | 2412.0482 | 391.5663 | 0 | 0 | 11557.1566 | 3993.9759 | 0 | 0 | 0 | 0 | 0 | 1936.8434 | 1253.012 | 1879.5181 | 0 | 0 | 0 | 109140.2214 | 0 | 243.9759 | 1480.1205 | 227.7108 | 569.2771 | 0 | 41006.5422 | 0 | 0 | 0 | 10888.4789 | 16289.8193 | 3915.6627 | 0 | 0 | 0 | 0 | 0 | 1566.2651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-26 | 212900.137 | 0 | 0 | 109303.6852 | 2621.9277 | 42646.8039 | 33966.6349 | 24361.0853 | 0 | 2508.5301 | 407.2289 | 0 | 0 | 12019.4429 | 4153.7349 | 0 | 0 | 0 | 0 | 0 | 2014.3171 | 1303.1325 | 1954.6988 | 0 | 0 | 0 | 109303.6852 | 0 | 253.7349 | 1539.3253 | 236.8193 | 592.0482 | 0 | 42646.8039 | 0 | 0 | 0 | 11324.0181 | 16941.412 | 4072.2892 | 0 | 0 | 0 | 0 | 0 | 1628.9157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-27 | 217048.0798 | 0 | 0 | 109467.1491 | 2722.7711 | 44287.0655 | 35273.044 | 25298.0501 | 0 | 2605.012 | 422.8916 | 0 | 0 | 12481.7292 | 4313.494 | 0 | 0 | 0 | 0 | 0 | 2091.7908 | 1353.253 | 2029.8795 | 0 | 0 | 0 | 109467.1491 | 0 | 263.494 | 1598.5301 | 245.9277 | 614.8193 | 0 | 44287.0655 | 0 | 0 | 0 | 11759.5572 | 17593.0048 | 4228.9157 | 0 | 0 | 0 | 0 | 0 | 1691.5663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-28 | 221196.0226 | 0 | 0 | 109630.613 | 2823.6145 | 45927.3272 | 36579.453 | 26235.0149 | 0 | 2701.494 | 438.5542 | 0 | 0 | 12944.0154 | 4473.253 | 0 | 0 | 0 | 0 | 0 | 2169.2646 | 1403.3735 | 2105.0602 | 0 | 0 | 0 | 109630.613 | 0 | 273.253 | 1657.7349 | 255.0361 | 637.5904 | 0 | 45927.3272 | 0 | 0 | 0 | 12195.0964 | 18244.5976 | 4385.5422 | 0 | 0 | 0 | 0 | 0 | 1754.2169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-29 | 225343.9654 | 0 | 0 | 109794.0768 | 2924.4578 | 47567.5889 | 37885.862 | 27171.9798 | 0 | 2797.9759 | 454.2169 | 0 | 0 | 13406.3017 | 4633.012 | 0 | 0 | 0 | 0 | 0 | 2246.7383 | 1453.494 | 2180.241 | 0 | 0 | 0 | 109794.0768 | 0 | 283.012 | 1716.9398 | 264.1446 | 660.3614 | 0 | 47567.5889 | 0 | 0 | 0 | 12630.6355 | 18896.1904 | 4542.1687 | 0 | 0 | 0 | 0 | 0 | 1816.8675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-30 | 229491.9081 | 0 | 0 | 109957.5407 | 3025.3012 | 49207.8506 | 39192.2711 | 28108.9446 | 0 | 2894.4578 | 469.8795 | 0 | 0 | 13868.588 | 4792.7711 | 0 | 0 | 0 | 0 | 0 | 2324.212 | 1503.6145 | 2255.4217 | 0 | 0 | 0 | 109957.5407 | 0 | 292.7711 | 1776.1446 | 273.253 | 683.1325 | 0 | 49207.8506 | 0 | 0 | 0 | 13066.1747 | 19547.7831 | 4698.7952 | 0 | 0 | 0 | 0 | 0 | 1879.5181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-01 | 233639.8509 | 0 | 0 | 110121.0045 | 3126.1446 | 50848.1123 | 40498.6801 | 29045.9094 | 0 | 2990.9398 | 485.5422 | 0 | 0 | 14330.8742 | 4952.5301 | 0 | 0 | 0 | 0 | 0 | 2401.6858 | 1553.7349 | 2330.6024 | 0 | 0 | 0 | 110121.0045 | 0 | 302.5301 | 1835.3494 | 282.3614 | 705.9036 | 0 | 50848.1123 | 0 | 0 | 0 | 13501.7139 | 20199.3759 | 4855.4217 | 0 | 0 | 0 | 0 | 0 | 1942.1687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-02 | 237787.7937 | 0 | 0 | 110284.4684 | 3226.988 | 52488.374 | 41805.0892 | 29982.8742 | 0 | 3087.4217 | 501.2048 | 0 | 0 | 14793.1605 | 5112.2892 | 0 | 0 | 0 | 0 | 0 | 2479.1595 | 1603.8554 | 2405.7831 | 0 | 0 | 0 | 110284.4684 | 0 | 312.2892 | 1894.5542 | 291.4699 | 728.6747 | 0 | 52488.374 | 0 | 0 | 0 | 13937.253 | 20850.9687 | 5012.0482 | 0 | 0 | 0 | 0 | 0 | 2004.8193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-03 | 241935.7364 | 0 | 0 | 110447.9322 | 3327.8313 | 54128.6357 | 43111.4982 | 30919.839 | 0 | 3183.9036 | 516.8675 | 0 | 0 | 15255.4467 | 5272.0482 | 0 | 0 | 0 | 0 | 0 | 2556.6333 | 1653.9759 | 2480.9639 | 0 | 0 | 0 | 110447.9322 | 0 | 322.0482 | 1953.759 | 300.5783 | 751.4458 | 0 | 54128.6357 | 0 | 0 | 0 | 14372.7922 | 21502.5614 | 5168.6747 | 0 | 0 | 0 | 0 | 0 | 2067.4699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-04 | 246083.6792 | 0 | 0 | 110611.3961 | 3428.6747 | 55768.8973 | 44417.9072 | 31856.8039 | 0 | 3280.3855 | 532.5301 | 0 | 0 | 15717.733 | 5431.8072 | 0 | 0 | 0 | 0 | 0 | 2634.107 | 1704.0964 | 2556.1446 | 0 | 0 | 0 | 110611.3961 | 0 | 331.8072 | 2012.9639 | 309.6867 | 774.2169 | 0 | 55768.8973 | 0 | 0 | 0 | 14808.3313 | 22154.1542 | 5325.3012 | 0 | 0 | 0 | 0 | 0 | 2130.1205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-05 | 250231.622 | 0 | 0 | 110774.8599 | 3529.5181 | 57409.159 | 45724.3163 | 32793.7687 | 0 | 3376.8675 | 548.1928 | 0 | 0 | 16180.0193 | 5591.5663 | 0 | 0 | 0 | 0 | 0 | 2711.5807 | 1754.2169 | 2631.3253 | 0 | 0 | 0 | 110774.8599 | 0 | 341.5663 | 2072.1687 | 318.7952 | 796.988 | 0 | 57409.159 | 0 | 0 | 0 | 15243.8705 | 22805.747 | 5481.9277 | 0 | 0 | 0 | 0 | 0 | 2192.7711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-06 | 254379.5648 | 0 | 0 | 110938.3238 | 3630.3614 | 59049.4207 | 47030.7253 | 33730.7335 | 0 | 3473.3494 | 563.8554 | 0 | 0 | 16642.3055 | 5751.3253 | 0 | 0 | 0 | 0 | 0 | 2789.0545 | 1804.3373 | 2706.506 | 0 | 0 | 0 | 110938.3238 | 0 | 351.3253 | 2131.3735 | 327.9036 | 819.759 | 0 | 59049.4207 | 0 | 0 | 0 | 15679.4096 | 23457.3398 | 5638.5542 | 0 | 0 | 0 | 0 | 0 | 2255.4217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-07 | 258527.5075 | 0 | 0 | 111101.7877 | 3731.2048 | 60689.6824 | 48337.1343 | 34667.6983 | 0 | 3569.8313 | 579.5181 | 0 | 0 | 17104.5918 | 5911.0843 | 0 | 0 | 0 | 0 | 0 | 2866.5282 | 1854.4578 | 2781.6867 | 0 | 0 | 0 | 111101.7877 | 0 | 361.0843 | 2190.5783 | 337.012 | 842.5301 | 0 | 60689.6824 | 0 | 0 | 0 | 16114.9488 | 24108.9325 | 5795.1807 | 0 | 0 | 0 | 0 | 0 | 2318.0723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-08 | 262675.4503 | 0 | 0 | 111265.2515 | 3832.0482 | 62329.9441 | 49643.5434 | 35604.6631 | 0 | 3666.3133 | 595.1807 | 0 | 0 | 17566.8781 | 6070.8434 | 0 | 0 | 0 | 0 | 0 | 2944.0019 | 1904.5783 | 2856.8675 | 0 | 0 | 0 | 111265.2515 | 0 | 370.8434 | 2249.7831 | 346.1205 | 865.3012 | 0 | 62329.9441 | 0 | 0 | 0 | 16550.488 | 24760.5253 | 5951.8072 | 0 | 0 | 0 | 0 | 0 | 2380.7229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-09 | 266823.3931 | 0 | 0 | 111428.7154 | 3932.8916 | 63970.2058 | 50949.9524 | 36541.628 | 0 | 3762.7952 | 610.8434 | 0 | 0 | 18029.1643 | 6230.6024 | 0 | 0 | 0 | 0 | 0 | 3021.4757 | 1954.6988 | 2932.0482 | 0 | 0 | 0 | 111428.7154 | 0 | 380.6024 | 2308.988 | 355.2289 | 888.0723 | 0 | 63970.2058 | 0 | 0 | 0 | 16986.0271 | 25412.1181 | 6108.4337 | 0 | 0 | 0 | 0 | 0 | 2443.3735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-10 | 270971.3358 | 0 | 0 | 111592.1792 | 4033.7349 | 65610.4675 | 52256.3614 | 37478.5928 | 0 | 3859.2771 | 626.506 | 0 | 0 | 18491.4506 | 6390.3614 | 0 | 0 | 0 | 0 | 0 | 3098.9494 | 2004.8193 | 3007.2289 | 0 | 0 | 0 | 111592.1792 | 0 | 390.3614 | 2368.1928 | 364.3373 | 910.8434 | 0 | 65610.4675 | 0 | 0 | 0 | 17421.5663 | 26063.7108 | 6265.0602 | 0 | 0 | 0 | 0 | 0 | 2506.0241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-11 | 275119.2786 | 0 | 0 | 111755.6431 | 4134.5783 | 67250.7292 | 53562.7705 | 38415.5576 | 0 | 3955.759 | 642.1687 | 0 | 0 | 18953.7369 | 6550.1205 | 0 | 0 | 0 | 0 | 0 | 3176.4231 | 2054.9398 | 3082.4096 | 0 | 0 | 0 | 111755.6431 | 0 | 400.1205 | 2427.3976 | 373.4458 | 933.6145 | 0 | 67250.7292 | 0 | 0 | 0 | 17857.1054 | 26715.3036 | 6421.6867 | 0 | 0 | 0 | 0 | 0 | 2568.6747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-12 | 279267.2214 | 0 | 0 | 111919.1069 | 4235.4217 | 68890.9908 | 54869.1795 | 39352.5224 | 0 | 4052.241 | 657.8313 | 0 | 0 | 19416.0231 | 6709.8795 | 0 | 0 | 0 | 0 | 0 | 3253.8969 | 2105.0602 | 3157.5904 | 0 | 0 | 0 | 111919.1069 | 0 | 409.8795 | 2486.6024 | 382.5542 | 956.3855 | 0 | 68890.9908 | 0 | 0 | 0 | 18292.6446 | 27366.8964 | 6578.3133 | 0 | 0 | 0 | 0 | 0 | 2631.3253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-13 | 283415.1642 | 0 | 0 | 112082.5708 | 4336.2651 | 70531.2525 | 56175.5886 | 40289.4872 | 0 | 4148.7229 | 673.494 | 0 | 0 | 19878.3094 | 6869.6386 | 0 | 0 | 0 | 0 | 0 | 3331.3706 | 2155.1807 | 3232.7711 | 0 | 0 | 0 | 112082.5708 | 0 | 419.6386 | 2545.8072 | 391.6627 | 979.1566 | 0 | 70531.2525 | 0 | 0 | 0 | 18728.1837 | 28018.4892 | 6734.9398 | 0 | 0 | 0 | 0 | 0 | 2693.9759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-14 | 287563.1069 | 0 | 0 | 112246.0346 | 4437.1084 | 72171.5142 | 57481.9976 | 41226.452 | 0 | 4245.2048 | 689.1566 | 0 | 0 | 20340.5957 | 7029.3976 | 0 | 0 | 0 | 0 | 0 | 3408.8443 | 2205.3012 | 3307.9518 | 0 | 0 | 0 | 112246.0346 | 0 | 429.3976 | 2605.012 | 400.7711 | 1001.9277 | 0 | 72171.5142 | 0 | 0 | 0 | 19163.7229 | 28670.0819 | 6891.5663 | 0 | 0 | 0 | 0 | 0 | 2756.6265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-15 | 291711.0497 | 0 | 0 | 112409.4985 | 4537.9518 | 73811.7759 | 58788.4066 | 42163.4169 | 0 | 4341.6867 | 704.8193 | 0 | 0 | 20802.8819 | 7189.1566 | 0 | 0 | 0 | 0 | 0 | 3486.3181 | 2255.4217 | 3383.1325 | 0 | 0 | 0 | 112409.4985 | 0 | 439.1566 | 2664.2169 | 409.8795 | 1024.6988 | 0 | 73811.7759 | 0 | 0 | 0 | 19599.262 | 29321.6747 | 7048.1928 | 0 | 0 | 0 | 0 | 0 | 2819.2771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-16 | 295858.9925 | 0 | 0 | 112572.9623 | 4638.7952 | 75452.0376 | 60094.8157 | 43100.3817 | 0 | 4438.1687 | 720.4819 | 0 | 0 | 21265.1682 | 7348.9157 | 0 | 0 | 0 | 0 | 0 | 3563.7918 | 2305.5422 | 3458.3133 | 0 | 0 | 0 | 112572.9623 | 0 | 448.9157 | 2723.4217 | 418.988 | 1047.4699 | 0 | 75452.0376 | 0 | 0 | 0 | 20034.8012 | 29973.2675 | 7204.8193 | 0 | 0 | 0 | 0 | 0 | 2881.9277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-17 | 300006.9352 | 0 | 0 | 112736.4262 | 4739.6386 | 77092.2993 | 61401.2247 | 44037.3465 | 0 | 4534.6506 | 736.1446 | 0 | 0 | 21727.4545 | 7508.6747 | 0 | 0 | 0 | 0 | 0 | 3641.2655 | 2355.6627 | 3533.494 | 0 | 0 | 0 | 112736.4262 | 0 | 458.6747 | 2782.6265 | 428.0964 | 1070.241 | 0 | 77092.2993 | 0 | 0 | 0 | 20470.3404 | 30624.8602 | 7361.4458 | 0 | 0 | 0 | 0 | 0 | 2944.5783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-18 | 304154.878 | 0 | 0 | 112899.8901 | 4840.4819 | 78732.561 | 62707.6337 | 44974.3113 | 0 | 4631.1325 | 751.8072 | 0 | 0 | 22189.7407 | 7668.4337 | 0 | 0 | 0 | 0 | 0 | 3718.7393 | 2405.7831 | 3608.6747 | 0 | 0 | 0 | 112899.8901 | 0 | 468.4337 | 2841.8313 | 437.2048 | 1093.012 | 0 | 78732.561 | 0 | 0 | 0 | 20905.8795 | 31276.453 | 7518.0723 | 0 | 0 | 0 | 0 | 0 | 3007.2289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-19 | 308302.8208 | 0 | 0 | 113063.3539 | 4941.3253 | 80372.8227 | 64014.0428 | 45911.2761 | 0 | 4727.6145 | 767.4699 | 0 | 0 | 22652.027 | 7828.1928 | 0 | 0 | 0 | 0 | 0 | 3796.213 | 2455.9036 | 3683.8554 | 0 | 0 | 0 | 113063.3539 | 0 | 478.1928 | 2901.0361 | 446.3133 | 1115.7831 | 0 | 80372.8227 | 0 | 0 | 0 | 21341.4187 | 31928.0458 | 7674.6988 | 0 | 0 | 0 | 0 | 0 | 3069.8795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-20 | 312450.7636 | 0 | 0 | 113226.8178 | 5042.1687 | 82013.0843 | 65320.4518 | 46848.241 | 0 | 4824.0964 | 783.1325 | 0 | 0 | 23114.3133 | 7987.9518 | 0 | 0 | 0 | 0 | 0 | 3873.6867 | 2506.0241 | 3759.0361 | 0 | 0 | 0 | 113226.8178 | 0 | 487.9518 | 2960.241 | 455.4217 | 1138.5542 | 0 | 82013.0843 | 0 | 0 | 0 | 21776.9578 | 32579.6386 | 7831.3253 | 0 | 0 | 0 | 0 | 0 | 3132.5301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-21 | 330378.0839 | 0 | 0 | 114848.5485 | 5824.2911 | 85054.3834 | 76865.6551 | 47785.2058 | 0 | 4920.5783 | 798.7952 | 0 | 0 | 23576.5995 | 8147.7108 | 0 | 0 | 0 | 0 | 0 | 3951.1605 | 2556.1446 | 3834.2169 | 0 | 0 | 7093.6413 | 114848.5485 | 0 | 563.6411 | 3419.4225 | 526.065 | 1315.1625 | 0 | 85054.3834 | 0 | 0 | 0 | 22332.2179 | 36256.6634 | 7987.9518 | 0 | 0 | 0 | 0 | 0 | 3195.1807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-22 | 348305.4042 | 0 | 0 | 116470.2792 | 6606.4136 | 88095.6825 | 88410.8584 | 48722.1706 | 0 | 5017.0602 | 814.4578 | 0 | 0 | 24038.8858 | 8307.4699 | 0 | 0 | 0 | 0 | 0 | 4028.6342 | 2606.2651 | 3909.3976 | 0 | 0 | 14187.2826 | 116470.2792 | 0 | 639.3303 | 3878.6041 | 596.7083 | 1491.7708 | 0 | 88095.6825 | 0 | 0 | 0 | 22887.478 | 39933.6882 | 8144.5783 | 0 | 0 | 0 | 0 | 0 | 3257.8313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-23 | 366232.7245 | 0 | 0 | 118092.0099 | 7388.536 | 91136.9815 | 99956.0617 | 49659.1354 | 0 | 5113.5422 | 830.1205 | 0 | 0 | 24501.172 | 8467.2289 | 0 | 0 | 0 | 0 | 0 | 4106.108 | 2656.3855 | 3984.5783 | 0 | 0 | 21280.9238 | 118092.0099 | 0 | 715.0196 | 4337.7857 | 667.3516 | 1668.3791 | 0 | 91136.9815 | 0 | 0 | 0 | 23442.7381 | 43610.713 | 8301.2048 | 0 | 0 | 0 | 0 | 0 | 3320.4819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-24 | 384160.0449 | 0 | 0 | 119713.7406 | 8170.6584 | 94178.2806 | 111501.265 | 50596.1002 | 0 | 5210.0241 | 845.7831 | 0 | 0 | 24963.4583 | 8626.988 | 0 | 0 | 0 | 0 | 0 | 4183.5817 | 2706.506 | 4059.759 | 0 | 0 | 28374.5651 | 119713.7406 | 0 | 790.7089 | 4796.9672 | 737.995 | 1844.9874 | 0 | 94178.2806 | 0 | 0 | 0 | 23997.9982 | 47287.7378 | 8457.8313 | 0 | 0 | 0 | 0 | 0 | 3383.1325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-25 | 402087.3652 | 0 | 0 | 121335.4714 | 8952.7809 | 97219.5796 | 123046.4683 | 51533.0651 | 0 | 5306.506 | 861.4458 | 0 | 0 | 25425.7446 | 8786.747 | 0 | 0 | 0 | 0 | 0 | 4261.0554 | 2756.6265 | 4134.9398 | 0 | 0 | 35468.2064 | 121335.4714 | 0 | 866.3982 | 5256.1488 | 808.6383 | 2021.5957 | 0 | 97219.5796 | 0 | 0 | 0 | 24553.2583 | 50964.7626 | 8614.4578 | 0 | 0 | 0 | 0 | 0 | 3445.7831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-26 | 420014.6855 | 0 | 0 | 122957.2021 | 9734.9033 | 100260.8787 | 134591.6715 | 52470.0299 | 0 | 5402.988 | 877.1084 | 0 | 0 | 25888.0308 | 8946.506 | 0 | 0 | 0 | 0 | 0 | 4338.5292 | 2806.747 | 4210.1205 | 0 | 0 | 42561.8477 | 122957.2021 | 0 | 942.0874 | 5715.3303 | 879.2816 | 2198.204 | 0 | 100260.8787 | 0 | 0 | 0 | 25108.5184 | 54641.7875 | 8771.0843 | 0 | 0 | 0 | 0 | 0 | 3508.4337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-27 | 437942.0059 | 0 | 0 | 124578.9328 | 10517.0258 | 103302.1778 | 146136.8748 | 53406.9947 | 0 | 5499.4699 | 892.7711 | 0 | 0 | 26350.3171 | 9106.2651 | 0 | 0 | 0 | 0 | 0 | 4416.0029 | 2856.8675 | 4285.3012 | 0 | 0 | 49655.489 | 124578.9328 | 0 | 1017.7767 | 6174.5119 | 949.9249 | 2374.8123 | 0 | 103302.1778 | 0 | 0 | 0 | 25663.7784 | 58318.8123 | 8927.7108 | 0 | 0 | 0 | 0 | 0 | 3571.0843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-28 | 455869.3262 | 0 | 0 | 126200.6635 | 11299.1482 | 106343.4768 | 157682.0781 | 54343.9595 | 0 | 5595.9518 | 908.4337 | 0 | 0 | 26812.6034 | 9266.0241 | 0 | 0 | 0 | 0 | 0 | 4493.4766 | 2906.988 | 4360.4819 | 0 | 0 | 56749.1302 | 126200.6635 | 0 | 1093.466 | 6633.6935 | 1020.5682 | 2551.4206 | 0 | 106343.4768 | 0 | 0 | 0 | 26219.0385 | 61995.8371 | 9084.3373 | 0 | 0 | 0 | 0 | 0 | 3633.7349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-29 | 473796.6465 | 0 | 0 | 127822.3942 | 12081.2707 | 109384.7759 | 169227.2814 | 55280.9243 | 0 | 5692.4337 | 924.0964 | 0 | 0 | 27274.8896 | 9425.7831 | 0 | 0 | 0 | 0 | 0 | 4570.9504 | 2957.1084 | 4435.6627 | 0 | 0 | 63842.7715 | 127822.3942 | 0 | 1169.1552 | 7092.875 | 1091.2115 | 2728.0289 | 0 | 109384.7759 | 0 | 0 | 0 | 26774.2986 | 65672.8619 | 9240.9639 | 0 | 0 | 0 | 0 | 0 | 3696.3855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-30 | 491723.9668 | 0 | 0 | 129444.1249 | 12863.3931 | 112426.0749 | 180772.4847 | 56217.8892 | 0 | 5788.9157 | 939.759 | 0 | 0 | 27737.1759 | 9585.5422 | 0 | 0 | 0 | 0 | 0 | 4648.4241 | 3007.2289 | 4510.8434 | 0 | 0 | 70936.4128 | 129444.1249 | 0 | 1244.8445 | 7552.0566 | 1161.8549 | 2904.6372 | 0 | 112426.0749 | 0 | 0 | 0 | 27329.5587 | 69349.8867 | 9397.5904 | 0 | 0 | 0 | 0 | 0 | 3759.0361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-31 | 509651.2872 | 484608.92 | 484608.92 | 131065.8556 | 13645.5156 | 115467.374 | 192317.688 | 57154.854 | 0 | 5885.3976 | 955.4217 | 0 | 0 | 28199.4622 | 9745.3012 | 0 | 0 | 0 | 0 | 0 | 4725.8978 | 3057.3494 | 4586.0241 | 0 | 0 | 78030.0541 | 131065.8556 | 0 | 1320.5338 | 8011.2382 | 1232.4982 | 3081.2454 | 0 | 115467.374 | 0 | 0 | 0 | 27884.8188 | 73026.9115 | 9554.2169 | 0 | 0 | 0 | 0 | 0 | 3821.6867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-01 | 527578.6075 | 0 | 484608.92 | 132687.5864 | 14427.638 | 118508.6731 | 203862.8913 | 58091.8188 | 0 | 5981.8795 | 971.0843 | 0 | 0 | 28661.7484 | 9905.0602 | 0 | 0 | 0 | 0 | 0 | 4803.3716 | 3107.4699 | 4661.2048 | 0 | 0 | 85123.6953 | 132687.5864 | 0 | 1396.223 | 8470.4197 | 1303.1415 | 3257.8537 | 0 | 118508.6731 | 0 | 0 | 0 | 28440.0789 | 76703.9363 | 9710.8434 | 0 | 0 | 0 | 0 | 0 | 3884.3373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-02 | 545505.9278 | 0 | 484608.92 | 134309.3171 | 15209.7604 | 121549.9721 | 215408.0946 | 59028.7836 | 0 | 6078.3614 | 986.747 | 0 | 0 | 29124.0347 | 10064.8193 | 0 | 0 | 0 | 0 | 0 | 4880.8453 | 3157.5904 | 4736.3855 | 0 | 0 | 92217.3366 | 134309.3171 | 0 | 1471.9123 | 8929.6013 | 1373.7848 | 3434.462 | 0 | 121549.9721 | 0 | 0 | 0 | 28995.339 | 80380.9612 | 9867.4699 | 0 | 0 | 0 | 0 | 0 | 3946.988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-03 | 563433.2482 | 0 | 484608.92 | 135931.0478 | 15991.8829 | 124591.2712 | 226953.2979 | 59965.7484 | 0 | 6174.8434 | 1002.4096 | 0 | 0 | 29586.321 | 10224.5783 | 0 | 0 | 0 | 0 | 0 | 4958.319 | 3207.7108 | 4811.5663 | 0 | 0 | 99310.9779 | 135931.0478 | 0 | 1547.6016 | 9388.7829 | 1444.4281 | 3611.0703 | 0 | 124591.2712 | 0 | 0 | 0 | 29550.599 | 84057.986 | 10024.0964 | 0 | 0 | 0 | 0 | 0 | 4009.6386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-04 | 581360.5685 | 0 | 484608.92 | 137552.7785 | 16774.0053 | 127632.5702 | 238498.5012 | 60902.7133 | 0 | 6271.3253 | 1018.0723 | 0 | 0 | 30048.6072 | 10384.3373 | 0 | 0 | 0 | 0 | 0 | 5035.7928 | 3257.8313 | 4886.747 | 0 | 0 | 106404.6192 | 137552.7785 | 0 | 1623.2908 | 9847.9644 | 1515.0714 | 3787.6786 | 0 | 127632.5702 | 0 | 0 | 0 | 30105.8591 | 87735.0108 | 10180.7229 | 0 | 0 | 0 | 0 | 0 | 4072.2892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-05 | 599287.8888 | 0 | 484608.92 | 139174.5092 | 17556.1278 | 130673.8693 | 250043.7045 | 61839.6781 | 0 | 6367.8072 | 1033.7349 | 0 | 0 | 30510.8935 | 10544.0964 | 0 | 0 | 0 | 0 | 0 | 5113.2665 | 3307.9518 | 4961.9277 | 0 | 0 | 113498.2605 | 139174.5092 | 0 | 1698.9801 | 10307.146 | 1585.7148 | 3964.2869 | 0 | 130673.8693 | 0 | 0 | 0 | 30661.1192 | 91412.0356 | 10337.3494 | 0 | 0 | 0 | 0 | 0 | 4134.9398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-06 | 617215.2092 | 0 | 484608.92 | 140796.2399 | 18338.2502 | 133715.1684 | 261588.9077 | 62776.6429 | 0 | 6464.2892 | 1049.3976 | 0 | 0 | 30973.1798 | 10703.8554 | 0 | 0 | 0 | 0 | 0 | 5190.7402 | 3358.0723 | 5037.1084 | 0 | 0 | 120591.9017 | 140796.2399 | 0 | 1774.6694 | 10766.3275 | 1656.3581 | 4140.8952 | 0 | 133715.1684 | 0 | 0 | 0 | 31216.3793 | 95089.0604 | 10493.9759 | 0 | 0 | 0 | 0 | 0 | 4197.5904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-07 | 635142.5295 | 0 | 484608.92 | 142417.9707 | 19120.3727 | 136756.4674 | 273134.111 | 63713.6077 | 0 | 6560.7711 | 1065.0602 | 0 | 0 | 31435.466 | 10863.6145 | 0 | 0 | 0 | 0 | 0 | 5268.214 | 3408.1928 | 5112.2892 | 0 | 0 | 127685.543 | 142417.9707 | 0 | 1850.3586 | 11225.5091 | 1727.0014 | 4317.5035 | 0 | 136756.4674 | 0 | 0 | 0 | 31771.6394 | 98766.0852 | 10650.6024 | 0 | 0 | 0 | 0 | 0 | 4260.241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-08 | 653069.8498 | 0 | 484608.92 | 144039.7014 | 19902.4951 | 139797.7665 | 284679.3143 | 64650.5725 | 0 | 6657.253 | 1080.7229 | 0 | 0 | 31897.7523 | 11023.3735 | 0 | 0 | 0 | 0 | 0 | 5345.6877 | 3458.3133 | 5187.4699 | 0 | 0 | 134779.1843 | 144039.7014 | 0 | 1926.0479 | 11684.6907 | 1797.6447 | 4494.1118 | 0 | 139797.7665 | 0 | 0 | 0 | 32326.8995 | 102443.1101 | 10807.2289 | 0 | 0 | 0 | 0 | 0 | 4322.8916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-09 | 670997.1701 | 0 | 484608.92 | 145661.4321 | 20684.6175 | 142839.0655 | 296224.5176 | 65587.5373 | 0 | 6753.7349 | 1096.3855 | 0 | 0 | 32360.0386 | 11183.1325 | 0 | 0 | 0 | 0 | 0 | 5423.1614 | 3508.4337 | 5262.6506 | 0 | 0 | 141872.8256 | 145661.4321 | 0 | 2001.7372 | 12143.8722 | 1868.288 | 4670.7201 | 0 | 142839.0655 | 0 | 0 | 0 | 32882.1596 | 106120.1349 | 10963.8554 | 0 | 0 | 0 | 0 | 0 | 4385.5422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-10 | 688924.4905 | 0 | 484608.92 | 147283.1628 | 21466.74 | 145880.3646 | 307769.7209 | 66524.5022 | 0 | 6850.2169 | 1112.0482 | 0 | 0 | 32822.3248 | 11342.8916 | 0 | 0 | 0 | 0 | 0 | 5500.6352 | 3558.5542 | 5337.8313 | 0 | 0 | 148966.4669 | 147283.1628 | 0 | 2077.4264 | 12603.0538 | 1938.9314 | 4847.3284 | 0 | 145880.3646 | 0 | 0 | 0 | 33437.4197 | 109797.1597 | 11120.4819 | 0 | 0 | 0 | 0 | 0 | 4448.1928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-11 | 706851.8108 | 0 | 484608.92 | 148904.8935 | 22248.8624 | 148921.6637 | 319314.9242 | 67461.467 | 0 | 6946.6988 | 1127.7108 | 0 | 0 | 33284.6111 | 11502.6506 | 0 | 0 | 0 | 0 | 0 | 5578.1089 | 3608.6747 | 5413.012 | 0 | 0 | 156060.1081 | 148904.8935 | 0 | 2153.1157 | 13062.2354 | 2009.5747 | 5023.9367 | 0 | 148921.6637 | 0 | 0 | 0 | 33992.6797 | 113474.1845 | 11277.1084 | 0 | 0 | 0 | 0 | 0 | 4510.8434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-12 | 724779.1311 | 0 | 484608.92 | 150526.6242 | 23030.9849 | 151962.9627 | 330860.1275 | 68398.4318 | 0 | 7043.1807 | 1143.3735 | 0 | 0 | 33746.8973 | 11662.4096 | 0 | 0 | 0 | 0 | 0 | 5655.5827 | 3658.7952 | 5488.1928 | 0 | 0 | 163153.7494 | 150526.6242 | 0 | 2228.805 | 13521.4169 | 2080.218 | 5200.545 | 0 | 151962.9627 | 0 | 0 | 0 | 34547.9398 | 117151.2093 | 11433.7349 | 0 | 0 | 0 | 0 | 0 | 4573.494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-13 | 742706.4515 | 0 | 484608.92 | 152148.355 | 23813.1073 | 155004.2618 | 342405.3308 | 69335.3966 | 0 | 7139.6627 | 1159.0361 | 0 | 0 | 34209.1836 | 11822.1687 | 0 | 0 | 0 | 0 | 0 | 5733.0564 | 3708.9157 | 5563.3735 | 0 | 0 | 170247.3907 | 152148.355 | 0 | 2304.4943 | 13980.5985 | 2150.8613 | 5377.1533 | 0 | 155004.2618 | 0 | 0 | 0 | 35103.1999 | 120828.2341 | 11590.3614 | 0 | 0 | 0 | 0 | 0 | 4636.1446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-14 | 760633.7718 | 0 | 484608.92 | 153770.0857 | 24595.2298 | 158045.5608 | 353950.5341 | 70272.3614 | 0 | 7236.1446 | 1174.6988 | 0 | 0 | 34671.4699 | 11981.9277 | 0 | 0 | 0 | 0 | 0 | 5810.5301 | 3759.0361 | 5638.5542 | 0 | 0 | 177341.032 | 153770.0857 | 0 | 2380.1835 | 14439.7801 | 2221.5046 | 5553.7616 | 0 | 158045.5608 | 0 | 0 | 0 | 35658.46 | 124505.259 | 11746.988 | 0 | 0 | 0 | 0 | 0 | 4698.7952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-15 | 778561.0921 | 0 | 484608.92 | 155391.8164 | 25377.3522 | 161086.8599 | 365495.7374 | 71209.3263 | 0 | 7332.6265 | 1190.3614 | 0 | 0 | 35133.7561 | 12141.6867 | 0 | 0 | 0 | 0 | 0 | 5888.0039 | 3809.1566 | 5713.7349 | 0 | 0 | 184434.6733 | 155391.8164 | 0 | 2455.8728 | 14898.9616 | 2292.1479 | 5730.3699 | 0 | 161086.8599 | 0 | 0 | 0 | 36213.7201 | 128182.2838 | 11903.6145 | 0 | 0 | 0 | 0 | 0 | 4761.4458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-16 | 796488.4124 | 0 | 484608.92 | 157013.5471 | 26159.4746 | 164128.159 | 377040.9406 | 72146.2911 | 0 | 7429.1084 | 1206.0241 | 0 | 0 | 35596.0424 | 12301.4458 | 0 | 0 | 0 | 0 | 0 | 5965.4776 | 3859.2771 | 5788.9157 | 0 | 0 | 191528.3145 | 157013.5471 | 0 | 2531.5621 | 15358.1432 | 2362.7913 | 5906.9781 | 0 | 164128.159 | 0 | 0 | 0 | 36768.9802 | 131859.3086 | 12060.241 | 0 | 0 | 0 | 0 | 0 | 4824.0964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-17 | 814415.7328 | 0 | 484608.92 | 158635.2778 | 26941.5971 | 167169.458 | 388586.1439 | 73083.2559 | 0 | 7525.5904 | 1221.6867 | 0 | 0 | 36058.3287 | 12461.2048 | 0 | 0 | 0 | 0 | 0 | 6042.9513 | 3909.3976 | 5864.0964 | 0 | 0 | 198621.9558 | 158635.2778 | 0 | 2607.2513 | 15817.3247 | 2433.4346 | 6083.5864 | 0 | 167169.458 | 0 | 0 | 0 | 37324.2403 | 135536.3334 | 12216.8675 | 0 | 0 | 0 | 0 | 0 | 4886.747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-18 | 832343.0531 | 0 | 484608.92 | 160257.0085 | 27723.7195 | 170210.7571 | 400131.3472 | 74020.2207 | 0 | 7622.0723 | 1237.3494 | 0 | 0 | 36520.6149 | 12620.9639 | 0 | 0 | 0 | 0 | 0 | 6120.4251 | 3959.5181 | 5939.2771 | 0 | 0 | 205715.5971 | 160257.0085 | 0 | 2682.9406 | 16276.5063 | 2504.0779 | 6260.1947 | 0 | 170210.7571 | 0 | 0 | 0 | 37879.5004 | 139213.3582 | 12373.494 | 0 | 0 | 0 | 0 | 0 | 4949.3976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-19 | 850270.3734 | 0 | 484608.92 | 161878.7392 | 28505.842 | 173252.0562 | 411676.5505 | 74957.1855 | 0 | 7718.5542 | 1253.012 | 0 | 0 | 36982.9012 | 12780.7229 | 0 | 0 | 0 | 0 | 0 | 6197.8988 | 4009.6386 | 6014.4578 | 0 | 0 | 212809.2384 | 161878.7392 | 0 | 2758.6299 | 16735.6879 | 2574.7212 | 6436.803 | 0 | 173252.0562 | 0 | 0 | 0 | 38434.7604 | 142890.383 | 12530.1205 | 0 | 0 | 0 | 0 | 0 | 5012.0482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-20 | 868197.6938 | 0 | 484608.92 | 163500.47 | 29287.9644 | 176293.3552 | 423221.7538 | 75894.1504 | 0 | 7815.0361 | 1268.6747 | 0 | 0 | 37445.1875 | 12940.4819 | 0 | 0 | 0 | 0 | 0 | 6275.3725 | 4059.759 | 6089.6386 | 0 | 0 | 219902.8797 | 163500.47 | 0 | 2834.3191 | 17194.8694 | 2645.3645 | 6613.4113 | 0 | 176293.3552 | 0 | 0 | 0 | 38990.0205 | 146567.4079 | 12686.747 | 0 | 0 | 0 | 0 | 0 | 5074.6988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-21 | 886125.0141 | 0 | 484608.92 | 165122.2007 | 30070.0869 | 179334.6543 | 434766.9571 | 76831.1152 | 0 | 7911.5181 | 1284.3373 | 0 | 0 | 37907.4737 | 13100.241 | 0 | 0 | 0 | 0 | 0 | 6352.8463 | 4109.8795 | 6164.8193 | 0 | 0 | 226996.5209 | 165122.2007 | 0 | 2910.0084 | 17654.051 | 2716.0078 | 6790.0196 | 0 | 179334.6543 | 0 | 0 | 0 | 39545.2806 | 150244.4327 | 12843.3735 | 0 | 0 | 0 | 0 | 0 | 5137.3494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-22 | 904052.3344 | 0 | 484608.92 | 166743.9314 | 30852.2093 | 182375.9533 | 446312.1604 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 234090.1622 | 166743.9314 | 0 | 2985.6977 | 18113.2326 | 2786.6512 | 6966.6279 | 0 | 182375.9533 | 0 | 0 | 0 | 40100.5407 | 153921.4575 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-23 | 917831.712 | 0 | 484608.92 | 168202.1983 | 31533.4884 | 183776.9907 | 456550.9546 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 241183.8035 | 168202.1983 | 0 | 3051.6279 | 18513.2093 | 2848.186 | 7120.4651 | 0 | 183776.9907 | 0 | 0 | 0 | 40220.2616 | 156946.8895 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-24 | 931611.0895 | 0 | 484608.92 | 169660.4651 | 32214.7674 | 185178.0281 | 466789.7489 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 248277.4448 | 169660.4651 | 0 | 3117.5581 | 18913.186 | 2909.7209 | 7274.3023 | 0 | 185178.0281 | 0 | 0 | 0 | 40339.9826 | 159972.3216 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-25 | 945390.4671 | 0 | 484608.92 | 171118.732 | 32896.0465 | 186579.0655 | 477028.5432 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 255371.086 | 171118.732 | 0 | 3183.4884 | 19313.1628 | 2971.2558 | 7428.1395 | 0 | 186579.0655 | 0 | 0 | 0 | 40459.7035 | 162997.7536 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-26 | 959169.8447 | 0 | 484608.92 | 172576.9988 | 33577.3256 | 187980.1028 | 487267.3374 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 262464.7273 | 172576.9988 | 0 | 3249.4186 | 19713.1395 | 3032.7907 | 7581.9767 | 0 | 187980.1028 | 0 | 0 | 0 | 40579.4244 | 166023.1857 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-27 | 972949.2222 | 0 | 484608.92 | 174035.2657 | 34258.6047 | 189381.1402 | 497506.1317 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 269558.3686 | 174035.2657 | 0 | 3315.3488 | 20113.1163 | 3094.3256 | 7735.814 | 0 | 189381.1402 | 0 | 0 | 0 | 40699.1453 | 169048.6177 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-28 | 986728.5998 | 0 | 484608.92 | 175493.5326 | 34939.8837 | 190782.1776 | 507744.9259 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 276652.0099 | 175493.5326 | 0 | 3381.2791 | 20513.093 | 3155.8605 | 7889.6512 | 0 | 190782.1776 | 0 | 0 | 0 | 40818.8663 | 172074.0498 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-29 | 1000507.9773 | 0 | 484608.92 | 176951.7994 | 35621.1628 | 192183.2149 | 517983.7202 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 283745.6512 | 176951.7994 | 0 | 3447.2093 | 20913.0698 | 3217.3953 | 8043.4884 | 0 | 192183.2149 | 0 | 0 | 0 | 40938.5872 | 175099.4818 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-30 | 1014287.3549 | 0 | 484608.92 | 178410.0663 | 36302.4419 | 193584.2523 | 528222.5144 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 290839.2924 | 178410.0663 | 0 | 3513.1395 | 21313.0465 | 3278.9302 | 8197.3256 | 0 | 193584.2523 | 0 | 0 | 0 | 41058.3081 | 178124.9138 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-31 | 1028066.7324 | 177336.99 | 661945.91 | 179868.3331 | 36983.7209 | 194985.2897 | 538461.3087 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 297932.9337 | 179868.3331 | 0 | 3579.0698 | 21713.0233 | 3340.4651 | 8351.1628 | 0 | 194985.2897 | 0 | 0 | 0 | 41178.0291 | 181150.3459 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-01 | 1041846.11 | 0 | 661945.91 | 181326.6 | 37665 | 196386.3271 | 548700.1029 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 181326.6 | 0 | 3645 | 22113 | 3402 | 8505 | 0 | 196386.3271 | 0 | 0 | 0 | 41297.75 | 184175.7779 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-02 | 1043719.8915 | 0 | 661945.91 | 182184.7107 | 38128.4396 | 196619.9388 | 549018.7224 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 182184.7107 | 0 | 3689.849 | 22385.0839 | 3443.8591 | 8609.6477 | 0 | 196619.9388 | 0 | 0 | 0 | 41297.75 | 184494.3974 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-03 | 1045593.673 | 0 | 661945.91 | 183042.8215 | 38591.8792 | 196853.5506 | 549337.3418 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 183042.8215 | 0 | 3734.698 | 22657.1678 | 3485.7181 | 8714.2953 | 0 | 196853.5506 | 0 | 0 | 0 | 41297.75 | 184813.0168 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-04 | 1047467.4545 | 0 | 661945.91 | 183900.9322 | 39055.3188 | 197087.1623 | 549655.9612 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 183900.9322 | 0 | 3779.547 | 22929.2517 | 3527.5772 | 8818.943 | 0 | 197087.1623 | 0 | 0 | 0 | 41297.75 | 185131.6362 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-05 | 1049341.2361 | 0 | 661945.91 | 184759.043 | 39518.7584 | 197320.7741 | 549974.5807 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 184759.043 | 0 | 3824.396 | 23201.3356 | 3569.4362 | 8923.5906 | 0 | 197320.7741 | 0 | 0 | 0 | 41297.75 | 185450.2557 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-06 | 1051215.0176 | 0 | 661945.91 | 185617.1537 | 39982.198 | 197554.3858 | 550293.2001 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 185617.1537 | 0 | 3869.245 | 23473.4195 | 3611.2953 | 9028.2383 | 0 | 197554.3858 | 0 | 0 | 0 | 41297.75 | 185768.8751 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-07 | 1053088.7991 | 0 | 661945.91 | 186475.2644 | 40445.6376 | 197787.9975 | 550611.8195 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 186475.2644 | 0 | 3914.094 | 23745.5034 | 3653.1544 | 9132.8859 | 0 | 197787.9975 | 0 | 0 | 0 | 41297.75 | 186087.4945 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-08 | 1054962.5806 | 0 | 661945.91 | 187333.3752 | 40909.0772 | 198021.6093 | 550930.439 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 187333.3752 | 0 | 3958.943 | 24017.5872 | 3695.0134 | 9237.5336 | 0 | 198021.6093 | 0 | 0 | 0 | 41297.75 | 186406.114 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-09 | 1056836.3621 | 0 | 661945.91 | 188191.4859 | 41372.5168 | 198255.221 | 551249.0584 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 188191.4859 | 0 | 4003.7919 | 24289.6711 | 3736.8725 | 9342.1812 | 0 | 198255.221 | 0 | 0 | 0 | 41297.75 | 186724.7334 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-10 | 1058710.1436 | 0 | 661945.91 | 189049.5966 | 41835.9564 | 198488.8328 | 551567.6778 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 189049.5966 | 0 | 4048.6409 | 24561.755 | 3778.7315 | 9446.8289 | 0 | 198488.8328 | 0 | 0 | 0 | 41297.75 | 187043.3528 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-11 | 1060583.9251 | 0 | 661945.91 | 189907.7074 | 42299.396 | 198722.4445 | 551886.2973 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 189907.7074 | 0 | 4093.4899 | 24833.8389 | 3820.5906 | 9551.4765 | 0 | 198722.4445 | 0 | 0 | 0 | 41297.75 | 187361.9723 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-12 | 1062457.7067 | 0 | 661945.91 | 190765.8181 | 42762.8356 | 198956.0563 | 552204.9167 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 190765.8181 | 0 | 4138.3389 | 25105.9228 | 3862.4497 | 9656.1242 | 0 | 198956.0563 | 0 | 0 | 0 | 41297.75 | 187680.5917 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-13 | 1064331.4882 | 0 | 661945.91 | 191623.9289 | 43226.2752 | 199189.668 | 552523.5361 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 191623.9289 | 0 | 4183.1879 | 25378.0067 | 3904.3087 | 9760.7718 | 0 | 199189.668 | 0 | 0 | 0 | 41297.75 | 187999.2111 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-14 | 1066205.2697 | 0 | 661945.91 | 192482.0396 | 43689.7148 | 199423.2798 | 552842.1556 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 192482.0396 | 0 | 4228.0369 | 25650.0906 | 3946.1678 | 9865.4195 | 0 | 199423.2798 | 0 | 0 | 0 | 41297.75 | 188317.8306 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-15 | 1068079.0512 | 0 | 661945.91 | 193340.1503 | 44153.1544 | 199656.8915 | 553160.775 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 193340.1503 | 0 | 4272.8859 | 25922.1745 | 3988.0268 | 9970.0671 | 0 | 199656.8915 | 0 | 0 | 0 | 41297.75 | 188636.45 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-16 | 1069952.8327 | 0 | 661945.91 | 194198.2611 | 44616.594 | 199890.5032 | 553479.3944 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 194198.2611 | 0 | 4317.7349 | 26194.2584 | 4029.8859 | 10074.7148 | 0 | 199890.5032 | 0 | 0 | 0 | 41297.75 | 188955.0694 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-17 | 1071826.6142 | 0 | 661945.91 | 195056.3718 | 45080.0336 | 200124.115 | 553798.0139 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 195056.3718 | 0 | 4362.5839 | 26466.3423 | 4071.745 | 10179.3624 | 0 | 200124.115 | 0 | 0 | 0 | 41297.75 | 189273.6889 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-18 | 1073700.3957 | 0 | 661945.91 | 195914.4826 | 45543.4732 | 200357.7267 | 554116.6333 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 195914.4826 | 0 | 4407.4329 | 26738.4262 | 4113.604 | 10284.0101 | 0 | 200357.7267 | 0 | 0 | 0 | 41297.75 | 189592.3083 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-19 | 1075574.1773 | 0 | 661945.91 | 196772.5933 | 46006.9128 | 200591.3385 | 554435.2527 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 196772.5933 | 0 | 4452.2819 | 27010.5101 | 4155.4631 | 10388.6577 | 0 | 200591.3385 | 0 | 0 | 0 | 41297.75 | 189910.9277 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-20 | 1077447.9588 | 0 | 661945.91 | 197630.704 | 46470.3523 | 200824.9502 | 554753.8722 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 197630.704 | 0 | 4497.1309 | 27282.594 | 4197.3221 | 10493.3054 | 0 | 200824.9502 | 0 | 0 | 0 | 41297.75 | 190229.5472 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-21 | 1079321.7403 | 0 | 661945.91 | 198488.8148 | 46933.7919 | 201058.562 | 555072.4916 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 198488.8148 | 0 | 4541.9799 | 27554.6779 | 4239.1812 | 10597.953 | 0 | 201058.562 | 0 | 0 | 0 | 41297.75 | 190548.1666 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-22 | 1081195.5218 | 0 | 661945.91 | 199346.9255 | 47397.2315 | 201292.1737 | 555391.111 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 199346.9255 | 0 | 4586.8289 | 27826.7617 | 4281.0403 | 10702.6007 | 0 | 201292.1737 | 0 | 0 | 0 | 41297.75 | 190866.786 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-23 | 1083069.3033 | 0 | 661945.91 | 200205.0362 | 47860.6711 | 201525.7855 | 555709.7305 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 200205.0362 | 0 | 4631.6779 | 28098.8456 | 4322.8993 | 10807.2483 | 0 | 201525.7855 | 0 | 0 | 0 | 41297.75 | 191185.4055 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-24 | 1084943.0848 | 0 | 661945.91 | 201063.147 | 48324.1107 | 201759.3972 | 556028.3499 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 201063.147 | 0 | 4676.5268 | 28370.9295 | 4364.7584 | 10911.896 | 0 | 201759.3972 | 0 | 0 | 0 | 41297.75 | 191504.0249 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-25 | 1086816.8663 | 0 | 661945.91 | 201921.2577 | 48787.5503 | 201993.0089 | 556346.9693 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 201921.2577 | 0 | 4721.3758 | 28643.0134 | 4406.6174 | 11016.5436 | 0 | 201993.0089 | 0 | 0 | 0 | 41297.75 | 191822.6443 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-26 | 1088690.6479 | 0 | 661945.91 | 202779.3685 | 49250.9899 | 202226.6207 | 556665.5888 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 202779.3685 | 0 | 4766.2248 | 28915.0973 | 4448.4765 | 11121.1913 | 0 | 202226.6207 | 0 | 0 | 0 | 41297.75 | 192141.2638 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-27 | 1090564.4294 | 0 | 661945.91 | 203637.4792 | 49714.4295 | 202460.2324 | 556984.2082 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 203637.4792 | 0 | 4811.0738 | 29187.1812 | 4490.3356 | 11225.8389 | 0 | 202460.2324 | 0 | 0 | 0 | 41297.75 | 192459.8832 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-28 | 1092438.2109 | 0 | 661945.91 | 204495.5899 | 50177.8691 | 202693.8442 | 557302.8276 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 204495.5899 | 0 | 4855.9228 | 29459.2651 | 4532.1946 | 11330.4866 | 0 | 202693.8442 | 0 | 0 | 0 | 41297.75 | 192778.5026 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-29 | 1094311.9924 | 0 | 661945.91 | 205353.7007 | 50641.3087 | 202927.4559 | 557621.4471 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 205353.7007 | 0 | 4900.7718 | 29731.349 | 4574.0537 | 11435.1342 | 0 | 202927.4559 | 0 | 0 | 0 | 41297.75 | 193097.1221 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-30 | 1096185.7739 | 0 | 661945.91 | 206211.8114 | 51104.7483 | 203161.0677 | 557940.0665 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 206211.8114 | 0 | 4945.6208 | 30003.4329 | 4615.9128 | 11539.7819 | 0 | 203161.0677 | 0 | 0 | 0 | 41297.75 | 193415.7415 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-01 | 1098059.5554 | 0 | 661945.91 | 207069.9221 | 51568.1879 | 203394.6794 | 558258.6859 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 207069.9221 | 0 | 4990.4698 | 30275.5168 | 4657.7718 | 11644.4295 | 0 | 203394.6794 | 0 | 0 | 0 | 41297.75 | 193734.3609 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-02 | 1099933.3369 | 0 | 661945.91 | 207928.0329 | 52031.6275 | 203628.2912 | 558577.3054 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 207928.0329 | 0 | 5035.3188 | 30547.6007 | 4699.6309 | 11749.0772 | 0 | 203628.2912 | 0 | 0 | 0 | 41297.75 | 194052.9804 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-03 | 1101807.1184 | 0 | 661945.91 | 208786.1436 | 52495.0671 | 203861.9029 | 558895.9248 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 208786.1436 | 0 | 5080.1678 | 30819.6846 | 4741.4899 | 11853.7248 | 0 | 203861.9029 | 0 | 0 | 0 | 41297.75 | 194371.5998 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-04 | 1103680.9 | 0 | 661945.91 | 209644.2544 | 52958.5067 | 204095.5147 | 559214.5442 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 209644.2544 | 0 | 5125.0168 | 31091.7685 | 4783.349 | 11958.3725 | 0 | 204095.5147 | 0 | 0 | 0 | 41297.75 | 194690.2192 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-05 | 1105554.6815 | 0 | 661945.91 | 210502.3651 | 53421.9463 | 204329.1264 | 559533.1637 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 210502.3651 | 0 | 5169.8658 | 31363.8523 | 4825.2081 | 12063.0201 | 0 | 204329.1264 | 0 | 0 | 0 | 41297.75 | 195008.8387 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-06 | 1107428.463 | 0 | 661945.91 | 211360.4758 | 53885.3859 | 204562.7381 | 559851.7831 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 211360.4758 | 0 | 5214.7148 | 31635.9362 | 4867.0671 | 12167.6678 | 0 | 204562.7381 | 0 | 0 | 0 | 41297.75 | 195327.4581 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-07 | 1109302.2445 | 0 | 661945.91 | 212218.5866 | 54348.8255 | 204796.3499 | 560170.4025 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 212218.5866 | 0 | 5259.5638 | 31908.0201 | 4908.9262 | 12272.3154 | 0 | 204796.3499 | 0 | 0 | 0 | 41297.75 | 195646.0775 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-08 | 1111176.026 | 0 | 661945.91 | 213076.6973 | 54812.2651 | 205029.9616 | 560489.022 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 213076.6973 | 0 | 5304.4128 | 32180.104 | 4950.7852 | 12376.9631 | 0 | 205029.9616 | 0 | 0 | 0 | 41297.75 | 195964.697 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-09 | 1113049.8075 | 0 | 661945.91 | 213934.8081 | 55275.7047 | 205263.5734 | 560807.6414 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 213934.8081 | 0 | 5349.2617 | 32452.1879 | 4992.6443 | 12481.6107 | 0 | 205263.5734 | 0 | 0 | 0 | 41297.75 | 196283.3164 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-10 | 1114923.589 | 0 | 661945.91 | 214792.9188 | 55739.1443 | 205497.1851 | 561126.2608 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 214792.9188 | 0 | 5394.1107 | 32724.2718 | 5034.5034 | 12586.2584 | 0 | 205497.1851 | 0 | 0 | 0 | 41297.75 | 196601.9358 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-11 | 1116797.3706 | 0 | 661945.91 | 215651.0295 | 56202.5839 | 205730.7969 | 561444.8803 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 215651.0295 | 0 | 5438.9597 | 32996.3557 | 5076.3624 | 12690.906 | 0 | 205730.7969 | 0 | 0 | 0 | 41297.75 | 196920.5553 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-12 | 1118671.1521 | 0 | 661945.91 | 216509.1403 | 56666.0235 | 205964.4086 | 561763.4997 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 216509.1403 | 0 | 5483.8087 | 33268.4396 | 5118.2215 | 12795.5537 | 0 | 205964.4086 | 0 | 0 | 0 | 41297.75 | 197239.1747 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-13 | 1120544.9336 | 0 | 661945.91 | 217367.251 | 57129.4631 | 206198.0204 | 562082.1191 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 217367.251 | 0 | 5528.6577 | 33540.5235 | 5160.0805 | 12900.2013 | 0 | 206198.0204 | 0 | 0 | 0 | 41297.75 | 197557.7941 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-14 | 1122418.7151 | 0 | 661945.91 | 218225.3617 | 57592.9027 | 206431.6321 | 562400.7386 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 218225.3617 | 0 | 5573.5067 | 33812.6074 | 5201.9396 | 13004.849 | 0 | 206431.6321 | 0 | 0 | 0 | 41297.75 | 197876.4136 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-15 | 1124292.4966 | 0 | 661945.91 | 219083.4725 | 58056.3423 | 206665.2438 | 562719.358 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 219083.4725 | 0 | 5618.3557 | 34084.6913 | 5243.7987 | 13109.4966 | 0 | 206665.2438 | 0 | 0 | 0 | 41297.75 | 198195.033 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-16 | 1126166.2781 | 0 | 661945.91 | 219941.5832 | 58519.7819 | 206898.8556 | 563037.9774 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 219941.5832 | 0 | 5663.2047 | 34356.7752 | 5285.6577 | 13214.1443 | 0 | 206898.8556 | 0 | 0 | 0 | 41297.75 | 198513.6524 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-17 | 1128040.0596 | 0 | 661945.91 | 220799.694 | 58983.2215 | 207132.4673 | 563356.5969 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 220799.694 | 0 | 5708.0537 | 34628.8591 | 5327.5168 | 13318.7919 | 0 | 207132.4673 | 0 | 0 | 0 | 41297.75 | 198832.2719 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-18 | 1129913.8412 | 0 | 661945.91 | 221657.8047 | 59446.6611 | 207366.0791 | 563675.2163 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 221657.8047 | 0 | 5752.9027 | 34900.943 | 5369.3758 | 13423.4396 | 0 | 207366.0791 | 0 | 0 | 0 | 41297.75 | 199150.8913 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-19 | 1131787.6227 | 0 | 661945.91 | 222515.9154 | 59910.1007 | 207599.6908 | 563993.8357 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 222515.9154 | 0 | 5797.7517 | 35173.0268 | 5411.2349 | 13528.0872 | 0 | 207599.6908 | 0 | 0 | 0 | 41297.75 | 199469.5107 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-20 | 1133661.4042 | 0 | 661945.91 | 223374.0262 | 60373.5403 | 207833.3026 | 564312.4552 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 223374.0262 | 0 | 5842.6007 | 35445.1107 | 5453.094 | 13632.7349 | 0 | 207833.3026 | 0 | 0 | 0 | 41297.75 | 199788.1302 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-21 | 1135535.1857 | 0 | 661945.91 | 224232.1369 | 60836.9799 | 208066.9143 | 564631.0746 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 224232.1369 | 0 | 5887.4497 | 35717.1946 | 5494.953 | 13737.3826 | 0 | 208066.9143 | 0 | 0 | 0 | 41297.75 | 200106.7496 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-22 | 1137408.9672 | 0 | 661945.91 | 225090.2477 | 61300.4195 | 208300.5261 | 564949.694 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 225090.2477 | 0 | 5932.2987 | 35989.2785 | 5536.8121 | 13842.0302 | 0 | 208300.5261 | 0 | 0 | 0 | 41297.75 | 200425.369 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-23 | 1139282.7487 | 0 | 661945.91 | 225948.3584 | 61763.8591 | 208534.1378 | 565268.3135 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 225948.3584 | 0 | 5977.1477 | 36261.3624 | 5578.6711 | 13946.6779 | 0 | 208534.1378 | 0 | 0 | 0 | 41297.75 | 200743.9885 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-24 | 1141156.5302 | 0 | 661945.91 | 226806.4691 | 62227.2987 | 208767.7496 | 565586.9329 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 226806.4691 | 0 | 6021.9966 | 36533.4463 | 5620.5302 | 14051.3255 | 0 | 208767.7496 | 0 | 0 | 0 | 41297.75 | 201062.6079 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-25 | 1143030.3118 | 0 | 661945.91 | 227664.5799 | 62690.7383 | 209001.3613 | 565905.5523 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 227664.5799 | 0 | 6066.8456 | 36805.5302 | 5662.3893 | 14155.9732 | 0 | 209001.3613 | 0 | 0 | 0 | 41297.75 | 201381.2273 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-26 | 1144904.0933 | 0 | 661945.91 | 228522.6906 | 63154.1779 | 209234.973 | 566224.1718 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 228522.6906 | 0 | 6111.6946 | 37077.6141 | 5704.2483 | 14260.6208 | 0 | 209234.973 | 0 | 0 | 0 | 41297.75 | 201699.8468 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-27 | 1146777.8748 | 0 | 661945.91 | 229380.8013 | 63617.6174 | 209468.5848 | 566542.7912 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 229380.8013 | 0 | 6156.5436 | 37349.698 | 5746.1074 | 14365.2685 | 0 | 209468.5848 | 0 | 0 | 0 | 41297.75 | 202018.4662 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-28 | 1148651.6563 | 0 | 661945.91 | 230238.9121 | 64081.057 | 209702.1965 | 566861.4106 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 230238.9121 | 0 | 6201.3926 | 37621.7819 | 5787.9664 | 14469.9161 | 0 | 209702.1965 | 0 | 0 | 0 | 41297.75 | 202337.0856 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-29 | 1150525.4378 | 0 | 661945.91 | 231097.0228 | 64544.4966 | 209935.8083 | 567180.0301 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 231097.0228 | 0 | 6246.2416 | 37893.8658 | 5829.8255 | 14574.5638 | 0 | 209935.8083 | 0 | 0 | 0 | 41297.75 | 202655.7051 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-30 | 1152399.2193 | 284433.61 | 946379.52 | 231955.1336 | 65007.9362 | 210169.42 | 567498.6495 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 231955.1336 | 0 | 6291.0906 | 38165.9497 | 5871.6846 | 14679.2114 | 0 | 210169.42 | 0 | 0 | 0 | 41297.75 | 202974.3245 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-31 | 1154273.0008 | 0 | 946379.52 | 232813.2443 | 65471.3758 | 210403.0318 | 567817.2689 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 232813.2443 | 0 | 6335.9396 | 38438.0336 | 5913.5436 | 14783.8591 | 0 | 210403.0318 | 0 | 0 | 0 | 41297.75 | 203292.9439 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-01 | 1156146.7824 | 0 | 946379.52 | 233671.355 | 65934.8154 | 210636.6435 | 568135.8884 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 233671.355 | 0 | 6380.7886 | 38710.1174 | 5955.4027 | 14888.5067 | 0 | 210636.6435 | 0 | 0 | 0 | 41297.75 | 203611.5634 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-02 | 1158020.5639 | 0 | 946379.52 | 234529.4658 | 66398.255 | 210870.2553 | 568454.5078 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 234529.4658 | 0 | 6425.6376 | 38982.2013 | 5997.2617 | 14993.1544 | 0 | 210870.2553 | 0 | 0 | 0 | 41297.75 | 203930.1828 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-03 | 1159894.3454 | 0 | 946379.52 | 235387.5765 | 66861.6946 | 211103.867 | 568773.1272 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 235387.5765 | 0 | 6470.4866 | 39254.2852 | 6039.1208 | 15097.802 | 0 | 211103.867 | 0 | 0 | 0 | 41297.75 | 204248.8022 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-04 | 1161768.1269 | 0 | 946379.52 | 236245.6872 | 67325.1342 | 211337.4787 | 569091.7467 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 236245.6872 | 0 | 6515.3356 | 39526.3691 | 6080.9799 | 15202.4497 | 0 | 211337.4787 | 0 | 0 | 0 | 41297.75 | 204567.4217 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-05 | 1163641.9084 | 0 | 946379.52 | 237103.798 | 67788.5738 | 211571.0905 | 569410.3661 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 237103.798 | 0 | 6560.1846 | 39798.453 | 6122.8389 | 15307.0973 | 0 | 211571.0905 | 0 | 0 | 0 | 41297.75 | 204886.0411 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-06 | 1165515.6899 | 0 | 946379.52 | 237961.9087 | 68252.0134 | 211804.7022 | 569728.9855 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 237961.9087 | 0 | 6605.0336 | 40070.5369 | 6164.698 | 15411.745 | 0 | 211804.7022 | 0 | 0 | 0 | 41297.75 | 205204.6605 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-07 | 1167389.4714 | 0 | 946379.52 | 238820.0195 | 68715.453 | 212038.314 | 570047.605 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 238820.0195 | 0 | 6649.8826 | 40342.6208 | 6206.557 | 15516.3926 | 0 | 212038.314 | 0 | 0 | 0 | 41297.75 | 205523.28 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-08 | 1169263.253 | 0 | 946379.52 | 239678.1302 | 69178.8926 | 212271.9257 | 570366.2244 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 239678.1302 | 0 | 6694.7315 | 40614.7047 | 6248.4161 | 15621.0403 | 0 | 212271.9257 | 0 | 0 | 0 | 41297.75 | 205841.8994 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-09 | 1171137.0345 | 0 | 946379.52 | 240536.2409 | 69642.3322 | 212505.5375 | 570684.8438 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 240536.2409 | 0 | 6739.5805 | 40886.7886 | 6290.2752 | 15725.6879 | 0 | 212505.5375 | 0 | 0 | 0 | 41297.75 | 206160.5188 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-10 | 1173010.816 | 0 | 946379.52 | 241394.3517 | 70105.7718 | 212739.1492 | 571003.4633 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 241394.3517 | 0 | 6784.4295 | 41158.8725 | 6332.1342 | 15830.3356 | 0 | 212739.1492 | 0 | 0 | 0 | 41297.75 | 206479.1383 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-11 | 1174884.5975 | 0 | 946379.52 | 242252.4624 | 70569.2114 | 212972.761 | 571322.0827 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 242252.4624 | 0 | 6829.2785 | 41430.9564 | 6373.9933 | 15934.9832 | 0 | 212972.761 | 0 | 0 | 0 | 41297.75 | 206797.7577 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-12 | 1176758.379 | 0 | 946379.52 | 243110.5732 | 71032.651 | 213206.3727 | 571640.7021 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 243110.5732 | 0 | 6874.1275 | 41703.0403 | 6415.8523 | 16039.6309 | 0 | 213206.3727 | 0 | 0 | 0 | 41297.75 | 207116.3771 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-13 | 1178632.1605 | 0 | 946379.52 | 243968.6839 | 71496.0906 | 213439.9845 | 571959.3216 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 243968.6839 | 0 | 6918.9765 | 41975.1242 | 6457.7114 | 16144.2785 | 0 | 213439.9845 | 0 | 0 | 0 | 41297.75 | 207434.9966 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-14 | 1180505.942 | 0 | 946379.52 | 244826.7946 | 71959.5302 | 213673.5962 | 572277.941 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 244826.7946 | 0 | 6963.8255 | 42247.2081 | 6499.5705 | 16248.9262 | 0 | 213673.5962 | 0 | 0 | 0 | 41297.75 | 207753.616 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-15 | 1182379.7235 | 0 | 946379.52 | 245684.9054 | 72422.9698 | 213907.2079 | 572596.5604 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 245684.9054 | 0 | 7008.6745 | 42519.2919 | 6541.4295 | 16353.5738 | 0 | 213907.2079 | 0 | 0 | 0 | 41297.75 | 208072.2354 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-16 | 1184253.5051 | 0 | 946379.52 | 246543.0161 | 72886.4094 | 214140.8197 | 572915.1799 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 246543.0161 | 0 | 7053.5235 | 42791.3758 | 6583.2886 | 16458.2215 | 0 | 214140.8197 | 0 | 0 | 0 | 41297.75 | 208390.8549 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-17 | 1186127.2866 | 0 | 946379.52 | 247401.1268 | 73349.849 | 214374.4314 | 573233.7993 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 247401.1268 | 0 | 7098.3725 | 43063.4597 | 6625.1477 | 16562.8691 | 0 | 214374.4314 | 0 | 0 | 0 | 41297.75 | 208709.4743 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-18 | 1188001.0681 | 0 | 946379.52 | 248259.2376 | 73813.2886 | 214608.0432 | 573552.4187 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 248259.2376 | 0 | 7143.2215 | 43335.5436 | 6667.0067 | 16667.5168 | 0 | 214608.0432 | 0 | 0 | 0 | 41297.75 | 209028.0937 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-19 | 1189874.8496 | 0 | 946379.52 | 249117.3483 | 74276.7282 | 214841.6549 | 573871.0382 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 249117.3483 | 0 | 7188.0705 | 43607.6275 | 6708.8658 | 16772.1644 | 0 | 214841.6549 | 0 | 0 | 0 | 41297.75 | 209346.7132 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-20 | 1191748.6311 | 0 | 946379.52 | 249975.4591 | 74740.1678 | 215075.2667 | 574189.6576 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 249975.4591 | 0 | 7232.9195 | 43879.7114 | 6750.7248 | 16876.8121 | 0 | 215075.2667 | 0 | 0 | 0 | 41297.75 | 209665.3326 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-21 | 1193622.4126 | 0 | 946379.52 | 250833.5698 | 75203.6074 | 215308.8784 | 574508.277 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 250833.5698 | 0 | 7277.7685 | 44151.7953 | 6792.5839 | 16981.4597 | 0 | 215308.8784 | 0 | 0 | 0 | 41297.75 | 209983.952 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-22 | 1195496.1941 | 0 | 946379.52 | 251691.6805 | 75667.047 | 215542.4902 | 574826.8965 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 251691.6805 | 0 | 7322.6174 | 44423.8792 | 6834.443 | 17086.1074 | 0 | 215542.4902 | 0 | 0 | 0 | 41297.75 | 210302.5715 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-23 | 1197369.9757 | 0 | 946379.52 | 252549.7913 | 76130.4866 | 215776.1019 | 575145.5159 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 252549.7913 | 0 | 7367.4664 | 44695.9631 | 6876.302 | 17190.755 | 0 | 215776.1019 | 0 | 0 | 0 | 41297.75 | 210621.1909 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-24 | 1199243.7572 | 0 | 946379.52 | 253407.902 | 76593.9262 | 216009.7136 | 575464.1353 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 253407.902 | 0 | 7412.3154 | 44968.047 | 6918.1611 | 17295.4027 | 0 | 216009.7136 | 0 | 0 | 0 | 41297.75 | 210939.8103 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-25 | 1201117.5387 | 0 | 946379.52 | 254266.0128 | 77057.3658 | 216243.3254 | 575782.7548 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 254266.0128 | 0 | 7457.1644 | 45240.1309 | 6960.0201 | 17400.0503 | 0 | 216243.3254 | 0 | 0 | 0 | 41297.75 | 211258.4298 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-26 | 1202991.3202 | 0 | 946379.52 | 255124.1235 | 77520.8054 | 216476.9371 | 576101.3742 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 255124.1235 | 0 | 7502.0134 | 45512.2148 | 7001.8792 | 17504.698 | 0 | 216476.9371 | 0 | 0 | 0 | 41297.75 | 211577.0492 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-27 | 1204865.1017 | 0 | 946379.52 | 255982.2342 | 77984.245 | 216710.5489 | 576419.9936 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 255982.2342 | 0 | 7546.8624 | 45784.2987 | 7043.7383 | 17609.3456 | 0 | 216710.5489 | 0 | 0 | 0 | 41297.75 | 211895.6686 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-28 | 1206738.8832 | 0 | 946379.52 | 256840.345 | 78447.6846 | 216944.1606 | 576738.6131 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 256840.345 | 0 | 7591.7114 | 46056.3826 | 7085.5973 | 17713.9933 | 0 | 216944.1606 | 0 | 0 | 0 | 41297.75 | 212214.2881 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-29 | 1208612.6647 | 0 | 946379.52 | 257698.4557 | 78911.1242 | 217177.7724 | 577057.2325 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 257698.4557 | 0 | 7636.5604 | 46328.4664 | 7127.4564 | 17818.6409 | 0 | 217177.7724 | 0 | 0 | 0 | 41297.75 | 212532.9075 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-30 | 1210486.4463 | 0 | 946379.52 | 258556.5664 | 79374.5638 | 217411.3841 | 577375.8519 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 258556.5664 | 0 | 7681.4094 | 46600.5503 | 7169.3154 | 17923.2886 | 0 | 217411.3841 | 0 | 0 | 0 | 41297.75 | 212851.5269 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-01 | 1212360.2278 | 0 | 946379.52 | 259414.6772 | 79838.0034 | 217644.9959 | 577694.4714 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 259414.6772 | 0 | 7726.2584 | 46872.6342 | 7211.1745 | 18027.9362 | 0 | 217644.9959 | 0 | 0 | 0 | 41297.75 | 213170.1464 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-02 | 1214234.0093 | 0 | 946379.52 | 260272.7879 | 80301.443 | 217878.6076 | 578013.0908 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 260272.7879 | 0 | 7771.1074 | 47144.7181 | 7253.0336 | 18132.5839 | 0 | 217878.6076 | 0 | 0 | 0 | 41297.75 | 213488.7658 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-03 | 1216107.7908 | 0 | 946379.52 | 261130.8987 | 80764.8826 | 218112.2194 | 578331.7102 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 261130.8987 | 0 | 7815.9564 | 47416.802 | 7294.8926 | 18237.2315 | 0 | 218112.2194 | 0 | 0 | 0 | 41297.75 | 213807.3852 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-04 | 1217981.5723 | 0 | 946379.52 | 261989.0094 | 81228.3221 | 218345.8311 | 578650.3297 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 261989.0094 | 0 | 7860.8054 | 47688.8859 | 7336.7517 | 18341.8792 | 0 | 218345.8311 | 0 | 0 | 0 | 41297.75 | 214126.0047 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-05 | 1219855.3538 | 0 | 946379.52 | 262847.1201 | 81691.7617 | 218579.4428 | 578968.9491 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 262847.1201 | 0 | 7905.6544 | 47960.9698 | 7378.6107 | 18446.5268 | 0 | 218579.4428 | 0 | 0 | 0 | 41297.75 | 214444.6241 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-06 | 1221729.1353 | 0 | 946379.52 | 263705.2309 | 82155.2013 | 218813.0546 | 579287.5685 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 263705.2309 | 0 | 7950.5034 | 48233.0537 | 7420.4698 | 18551.1745 | 0 | 218813.0546 | 0 | 0 | 0 | 41297.75 | 214763.2435 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-07 | 1223602.9169 | 0 | 946379.52 | 264563.3416 | 82618.6409 | 219046.6663 | 579606.188 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 264563.3416 | 0 | 7995.3523 | 48505.1376 | 7462.3289 | 18655.8221 | 0 | 219046.6663 | 0 | 0 | 0 | 41297.75 | 215081.863 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-08 | 1225476.6984 | 0 | 946379.52 | 265421.4523 | 83082.0805 | 219280.2781 | 579924.8074 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 265421.4523 | 0 | 8040.2013 | 48777.2215 | 7504.1879 | 18760.4698 | 0 | 219280.2781 | 0 | 0 | 0 | 41297.75 | 215400.4824 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-09 | 1227350.4799 | 0 | 946379.52 | 266279.5631 | 83545.5201 | 219513.8898 | 580243.4268 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 266279.5631 | 0 | 8085.0503 | 49049.3054 | 7546.047 | 18865.1174 | 0 | 219513.8898 | 0 | 0 | 0 | 41297.75 | 215719.1018 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-10 | 1229224.2614 | 86347.08 | 1032726.6 | 267137.6738 | 84008.9597 | 219747.5016 | 580562.0463 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 267137.6738 | 0 | 8129.8993 | 49321.3893 | 7587.906 | 18969.7651 | 0 | 219747.5016 | 0 | 0 | 0 | 41297.75 | 216037.7213 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-11 | 1231098.0429 | 0 | 1032726.6 | 267995.7846 | 84472.3993 | 219981.1133 | 580880.6657 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 267995.7846 | 0 | 8174.7483 | 49593.4732 | 7629.7651 | 19074.4128 | 0 | 219981.1133 | 0 | 0 | 0 | 41297.75 | 216356.3407 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-12 | 1232971.8244 | 0 | 1032726.6 | 268853.8953 | 84935.8389 | 220214.7251 | 581199.2851 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 268853.8953 | 0 | 8219.5973 | 49865.557 | 7671.6242 | 19179.0604 | 0 | 220214.7251 | 0 | 0 | 0 | 41297.75 | 216674.9601 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-13 | 1234845.6059 | 0 | 1032726.6 | 269712.006 | 85399.2785 | 220448.3368 | 581517.9046 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 269712.006 | 0 | 8264.4463 | 50137.6409 | 7713.4832 | 19283.7081 | 0 | 220448.3368 | 0 | 0 | 0 | 41297.75 | 216993.5796 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-14 | 1236719.3875 | 0 | 1032726.6 | 270570.1168 | 85862.7181 | 220681.9485 | 581836.524 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 270570.1168 | 0 | 8309.2953 | 50409.7248 | 7755.3423 | 19388.3557 | 0 | 220681.9485 | 0 | 0 | 0 | 41297.75 | 217312.199 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-15 | 1238593.169 | 0 | 1032726.6 | 271428.2275 | 86326.1577 | 220915.5603 | 582155.1434 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 271428.2275 | 0 | 8354.1443 | 50681.8087 | 7797.2013 | 19493.0034 | 0 | 220915.5603 | 0 | 0 | 0 | 41297.75 | 217630.8184 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-16 | 1240466.9505 | 0 | 1032726.6 | 272286.3383 | 86789.5973 | 221149.172 | 582473.7629 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 272286.3383 | 0 | 8398.9933 | 50953.8926 | 7839.0604 | 19597.651 | 0 | 221149.172 | 0 | 0 | 0 | 41297.75 | 217949.4379 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-17 | 1242340.732 | 0 | 1032726.6 | 273144.449 | 87253.0369 | 221382.7838 | 582792.3823 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 273144.449 | 0 | 8443.8423 | 51225.9765 | 7880.9195 | 19702.2987 | 0 | 221382.7838 | 0 | 0 | 0 | 41297.75 | 218268.0573 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-18 | 1244214.5135 | 0 | 1032726.6 | 274002.5597 | 87716.4765 | 221616.3955 | 583111.0017 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 274002.5597 | 0 | 8488.6913 | 51498.0604 | 7922.7785 | 19806.9463 | 0 | 221616.3955 | 0 | 0 | 0 | 41297.75 | 218586.6767 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-19 | 1246088.295 | 0 | 1032726.6 | 274860.6705 | 88179.9161 | 221850.0073 | 583429.6212 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 274860.6705 | 0 | 8533.5403 | 51770.1443 | 7964.6376 | 19911.594 | 0 | 221850.0073 | 0 | 0 | 0 | 41297.75 | 218905.2962 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-20 | 1247962.0765 | 0 | 1032726.6 | 275718.7812 | 88643.3557 | 222083.619 | 583748.2406 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 275718.7812 | 0 | 8578.3893 | 52042.2282 | 8006.4966 | 20016.2416 | 0 | 222083.619 | 0 | 0 | 0 | 41297.75 | 219223.9156 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-21 | 1249835.8581 | 0 | 1032726.6 | 276576.8919 | 89106.7953 | 222317.2308 | 584066.86 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 276576.8919 | 0 | 8623.2383 | 52314.3121 | 8048.3557 | 20120.8893 | 0 | 222317.2308 | 0 | 0 | 0 | 41297.75 | 219542.535 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-22 | 1251709.6396 | 0 | 1032726.6 | 277435.0027 | 89570.2349 | 222550.8425 | 584385.4795 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 277435.0027 | 0 | 8668.0872 | 52586.396 | 8090.2148 | 20225.5369 | 0 | 222550.8425 | 0 | 0 | 0 | 41297.75 | 219861.1545 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-23 | 1253583.4211 | 0 | 1032726.6 | 278293.1134 | 90033.6745 | 222784.4543 | 584704.0989 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 278293.1134 | 0 | 8712.9362 | 52858.4799 | 8132.0738 | 20330.1846 | 0 | 222784.4543 | 0 | 0 | 0 | 41297.75 | 220179.7739 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-24 | 1255457.2026 | 0 | 1032726.6 | 279151.2242 | 90497.1141 | 223018.066 | 585022.7183 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 279151.2242 | 0 | 8757.7852 | 53130.5638 | 8173.9329 | 20434.8322 | 0 | 223018.066 | 0 | 0 | 0 | 41297.75 | 220498.3933 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-25 | 1257330.9841 | 0 | 1032726.6 | 280009.3349 | 90960.5537 | 223251.6777 | 585341.3378 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 280009.3349 | 0 | 8802.6342 | 53402.6477 | 8215.7919 | 20539.4799 | 0 | 223251.6777 | 0 | 0 | 0 | 41297.75 | 220817.0128 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-26 | 1259204.7656 | 0 | 1032726.6 | 280867.4456 | 91423.9933 | 223485.2895 | 585659.9572 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 280867.4456 | 0 | 8847.4832 | 53674.7315 | 8257.651 | 20644.1275 | 0 | 223485.2895 | 0 | 0 | 0 | 41297.75 | 221135.6322 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-27 | 1261078.5471 | 0 | 1032726.6 | 281725.5564 | 91887.4329 | 223718.9012 | 585978.5766 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 281725.5564 | 0 | 8892.3322 | 53946.8154 | 8299.5101 | 20748.7752 | 0 | 223718.9012 | 0 | 0 | 0 | 41297.75 | 221454.2516 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-28 | 1262952.3286 | 0 | 1032726.6 | 282583.6671 | 92350.8725 | 223952.513 | 586297.1961 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 282583.6671 | 0 | 8937.1812 | 54218.8993 | 8341.3691 | 20853.4228 | 0 | 223952.513 | 0 | 0 | 0 | 41297.75 | 221772.8711 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-29 | 1264826.1102 | 0 | 1032726.6 | 283441.7779 | 92814.3121 | 224186.1247 | 586615.8155 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 283441.7779 | 0 | 8982.0302 | 54490.9832 | 8383.2282 | 20958.0705 | 0 | 224186.1247 | 0 | 0 | 0 | 41297.75 | 222091.4905 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-30 | 1266699.8917 | 0 | 1032726.6 | 284299.8886 | 93277.7517 | 224419.7365 | 586934.4349 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 284299.8886 | 0 | 9026.8792 | 54763.0671 | 8425.0872 | 21062.7181 | 0 | 224419.7365 | 0 | 0 | 0 | 41297.75 | 222410.1099 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-31 | 1268573.6732 | 0 | 1032726.6 | 285157.9993 | 93741.1913 | 224653.3482 | 587253.0544 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 285157.9993 | 0 | 9071.7282 | 55035.151 | 8466.9463 | 21167.3658 | 0 | 224653.3482 | 0 | 0 | 0 | 41297.75 | 222728.7294 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-01 | 1270447.4547 | 0 | 1032726.6 | 286016.1101 | 94204.6309 | 224886.96 | 587571.6738 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 286016.1101 | 0 | 9116.5772 | 55307.2349 | 8508.8054 | 21272.0134 | 0 | 224886.96 | 0 | 0 | 0 | 41297.75 | 223047.3488 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-02 | 1272321.2362 | 0 | 1032726.6 | 286874.2208 | 94668.0705 | 225120.5717 | 587890.2932 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 286874.2208 | 0 | 9161.4262 | 55579.3188 | 8550.6644 | 21376.6611 | 0 | 225120.5717 | 0 | 0 | 0 | 41297.75 | 223365.9682 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-03 | 1274195.0177 | 0 | 1032726.6 | 287732.3315 | 95131.5101 | 225354.1834 | 588208.9127 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 287732.3315 | 0 | 9206.2752 | 55851.4027 | 8592.5235 | 21481.3087 | 0 | 225354.1834 | 0 | 0 | 0 | 41297.75 | 223684.5877 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-04 | 1276068.7992 | 0 | 1032726.6 | 288590.4423 | 95594.9497 | 225587.7952 | 588527.5321 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 288590.4423 | 0 | 9251.1242 | 56123.4866 | 8634.3826 | 21585.9564 | 0 | 225587.7952 | 0 | 0 | 0 | 41297.75 | 224003.2071 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-05 | 1277942.5808 | 0 | 1032726.6 | 289448.553 | 96058.3893 | 225821.4069 | 588846.1515 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 289448.553 | 0 | 9295.9732 | 56395.5705 | 8676.2416 | 21690.604 | 0 | 225821.4069 | 0 | 0 | 0 | 41297.75 | 224321.8265 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-06 | 1279816.3623 | 0 | 1032726.6 | 290306.6638 | 96521.8289 | 226055.0187 | 589164.771 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 290306.6638 | 0 | 9340.8221 | 56667.6544 | 8718.1007 | 21795.2517 | 0 | 226055.0187 | 0 | 0 | 0 | 41297.75 | 224640.446 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-07 | 1281690.1438 | 0 | 1032726.6 | 291164.7745 | 96985.2685 | 226288.6304 | 589483.3904 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 291164.7745 | 0 | 9385.6711 | 56939.7383 | 8759.9597 | 21899.8993 | 0 | 226288.6304 | 0 | 0 | 0 | 41297.75 | 224959.0654 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-08 | 1283563.9253 | 98711.01 | 1131437.61 | 292022.8852 | 97448.7081 | 226522.2422 | 589802.0098 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 292022.8852 | 0 | 9430.5201 | 57211.8221 | 8801.8188 | 22004.547 | 0 | 226522.2422 | 0 | 0 | 0 | 41297.75 | 225277.6848 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-09 | 1285437.7068 | 0 | 1131437.61 | 292880.996 | 97912.1477 | 226755.8539 | 590120.6293 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 292880.996 | 0 | 9475.3691 | 57483.906 | 8843.6779 | 22109.1946 | 0 | 226755.8539 | 0 | 0 | 0 | 41297.75 | 225596.3043 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-10 | 1287311.4883 | 0 | 1131437.61 | 293739.1067 | 98375.5872 | 226989.4657 | 590439.2487 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 293739.1067 | 0 | 9520.2181 | 57755.9899 | 8885.5369 | 22213.8423 | 0 | 226989.4657 | 0 | 0 | 0 | 41297.75 | 225914.9237 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-11 | 1289185.2698 | 0 | 1131437.61 | 294597.2174 | 98839.0268 | 227223.0774 | 590757.8681 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 294597.2174 | 0 | 9565.0671 | 58028.0738 | 8927.396 | 22318.4899 | 0 | 227223.0774 | 0 | 0 | 0 | 41297.75 | 226233.5431 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-12 | 1291059.0514 | 0 | 1131437.61 | 295455.3282 | 99302.4664 | 227456.6892 | 591076.4876 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 295455.3282 | 0 | 9609.9161 | 58300.1577 | 8969.255 | 22423.1376 | 0 | 227456.6892 | 0 | 0 | 0 | 41297.75 | 226552.1626 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-13 | 1292932.8329 | 0 | 1131437.61 | 296313.4389 | 99765.906 | 227690.3009 | 591395.107 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 296313.4389 | 0 | 9654.7651 | 58572.2416 | 9011.1141 | 22527.7852 | 0 | 227690.3009 | 0 | 0 | 0 | 41297.75 | 226870.782 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-14 | 1294806.6144 | 0 | 1131437.61 | 297171.5497 | 100229.3456 | 227923.9126 | 591713.7264 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 297171.5497 | 0 | 9699.6141 | 58844.3255 | 9052.9732 | 22632.4329 | 0 | 227923.9126 | 0 | 0 | 0 | 41297.75 | 227189.4014 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-15 | 1296680.3959 | 0 | 1131437.61 | 298029.6604 | 100692.7852 | 228157.5244 | 592032.3459 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 298029.6604 | 0 | 9744.4631 | 59116.4094 | 9094.8322 | 22737.0805 | 0 | 228157.5244 | 0 | 0 | 0 | 41297.75 | 227508.0209 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-16 | 1298554.1774 | 0 | 1131437.61 | 298887.7711 | 101156.2248 | 228391.1361 | 592350.9653 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 298887.7711 | 0 | 9789.3121 | 59388.4933 | 9136.6913 | 22841.7282 | 0 | 228391.1361 | 0 | 0 | 0 | 41297.75 | 227826.6403 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-17 | 1300427.9589 | 0 | 1131437.61 | 299745.8819 | 101619.6644 | 228624.7479 | 592669.5847 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 299745.8819 | 0 | 9834.1611 | 59660.5772 | 9178.5503 | 22946.3758 | 0 | 228624.7479 | 0 | 0 | 0 | 41297.75 | 228145.2597 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-18 | 1302301.7404 | 0 | 1131437.61 | 300603.9926 | 102083.104 | 228858.3596 | 592988.2042 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 300603.9926 | 0 | 9879.0101 | 59932.6611 | 9220.4094 | 23051.0235 | 0 | 228858.3596 | 0 | 0 | 0 | 41297.75 | 228463.8792 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-19 | 1304175.522 | 0 | 1131437.61 | 301462.1034 | 102546.5436 | 229091.9714 | 593306.8236 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 301462.1034 | 0 | 9923.8591 | 60204.745 | 9262.2685 | 23155.6711 | 0 | 229091.9714 | 0 | 0 | 0 | 41297.75 | 228782.4986 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-20 | 1306049.3035 | 0 | 1131437.61 | 302320.2141 | 103009.9832 | 229325.5831 | 593625.443 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 302320.2141 | 0 | 9968.7081 | 60476.8289 | 9304.1275 | 23260.3188 | 0 | 229325.5831 | 0 | 0 | 0 | 41297.75 | 229101.118 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-21 | 1307923.085 | 0 | 1131437.61 | 303178.3248 | 103473.4228 | 229559.1949 | 593944.0625 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 303178.3248 | 0 | 10013.557 | 60748.9128 | 9345.9866 | 23364.9664 | 0 | 229559.1949 | 0 | 0 | 0 | 41297.75 | 229419.7375 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-22 | 1309796.8665 | 0 | 1131437.61 | 304036.4356 | 103936.8624 | 229792.8066 | 594262.6819 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 304036.4356 | 0 | 10058.406 | 61020.9966 | 9387.8456 | 23469.6141 | 0 | 229792.8066 | 0 | 0 | 0 | 41297.75 | 229738.3569 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-23 | 1311670.648 | 0 | 1131437.61 | 304894.5463 | 104400.302 | 230026.4183 | 594581.3013 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 304894.5463 | 0 | 10103.255 | 61293.0805 | 9429.7047 | 23574.2617 | 0 | 230026.4183 | 0 | 0 | 0 | 41297.75 | 230056.9763 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-24 | 1313544.4295 | 0 | 1131437.61 | 305752.657 | 104863.7416 | 230260.0301 | 594899.9208 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 305752.657 | 0 | 10148.104 | 61565.1644 | 9471.5638 | 23678.9094 | 0 | 230260.0301 | 0 | 0 | 0 | 41297.75 | 230375.5958 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-25 | 1315418.211 | 0 | 1131437.61 | 306610.7678 | 105327.1812 | 230493.6418 | 595218.5402 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 306610.7678 | 0 | 10192.953 | 61837.2483 | 9513.4228 | 23783.557 | 0 | 230493.6418 | 0 | 0 | 0 | 41297.75 | 230694.2152 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-26 | 1317291.9926 | 0 | 1131437.61 | 307468.8785 | 105790.6208 | 230727.2536 | 595537.1596 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 307468.8785 | 0 | 10237.802 | 62109.3322 | 9555.2819 | 23888.2047 | 0 | 230727.2536 | 0 | 0 | 0 | 41297.75 | 231012.8346 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-27 | 1319165.7741 | 0 | 1131437.61 | 308326.9893 | 106254.0604 | 230960.8653 | 595855.7791 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 308326.9893 | 0 | 10282.651 | 62381.4161 | 9597.1409 | 23992.8523 | 0 | 230960.8653 | 0 | 0 | 0 | 41297.75 | 231331.4541 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-28 | 1321039.5556 | 0 | 1131437.61 | 309185.1 | 106717.5 | 231194.4771 | 596174.3985 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 309185.1 | 0 | 10327.5 | 62653.5 | 9639 | 24097.5 | 0 | 231194.4771 | 0 | 0 | 0 | 41297.75 | 231650.0735 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-29 | 1324281.088 | 0 | 1131437.61 | 310943.4557 | 107548.7247 | 231194.4771 | 596437.5102 | 78156.9204 | 0 | 8048.04 | 1306.5 | 0 | 0 | 38561.6088 | 13326.3 | 0 | 0 | 0 | 0 | 0 | 6462.4716 | 4180.8 | 6271.2 | 0 | 0 | 305026.575 | 310943.4557 | 0 | 10407.9411 | 63141.5093 | 9714.0784 | 24285.1959 | 0 | 231194.4771 | 89.2125 | 0 | 0 | 41297.75 | 231823.9727 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-30 | 1327522.6205 | 0 | 1131437.61 | 312701.8114 | 108379.9494 | 231194.4771 | 596700.6218 | 78545.7608 | 0 | 8088.08 | 1313 | 0 | 0 | 38753.4576 | 13392.6 | 0 | 0 | 0 | 0 | 0 | 6494.6232 | 4201.6 | 6302.4 | 0 | 0 | 305026.575 | 312701.8114 | 0 | 10488.3822 | 63629.5187 | 9789.1567 | 24472.8918 | 0 | 231194.4771 | 178.425 | 0 | 0 | 41297.75 | 231997.8718 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-31 | 1330764.153 | 39314.5 | 1170752.11 | 314460.1671 | 109211.1741 | 231194.4771 | 596963.7335 | 78934.6012 | 0 | 8128.12 | 1319.5 | 0 | 0 | 38945.3064 | 13458.9 | 0 | 0 | 0 | 0 | 0 | 6526.7748 | 4222.4 | 6333.6 | 0 | 0 | 305026.575 | 314460.1671 | 0 | 10568.8233 | 64117.528 | 9864.2351 | 24660.5877 | 0 | 231194.4771 | 267.6375 | 0 | 0 | 41297.75 | 232171.771 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-01 | 1334005.6854 | 0 | 1170752.11 | 316218.5228 | 110042.3988 | 231194.4771 | 597226.8452 | 79323.4416 | 0 | 8168.16 | 1326 | 0 | 0 | 39137.1552 | 13525.2 | 0 | 0 | 0 | 0 | 0 | 6558.9264 | 4243.2 | 6364.8 | 0 | 0 | 305026.575 | 316218.5228 | 0 | 10649.2644 | 64605.5374 | 9939.3134 | 24848.2836 | 0 | 231194.4771 | 356.85 | 0 | 0 | 41297.75 | 232345.6702 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-02 | 1337247.2179 | 0 | 1170752.11 | 317976.8785 | 110873.6235 | 231194.4771 | 597489.9568 | 79712.282 | 0 | 8208.2 | 1332.5 | 0 | 0 | 39329.004 | 13591.5 | 0 | 0 | 0 | 0 | 0 | 6591.078 | 4264 | 6396 | 0 | 0 | 305026.575 | 317976.8785 | 0 | 10729.7055 | 65093.5467 | 10014.3918 | 25035.9795 | 0 | 231194.4771 | 446.0625 | 0 | 0 | 41297.75 | 232519.5693 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-03 | 1340488.7504 | 0 | 1170752.11 | 319735.2342 | 111704.8482 | 231194.4771 | 597753.0685 | 80101.1224 | 0 | 8248.24 | 1339 | 0 | 0 | 39520.8528 | 13657.8 | 0 | 0 | 0 | 0 | 0 | 6623.2296 | 4284.8 | 6427.2 | 0 | 0 | 305026.575 | 319735.2342 | 0 | 10810.1466 | 65581.556 | 10089.4702 | 25223.6754 | 0 | 231194.4771 | 535.275 | 0 | 0 | 41297.75 | 232693.4685 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-04 | 1343730.2828 | 0 | 1170752.11 | 321493.5899 | 112536.0729 | 231194.4771 | 598016.1802 | 80489.9628 | 0 | 8288.28 | 1345.5 | 0 | 0 | 39712.7016 | 13724.1 | 0 | 0 | 0 | 0 | 0 | 6655.3812 | 4305.6 | 6458.4 | 0 | 0 | 305026.575 | 321493.5899 | 0 | 10890.5877 | 66069.5654 | 10164.5485 | 25411.3713 | 0 | 231194.4771 | 624.4875 | 0 | 0 | 41297.75 | 232867.3677 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-05 | 1346971.8153 | 0 | 1170752.11 | 323251.9456 | 113367.2976 | 231194.4771 | 598279.2918 | 80878.8032 | 0 | 8328.32 | 1352 | 0 | 0 | 39904.5504 | 13790.4 | 0 | 0 | 0 | 0 | 0 | 6687.5328 | 4326.4 | 6489.6 | 0 | 0 | 305026.575 | 323251.9456 | 0 | 10971.0288 | 66557.5747 | 10239.6269 | 25599.0672 | 0 | 231194.4771 | 713.7 | 0 | 0 | 41297.75 | 233041.2668 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-06 | 1350213.3477 | 0 | 1170752.11 | 325010.3013 | 114198.5223 | 231194.4771 | 598542.4035 | 81267.6436 | 0 | 8368.36 | 1358.5 | 0 | 0 | 40096.3992 | 13856.7 | 0 | 0 | 0 | 0 | 0 | 6719.6844 | 4347.2 | 6520.8 | 0 | 0 | 305026.575 | 325010.3013 | 0 | 11051.4699 | 67045.5841 | 10314.7052 | 25786.7631 | 0 | 231194.4771 | 802.9125 | 0 | 0 | 41297.75 | 233215.166 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-07 | 1353454.8802 | 0 | 1170752.11 | 326768.6569 | 115029.747 | 231194.4771 | 598805.5152 | 81656.484 | 0 | 8408.4 | 1365 | 0 | 0 | 40288.248 | 13923 | 0 | 0 | 0 | 0 | 0 | 6751.836 | 4368 | 6552 | 0 | 0 | 305026.575 | 326768.6569 | 0 | 11131.911 | 67533.5934 | 10389.7836 | 25974.459 | 0 | 231194.4771 | 892.125 | 0 | 0 | 41297.75 | 233389.0652 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-08 | 1356696.4127 | 0 | 1170752.11 | 328527.0126 | 115860.9717 | 231194.4771 | 599068.6268 | 82045.3244 | 0 | 8448.44 | 1371.5 | 0 | 0 | 40480.0968 | 13989.3 | 0 | 0 | 0 | 0 | 0 | 6783.9876 | 4388.8 | 6583.2 | 0 | 0 | 305026.575 | 328527.0126 | 0 | 11212.3521 | 68021.6027 | 10464.862 | 26162.1549 | 0 | 231194.4771 | 981.3375 | 0 | 0 | 41297.75 | 233562.9643 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-09 | 1359937.9451 | 0 | 1170752.11 | 330285.3683 | 116692.1964 | 231194.4771 | 599331.7385 | 82434.1648 | 0 | 8488.48 | 1378 | 0 | 0 | 40671.9456 | 14055.6 | 0 | 0 | 0 | 0 | 0 | 6816.1392 | 4409.6 | 6614.4 | 0 | 0 | 305026.575 | 330285.3683 | 0 | 11292.7932 | 68509.6121 | 10539.9403 | 26349.8508 | 0 | 231194.4771 | 1070.55 | 0 | 0 | 41297.75 | 233736.8635 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-10 | 1363179.4776 | 0 | 1170752.11 | 332043.724 | 117523.4211 | 231194.4771 | 599594.8502 | 82823.0052 | 0 | 8528.52 | 1384.5 | 0 | 0 | 40863.7944 | 14121.9 | 0 | 0 | 0 | 0 | 0 | 6848.2908 | 4430.4 | 6645.6 | 0 | 0 | 305026.575 | 332043.724 | 0 | 11373.2343 | 68997.6214 | 10615.0187 | 26537.5467 | 0 | 231194.4771 | 1159.7625 | 0 | 0 | 41297.75 | 233910.7627 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-11 | 1366421.01 | 0 | 1170752.11 | 333802.0797 | 118354.6458 | 231194.4771 | 599857.9618 | 83211.8456 | 0 | 8568.56 | 1391 | 0 | 0 | 41055.6432 | 14188.2 | 0 | 0 | 0 | 0 | 0 | 6880.4424 | 4451.2 | 6676.8 | 0 | 0 | 305026.575 | 333802.0797 | 0 | 11453.6754 | 69485.6308 | 10690.097 | 26725.2426 | 0 | 231194.4771 | 1248.975 | 0 | 0 | 41297.75 | 234084.6618 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-12 | 1369662.5425 | 0 | 1170752.11 | 335560.4354 | 119185.8705 | 231194.4771 | 600121.0735 | 83600.686 | 0 | 8608.6 | 1397.5 | 0 | 0 | 41247.492 | 14254.5 | 0 | 0 | 0 | 0 | 0 | 6912.594 | 4472 | 6708 | 0 | 0 | 305026.575 | 335560.4354 | 0 | 11534.1165 | 69973.6401 | 10765.1754 | 26912.9385 | 0 | 231194.4771 | 1338.1875 | 0 | 0 | 41297.75 | 234258.561 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-13 | 1372904.075 | 0 | 1170752.11 | 337318.7911 | 120017.0952 | 231194.4771 | 600384.1852 | 83989.5264 | 0 | 8648.64 | 1404 | 0 | 0 | 41439.3408 | 14320.8 | 0 | 0 | 0 | 0 | 0 | 6944.7456 | 4492.8 | 6739.2 | 0 | 0 | 305026.575 | 337318.7911 | 0 | 11614.5576 | 70461.6494 | 10840.2538 | 27100.6344 | 0 | 231194.4771 | 1427.4 | 0 | 0 | 41297.75 | 234432.4602 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-14 | 1376145.6074 | 0 | 1170752.11 | 339077.1468 | 120848.3199 | 231194.4771 | 600647.2968 | 84378.3668 | 0 | 8688.68 | 1410.5 | 0 | 0 | 41631.1896 | 14387.1 | 0 | 0 | 0 | 0 | 0 | 6976.8972 | 4513.6 | 6770.4 | 0 | 0 | 305026.575 | 339077.1468 | 0 | 11694.9987 | 70949.6588 | 10915.3321 | 27288.3303 | 0 | 231194.4771 | 1516.6125 | 0 | 0 | 41297.75 | 234606.3593 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-15 | 1379387.1399 | 0 | 1170752.11 | 340835.5025 | 121679.5446 | 231194.4771 | 600910.4085 | 84767.2072 | 0 | 8728.72 | 1417 | 0 | 0 | 41823.0384 | 14453.4 | 0 | 0 | 0 | 0 | 0 | 7009.0488 | 4534.4 | 6801.6 | 0 | 0 | 305026.575 | 340835.5025 | 0 | 11775.4398 | 71437.6681 | 10990.4105 | 27476.0262 | 0 | 231194.4771 | 1605.825 | 0 | 0 | 41297.75 | 234780.2585 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-16 | 1382628.6724 | 0 | 1170752.11 | 342593.8582 | 122510.7693 | 231194.4771 | 601173.5202 | 85156.0476 | 0 | 8768.76 | 1423.5 | 0 | 0 | 42014.8872 | 14519.7 | 0 | 0 | 0 | 0 | 0 | 7041.2004 | 4555.2 | 6832.8 | 0 | 0 | 305026.575 | 342593.8582 | 0 | 11855.8809 | 71925.6775 | 11065.4888 | 27663.7221 | 0 | 231194.4771 | 1695.0375 | 0 | 0 | 41297.75 | 234954.1577 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-17 | 1385870.2048 | 0 | 1170752.11 | 344352.2139 | 123341.994 | 231194.4771 | 601436.6318 | 85544.888 | 0 | 8808.8 | 1430 | 0 | 0 | 42206.736 | 14586 | 0 | 0 | 0 | 0 | 0 | 7073.352 | 4576 | 6864 | 0 | 0 | 305026.575 | 344352.2139 | 0 | 11936.322 | 72413.6868 | 11140.5672 | 27851.418 | 0 | 231194.4771 | 1784.25 | 0 | 0 | 41297.75 | 235128.0568 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-18 | 1389111.7373 | 0 | 1170752.11 | 346110.5696 | 124173.2187 | 231194.4771 | 601699.7435 | 85933.7284 | 0 | 8848.84 | 1436.5 | 0 | 0 | 42398.5848 | 14652.3 | 0 | 0 | 0 | 0 | 0 | 7105.5036 | 4596.8 | 6895.2 | 0 | 0 | 305026.575 | 346110.5696 | 0 | 12016.7631 | 72901.6961 | 11215.6456 | 28039.1139 | 0 | 231194.4771 | 1873.4625 | 0 | 0 | 41297.75 | 235301.956 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-19 | 1392353.2697 | 0 | 1170752.11 | 347868.9253 | 125004.4434 | 231194.4771 | 601962.8552 | 86322.5688 | 0 | 8888.88 | 1443 | 0 | 0 | 42590.4336 | 14718.6 | 0 | 0 | 0 | 0 | 0 | 7137.6552 | 4617.6 | 6926.4 | 0 | 0 | 305026.575 | 347868.9253 | 0 | 12097.2042 | 73389.7055 | 11290.7239 | 28226.8098 | 0 | 231194.4771 | 1962.675 | 0 | 0 | 41297.75 | 235475.8552 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-20 | 1395594.8022 | 0 | 1170752.11 | 349627.281 | 125835.6681 | 231194.4771 | 602225.9668 | 86711.4092 | 0 | 8928.92 | 1449.5 | 0 | 0 | 42782.2824 | 14784.9 | 0 | 0 | 0 | 0 | 0 | 7169.8068 | 4638.4 | 6957.6 | 0 | 0 | 305026.575 | 349627.281 | 0 | 12177.6453 | 73877.7148 | 11365.8023 | 28414.5057 | 0 | 231194.4771 | 2051.8875 | 0 | 0 | 41297.75 | 235649.7543 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-21 | 1398836.3347 | 0 | 1170752.11 | 351385.6367 | 126666.8928 | 231194.4771 | 602489.0785 | 87100.2496 | 0 | 8968.96 | 1456 | 0 | 0 | 42974.1312 | 14851.2 | 0 | 0 | 0 | 0 | 0 | 7201.9584 | 4659.2 | 6988.8 | 0 | 0 | 305026.575 | 351385.6367 | 0 | 12258.0864 | 74365.7242 | 11440.8806 | 28602.2016 | 0 | 231194.4771 | 2141.1 | 0 | 0 | 41297.75 | 235823.6535 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-22 | 1402077.8671 | 0 | 1170752.11 | 353143.9924 | 127498.1175 | 231194.4771 | 602752.1902 | 87489.09 | 0 | 9009 | 1462.5 | 0 | 0 | 43165.98 | 14917.5 | 0 | 0 | 0 | 0 | 0 | 7234.11 | 4680 | 7020 | 0 | 0 | 305026.575 | 353143.9924 | 0 | 12338.5275 | 74853.7335 | 11515.959 | 28789.8975 | 0 | 231194.4771 | 2230.3125 | 0 | 0 | 41297.75 | 235997.5527 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-23 | 1405319.3996 | 0 | 1170752.11 | 354902.3481 | 128329.3422 | 231194.4771 | 603015.3018 | 87877.9304 | 0 | 9049.04 | 1469 | 0 | 0 | 43357.8288 | 14983.8 | 0 | 0 | 0 | 0 | 0 | 7266.2616 | 4700.8 | 7051.2 | 0 | 0 | 305026.575 | 354902.3481 | 0 | 12418.9686 | 75341.7428 | 11591.0374 | 28977.5934 | 0 | 231194.4771 | 2319.525 | 0 | 0 | 41297.75 | 236171.4518 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-24 | 1408560.932 | 0 | 1170752.11 | 356660.7038 | 129160.5669 | 231194.4771 | 603278.4135 | 88266.7708 | 0 | 9089.08 | 1475.5 | 0 | 0 | 43549.6776 | 15050.1 | 0 | 0 | 0 | 0 | 0 | 7298.4132 | 4721.6 | 7082.4 | 0 | 0 | 305026.575 | 356660.7038 | 0 | 12499.4097 | 75829.7522 | 11666.1157 | 29165.2893 | 0 | 231194.4771 | 2408.7375 | 0 | 0 | 41297.75 | 236345.351 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-25 | 1411802.4645 | 0 | 1170752.11 | 358419.0595 | 129991.7916 | 231194.4771 | 603541.5252 | 88655.6112 | 0 | 9129.12 | 1482 | 0 | 0 | 43741.5264 | 15116.4 | 0 | 0 | 0 | 0 | 0 | 7330.5648 | 4742.4 | 7113.6 | 0 | 0 | 305026.575 | 358419.0595 | 0 | 12579.8508 | 76317.7615 | 11741.1941 | 29352.9852 | 0 | 231194.4771 | 2497.95 | 0 | 0 | 41297.75 | 236519.2502 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-26 | 1415043.997 | 0 | 1170752.11 | 360177.4152 | 130823.0163 | 231194.4771 | 603804.6368 | 89044.4516 | 0 | 9169.16 | 1488.5 | 0 | 0 | 43933.3752 | 15182.7 | 0 | 0 | 0 | 0 | 0 | 7362.7164 | 4763.2 | 7144.8 | 0 | 0 | 305026.575 | 360177.4152 | 0 | 12660.2919 | 76805.7709 | 11816.2724 | 29540.6811 | 0 | 231194.4771 | 2587.1625 | 0 | 0 | 41297.75 | 236693.1493 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-27 | 1418285.5294 | 0 | 1170752.11 | 361935.7708 | 131654.241 | 231194.4771 | 604067.7485 | 89433.292 | 0 | 9209.2 | 1495 | 0 | 0 | 44125.224 | 15249 | 0 | 0 | 0 | 0 | 0 | 7394.868 | 4784 | 7176 | 0 | 0 | 305026.575 | 361935.7708 | 0 | 12740.733 | 77293.7802 | 11891.3508 | 29728.377 | 0 | 231194.4771 | 2676.375 | 0 | 0 | 41297.75 | 236867.0485 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-28 | 1421527.0619 | 0 | 1170752.11 | 363694.1265 | 132485.4657 | 231194.4771 | 604330.8602 | 89822.1324 | 0 | 9249.24 | 1501.5 | 0 | 0 | 44317.0728 | 15315.3 | 0 | 0 | 0 | 0 | 0 | 7427.0196 | 4804.8 | 7207.2 | 0 | 0 | 305026.575 | 363694.1265 | 0 | 12821.1741 | 77781.7895 | 11966.4292 | 29916.0729 | 0 | 231194.4771 | 2765.5875 | 0 | 0 | 41297.75 | 237040.9477 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-01 | 1424768.5944 | 0 | 1170752.11 | 365452.4822 | 133316.6904 | 231194.4771 | 604593.9718 | 90210.9728 | 0 | 9289.28 | 1508 | 0 | 0 | 44508.9216 | 15381.6 | 0 | 0 | 0 | 0 | 0 | 7459.1712 | 4825.6 | 7238.4 | 0 | 0 | 305026.575 | 365452.4822 | 0 | 12901.6152 | 78269.7989 | 12041.5075 | 30103.7688 | 0 | 231194.4771 | 2854.8 | 0 | 0 | 41297.75 | 237214.8468 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-02 | 1428010.1268 | 0 | 1170752.11 | 367210.8379 | 134147.9151 | 231194.4771 | 604857.0835 | 90599.8132 | 0 | 9329.32 | 1514.5 | 0 | 0 | 44700.7704 | 15447.9 | 0 | 0 | 0 | 0 | 0 | 7491.3228 | 4846.4 | 7269.6 | 0 | 0 | 305026.575 | 367210.8379 | 0 | 12982.0563 | 78757.8082 | 12116.5859 | 30291.4647 | 0 | 231194.4771 | 2944.0125 | 0 | 0 | 41297.75 | 237388.746 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-03 | 1431251.6593 | 0 | 1170752.11 | 368969.1936 | 134979.1398 | 231194.4771 | 605120.1952 | 90988.6536 | 0 | 9369.36 | 1521 | 0 | 0 | 44892.6192 | 15514.2 | 0 | 0 | 0 | 0 | 0 | 7523.4744 | 4867.2 | 7300.8 | 0 | 0 | 305026.575 | 368969.1936 | 0 | 13062.4974 | 79245.8176 | 12191.6642 | 30479.1606 | 0 | 231194.4771 | 3033.225 | 0 | 0 | 41297.75 | 237562.6452 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-04 | 1434493.1917 | 131284.23 | 1302036.34 | 370727.5493 | 135810.3645 | 231194.4771 | 605383.3068 | 91377.494 | 0 | 9409.4 | 1527.5 | 0 | 0 | 45084.468 | 15580.5 | 0 | 0 | 0 | 0 | 0 | 7555.626 | 4888 | 7332 | 0 | 0 | 305026.575 | 370727.5493 | 0 | 13142.9385 | 79733.8269 | 12266.7426 | 30666.8565 | 0 | 231194.4771 | 3122.4375 | 0 | 0 | 41297.75 | 237736.5443 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-05 | 1437734.7242 | 0 | 1302036.34 | 372485.905 | 136641.5892 | 231194.4771 | 605646.4185 | 91766.3344 | 0 | 9449.44 | 1534 | 0 | 0 | 45276.3168 | 15646.8 | 0 | 0 | 0 | 0 | 0 | 7587.7776 | 4908.8 | 7363.2 | 0 | 0 | 305026.575 | 372485.905 | 0 | 13223.3796 | 80221.8362 | 12341.821 | 30854.5524 | 0 | 231194.4771 | 3211.65 | 0 | 0 | 41297.75 | 237910.4435 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-06 | 1440976.2567 | 0 | 1302036.34 | 374244.2607 | 137472.8139 | 231194.4771 | 605909.5302 | 92155.1748 | 0 | 9489.48 | 1540.5 | 0 | 0 | 45468.1656 | 15713.1 | 0 | 0 | 0 | 0 | 0 | 7619.9292 | 4929.6 | 7394.4 | 0 | 0 | 305026.575 | 374244.2607 | 0 | 13303.8207 | 80709.8456 | 12416.8993 | 31042.2483 | 0 | 231194.4771 | 3300.8625 | 0 | 0 | 41297.75 | 238084.3427 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-07 | 1444217.7891 | 0 | 1302036.34 | 376002.6164 | 138304.0386 | 231194.4771 | 606172.6418 | 92544.0152 | 0 | 9529.52 | 1547 | 0 | 0 | 45660.0144 | 15779.4 | 0 | 0 | 0 | 0 | 0 | 7652.0808 | 4950.4 | 7425.6 | 0 | 0 | 305026.575 | 376002.6164 | 0 | 13384.2618 | 81197.8549 | 12491.9777 | 31229.9442 | 0 | 231194.4771 | 3390.075 | 0 | 0 | 41297.75 | 238258.2418 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-08 | 1447459.3216 | 0 | 1302036.34 | 377760.9721 | 139135.2633 | 231194.4771 | 606435.7535 | 92932.8556 | 0 | 9569.56 | 1553.5 | 0 | 0 | 45851.8632 | 15845.7 | 0 | 0 | 0 | 0 | 0 | 7684.2324 | 4971.2 | 7456.8 | 0 | 0 | 305026.575 | 377760.9721 | 0 | 13464.7029 | 81685.8643 | 12567.056 | 31417.6401 | 0 | 231194.4771 | 3479.2875 | 0 | 0 | 41297.75 | 238432.141 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-09 | 1450700.854 | 0 | 1302036.34 | 379519.3278 | 139966.488 | 231194.4771 | 606698.8652 | 93321.696 | 0 | 9609.6 | 1560 | 0 | 0 | 46043.712 | 15912 | 0 | 0 | 0 | 0 | 0 | 7716.384 | 4992 | 7488 | 0 | 0 | 305026.575 | 379519.3278 | 0 | 13545.144 | 82173.8736 | 12642.1344 | 31605.336 | 0 | 231194.4771 | 3568.5 | 0 | 0 | 41297.75 | 238606.0402 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-10 | 1453942.3865 | 0 | 1302036.34 | 381277.6835 | 140797.7127 | 231194.4771 | 606961.9768 | 93710.5364 | 0 | 9649.64 | 1566.5 | 0 | 0 | 46235.5608 | 15978.3 | 0 | 0 | 0 | 0 | 0 | 7748.5356 | 5012.8 | 7519.2 | 0 | 0 | 305026.575 | 381277.6835 | 0 | 13625.5851 | 82661.8829 | 12717.2128 | 31793.0319 | 0 | 231194.4771 | 3657.7125 | 0 | 0 | 41297.75 | 238779.9393 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-11 | 1457183.919 | 0 | 1302036.34 | 383036.0392 | 141628.9374 | 231194.4771 | 607225.0885 | 94099.3768 | 0 | 9689.68 | 1573 | 0 | 0 | 46427.4096 | 16044.6 | 0 | 0 | 0 | 0 | 0 | 7780.6872 | 5033.6 | 7550.4 | 0 | 0 | 305026.575 | 383036.0392 | 0 | 13706.0262 | 83149.8923 | 12792.2911 | 31980.7278 | 0 | 231194.4771 | 3746.925 | 0 | 0 | 41297.75 | 238953.8385 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-12 | 1460425.4514 | 0 | 1302036.34 | 384794.3949 | 142460.1621 | 231194.4771 | 607488.2002 | 94488.2172 | 0 | 9729.72 | 1579.5 | 0 | 0 | 46619.2584 | 16110.9 | 0 | 0 | 0 | 0 | 0 | 7812.8388 | 5054.4 | 7581.6 | 0 | 0 | 305026.575 | 384794.3949 | 0 | 13786.4673 | 83637.9016 | 12867.3695 | 32168.4237 | 0 | 231194.4771 | 3836.1375 | 0 | 0 | 41297.75 | 239127.7377 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-13 | 1463666.9839 | 0 | 1302036.34 | 386552.7506 | 143291.3868 | 231194.4771 | 607751.3118 | 94877.0576 | 0 | 9769.76 | 1586 | 0 | 0 | 46811.1072 | 16177.2 | 0 | 0 | 0 | 0 | 0 | 7844.9904 | 5075.2 | 7612.8 | 0 | 0 | 305026.575 | 386552.7506 | 0 | 13866.9084 | 84125.911 | 12942.4478 | 32356.1196 | 0 | 231194.4771 | 3925.35 | 0 | 0 | 41297.75 | 239301.6368 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-14 | 1466908.5164 | 0 | 1302036.34 | 388311.1063 | 144122.6115 | 231194.4771 | 608014.4235 | 95265.898 | 0 | 9809.8 | 1592.5 | 0 | 0 | 47002.956 | 16243.5 | 0 | 0 | 0 | 0 | 0 | 7877.142 | 5096 | 7644 | 0 | 0 | 305026.575 | 388311.1063 | 0 | 13947.3495 | 84613.9203 | 13017.5262 | 32543.8155 | 0 | 231194.4771 | 4014.5625 | 0 | 0 | 41297.75 | 239475.536 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-15 | 1470150.0488 | 0 | 1302036.34 | 390069.462 | 144953.8362 | 231194.4771 | 608277.5352 | 95654.7384 | 0 | 9849.84 | 1599 | 0 | 0 | 47194.8048 | 16309.8 | 0 | 0 | 0 | 0 | 0 | 7909.2936 | 5116.8 | 7675.2 | 0 | 0 | 305026.575 | 390069.462 | 0 | 14027.7906 | 85101.9296 | 13092.6046 | 32731.5114 | 0 | 231194.4771 | 4103.775 | 0 | 0 | 41297.75 | 239649.4352 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-16 | 1473391.5813 | 0 | 1302036.34 | 391827.8177 | 145785.0609 | 231194.4771 | 608540.6468 | 96043.5788 | 0 | 9889.88 | 1605.5 | 0 | 0 | 47386.6536 | 16376.1 | 0 | 0 | 0 | 0 | 0 | 7941.4452 | 5137.6 | 7706.4 | 0 | 0 | 305026.575 | 391827.8177 | 0 | 14108.2317 | 85589.939 | 13167.6829 | 32919.2073 | 0 | 231194.4771 | 4192.9875 | 0 | 0 | 41297.75 | 239823.3343 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-17 | 1476633.1137 | 0 | 1302036.34 | 393586.1734 | 146616.2856 | 231194.4771 | 608803.7585 | 96432.4192 | 0 | 9929.92 | 1612 | 0 | 0 | 47578.5024 | 16442.4 | 0 | 0 | 0 | 0 | 0 | 7973.5968 | 5158.4 | 7737.6 | 0 | 0 | 305026.575 | 393586.1734 | 0 | 14188.6728 | 86077.9483 | 13242.7613 | 33106.9032 | 0 | 231194.4771 | 4282.2 | 0 | 0 | 41297.75 | 239997.2335 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-18 | 1479874.6462 | 0 | 1302036.34 | 395344.5291 | 147447.5103 | 231194.4771 | 609066.8702 | 96821.2596 | 0 | 9969.96 | 1618.5 | 0 | 0 | 47770.3512 | 16508.7 | 0 | 0 | 0 | 0 | 0 | 8005.7484 | 5179.2 | 7768.8 | 0 | 0 | 305026.575 | 395344.5291 | 0 | 14269.1139 | 86565.9577 | 13317.8396 | 33294.5991 | 0 | 231194.4771 | 4371.4125 | 0 | 0 | 41297.75 | 240171.1327 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-19 | 1483116.1787 | 0 | 1302036.34 | 397102.8847 | 148278.735 | 231194.4771 | 609329.9818 | 97210.1 | 0 | 10010 | 1625 | 0 | 0 | 47962.2 | 16575 | 0 | 0 | 0 | 0 | 0 | 8037.9 | 5200 | 7800 | 0 | 0 | 305026.575 | 397102.8847 | 0 | 14349.555 | 87053.967 | 13392.918 | 33482.295 | 0 | 231194.4771 | 4460.625 | 0 | 0 | 41297.75 | 240345.0318 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-20 | 1486357.7111 | 0 | 1302036.34 | 398861.2404 | 149109.9597 | 231194.4771 | 609593.0935 | 97598.9404 | 0 | 10050.04 | 1631.5 | 0 | 0 | 48154.0488 | 16641.3 | 0 | 0 | 0 | 0 | 0 | 8070.0516 | 5220.8 | 7831.2 | 0 | 0 | 305026.575 | 398861.2404 | 0 | 14429.9961 | 87541.9763 | 13467.9964 | 33669.9909 | 0 | 231194.4771 | 4549.8375 | 0 | 0 | 41297.75 | 240518.931 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-21 | 1489599.2436 | 0 | 1302036.34 | 400619.5961 | 149941.1844 | 231194.4771 | 609856.2052 | 97987.7808 | 0 | 10090.08 | 1638 | 0 | 0 | 48345.8976 | 16707.6 | 0 | 0 | 0 | 0 | 0 | 8102.2032 | 5241.6 | 7862.4 | 0 | 0 | 305026.575 | 400619.5961 | 0 | 14510.4372 | 88029.9857 | 13543.0747 | 33857.6868 | 0 | 231194.4771 | 4639.05 | 0 | 0 | 41297.75 | 240692.8302 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-22 | 1492840.776 | 0 | 1302036.34 | 402377.9518 | 150772.4091 | 231194.4771 | 610119.3168 | 98376.6212 | 0 | 10130.12 | 1644.5 | 0 | 0 | 48537.7464 | 16773.9 | 0 | 0 | 0 | 0 | 0 | 8134.3548 | 5262.4 | 7893.6 | 0 | 0 | 305026.575 | 402377.9518 | 0 | 14590.8783 | 88517.995 | 13618.1531 | 34045.3827 | 0 | 231194.4771 | 4728.2625 | 0 | 0 | 41297.75 | 240866.7293 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-23 | 1496082.3085 |  |  | 404136.3075 | 151603.6338 | 231194.4771 | 610382.4285 | 98765.4616 | 0 | 10170.16 | 1651 | 0 | 0 | 48729.5952 | 16840.2 | 0 | 0 | 0 | 0 | 0 | 8166.5064 | 5283.2 | 7924.8 | 0 | 0 | 305026.575 | 404136.3075 | 0 | 14671.3194 | 89006.0044 | 13693.2314 | 34233.0786 | 0 | 231194.4771 | 4817.475 | 0 | 0 | 41297.75 | 241040.6285 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-24 | 1499323.841 |  |  | 405894.6632 | 152434.8585 | 231194.4771 | 610645.5402 | 99154.302 | 0 | 10210.2 | 1657.5 | 0 | 0 | 48921.444 | 16906.5 | 0 | 0 | 0 | 0 | 0 | 8198.658 | 5304 | 7956 | 0 | 0 | 305026.575 | 405894.6632 | 0 | 14751.7605 | 89494.0137 | 13768.3098 | 34420.7745 | 0 | 231194.4771 | 4906.6875 | 0 | 0 | 41297.75 | 241214.5277 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-25 | 1502565.3734 |  |  | 407653.0189 | 153266.0832 | 231194.4771 | 610908.6518 | 99543.1424 | 0 | 10250.24 | 1664 | 0 | 0 | 49113.2928 | 16972.8 | 0 | 0 | 0 | 0 | 0 | 8230.8096 | 5324.8 | 7987.2 | 0 | 0 | 305026.575 | 407653.0189 | 0 | 14832.2016 | 89982.023 | 13843.3882 | 34608.4704 | 0 | 231194.4771 | 4995.9 | 0 | 0 | 41297.75 | 241388.4268 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-26 | 1505806.9059 |  |  | 409411.3746 | 154097.3079 | 231194.4771 | 611171.7635 | 99931.9828 | 0 | 10290.28 | 1670.5 | 0 | 0 | 49305.1416 | 17039.1 | 0 | 0 | 0 | 0 | 0 | 8262.9612 | 5345.6 | 8018.4 | 0 | 0 | 305026.575 | 409411.3746 | 0 | 14912.6427 | 90470.0324 | 13918.4665 | 34796.1663 | 0 | 231194.4771 | 5085.1125 | 0 | 0 | 41297.75 | 241562.326 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-27 | 1509048.4384 |  |  | 411169.7303 | 154928.5326 | 231194.4771 | 611434.8752 | 100320.8232 | 0 | 10330.32 | 1677 | 0 | 0 | 49496.9904 | 17105.4 | 0 | 0 | 0 | 0 | 0 | 8295.1128 | 5366.4 | 8049.6 | 0 | 0 | 305026.575 | 411169.7303 | 0 | 14993.0838 | 90958.0417 | 13993.5449 | 34983.8622 | 0 | 231194.4771 | 5174.325 | 0 | 0 | 41297.75 | 241736.2252 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-28 | 1512289.9708 |  |  | 412928.086 | 155759.7573 | 231194.4771 | 611697.9868 | 100709.6636 | 0 | 10370.36 | 1683.5 | 0 | 0 | 49688.8392 | 17171.7 | 0 | 0 | 0 | 0 | 0 | 8327.2644 | 5387.2 | 8080.8 | 0 | 0 | 305026.575 | 412928.086 | 0 | 15073.5249 | 91446.0511 | 14068.6232 | 35171.5581 | 0 | 231194.4771 | 5263.5375 | 0 | 0 | 41297.75 | 241910.1243 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-29 | 1515531.5033 |  |  | 414686.4417 | 156590.982 | 231194.4771 | 611961.0985 | 101098.504 | 0 | 10410.4 | 1690 | 0 | 0 | 49880.688 | 17238 | 0 | 0 | 0 | 0 | 0 | 8359.416 | 5408 | 8112 | 0 | 0 | 305026.575 | 414686.4417 | 0 | 15153.966 | 91934.0604 | 14143.7016 | 35359.254 | 0 | 231194.4771 | 5352.75 | 0 | 0 | 41297.75 | 242084.0235 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-30 | 1518773.0357 |  |  | 416444.7974 | 157422.2067 | 231194.4771 | 612224.2102 | 101487.3444 | 0 | 10450.44 | 1696.5 | 0 | 0 | 50072.5368 | 17304.3 | 0 | 0 | 0 | 0 | 0 | 8391.5676 | 5428.8 | 8143.2 | 0 | 0 | 305026.575 | 416444.7974 | 0 | 15234.4071 | 92422.0697 | 14218.78 | 35546.9499 | 0 | 231194.4771 | 5441.9625 | 0 | 0 | 41297.75 | 242257.9227 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-31 | 1522014.5682 |  |  | 418203.1531 | 158253.4314 | 231194.4771 | 612487.3218 | 101876.1848 | 0 | 10490.48 | 1703 | 0 | 0 | 50264.3856 | 17370.6 | 0 | 0 | 0 | 0 | 0 | 8423.7192 | 5449.6 | 8174.4 | 0 | 0 | 305026.575 | 418203.1531 | 0 | 15314.8482 | 92910.0791 | 14293.8583 | 35734.6458 | 0 | 231194.4771 | 5531.175 | 0 | 0 | 41297.75 | 242431.8218 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-01 | 1525256.1007 |  |  | 419961.5088 | 159084.6561 | 231194.4771 | 612750.4335 | 102265.0252 | 0 | 10530.52 | 1709.5 | 0 | 0 | 50456.2344 | 17436.9 | 0 | 0 | 0 | 0 | 0 | 8455.8708 | 5470.4 | 8205.6 | 0 | 0 | 305026.575 | 419961.5088 | 0 | 15395.2893 | 93398.0884 | 14368.9367 | 35922.3417 | 0 | 231194.4771 | 5620.3875 | 0 | 0 | 41297.75 | 242605.721 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-02 | 1528497.6331 |  |  | 421719.8645 | 159915.8808 | 231194.4771 | 613013.5452 | 102653.8656 | 0 | 10570.56 | 1716 | 0 | 0 | 50648.0832 | 17503.2 | 0 | 0 | 0 | 0 | 0 | 8488.0224 | 5491.2 | 8236.8 | 0 | 0 | 305026.575 | 421719.8645 | 0 | 15475.7304 | 93886.0978 | 14444.015 | 36110.0376 | 0 | 231194.4771 | 5709.6 | 0 | 0 | 41297.75 | 242779.6202 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-03 | 1531739.1656 |  |  | 423478.2202 | 160747.1055 | 231194.4771 | 613276.6568 | 103042.706 | 0 | 10610.6 | 1722.5 | 0 | 0 | 50839.932 | 17569.5 | 0 | 0 | 0 | 0 | 0 | 8520.174 | 5512 | 8268 | 0 | 0 | 305026.575 | 423478.2202 | 0 | 15556.1715 | 94374.1071 | 14519.0934 | 36297.7335 | 0 | 231194.4771 | 5798.8125 | 0 | 0 | 41297.75 | 242953.5193 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-04 | 1534980.6981 |  |  | 425236.5759 | 161578.3302 | 231194.4771 | 613539.7685 | 103431.5464 | 0 | 10650.64 | 1729 | 0 | 0 | 51031.7808 | 17635.8 | 0 | 0 | 0 | 0 | 0 | 8552.3256 | 5532.8 | 8299.2 | 0 | 0 | 305026.575 | 425236.5759 | 0 | 15636.6126 | 94862.1164 | 14594.1718 | 36485.4294 | 0 | 231194.4771 | 5888.025 | 0 | 0 | 41297.75 | 243127.4185 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-05 | 1538222.2305 |  |  | 426994.9316 | 162409.5549 | 231194.4771 | 613802.8802 | 103820.3868 | 0 | 10690.68 | 1735.5 | 0 | 0 | 51223.6296 | 17702.1 | 0 | 0 | 0 | 0 | 0 | 8584.4772 | 5553.6 | 8330.4 | 0 | 0 | 305026.575 | 426994.9316 | 0 | 15717.0537 | 95350.1258 | 14669.2501 | 36673.1253 | 0 | 231194.4771 | 5977.2375 | 0 | 0 | 41297.75 | 243301.3177 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-06 | 1541463.763 |  |  | 428753.2873 | 163240.7796 | 231194.4771 | 614065.9918 | 104209.2272 | 0 | 10730.72 | 1742 | 0 | 0 | 51415.4784 | 17768.4 | 0 | 0 | 0 | 0 | 0 | 8616.6288 | 5574.4 | 8361.6 | 0 | 0 | 305026.575 | 428753.2873 | 0 | 15797.4948 | 95838.1351 | 14744.3285 | 36860.8212 | 0 | 231194.4771 | 6066.45 | 0 | 0 | 41297.75 | 243475.2168 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-07 | 1544705.2954 |  |  | 430511.643 | 164072.0043 | 231194.4771 | 614329.1035 | 104598.0676 | 0 | 10770.76 | 1748.5 | 0 | 0 | 51607.3272 | 17834.7 | 0 | 0 | 0 | 0 | 0 | 8648.7804 | 5595.2 | 8392.8 | 0 | 0 | 305026.575 | 430511.643 | 0 | 15877.9359 | 96326.1445 | 14819.4068 | 37048.5171 | 0 | 231194.4771 | 6155.6625 | 0 | 0 | 41297.75 | 243649.116 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-08 | 1547946.8279 |  |  | 432269.9986 | 164903.229 | 231194.4771 | 614592.2152 | 104986.908 | 0 | 10810.8 | 1755 | 0 | 0 | 51799.176 | 17901 | 0 | 0 | 0 | 0 | 0 | 8680.932 | 5616 | 8424 | 0 | 0 | 305026.575 | 432269.9986 | 0 | 15958.377 | 96814.1538 | 14894.4852 | 37236.213 | 0 | 231194.4771 | 6244.875 | 0 | 0 | 41297.75 | 243823.0152 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-09 | 1551188.3604 |  |  | 434028.3543 | 165734.4537 | 231194.4771 | 614855.3268 | 105375.7484 | 0 | 10850.84 | 1761.5 | 0 | 0 | 51991.0248 | 17967.3 | 0 | 0 | 0 | 0 | 0 | 8713.0836 | 5636.8 | 8455.2 | 0 | 0 | 305026.575 | 434028.3543 | 0 | 16038.8181 | 97302.1631 | 14969.5636 | 37423.9089 | 0 | 231194.4771 | 6334.0875 | 0 | 0 | 41297.75 | 243996.9143 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-10 | 1554429.8928 |  |  | 435786.71 | 166565.6784 | 231194.4771 | 615118.4385 | 105764.5888 | 0 | 10890.88 | 1768 | 0 | 0 | 52182.8736 | 18033.6 | 0 | 0 | 0 | 0 | 0 | 8745.2352 | 5657.6 | 8486.4 | 0 | 0 | 305026.575 | 435786.71 | 0 | 16119.2592 | 97790.1725 | 15044.6419 | 37611.6048 | 0 | 231194.4771 | 6423.3 | 0 | 0 | 41297.75 | 244170.8135 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-11 | 1557671.4253 |  |  | 437545.0657 | 167396.9031 | 231194.4771 | 615381.5502 | 106153.4292 | 0 | 10930.92 | 1774.5 | 0 | 0 | 52374.7224 | 18099.9 | 0 | 0 | 0 | 0 | 0 | 8777.3868 | 5678.4 | 8517.6 | 0 | 0 | 305026.575 | 437545.0657 | 0 | 16199.7003 | 98278.1818 | 15119.7203 | 37799.3007 | 0 | 231194.4771 | 6512.5125 | 0 | 0 | 41297.75 | 244344.7127 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-12 | 1560912.9577 |  |  | 439303.4214 | 168228.1278 | 231194.4771 | 615644.6618 | 106542.2696 | 0 | 10970.96 | 1781 | 0 | 0 | 52566.5712 | 18166.2 | 0 | 0 | 0 | 0 | 0 | 8809.5384 | 5699.2 | 8548.8 | 0 | 0 | 305026.575 | 439303.4214 | 0 | 16280.1414 | 98766.1912 | 15194.7986 | 37986.9966 | 0 | 231194.4771 | 6601.725 | 0 | 0 | 41297.75 | 244518.6118 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-13 | 1564154.4902 |  |  | 441061.7771 | 169059.3525 | 231194.4771 | 615907.7735 | 106931.11 | 0 | 11011 | 1787.5 | 0 | 0 | 52758.42 | 18232.5 | 0 | 0 | 0 | 0 | 0 | 8841.69 | 5720 | 8580 | 0 | 0 | 305026.575 | 441061.7771 | 0 | 16360.5825 | 99254.2005 | 15269.877 | 38174.6925 | 0 | 231194.4771 | 6690.9375 | 0 | 0 | 41297.75 | 244692.511 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-14 | 1567396.0227 |  |  | 442820.1328 | 169890.5772 | 231194.4771 | 616170.8852 | 107319.9504 | 0 | 11051.04 | 1794 | 0 | 0 | 52950.2688 | 18298.8 | 0 | 0 | 0 | 0 | 0 | 8873.8416 | 5740.8 | 8611.2 | 0 | 0 | 305026.575 | 442820.1328 | 0 | 16441.0236 | 99742.2098 | 15344.9554 | 38362.3884 | 0 | 231194.4771 | 6780.15 | 0 | 0 | 41297.75 | 244866.4102 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-15 | 1570637.5551 |  |  | 444578.4885 | 170721.8019 | 231194.4771 | 616433.9968 | 107708.7908 | 0 | 11091.08 | 1800.5 | 0 | 0 | 53142.1176 | 18365.1 | 0 | 0 | 0 | 0 | 0 | 8905.9932 | 5761.6 | 8642.4 | 0 | 0 | 305026.575 | 444578.4885 | 0 | 16521.4647 | 100230.2192 | 15420.0337 | 38550.0843 | 0 | 231194.4771 | 6869.3625 | 0 | 0 | 41297.75 | 245040.3093 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-16 | 1573879.0876 |  |  | 446336.8442 | 171553.0266 | 231194.4771 | 616697.1085 | 108097.6312 | 0 | 11131.12 | 1807 | 0 | 0 | 53333.9664 | 18431.4 | 0 | 0 | 0 | 0 | 0 | 8938.1448 | 5782.4 | 8673.6 | 0 | 0 | 305026.575 | 446336.8442 | 0 | 16601.9058 | 100718.2285 | 15495.1121 | 38737.7802 | 0 | 231194.4771 | 6958.575 | 0 | 0 | 41297.75 | 245214.2085 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-17 | 1577120.6201 |  |  | 448095.1999 | 172384.2513 | 231194.4771 | 616960.2202 | 108486.4716 | 0 | 11171.16 | 1813.5 | 0 | 0 | 53525.8152 | 18497.7 | 0 | 0 | 0 | 0 | 0 | 8970.2964 | 5803.2 | 8704.8 | 0 | 0 | 305026.575 | 448095.1999 | 0 | 16682.3469 | 101206.2379 | 15570.1904 | 38925.4761 | 0 | 231194.4771 | 7047.7875 | 0 | 0 | 41297.75 | 245388.1077 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-18 | 1580362.1525 |  |  | 449853.5556 | 173215.476 | 231194.4771 | 617223.3318 | 108875.312 | 0 | 11211.2 | 1820 | 0 | 0 | 53717.664 | 18564 | 0 | 0 | 0 | 0 | 0 | 9002.448 | 5824 | 8736 | 0 | 0 | 305026.575 | 449853.5556 | 0 | 16762.788 | 101694.2472 | 15645.2688 | 39113.172 | 0 | 231194.4771 | 7137 | 0 | 0 | 41297.75 | 245562.0068 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-19 | 1583603.685 |  |  | 451611.9113 | 174046.7007 | 231194.4771 | 617486.4435 | 109264.1524 | 0 | 11251.24 | 1826.5 | 0 | 0 | 53909.5128 | 18630.3 | 0 | 0 | 0 | 0 | 0 | 9034.5996 | 5844.8 | 8767.2 | 0 | 0 | 305026.575 | 451611.9113 | 0 | 16843.2291 | 102182.2565 | 15720.3472 | 39300.8679 | 0 | 231194.4771 | 7226.2125 | 0 | 0 | 41297.75 | 245735.906 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-20 | 1586845.2174 |  |  | 453370.267 | 174877.9254 | 231194.4771 | 617749.5552 | 109652.9928 | 0 | 11291.28 | 1833 | 0 | 0 | 54101.3616 | 18696.6 | 0 | 0 | 0 | 0 | 0 | 9066.7512 | 5865.6 | 8798.4 | 0 | 0 | 305026.575 | 453370.267 | 0 | 16923.6702 | 102670.2659 | 15795.4255 | 39488.5638 | 0 | 231194.4771 | 7315.425 | 0 | 0 | 41297.75 | 245909.8052 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-21 | 1590086.7499 |  |  | 455128.6227 | 175709.1501 | 231194.4771 | 618012.6668 | 110041.8332 | 0 | 11331.32 | 1839.5 | 0 | 0 | 54293.2104 | 18762.9 | 0 | 0 | 0 | 0 | 0 | 9098.9028 | 5886.4 | 8829.6 | 0 | 0 | 305026.575 | 455128.6227 | 0 | 17004.1113 | 103158.2752 | 15870.5039 | 39676.2597 | 0 | 231194.4771 | 7404.6375 | 0 | 0 | 41297.75 | 246083.7043 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-22 | 1593328.2824 |  |  | 456886.9784 | 176540.3748 | 231194.4771 | 618275.7785 | 110430.6736 | 0 | 11371.36 | 1846 | 0 | 0 | 54485.0592 | 18829.2 | 0 | 0 | 0 | 0 | 0 | 9131.0544 | 5907.2 | 8860.8 | 0 | 0 | 305026.575 | 456886.9784 | 0 | 17084.5524 | 103646.2846 | 15945.5822 | 39863.9556 | 0 | 231194.4771 | 7493.85 | 0 | 0 | 41297.75 | 246257.6035 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-23 | 1596569.8148 |  |  | 458645.3341 | 177371.5995 | 231194.4771 | 618538.8902 | 110819.514 | 0 | 11411.4 | 1852.5 | 0 | 0 | 54676.908 | 18895.5 | 0 | 0 | 0 | 0 | 0 | 9163.206 | 5928 | 8892 | 0 | 0 | 305026.575 | 458645.3341 | 0 | 17164.9935 | 104134.2939 | 16020.6606 | 40051.6515 | 0 | 231194.4771 | 7583.0625 | 0 | 0 | 41297.75 | 246431.5027 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-24 | 1599811.3473 |  |  | 460403.6898 | 178202.8242 | 231194.4771 | 618802.0018 | 111208.3544 | 0 | 11451.44 | 1859 | 0 | 0 | 54868.7568 | 18961.8 | 0 | 0 | 0 | 0 | 0 | 9195.3576 | 5948.8 | 8923.2 | 0 | 0 | 305026.575 | 460403.6898 | 0 | 17245.4346 | 104622.3032 | 16095.739 | 40239.3474 | 0 | 231194.4771 | 7672.275 | 0 | 0 | 41297.75 | 246605.4018 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-25 | 1603052.8797 |  |  | 462162.0455 | 179034.0489 | 231194.4771 | 619065.1135 | 111597.1948 | 0 | 11491.48 | 1865.5 | 0 | 0 | 55060.6056 | 19028.1 | 0 | 0 | 0 | 0 | 0 | 9227.5092 | 5969.6 | 8954.4 | 0 | 0 | 305026.575 | 462162.0455 | 0 | 17325.8757 | 105110.3126 | 16170.8173 | 40427.0433 | 0 | 231194.4771 | 7761.4875 | 0 | 0 | 41297.75 | 246779.301 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-26 | 1606294.4122 |  |  | 463920.4012 | 179865.2736 | 231194.4771 | 619328.2252 | 111986.0352 | 0 | 11531.52 | 1872 | 0 | 0 | 55252.4544 | 19094.4 | 0 | 0 | 0 | 0 | 0 | 9259.6608 | 5990.4 | 8985.6 | 0 | 0 | 305026.575 | 463920.4012 | 0 | 17406.3168 | 105598.3219 | 16245.8957 | 40614.7392 | 0 | 231194.4771 | 7850.7 | 0 | 0 | 41297.75 | 246953.2002 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-27 | 1609535.9447 |  |  | 465678.7569 | 180696.4983 | 231194.4771 | 619591.3368 | 112374.8756 | 0 | 11571.56 | 1878.5 | 0 | 0 | 55444.3032 | 19160.7 | 0 | 0 | 0 | 0 | 0 | 9291.8124 | 6011.2 | 9016.8 | 0 | 0 | 305026.575 | 465678.7569 | 0 | 17486.7579 | 106086.3313 | 16320.974 | 40802.4351 | 0 | 231194.4771 | 7939.9125 | 0 | 0 | 41297.75 | 247127.0993 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-28 | 1612777.4771 |  |  | 467437.1125 | 181527.723 | 231194.4771 | 619854.4485 | 112763.716 | 0 | 11611.6 | 1885 | 0 | 0 | 55636.152 | 19227 | 0 | 0 | 0 | 0 | 0 | 9323.964 | 6032 | 9048 | 0 | 0 | 305026.575 | 467437.1125 | 0 | 17567.199 | 106574.3406 | 16396.0524 | 40990.131 | 0 | 231194.4771 | 8029.125 | 0 | 0 | 41297.75 | 247300.9985 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-29 | 1616019.0096 |  |  | 469195.4682 | 182358.9477 | 231194.4771 | 620117.5602 | 113152.5564 | 0 | 11651.64 | 1891.5 | 0 | 0 | 55828.0008 | 19293.3 | 0 | 0 | 0 | 0 | 0 | 9356.1156 | 6052.8 | 9079.2 | 0 | 0 | 305026.575 | 469195.4682 | 0 | 17647.6401 | 107062.3499 | 16471.1308 | 41177.8269 | 0 | 231194.4771 | 8118.3375 | 0 | 0 | 41297.75 | 247474.8977 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-30 | 1619260.5421 |  |  | 470953.8239 | 183190.1724 | 231194.4771 | 620380.6718 | 113541.3968 | 0 | 11691.68 | 1898 | 0 | 0 | 56019.8496 | 19359.6 | 0 | 0 | 0 | 0 | 0 | 9388.2672 | 6073.6 | 9110.4 | 0 | 0 | 305026.575 | 470953.8239 | 0 | 17728.0812 | 107550.3593 | 16546.2091 | 41365.5228 | 0 | 231194.4771 | 8207.55 | 0 | 0 | 41297.75 | 247648.7968 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-01 | 1622502.0745 |  |  | 472712.1796 | 184021.3971 | 231194.4771 | 620643.7835 | 113930.2372 | 0 | 11731.72 | 1904.5 | 0 | 0 | 56211.6984 | 19425.9 | 0 | 0 | 0 | 0 | 0 | 9420.4188 | 6094.4 | 9141.6 | 0 | 0 | 305026.575 | 472712.1796 | 0 | 17808.5223 | 108038.3686 | 16621.2875 | 41553.2187 | 0 | 231194.4771 | 8296.7625 | 0 | 0 | 41297.75 | 247822.696 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-02 | 1625743.607 |  |  | 474470.5353 | 184852.6218 | 231194.4771 | 620906.8952 | 114319.0776 | 0 | 11771.76 | 1911 | 0 | 0 | 56403.5472 | 19492.2 | 0 | 0 | 0 | 0 | 0 | 9452.5704 | 6115.2 | 9172.8 | 0 | 0 | 305026.575 | 474470.5353 | 0 | 17888.9634 | 108526.378 | 16696.3658 | 41740.9146 | 0 | 231194.4771 | 8385.975 | 0 | 0 | 41297.75 | 247996.5952 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-03 | 1628985.1394 |  |  | 476228.891 | 185683.8465 | 231194.4771 | 621170.0068 | 114707.918 | 0 | 11811.8 | 1917.5 | 0 | 0 | 56595.396 | 19558.5 | 0 | 0 | 0 | 0 | 0 | 9484.722 | 6136 | 9204 | 0 | 0 | 305026.575 | 476228.891 | 0 | 17969.4045 | 109014.3873 | 16771.4442 | 41928.6105 | 0 | 231194.4771 | 8475.1875 | 0 | 0 | 41297.75 | 248170.4943 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-04 | 1632226.6719 |  |  | 477987.2467 | 186515.0712 | 231194.4771 | 621433.1185 | 115096.7584 | 0 | 11851.84 | 1924 | 0 | 0 | 56787.2448 | 19624.8 | 0 | 0 | 0 | 0 | 0 | 9516.8736 | 6156.8 | 9235.2 | 0 | 0 | 305026.575 | 477987.2467 | 0 | 18049.8456 | 109502.3966 | 16846.5226 | 42116.3064 | 0 | 231194.4771 | 8564.4 | 0 | 0 | 41297.75 | 248344.3935 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-05 | 1635468.2044 |  |  | 479745.6024 | 187346.2959 | 231194.4771 | 621696.2302 | 115485.5988 | 0 | 11891.88 | 1930.5 | 0 | 0 | 56979.0936 | 19691.1 | 0 | 0 | 0 | 0 | 0 | 9549.0252 | 6177.6 | 9266.4 | 0 | 0 | 305026.575 | 479745.6024 | 0 | 18130.2867 | 109990.406 | 16921.6009 | 42304.0023 | 0 | 231194.4771 | 8653.6125 | 0 | 0 | 41297.75 | 248518.2927 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-06 | 1638709.7368 |  |  | 481503.9581 | 188177.5206 | 231194.4771 | 621959.3418 | 115874.4392 | 0 | 11931.92 | 1937 | 0 | 0 | 57170.9424 | 19757.4 | 0 | 0 | 0 | 0 | 0 | 9581.1768 | 6198.4 | 9297.6 | 0 | 0 | 305026.575 | 481503.9581 | 0 | 18210.7278 | 110478.4153 | 16996.6793 | 42491.6982 | 0 | 231194.4771 | 8742.825 | 0 | 0 | 41297.75 | 248692.1918 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-07 | 1641951.2693 |  |  | 483262.3138 | 189008.7453 | 231194.4771 | 622222.4535 | 116263.2796 | 0 | 11971.96 | 1943.5 | 0 | 0 | 57362.7912 | 19823.7 | 0 | 0 | 0 | 0 | 0 | 9613.3284 | 6219.2 | 9328.8 | 0 | 0 | 305026.575 | 483262.3138 | 0 | 18291.1689 | 110966.4247 | 17071.7576 | 42679.3941 | 0 | 231194.4771 | 8832.0375 | 0 | 0 | 41297.75 | 248866.091 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-08 | 1645192.8017 |  |  | 485020.6695 | 189839.97 | 231194.4771 | 622485.5652 | 116652.12 | 0 | 12012 | 1950 | 0 | 0 | 57554.64 | 19890 | 0 | 0 | 0 | 0 | 0 | 9645.48 | 6240 | 9360 | 0 | 0 | 305026.575 | 485020.6695 | 0 | 18371.61 | 111454.434 | 17146.836 | 42867.09 | 0 | 231194.4771 | 8921.25 | 0 | 0 | 41297.75 | 249039.9902 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-09 | 1648434.3342 |  |  | 486779.0252 | 190671.1947 | 231194.4771 | 622748.6768 | 117040.9604 | 0 | 12052.04 | 1956.5 | 0 | 0 | 57746.4888 | 19956.3 | 0 | 0 | 0 | 0 | 0 | 9677.6316 | 6260.8 | 9391.2 | 0 | 0 | 305026.575 | 486779.0252 | 0 | 18452.0511 | 111942.4433 | 17221.9144 | 43054.7859 | 0 | 231194.4771 | 9010.4625 | 0 | 0 | 41297.75 | 249213.8893 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-10 | 1651675.8667 |  |  | 488537.3809 | 191502.4194 | 231194.4771 | 623011.7885 | 117429.8008 | 0 | 12092.08 | 1963 | 0 | 0 | 57938.3376 | 20022.6 | 0 | 0 | 0 | 0 | 0 | 9709.7832 | 6281.6 | 9422.4 | 0 | 0 | 305026.575 | 488537.3809 | 0 | 18532.4922 | 112430.4527 | 17296.9927 | 43242.4818 | 0 | 231194.4771 | 9099.675 | 0 | 0 | 41297.75 | 249387.7885 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-11 | 1654917.3991 |  |  | 490295.7366 | 192333.6441 | 231194.4771 | 623274.9002 | 117818.6412 | 0 | 12132.12 | 1969.5 | 0 | 0 | 58130.1864 | 20088.9 | 0 | 0 | 0 | 0 | 0 | 9741.9348 | 6302.4 | 9453.6 | 0 | 0 | 305026.575 | 490295.7366 | 0 | 18612.9333 | 112918.462 | 17372.0711 | 43430.1777 | 0 | 231194.4771 | 9188.8875 | 0 | 0 | 41297.75 | 249561.6877 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-12 | 1658158.9316 |  |  | 492054.0923 | 193164.8688 | 231194.4771 | 623538.0118 | 118207.4816 | 0 | 12172.16 | 1976 | 0 | 0 | 58322.0352 | 20155.2 | 0 | 0 | 0 | 0 | 0 | 9774.0864 | 6323.2 | 9484.8 | 0 | 0 | 305026.575 | 492054.0923 | 0 | 18693.3744 | 113406.4714 | 17447.1494 | 43617.8736 | 0 | 231194.4771 | 9278.1 | 0 | 0 | 41297.75 | 249735.5868 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-13 | 1661400.4641 |  |  | 493812.448 | 193996.0935 | 231194.4771 | 623801.1235 | 118596.322 | 0 | 12212.2 | 1982.5 | 0 | 0 | 58513.884 | 20221.5 | 0 | 0 | 0 | 0 | 0 | 9806.238 | 6344 | 9516 | 0 | 0 | 305026.575 | 493812.448 | 0 | 18773.8155 | 113894.4807 | 17522.2278 | 43805.5695 | 0 | 231194.4771 | 9367.3125 | 0 | 0 | 41297.75 | 249909.486 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-14 | 1664641.9965 |  |  | 495570.8037 | 194827.3182 | 231194.4771 | 624064.2352 | 118985.1624 | 0 | 12252.24 | 1989 | 0 | 0 | 58705.7328 | 20287.8 | 0 | 0 | 0 | 0 | 0 | 9838.3896 | 6364.8 | 9547.2 | 0 | 0 | 305026.575 | 495570.8037 | 0 | 18854.2566 | 114382.49 | 17597.3062 | 43993.2654 | 0 | 231194.4771 | 9456.525 | 0 | 0 | 41297.75 | 250083.3852 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-15 | 1667883.529 |  |  | 497329.1594 | 195658.5429 | 231194.4771 | 624327.3468 | 119374.0028 | 0 | 12292.28 | 1995.5 | 0 | 0 | 58897.5816 | 20354.1 | 0 | 0 | 0 | 0 | 0 | 9870.5412 | 6385.6 | 9578.4 | 0 | 0 | 305026.575 | 497329.1594 | 0 | 18934.6977 | 114870.4994 | 17672.3845 | 44180.9613 | 0 | 231194.4771 | 9545.7375 | 0 | 0 | 41297.75 | 250257.2843 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-16 | 1671125.0614 |  |  | 499087.5151 | 196489.7676 | 231194.4771 | 624590.4585 | 119762.8432 | 0 | 12332.32 | 2002 | 0 | 0 | 59089.4304 | 20420.4 | 0 | 0 | 0 | 0 | 0 | 9902.6928 | 6406.4 | 9609.6 | 0 | 0 | 305026.575 | 499087.5151 | 0 | 19015.1388 | 115358.5087 | 17747.4629 | 44368.6572 | 0 | 231194.4771 | 9634.95 | 0 | 0 | 41297.75 | 250431.1835 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-17 | 1674366.5939 |  |  | 500845.8708 | 197320.9923 | 231194.4771 | 624853.5702 | 120151.6836 | 0 | 12372.36 | 2008.5 | 0 | 0 | 59281.2792 | 20486.7 | 0 | 0 | 0 | 0 | 0 | 9934.8444 | 6427.2 | 9640.8 | 0 | 0 | 305026.575 | 500845.8708 | 0 | 19095.5799 | 115846.5181 | 17822.5412 | 44556.3531 | 0 | 231194.4771 | 9724.1625 | 0 | 0 | 41297.75 | 250605.0827 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-18 | 1677608.1264 |  |  | 502604.2264 | 198152.217 | 231194.4771 | 625116.6818 | 120540.524 | 0 | 12412.4 | 2015 | 0 | 0 | 59473.128 | 20553 | 0 | 0 | 0 | 0 | 0 | 9966.996 | 6448 | 9672 | 0 | 0 | 305026.575 | 502604.2264 | 0 | 19176.021 | 116334.5274 | 17897.6196 | 44744.049 | 0 | 231194.4771 | 9813.375 | 0 | 0 | 41297.75 | 250778.9818 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-19 | 1680849.6588 |  |  | 504362.5821 | 198983.4417 | 231194.4771 | 625379.7935 | 120929.3644 | 0 | 12452.44 | 2021.5 | 0 | 0 | 59664.9768 | 20619.3 | 0 | 0 | 0 | 0 | 0 | 9999.1476 | 6468.8 | 9703.2 | 0 | 0 | 305026.575 | 504362.5821 | 0 | 19256.4621 | 116822.5367 | 17972.698 | 44931.7449 | 0 | 231194.4771 | 9902.5875 | 0 | 0 | 41297.75 | 250952.881 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-20 | 1684091.1913 |  |  | 506120.9378 | 199814.6664 | 231194.4771 | 625642.9052 | 121318.2048 | 0 | 12492.48 | 2028 | 0 | 0 | 59856.8256 | 20685.6 | 0 | 0 | 0 | 0 | 0 | 10031.2992 | 6489.6 | 9734.4 | 0 | 0 | 305026.575 | 506120.9378 | 0 | 19336.9032 | 117310.5461 | 18047.7763 | 45119.4408 | 0 | 231194.4771 | 9991.8 | 0 | 0 | 41297.75 | 251126.7802 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-21 | 1687332.7237 |  |  | 507879.2935 | 200645.8911 | 231194.4771 | 625906.0168 | 121707.0452 | 0 | 12532.52 | 2034.5 | 0 | 0 | 60048.6744 | 20751.9 | 0 | 0 | 0 | 0 | 0 | 10063.4508 | 6510.4 | 9765.6 | 0 | 0 | 305026.575 | 507879.2935 | 0 | 19417.3443 | 117798.5554 | 18122.8547 | 45307.1367 | 0 | 231194.4771 | 10081.0125 | 0 | 0 | 41297.75 | 251300.6793 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-22 | 1690574.2562 |  |  | 509637.6492 | 201477.1158 | 231194.4771 | 626169.1285 | 122095.8856 | 0 | 12572.56 | 2041 | 0 | 0 | 60240.5232 | 20818.2 | 0 | 0 | 0 | 0 | 0 | 10095.6024 | 6531.2 | 9796.8 | 0 | 0 | 305026.575 | 509637.6492 | 0 | 19497.7854 | 118286.5648 | 18197.933 | 45494.8326 | 0 | 231194.4771 | 10170.225 | 0 | 0 | 41297.75 | 251474.5785 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-23 | 1693815.7887 |  |  | 511396.0049 | 202308.3405 | 231194.4771 | 626432.2402 | 122484.726 | 0 | 12612.6 | 2047.5 | 0 | 0 | 60432.372 | 20884.5 | 0 | 0 | 0 | 0 | 0 | 10127.754 | 6552 | 9828 | 0 | 0 | 305026.575 | 511396.0049 | 0 | 19578.2265 | 118774.5741 | 18273.0114 | 45682.5285 | 0 | 231194.4771 | 10259.4375 | 0 | 0 | 41297.75 | 251648.4777 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-24 | 1697057.3211 |  |  | 513154.3606 | 203139.5652 | 231194.4771 | 626695.3518 | 122873.5664 | 0 | 12652.64 | 2054 | 0 | 0 | 60624.2208 | 20950.8 | 0 | 0 | 0 | 0 | 0 | 10159.9056 | 6572.8 | 9859.2 | 0 | 0 | 305026.575 | 513154.3606 | 0 | 19658.6676 | 119262.5834 | 18348.0898 | 45870.2244 | 0 | 231194.4771 | 10348.65 | 0 | 0 | 41297.75 | 251822.3768 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-25 | 1700298.8536 |  |  | 514912.7163 | 203970.7899 | 231194.4771 | 626958.4635 | 123262.4068 | 0 | 12692.68 | 2060.5 | 0 | 0 | 60816.0696 | 21017.1 | 0 | 0 | 0 | 0 | 0 | 10192.0572 | 6593.6 | 9890.4 | 0 | 0 | 305026.575 | 514912.7163 | 0 | 19739.1087 | 119750.5928 | 18423.1681 | 46057.9203 | 0 | 231194.4771 | 10437.8625 | 0 | 0 | 41297.75 | 251996.276 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-26 | 1703540.3861 |  |  | 516671.072 | 204802.0146 | 231194.4771 | 627221.5752 | 123651.2472 | 0 | 12732.72 | 2067 | 0 | 0 | 61007.9184 | 21083.4 | 0 | 0 | 0 | 0 | 0 | 10224.2088 | 6614.4 | 9921.6 | 0 | 0 | 305026.575 | 516671.072 | 0 | 19819.5498 | 120238.6021 | 18498.2465 | 46245.6162 | 0 | 231194.4771 | 10527.075 | 0 | 0 | 41297.75 | 252170.1752 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-27 | 1706781.9185 |  |  | 518429.4277 | 205633.2393 | 231194.4771 | 627484.6868 | 124040.0876 | 0 | 12772.76 | 2073.5 | 0 | 0 | 61199.7672 | 21149.7 | 0 | 0 | 0 | 0 | 0 | 10256.3604 | 6635.2 | 9952.8 | 0 | 0 | 305026.575 | 518429.4277 | 0 | 19899.9909 | 120726.6115 | 18573.3248 | 46433.3121 | 0 | 231194.4771 | 10616.2875 | 0 | 0 | 41297.75 | 252344.0743 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-28 | 1710023.451 |  |  | 520187.7834 | 206464.464 | 231194.4771 | 627747.7985 | 124428.928 | 0 | 12812.8 | 2080 | 0 | 0 | 61391.616 | 21216 | 0 | 0 | 0 | 0 | 0 | 10288.512 | 6656 | 9984 | 0 | 0 | 305026.575 | 520187.7834 | 0 | 19980.432 | 121214.6208 | 18648.4032 | 46621.008 | 0 | 231194.4771 | 10705.5 | 0 | 0 | 41297.75 | 252517.9735 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-29 | 1713264.9834 |  |  | 521946.1391 | 207295.6887 | 231194.4771 | 628010.9102 | 124817.7684 | 0 | 12852.84 | 2086.5 | 0 | 0 | 61583.4648 | 21282.3 | 0 | 0 | 0 | 0 | 0 | 10320.6636 | 6676.8 | 10015.2 | 0 | 0 | 305026.575 | 521946.1391 | 0 | 20060.8731 | 121702.6301 | 18723.4816 | 46808.7039 | 0 | 231194.4771 | 10794.7125 | 0 | 0 | 41297.75 | 252691.8727 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-30 | 1716506.5159 |  |  | 523704.4948 | 208126.9134 | 231194.4771 | 628274.0218 | 125206.6088 | 0 | 12892.88 | 2093 | 0 | 0 | 61775.3136 | 21348.6 | 0 | 0 | 0 | 0 | 0 | 10352.8152 | 6697.6 | 10046.4 | 0 | 0 | 305026.575 | 523704.4948 | 0 | 20141.3142 | 122190.6395 | 18798.5599 | 46996.3998 | 0 | 231194.4771 | 10883.925 | 0 | 0 | 41297.75 | 252865.7718 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-31 | 1719748.0484 |  |  | 525462.8505 | 208958.1381 | 231194.4771 | 628537.1335 | 125595.4492 | 0 | 12932.92 | 2099.5 | 0 | 0 | 61967.1624 | 21414.9 | 0 | 0 | 0 | 0 | 0 | 10384.9668 | 6718.4 | 10077.6 | 0 | 0 | 305026.575 | 525462.8505 | 0 | 20221.7553 | 122678.6488 | 18873.6383 | 47184.0957 | 0 | 231194.4771 | 10973.1375 | 0 | 0 | 41297.75 | 253039.671 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-01 | 1722989.5808 |  |  | 527221.2062 | 209789.3628 | 231194.4771 | 628800.2452 | 125984.2896 | 0 | 12972.96 | 2106 | 0 | 0 | 62159.0112 | 21481.2 | 0 | 0 | 0 | 0 | 0 | 10417.1184 | 6739.2 | 10108.8 | 0 | 0 | 305026.575 | 527221.2062 | 0 | 20302.1964 | 123166.6582 | 18948.7166 | 47371.7916 | 0 | 231194.4771 | 11062.35 | 0 | 0 | 41297.75 | 253213.5702 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-02 | 1726231.1133 |  |  | 528979.5619 | 210620.5875 | 231194.4771 | 629063.3568 | 126373.13 | 0 | 13013 | 2112.5 | 0 | 0 | 62350.86 | 21547.5 | 0 | 0 | 0 | 0 | 0 | 10449.27 | 6760 | 10140 | 0 | 0 | 305026.575 | 528979.5619 | 0 | 20382.6375 | 123654.6675 | 19023.795 | 47559.4875 | 0 | 231194.4771 | 11151.5625 | 0 | 0 | 41297.75 | 253387.4693 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-03 | 1729472.6458 |  |  | 530737.9176 | 211451.8122 | 231194.4771 | 629326.4685 | 126761.9704 | 0 | 13053.04 | 2119 | 0 | 0 | 62542.7088 | 21613.8 | 0 | 0 | 0 | 0 | 0 | 10481.4216 | 6780.8 | 10171.2 | 0 | 0 | 305026.575 | 530737.9176 | 0 | 20463.0786 | 124142.6768 | 19098.8734 | 47747.1834 | 0 | 231194.4771 | 11240.775 | 0 | 0 | 41297.75 | 253561.3685 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-04 | 1732714.1782 |  |  | 532496.2733 | 212283.0369 | 231194.4771 | 629589.5802 | 127150.8108 | 0 | 13093.08 | 2125.5 | 0 | 0 | 62734.5576 | 21680.1 | 0 | 0 | 0 | 0 | 0 | 10513.5732 | 6801.6 | 10202.4 | 0 | 0 | 305026.575 | 532496.2733 | 0 | 20543.5197 | 124630.6862 | 19173.9517 | 47934.8793 | 0 | 231194.4771 | 11329.9875 | 0 | 0 | 41297.75 | 253735.2677 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-05 | 1735955.7107 |  |  | 534254.629 | 213114.2616 | 231194.4771 | 629852.6918 | 127539.6512 | 0 | 13133.12 | 2132 | 0 | 0 | 62926.4064 | 21746.4 | 0 | 0 | 0 | 0 | 0 | 10545.7248 | 6822.4 | 10233.6 | 0 | 0 | 305026.575 | 534254.629 | 0 | 20623.9608 | 125118.6955 | 19249.0301 | 48122.5752 | 0 | 231194.4771 | 11419.2 | 0 | 0 | 41297.75 | 253909.1668 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-06 | 1739197.2431 |  |  | 536012.9847 | 213945.4863 | 231194.4771 | 630115.8035 | 127928.4916 | 0 | 13173.16 | 2138.5 | 0 | 0 | 63118.2552 | 21812.7 | 0 | 0 | 0 | 0 | 0 | 10577.8764 | 6843.2 | 10264.8 | 0 | 0 | 305026.575 | 536012.9847 | 0 | 20704.4019 | 125606.7049 | 19324.1084 | 48310.2711 | 0 | 231194.4771 | 11508.4125 | 0 | 0 | 41297.75 | 254083.066 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-07 | 1742438.7756 |  |  | 537771.3403 | 214776.711 | 231194.4771 | 630378.9152 | 128317.332 | 0 | 13213.2 | 2145 | 0 | 0 | 63310.104 | 21879 | 0 | 0 | 0 | 0 | 0 | 10610.028 | 6864 | 10296 | 0 | 0 | 305026.575 | 537771.3403 | 0 | 20784.843 | 126094.7142 | 19399.1868 | 48497.967 | 0 | 231194.4771 | 11597.625 | 0 | 0 | 41297.75 | 254256.9652 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-08 | 1745680.3081 |  |  | 539529.696 | 215607.9357 | 231194.4771 | 630642.0268 | 128706.1724 | 0 | 13253.24 | 2151.5 | 0 | 0 | 63501.9528 | 21945.3 | 0 | 0 | 0 | 0 | 0 | 10642.1796 | 6884.8 | 10327.2 | 0 | 0 | 305026.575 | 539529.696 | 0 | 20865.2841 | 126582.7235 | 19474.2652 | 48685.6629 | 0 | 231194.4771 | 11686.8375 | 0 | 0 | 41297.75 | 254430.8643 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-09 | 1748921.8405 |  |  | 541288.0517 | 216439.1604 | 231194.4771 | 630905.1385 | 129095.0128 | 0 | 13293.28 | 2158 | 0 | 0 | 63693.8016 | 22011.6 | 0 | 0 | 0 | 0 | 0 | 10674.3312 | 6905.6 | 10358.4 | 0 | 0 | 305026.575 | 541288.0517 | 0 | 20945.7252 | 127070.7329 | 19549.3435 | 48873.3588 | 0 | 231194.4771 | 11776.05 | 0 | 0 | 41297.75 | 254604.7635 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-10 | 1752163.373 |  |  | 543046.4074 | 217270.3851 | 231194.4771 | 631168.2502 | 129483.8532 | 0 | 13333.32 | 2164.5 | 0 | 0 | 63885.6504 | 22077.9 | 0 | 0 | 0 | 0 | 0 | 10706.4828 | 6926.4 | 10389.6 | 0 | 0 | 305026.575 | 543046.4074 | 0 | 21026.1663 | 127558.7422 | 19624.4219 | 49061.0547 | 0 | 231194.4771 | 11865.2625 | 0 | 0 | 41297.75 | 254778.6627 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-11 | 1755404.9054 |  |  | 544804.7631 | 218101.6098 | 231194.4771 | 631431.3618 | 129872.6936 | 0 | 13373.36 | 2171 | 0 | 0 | 64077.4992 | 22144.2 | 0 | 0 | 0 | 0 | 0 | 10738.6344 | 6947.2 | 10420.8 | 0 | 0 | 305026.575 | 544804.7631 | 0 | 21106.6074 | 128046.7516 | 19699.5002 | 49248.7506 | 0 | 231194.4771 | 11954.475 | 0 | 0 | 41297.75 | 254952.5618 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-12 | 1758646.4379 |  |  | 546563.1188 | 218932.8345 | 231194.4771 | 631694.4735 | 130261.534 | 0 | 13413.4 | 2177.5 | 0 | 0 | 64269.348 | 22210.5 | 0 | 0 | 0 | 0 | 0 | 10770.786 | 6968 | 10452 | 0 | 0 | 305026.575 | 546563.1188 | 0 | 21187.0485 | 128534.7609 | 19774.5786 | 49436.4465 | 0 | 231194.4771 | 12043.6875 | 0 | 0 | 41297.75 | 255126.461 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-13 | 1761887.9704 |  |  | 548321.4745 | 219764.0592 | 231194.4771 | 631957.5852 | 130650.3744 | 0 | 13453.44 | 2184 | 0 | 0 | 64461.1968 | 22276.8 | 0 | 0 | 0 | 0 | 0 | 10802.9376 | 6988.8 | 10483.2 | 0 | 0 | 305026.575 | 548321.4745 | 0 | 21267.4896 | 129022.7702 | 19849.657 | 49624.1424 | 0 | 231194.4771 | 12132.9 | 0 | 0 | 41297.75 | 255300.3602 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-14 | 1765129.5028 |  |  | 550079.8302 | 220595.2839 | 231194.4771 | 632220.6968 | 131039.2148 | 0 | 13493.48 | 2190.5 | 0 | 0 | 64653.0456 | 22343.1 | 0 | 0 | 0 | 0 | 0 | 10835.0892 | 7009.6 | 10514.4 | 0 | 0 | 305026.575 | 550079.8302 | 0 | 21347.9307 | 129510.7796 | 19924.7353 | 49811.8383 | 0 | 231194.4771 | 12222.1125 | 0 | 0 | 41297.75 | 255474.2593 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-15 | 1768371.0353 |  |  | 551838.1859 | 221426.5086 | 231194.4771 | 632483.8085 | 131428.0552 | 0 | 13533.52 | 2197 | 0 | 0 | 64844.8944 | 22409.4 | 0 | 0 | 0 | 0 | 0 | 10867.2408 | 7030.4 | 10545.6 | 0 | 0 | 305026.575 | 551838.1859 | 0 | 21428.3718 | 129998.7889 | 19999.8137 | 49999.5342 | 0 | 231194.4771 | 12311.325 | 0 | 0 | 41297.75 | 255648.1585 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-16 | 1771612.5678 |  |  | 553596.5416 | 222257.7333 | 231194.4771 | 632746.9202 | 131816.8956 | 0 | 13573.56 | 2203.5 | 0 | 0 | 65036.7432 | 22475.7 | 0 | 0 | 0 | 0 | 0 | 10899.3924 | 7051.2 | 10576.8 | 0 | 0 | 305026.575 | 553596.5416 | 0 | 21508.8129 | 130486.7983 | 20074.892 | 50187.2301 | 0 | 231194.4771 | 12400.5375 | 0 | 0 | 41297.75 | 255822.0577 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-17 | 1774854.1002 |  |  | 555354.8973 | 223088.958 | 231194.4771 | 633010.0318 | 132205.736 | 0 | 13613.6 | 2210 | 0 | 0 | 65228.592 | 22542 | 0 | 0 | 0 | 0 | 0 | 10931.544 | 7072 | 10608 | 0 | 0 | 305026.575 | 555354.8973 | 0 | 21589.254 | 130974.8076 | 20149.9704 | 50374.926 | 0 | 231194.4771 | 12489.75 | 0 | 0 | 41297.75 | 255995.9568 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-18 | 1778095.6327 |  |  | 557113.253 | 223920.1827 | 231194.4771 | 633273.1435 | 132594.5764 | 0 | 13653.64 | 2216.5 | 0 | 0 | 65420.4408 | 22608.3 | 0 | 0 | 0 | 0 | 0 | 10963.6956 | 7092.8 | 10639.2 | 0 | 0 | 305026.575 | 557113.253 | 0 | 21669.6951 | 131462.8169 | 20225.0488 | 50562.6219 | 0 | 231194.4771 | 12578.9625 | 0 | 0 | 41297.75 | 256169.856 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-19 | 1781337.1651 |  |  | 558871.6087 | 224751.4074 | 231194.4771 | 633536.2552 | 132983.4168 | 0 | 13693.68 | 2223 | 0 | 0 | 65612.2896 | 22674.6 | 0 | 0 | 0 | 0 | 0 | 10995.8472 | 7113.6 | 10670.4 | 0 | 0 | 305026.575 | 558871.6087 | 0 | 21750.1362 | 131950.8263 | 20300.1271 | 50750.3178 | 0 | 231194.4771 | 12668.175 | 0 | 0 | 41297.75 | 256343.7552 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-20 | 1784578.6976 |  |  | 560629.9644 | 225582.6321 | 231194.4771 | 633799.3668 | 133372.2572 | 0 | 13733.72 | 2229.5 | 0 | 0 | 65804.1384 | 22740.9 | 0 | 0 | 0 | 0 | 0 | 11027.9988 | 7134.4 | 10701.6 | 0 | 0 | 305026.575 | 560629.9644 | 0 | 21830.5773 | 132438.8356 | 20375.2055 | 50938.0137 | 0 | 231194.4771 | 12757.3875 | 0 | 0 | 41297.75 | 256517.6543 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-21 | 1787820.2301 |  |  | 562388.3201 | 226413.8568 | 231194.4771 | 634062.4785 | 133761.0976 | 0 | 13773.76 | 2236 | 0 | 0 | 65995.9872 | 22807.2 | 0 | 0 | 0 | 0 | 0 | 11060.1504 | 7155.2 | 10732.8 | 0 | 0 | 305026.575 | 562388.3201 | 0 | 21911.0184 | 132926.845 | 20450.2838 | 51125.7096 | 0 | 231194.4771 | 12846.6 | 0 | 0 | 41297.75 | 256691.5535 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-22 | 1791061.7625 |  |  | 564146.6758 | 227245.0815 | 231194.4771 | 634325.5902 | 134149.938 | 0 | 13813.8 | 2242.5 | 0 | 0 | 66187.836 | 22873.5 | 0 | 0 | 0 | 0 | 0 | 11092.302 | 7176 | 10764 | 0 | 0 | 305026.575 | 564146.6758 | 0 | 21991.4595 | 133414.8543 | 20525.3622 | 51313.4055 | 0 | 231194.4771 | 12935.8125 | 0 | 0 | 41297.75 | 256865.4527 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-23 | 1794303.295 |  |  | 565905.0315 | 228076.3062 | 231194.4771 | 634588.7018 | 134538.7784 | 0 | 13853.84 | 2249 | 0 | 0 | 66379.6848 | 22939.8 | 0 | 0 | 0 | 0 | 0 | 11124.4536 | 7196.8 | 10795.2 | 0 | 0 | 305026.575 | 565905.0315 | 0 | 22071.9006 | 133902.8636 | 20600.4406 | 51501.1014 | 0 | 231194.4771 | 13025.025 | 0 | 0 | 41297.75 | 257039.3518 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-24 | 1797544.8274 |  |  | 567663.3872 | 228907.5309 | 231194.4771 | 634851.8135 | 134927.6188 | 0 | 13893.88 | 2255.5 | 0 | 0 | 66571.5336 | 23006.1 | 0 | 0 | 0 | 0 | 0 | 11156.6052 | 7217.6 | 10826.4 | 0 | 0 | 305026.575 | 567663.3872 | 0 | 22152.3417 | 134390.873 | 20675.5189 | 51688.7973 | 0 | 231194.4771 | 13114.2375 | 0 | 0 | 41297.75 | 257213.251 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-25 | 1800786.3599 |  |  | 569421.7429 | 229738.7556 | 231194.4771 | 635114.9252 | 135316.4592 | 0 | 13933.92 | 2262 | 0 | 0 | 66763.3824 | 23072.4 | 0 | 0 | 0 | 0 | 0 | 11188.7568 | 7238.4 | 10857.6 | 0 | 0 | 305026.575 | 569421.7429 | 0 | 22232.7828 | 134878.8823 | 20750.5973 | 51876.4932 | 0 | 231194.4771 | 13203.45 | 0 | 0 | 41297.75 | 257387.1502 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-26 | 1804027.8924 |  |  | 571180.0986 | 230569.9803 | 231194.4771 | 635378.0368 | 135705.2996 | 0 | 13973.96 | 2268.5 | 0 | 0 | 66955.2312 | 23138.7 | 0 | 0 | 0 | 0 | 0 | 11220.9084 | 7259.2 | 10888.8 | 0 | 0 | 305026.575 | 571180.0986 | 0 | 22313.2239 | 135366.8917 | 20825.6756 | 52064.1891 | 0 | 231194.4771 | 13292.6625 | 0 | 0 | 41297.75 | 257561.0493 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-27 | 1807269.4248 |  |  | 572938.4542 | 231401.205 | 231194.4771 | 635641.1485 | 136094.14 | 0 | 14014 | 2275 | 0 | 0 | 67147.08 | 23205 | 0 | 0 | 0 | 0 | 0 | 11253.06 | 7280 | 10920 | 0 | 0 | 305026.575 | 572938.4542 | 0 | 22393.665 | 135854.901 | 20900.754 | 52251.885 | 0 | 231194.4771 | 13381.875 | 0 | 0 | 41297.75 | 257734.9485 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-28 | 1810510.9573 |  |  | 574696.8099 | 232232.4297 | 231194.4771 | 635904.2602 | 136482.9804 | 0 | 14054.04 | 2281.5 | 0 | 0 | 67338.9288 | 23271.3 | 0 | 0 | 0 | 0 | 0 | 11285.2116 | 7300.8 | 10951.2 | 0 | 0 | 305026.575 | 574696.8099 | 0 | 22474.1061 | 136342.9103 | 20975.8324 | 52439.5809 | 0 | 231194.4771 | 13471.0875 | 0 | 0 | 41297.75 | 257908.8477 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-29 | 1813752.4898 |  |  | 576455.1656 | 233063.6544 | 231194.4771 | 636167.3718 | 136871.8208 | 0 | 14094.08 | 2288 | 0 | 0 | 67530.7776 | 23337.6 | 0 | 0 | 0 | 0 | 0 | 11317.3632 | 7321.6 | 10982.4 | 0 | 0 | 305026.575 | 576455.1656 | 0 | 22554.5472 | 136830.9197 | 21050.9107 | 52627.2768 | 0 | 231194.4771 | 13560.3 | 0 | 0 | 41297.75 | 258082.7468 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-30 | 1816994.0222 |  |  | 578213.5213 | 233894.8791 | 231194.4771 | 636430.4835 | 137260.6612 | 0 | 14134.12 | 2294.5 | 0 | 0 | 67722.6264 | 23403.9 | 0 | 0 | 0 | 0 | 0 | 11349.5148 | 7342.4 | 11013.6 | 0 | 0 | 305026.575 | 578213.5213 | 0 | 22634.9883 | 137318.929 | 21125.9891 | 52814.9727 | 0 | 231194.4771 | 13649.5125 | 0 | 0 | 41297.75 | 258256.646 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-01 | 1820235.5547 |  |  | 579971.877 | 234726.1038 | 231194.4771 | 636693.5952 | 137649.5016 | 0 | 14174.16 | 2301 | 0 | 0 | 67914.4752 | 23470.2 | 0 | 0 | 0 | 0 | 0 | 11381.6664 | 7363.2 | 11044.8 | 0 | 0 | 305026.575 | 579971.877 | 0 | 22715.4294 | 137806.9384 | 21201.0674 | 53002.6686 | 0 | 231194.4771 | 13738.725 | 0 | 0 | 41297.75 | 258430.5452 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-02 | 1823477.0871 |  |  | 581730.2327 | 235557.3285 | 231194.4771 | 636956.7068 | 138038.342 | 0 | 14214.2 | 2307.5 | 0 | 0 | 68106.324 | 23536.5 | 0 | 0 | 0 | 0 | 0 | 11413.818 | 7384 | 11076 | 0 | 0 | 305026.575 | 581730.2327 | 0 | 22795.8705 | 138294.9477 | 21276.1458 | 53190.3645 | 0 | 231194.4771 | 13827.9375 | 0 | 0 | 41297.75 | 258604.4443 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-03 | 1826718.6196 |  |  | 583488.5884 | 236388.5532 | 231194.4771 | 637219.8185 | 138427.1824 | 0 | 14254.24 | 2314 | 0 | 0 | 68298.1728 | 23602.8 | 0 | 0 | 0 | 0 | 0 | 11445.9696 | 7404.8 | 11107.2 | 0 | 0 | 305026.575 | 583488.5884 | 0 | 22876.3116 | 138782.957 | 21351.2242 | 53378.0604 | 0 | 231194.4771 | 13917.15 | 0 | 0 | 41297.75 | 258778.3435 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-04 | 1829960.1521 |  |  | 585246.9441 | 237219.7779 | 231194.4771 | 637482.9302 | 138816.0228 | 0 | 14294.28 | 2320.5 | 0 | 0 | 68490.0216 | 23669.1 | 0 | 0 | 0 | 0 | 0 | 11478.1212 | 7425.6 | 11138.4 | 0 | 0 | 305026.575 | 585246.9441 | 0 | 22956.7527 | 139270.9664 | 21426.3025 | 53565.7563 | 0 | 231194.4771 | 14006.3625 | 0 | 0 | 41297.75 | 258952.2427 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-05 | 1833201.6845 |  |  | 587005.2998 | 238051.0026 | 231194.4771 | 637746.0418 | 139204.8632 | 0 | 14334.32 | 2327 | 0 | 0 | 68681.8704 | 23735.4 | 0 | 0 | 0 | 0 | 0 | 11510.2728 | 7446.4 | 11169.6 | 0 | 0 | 305026.575 | 587005.2998 | 0 | 23037.1938 | 139758.9757 | 21501.3809 | 53753.4522 | 0 | 231194.4771 | 14095.575 | 0 | 0 | 41297.75 | 259126.1418 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-06 | 1836443.217 |  |  | 588763.6555 | 238882.2273 | 231194.4771 | 638009.1535 | 139593.7036 | 0 | 14374.36 | 2333.5 | 0 | 0 | 68873.7192 | 23801.7 | 0 | 0 | 0 | 0 | 0 | 11542.4244 | 7467.2 | 11200.8 | 0 | 0 | 305026.575 | 588763.6555 | 0 | 23117.6349 | 140246.9851 | 21576.4592 | 53941.1481 | 0 | 231194.4771 | 14184.7875 | 0 | 0 | 41297.75 | 259300.041 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-07 | 1839684.7494 |  |  | 590522.0112 | 239713.452 | 231194.4771 | 638272.2652 | 139982.544 | 0 | 14414.4 | 2340 | 0 | 0 | 69065.568 | 23868 | 0 | 0 | 0 | 0 | 0 | 11574.576 | 7488 | 11232 | 0 | 0 | 305026.575 | 590522.0112 | 0 | 23198.076 | 140734.9944 | 21651.5376 | 54128.844 | 0 | 231194.4771 | 14274 | 0 | 0 | 41297.75 | 259473.9402 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-08 | 1842926.2819 |  |  | 592280.3669 | 240544.6767 | 231194.4771 | 638535.3768 | 140371.3844 | 0 | 14454.44 | 2346.5 | 0 | 0 | 69257.4168 | 23934.3 | 0 | 0 | 0 | 0 | 0 | 11606.7276 | 7508.8 | 11263.2 | 0 | 0 | 305026.575 | 592280.3669 | 0 | 23278.5171 | 141223.0037 | 21726.616 | 54316.5399 | 0 | 231194.4771 | 14363.2125 | 0 | 0 | 41297.75 | 259647.8393 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-09 | 1846167.8144 |  |  | 594038.7226 | 241375.9014 | 231194.4771 | 638798.4885 | 140760.2248 | 0 | 14494.48 | 2353 | 0 | 0 | 69449.2656 | 24000.6 | 0 | 0 | 0 | 0 | 0 | 11638.8792 | 7529.6 | 11294.4 | 0 | 0 | 305026.575 | 594038.7226 | 0 | 23358.9582 | 141711.0131 | 21801.6943 | 54504.2358 | 0 | 231194.4771 | 14452.425 | 0 | 0 | 41297.75 | 259821.7385 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-10 | 1849409.3468 |  |  | 595797.0783 | 242207.1261 | 231194.4771 | 639061.6002 | 141149.0652 | 0 | 14534.52 | 2359.5 | 0 | 0 | 69641.1144 | 24066.9 | 0 | 0 | 0 | 0 | 0 | 11671.0308 | 7550.4 | 11325.6 | 0 | 0 | 305026.575 | 595797.0783 | 0 | 23439.3993 | 142199.0224 | 21876.7727 | 54691.9317 | 0 | 231194.4771 | 14541.6375 | 0 | 0 | 41297.75 | 259995.6377 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-11 | 1852650.8793 |  |  | 597555.434 | 243038.3508 | 231194.4771 | 639324.7118 | 141537.9056 | 0 | 14574.56 | 2366 | 0 | 0 | 69832.9632 | 24133.2 | 0 | 0 | 0 | 0 | 0 | 11703.1824 | 7571.2 | 11356.8 | 0 | 0 | 305026.575 | 597555.434 | 0 | 23519.8404 | 142687.0318 | 21951.851 | 54879.6276 | 0 | 231194.4771 | 14630.85 | 0 | 0 | 41297.75 | 260169.5368 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-12 | 1855892.4118 |  |  | 599313.7897 | 243869.5755 | 231194.4771 | 639587.8235 | 141926.746 | 0 | 14614.6 | 2372.5 | 0 | 0 | 70024.812 | 24199.5 | 0 | 0 | 0 | 0 | 0 | 11735.334 | 7592 | 11388 | 0 | 0 | 305026.575 | 599313.7897 | 0 | 23600.2815 | 143175.0411 | 22026.9294 | 55067.3235 | 0 | 231194.4771 | 14720.0625 | 0 | 0 | 41297.75 | 260343.436 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-13 | 1859133.9442 |  |  | 601072.1454 | 244700.8002 | 231194.4771 | 639850.9352 | 142315.5864 | 0 | 14654.64 | 2379 | 0 | 0 | 70216.6608 | 24265.8 | 0 | 0 | 0 | 0 | 0 | 11767.4856 | 7612.8 | 11419.2 | 0 | 0 | 305026.575 | 601072.1454 | 0 | 23680.7226 | 143663.0504 | 22102.0078 | 55255.0194 | 0 | 231194.4771 | 14809.275 | 0 | 0 | 41297.75 | 260517.3352 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-14 | 1862375.4767 |  |  | 602830.5011 | 245532.0249 | 231194.4771 | 640114.0468 | 142704.4268 | 0 | 14694.68 | 2385.5 | 0 | 0 | 70408.5096 | 24332.1 | 0 | 0 | 0 | 0 | 0 | 11799.6372 | 7633.6 | 11450.4 | 0 | 0 | 305026.575 | 602830.5011 | 0 | 23761.1637 | 144151.0598 | 22177.0861 | 55442.7153 | 0 | 231194.4771 | 14898.4875 | 0 | 0 | 41297.75 | 260691.2343 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-15 | 1865617.0091 |  |  | 604588.8568 | 246363.2496 | 231194.4771 | 640377.1585 | 143093.2672 | 0 | 14734.72 | 2392 | 0 | 0 | 70600.3584 | 24398.4 | 0 | 0 | 0 | 0 | 0 | 11831.7888 | 7654.4 | 11481.6 | 0 | 0 | 305026.575 | 604588.8568 | 0 | 23841.6048 | 144639.0691 | 22252.1645 | 55630.4112 | 0 | 231194.4771 | 14987.7 | 0 | 0 | 41297.75 | 260865.1335 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-16 | 1868858.5416 |  |  | 606347.2125 | 247194.4743 | 231194.4771 | 640640.2702 | 143482.1076 | 0 | 14774.76 | 2398.5 | 0 | 0 | 70792.2072 | 24464.7 | 0 | 0 | 0 | 0 | 0 | 11863.9404 | 7675.2 | 11512.8 | 0 | 0 | 305026.575 | 606347.2125 | 0 | 23922.0459 | 145127.0785 | 22327.2428 | 55818.1071 | 0 | 231194.4771 | 15076.9125 | 0 | 0 | 41297.75 | 261039.0327 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-17 | 1872100.0741 |  |  | 608105.5681 | 248025.699 | 231194.4771 | 640903.3818 | 143870.948 | 0 | 14814.8 | 2405 | 0 | 0 | 70984.056 | 24531 | 0 | 0 | 0 | 0 | 0 | 11896.092 | 7696 | 11544 | 0 | 0 | 305026.575 | 608105.5681 | 0 | 24002.487 | 145615.0878 | 22402.3212 | 56005.803 | 0 | 231194.4771 | 15166.125 | 0 | 0 | 41297.75 | 261212.9318 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-18 | 1875341.6065 |  |  | 609863.9238 | 248856.9237 | 231194.4771 | 641166.4935 | 144259.7884 | 0 | 14854.84 | 2411.5 | 0 | 0 | 71175.9048 | 24597.3 | 0 | 0 | 0 | 0 | 0 | 11928.2436 | 7716.8 | 11575.2 | 0 | 0 | 305026.575 | 609863.9238 | 0 | 24082.9281 | 146103.0971 | 22477.3996 | 56193.4989 | 0 | 231194.4771 | 15255.3375 | 0 | 0 | 41297.75 | 261386.831 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-19 | 1878583.139 |  |  | 611622.2795 | 249688.1484 | 231194.4771 | 641429.6052 | 144648.6288 | 0 | 14894.88 | 2418 | 0 | 0 | 71367.7536 | 24663.6 | 0 | 0 | 0 | 0 | 0 | 11960.3952 | 7737.6 | 11606.4 | 0 | 0 | 305026.575 | 611622.2795 | 0 | 24163.3692 | 146591.1065 | 22552.4779 | 56381.1948 | 0 | 231194.4771 | 15344.55 | 0 | 0 | 41297.75 | 261560.7302 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-20 | 1881824.6714 |  |  | 613380.6352 | 250519.3731 | 231194.4771 | 641692.7168 | 145037.4692 | 0 | 14934.92 | 2424.5 | 0 | 0 | 71559.6024 | 24729.9 | 0 | 0 | 0 | 0 | 0 | 11992.5468 | 7758.4 | 11637.6 | 0 | 0 | 305026.575 | 613380.6352 | 0 | 24243.8103 | 147079.1158 | 22627.5563 | 56568.8907 | 0 | 231194.4771 | 15433.7625 | 0 | 0 | 41297.75 | 261734.6293 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-21 | 1885066.2039 |  |  | 615138.9909 | 251350.5978 | 231194.4771 | 641955.8285 | 145426.3096 | 0 | 14974.96 | 2431 | 0 | 0 | 71751.4512 | 24796.2 | 0 | 0 | 0 | 0 | 0 | 12024.6984 | 7779.2 | 11668.8 | 0 | 0 | 305026.575 | 615138.9909 | 0 | 24324.2514 | 147567.1252 | 22702.6346 | 56756.5866 | 0 | 231194.4771 | 15522.975 | 0 | 0 | 41297.75 | 261908.5285 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-22 | 1888307.7364 |  |  | 616897.3466 | 252181.8225 | 231194.4771 | 642218.9402 | 145815.15 | 0 | 15015 | 2437.5 | 0 | 0 | 71943.3 | 24862.5 | 0 | 0 | 0 | 0 | 0 | 12056.85 | 7800 | 11700 | 0 | 0 | 305026.575 | 616897.3466 | 0 | 24404.6925 | 148055.1345 | 22777.713 | 56944.2825 | 0 | 231194.4771 | 15612.1875 | 0 | 0 | 41297.75 | 262082.4277 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-23 | 1891549.2688 |  |  | 618655.7023 | 253013.0472 | 231194.4771 | 642482.0518 | 146203.9904 | 0 | 15055.04 | 2444 | 0 | 0 | 72135.1488 | 24928.8 | 0 | 0 | 0 | 0 | 0 | 12089.0016 | 7820.8 | 11731.2 | 0 | 0 | 305026.575 | 618655.7023 | 0 | 24485.1336 | 148543.1438 | 22852.7914 | 57131.9784 | 0 | 231194.4771 | 15701.4 | 0 | 0 | 41297.75 | 262256.3268 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-24 | 1894790.8013 |  |  | 620414.058 | 253844.2719 | 231194.4771 | 642745.1635 | 146592.8308 | 0 | 15095.08 | 2450.5 | 0 | 0 | 72326.9976 | 24995.1 | 0 | 0 | 0 | 0 | 0 | 12121.1532 | 7841.6 | 11762.4 | 0 | 0 | 305026.575 | 620414.058 | 0 | 24565.5747 | 149031.1532 | 22927.8697 | 57319.6743 | 0 | 231194.4771 | 15790.6125 | 0 | 0 | 41297.75 | 262430.226 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-25 | 1898032.3338 |  |  | 622172.4137 | 254675.4966 | 231194.4771 | 643008.2752 | 146981.6712 | 0 | 15135.12 | 2457 | 0 | 0 | 72518.8464 | 25061.4 | 0 | 0 | 0 | 0 | 0 | 12153.3048 | 7862.4 | 11793.6 | 0 | 0 | 305026.575 | 622172.4137 | 0 | 24646.0158 | 149519.1625 | 23002.9481 | 57507.3702 | 0 | 231194.4771 | 15879.825 | 0 | 0 | 41297.75 | 262604.1252 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-26 | 1901273.8662 |  |  | 623930.7694 | 255506.7213 | 231194.4771 | 643271.3868 | 147370.5116 | 0 | 15175.16 | 2463.5 | 0 | 0 | 72710.6952 | 25127.7 | 0 | 0 | 0 | 0 | 0 | 12185.4564 | 7883.2 | 11824.8 | 0 | 0 | 305026.575 | 623930.7694 | 0 | 24726.4569 | 150007.1719 | 23078.0264 | 57695.0661 | 0 | 231194.4771 | 15969.0375 | 0 | 0 | 41297.75 | 262778.0243 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-27 | 1904515.3987 |  |  | 625689.1251 | 256337.946 | 231194.4771 | 643534.4985 | 147759.352 | 0 | 15215.2 | 2470 | 0 | 0 | 72902.544 | 25194 | 0 | 0 | 0 | 0 | 0 | 12217.608 | 7904 | 11856 | 0 | 0 | 305026.575 | 625689.1251 | 0 | 24806.898 | 150495.1812 | 23153.1048 | 57882.762 | 0 | 231194.4771 | 16058.25 | 0 | 0 | 41297.75 | 262951.9235 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-28 | 1907756.9311 |  |  | 627447.4808 | 257169.1707 | 231194.4771 | 643797.6102 | 148148.1924 | 0 | 15255.24 | 2476.5 | 0 | 0 | 73094.3928 | 25260.3 | 0 | 0 | 0 | 0 | 0 | 12249.7596 | 7924.8 | 11887.2 | 0 | 0 | 305026.575 | 627447.4808 | 0 | 24887.3391 | 150983.1905 | 23228.1832 | 58070.4579 | 0 | 231194.4771 | 16147.4625 | 0 | 0 | 41297.75 | 263125.8227 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-29 | 1910998.4636 |  |  | 629205.8365 | 258000.3954 | 231194.4771 | 644060.7218 | 148537.0328 | 0 | 15295.28 | 2483 | 0 | 0 | 73286.2416 | 25326.6 | 0 | 0 | 0 | 0 | 0 | 12281.9112 | 7945.6 | 11918.4 | 0 | 0 | 305026.575 | 629205.8365 | 0 | 24967.7802 | 151471.1999 | 23303.2615 | 58258.1538 | 0 | 231194.4771 | 16236.675 | 0 | 0 | 41297.75 | 263299.7218 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-30 | 1914239.9961 |  |  | 630964.1922 | 258831.6201 | 231194.4771 | 644323.8335 | 148925.8732 | 0 | 15335.32 | 2489.5 | 0 | 0 | 73478.0904 | 25392.9 | 0 | 0 | 0 | 0 | 0 | 12314.0628 | 7966.4 | 11949.6 | 0 | 0 | 305026.575 | 630964.1922 | 0 | 25048.2213 | 151959.2092 | 23378.3399 | 58445.8497 | 0 | 231194.4771 | 16325.8875 | 0 | 0 | 41297.75 | 263473.621 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-31 | 1917481.5285 |  |  | 632722.5479 | 259662.8448 | 231194.4771 | 644586.9452 | 149314.7136 | 0 | 15375.36 | 2496 | 0 | 0 | 73669.9392 | 25459.2 | 0 | 0 | 0 | 0 | 0 | 12346.2144 | 7987.2 | 11980.8 | 0 | 0 | 305026.575 | 632722.5479 | 0 | 25128.6624 | 152447.2186 | 23453.4182 | 58633.5456 | 0 | 231194.4771 | 16415.1 | 0 | 0 | 41297.75 | 263647.5202 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-01 | 1920723.061 |  |  | 634480.9036 | 260494.0695 | 231194.4771 | 644850.0568 | 149703.554 | 0 | 15415.4 | 2502.5 | 0 | 0 | 73861.788 | 25525.5 | 0 | 0 | 0 | 0 | 0 | 12378.366 | 8008 | 12012 | 0 | 0 | 305026.575 | 634480.9036 | 0 | 25209.1035 | 152935.2279 | 23528.4966 | 58821.2415 | 0 | 231194.4771 | 16504.3125 | 0 | 0 | 41297.75 | 263821.4193 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-02 | 1923964.5935 |  |  | 636239.2593 | 261325.2942 | 231194.4771 | 645113.1685 | 150092.3944 | 0 | 15455.44 | 2509 | 0 | 0 | 74053.6368 | 25591.8 | 0 | 0 | 0 | 0 | 0 | 12410.5176 | 8028.8 | 12043.2 | 0 | 0 | 305026.575 | 636239.2593 | 0 | 25289.5446 | 153423.2372 | 23603.575 | 59008.9374 | 0 | 231194.4771 | 16593.525 | 0 | 0 | 41297.75 | 263995.3185 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-03 | 1927206.1259 |  |  | 637997.615 | 262156.5189 | 231194.4771 | 645376.2802 | 150481.2348 | 0 | 15495.48 | 2515.5 | 0 | 0 | 74245.4856 | 25658.1 | 0 | 0 | 0 | 0 | 0 | 12442.6692 | 8049.6 | 12074.4 | 0 | 0 | 305026.575 | 637997.615 | 0 | 25369.9857 | 153911.2466 | 23678.6533 | 59196.6333 | 0 | 231194.4771 | 16682.7375 | 0 | 0 | 41297.75 | 264169.2177 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-04 | 1930447.6584 |  |  | 639755.9707 | 262987.7436 | 231194.4771 | 645639.3918 | 150870.0752 | 0 | 15535.52 | 2522 | 0 | 0 | 74437.3344 | 25724.4 | 0 | 0 | 0 | 0 | 0 | 12474.8208 | 8070.4 | 12105.6 | 0 | 0 | 305026.575 | 639755.9707 | 0 | 25450.4268 | 154399.2559 | 23753.7317 | 59384.3292 | 0 | 231194.4771 | 16771.95 | 0 | 0 | 41297.75 | 264343.1168 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-05 | 1933689.1908 |  |  | 641514.3264 | 263818.9683 | 231194.4771 | 645902.5035 | 151258.9156 | 0 | 15575.56 | 2528.5 | 0 | 0 | 74629.1832 | 25790.7 | 0 | 0 | 0 | 0 | 0 | 12506.9724 | 8091.2 | 12136.8 | 0 | 0 | 305026.575 | 641514.3264 | 0 | 25530.8679 | 154887.2653 | 23828.81 | 59572.0251 | 0 | 231194.4771 | 16861.1625 | 0 | 0 | 41297.75 | 264517.016 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-06 | 1936930.7233 |  |  | 643272.682 | 264650.193 | 231194.4771 | 646165.6152 | 151647.756 | 0 | 15615.6 | 2535 | 0 | 0 | 74821.032 | 25857 | 0 | 0 | 0 | 0 | 0 | 12539.124 | 8112 | 12168 | 0 | 0 | 305026.575 | 643272.682 | 0 | 25611.309 | 155375.2746 | 23903.8884 | 59759.721 | 0 | 231194.4771 | 16950.375 | 0 | 0 | 41297.75 | 264690.9152 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-07 | 1940172.2558 |  |  | 645031.0377 | 265481.4177 | 231194.4771 | 646428.7268 | 152036.5964 | 0 | 15655.64 | 2541.5 | 0 | 0 | 75012.8808 | 25923.3 | 0 | 0 | 0 | 0 | 0 | 12571.2756 | 8132.8 | 12199.2 | 0 | 0 | 305026.575 | 645031.0377 | 0 | 25691.7501 | 155863.2839 | 23978.9668 | 59947.4169 | 0 | 231194.4771 | 17039.5875 | 0 | 0 | 41297.75 | 264864.8143 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-08 | 1943413.7882 |  |  | 646789.3934 | 266312.6424 | 231194.4771 | 646691.8385 | 152425.4368 | 0 | 15695.68 | 2548 | 0 | 0 | 75204.7296 | 25989.6 | 0 | 0 | 0 | 0 | 0 | 12603.4272 | 8153.6 | 12230.4 | 0 | 0 | 305026.575 | 646789.3934 | 0 | 25772.1912 | 156351.2933 | 24054.0451 | 60135.1128 | 0 | 231194.4771 | 17128.8 | 0 | 0 | 41297.75 | 265038.7135 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-09 | 1946655.3207 |  |  | 648547.7491 | 267143.8671 | 231194.4771 | 646954.9502 | 152814.2772 | 0 | 15735.72 | 2554.5 | 0 | 0 | 75396.5784 | 26055.9 | 0 | 0 | 0 | 0 | 0 | 12635.5788 | 8174.4 | 12261.6 | 0 | 0 | 305026.575 | 648547.7491 | 0 | 25852.6323 | 156839.3026 | 24129.1235 | 60322.8087 | 0 | 231194.4771 | 17218.0125 | 0 | 0 | 41297.75 | 265212.6127 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-10 | 1949896.8531 |  |  | 650306.1048 | 267975.0918 | 231194.4771 | 647218.0618 | 153203.1176 | 0 | 15775.76 | 2561 | 0 | 0 | 75588.4272 | 26122.2 | 0 | 0 | 0 | 0 | 0 | 12667.7304 | 8195.2 | 12292.8 | 0 | 0 | 305026.575 | 650306.1048 | 0 | 25933.0734 | 157327.312 | 24204.2018 | 60510.5046 | 0 | 231194.4771 | 17307.225 | 0 | 0 | 41297.75 | 265386.5118 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-11 | 1953138.3856 |  |  | 652064.4605 | 268806.3165 | 231194.4771 | 647481.1735 | 153591.958 | 0 | 15815.8 | 2567.5 | 0 | 0 | 75780.276 | 26188.5 | 0 | 0 | 0 | 0 | 0 | 12699.882 | 8216 | 12324 | 0 | 0 | 305026.575 | 652064.4605 | 0 | 26013.5145 | 157815.3213 | 24279.2802 | 60698.2005 | 0 | 231194.4771 | 17396.4375 | 0 | 0 | 41297.75 | 265560.411 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-12 | 1956379.9181 |  |  | 653822.8162 | 269637.5412 | 231194.4771 | 647744.2852 | 153980.7984 | 0 | 15855.84 | 2574 | 0 | 0 | 75972.1248 | 26254.8 | 0 | 0 | 0 | 0 | 0 | 12732.0336 | 8236.8 | 12355.2 | 0 | 0 | 305026.575 | 653822.8162 | 0 | 26093.9556 | 158303.3306 | 24354.3586 | 60885.8964 | 0 | 231194.4771 | 17485.65 | 0 | 0 | 41297.75 | 265734.3102 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-13 | 1959621.4505 |  |  | 655581.1719 | 270468.7659 | 231194.4771 | 648007.3968 | 154369.6388 | 0 | 15895.88 | 2580.5 | 0 | 0 | 76163.9736 | 26321.1 | 0 | 0 | 0 | 0 | 0 | 12764.1852 | 8257.6 | 12386.4 | 0 | 0 | 305026.575 | 655581.1719 | 0 | 26174.3967 | 158791.34 | 24429.4369 | 61073.5923 | 0 | 231194.4771 | 17574.8625 | 0 | 0 | 41297.75 | 265908.2093 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-14 | 1962862.983 |  |  | 657339.5276 | 271299.9906 | 231194.4771 | 648270.5085 | 154758.4792 | 0 | 15935.92 | 2587 | 0 | 0 | 76355.8224 | 26387.4 | 0 | 0 | 0 | 0 | 0 | 12796.3368 | 8278.4 | 12417.6 | 0 | 0 | 305026.575 | 657339.5276 | 0 | 26254.8378 | 159279.3493 | 24504.5153 | 61261.2882 | 0 | 231194.4771 | 17664.075 | 0 | 0 | 41297.75 | 266082.1085 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-15 | 1966104.5155 |  |  | 659097.8833 | 272131.2153 | 231194.4771 | 648533.6202 | 155147.3196 | 0 | 15975.96 | 2593.5 | 0 | 0 | 76547.6712 | 26453.7 | 0 | 0 | 0 | 0 | 0 | 12828.4884 | 8299.2 | 12448.8 | 0 | 0 | 305026.575 | 659097.8833 | 0 | 26335.2789 | 159767.3587 | 24579.5936 | 61448.9841 | 0 | 231194.4771 | 17753.2875 | 0 | 0 | 41297.75 | 266256.0077 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-16 | 1969346.0479 |  |  | 660856.239 | 272962.44 | 231194.4771 | 648796.7318 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 660856.239 | 0 | 26415.72 | 160255.368 | 24654.672 | 61636.68 | 0 | 231194.4771 | 17842.5 | 0 | 0 | 41297.75 | 266429.9068 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-18 | 1982846.1525 |  |  | 665023.8253 | 275131.0309 | 231484.2631 | 655670.8731 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 665023.8253 | 0 | 26625.5836 | 161528.5407 | 24850.5447 | 62126.3618 | 3057.2208 | 231484.2631 | 17842.5 | 0 | 0 | 43118.1932 | 267953.6568 | 13472.7273 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-19 | 1996346.257 |  |  | 669191.4116 | 277299.6218 | 231774.0492 | 662545.0144 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 669191.4116 | 0 | 26835.4473 | 162801.7135 | 25046.4175 | 62616.0436 | 6114.4417 | 231774.0492 | 17842.5 | 0 | 0 | 44938.6364 | 269477.4068 | 13945.4545 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-20 | 2009846.3616 |  |  | 673358.9979 | 279468.2127 | 232063.8352 | 669419.1557 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 673358.9979 | 0 | 27045.3109 | 164074.8862 | 25242.2902 | 63105.7255 | 9171.6625 | 232063.8352 | 17842.5 | 0 | 0 | 46759.0795 | 271001.1568 | 14418.1818 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-21 | 2023346.4661 |  |  | 677526.5843 | 281636.8036 | 232353.6212 | 676293.297 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 677526.5843 | 0 | 27255.1745 | 165348.0589 | 25438.1629 | 63595.4073 | 12228.8833 | 232353.6212 | 17842.5 | 0 | 0 | 48579.5227 | 272524.9068 | 14890.9091 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-22 | 2036846.5707 |  |  | 681694.1706 | 283805.3945 | 232643.4073 | 683167.4383 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 681694.1706 | 0 | 27465.0382 | 166621.2316 | 25634.0356 | 64085.0891 | 15286.1042 | 232643.4073 | 17842.5 | 0 | 0 | 50399.9659 | 274048.6568 | 15363.6364 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-23 | 2050346.6752 |  |  | 685861.7569 | 285973.9855 | 232933.1933 | 690041.5796 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 685861.7569 | 0 | 27674.9018 | 167894.4044 | 25829.9084 | 64574.7709 | 18343.325 | 232933.1933 | 17842.5 | 0 | 0 | 52220.4091 | 275572.4068 | 15836.3636 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-24 | 2063846.7798 |  |  | 690029.3432 | 288142.5764 | 233222.9794 | 696915.7209 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 690029.3432 | 0 | 27884.7655 | 169167.5771 | 26025.7811 | 65064.4527 | 21400.5458 | 233222.9794 | 17842.5 | 0 | 0 | 54040.8523 | 277096.1568 | 16309.0909 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-25 | 2077346.8844 |  |  | 694196.9295 | 290311.1673 | 233512.7654 | 703789.8621 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 694196.9295 | 0 | 28094.6291 | 170440.7498 | 26221.6538 | 65554.1345 | 24457.7667 | 233512.7654 | 17842.5 | 0 | 0 | 55861.2955 | 278619.9068 | 16781.8182 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-26 | 2090846.9889 |  |  | 698364.5158 | 292479.7582 | 233802.5515 | 710664.0034 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 698364.5158 | 0 | 28304.4927 | 171713.9225 | 26417.5265 | 66043.8164 | 27514.9875 | 233802.5515 | 17842.5 | 0 | 0 | 57681.7386 | 280143.6568 | 17254.5455 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-27 | 2104347.0935 |  |  | 702532.1021 | 294648.3491 | 234092.3375 | 717538.1447 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 702532.1021 | 0 | 28514.3564 | 172987.0953 | 26613.3993 | 66533.4982 | 30572.2083 | 234092.3375 | 17842.5 | 0 | 0 | 59502.1818 | 281667.4068 | 17727.2727 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-28 | 2117847.198 |  |  | 706699.6885 | 296816.94 | 234382.1235 | 724412.286 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 706699.6885 | 0 | 28724.22 | 174260.268 | 26809.272 | 67023.18 | 33629.4292 | 234382.1235 | 17842.5 | 0 | 0 | 61322.625 | 283191.1568 | 18200 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-29 | 2131347.3026 |  |  | 710867.2748 | 298985.5309 | 234671.9096 | 731286.4273 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 710867.2748 | 0 | 28934.0836 | 175533.4407 | 27005.1447 | 67512.8618 | 36686.65 | 234671.9096 | 17842.5 | 0 | 0 | 63143.0682 | 284714.9068 | 18672.7273 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-30 | 2144847.4071 |  |  | 715034.8611 | 301154.1218 | 234961.6956 | 738160.5686 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 715034.8611 | 0 | 29143.9473 | 176806.6135 | 27201.0175 | 68002.5436 | 39743.8708 | 234961.6956 | 17842.5 | 0 | 0 | 64963.5114 | 286238.6568 | 19145.4545 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-08-31 | 2158347.5117 |  |  | 719202.4474 | 303322.7127 | 235251.4817 | 745034.7099 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 719202.4474 | 0 | 29353.8109 | 178079.7862 | 27396.8902 | 68492.2255 | 42801.0917 | 235251.4817 | 17842.5 | 0 | 0 | 66783.9545 | 287762.4068 | 19618.1818 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-01 | 2171847.6162 |  |  | 723370.0337 | 305491.3036 | 235541.2677 | 751908.8512 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 723370.0337 | 0 | 29563.6745 | 179352.9589 | 27592.7629 | 68981.9073 | 45858.3125 | 235541.2677 | 17842.5 | 0 | 0 | 68604.3977 | 289286.1568 | 20090.9091 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-02 | 2185347.7208 |  |  | 727537.62 | 307659.8945 | 235831.0538 | 758782.9924 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 727537.62 | 0 | 29773.5382 | 180626.1316 | 27788.6356 | 69471.5891 | 48915.5333 | 235831.0538 | 17842.5 | 0 | 0 | 70424.8409 | 290809.9068 | 20563.6364 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-03 | 2198847.8253 |  |  | 731705.2064 | 309828.4855 | 236120.8398 | 765657.1337 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 731705.2064 | 0 | 29983.4018 | 181899.3044 | 27984.5084 | 69961.2709 | 51972.7542 | 236120.8398 | 17842.5 | 0 | 0 | 72245.2841 | 292333.6568 | 21036.3636 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-04 | 2212347.9299 |  |  | 735872.7927 | 311997.0764 | 236410.6258 | 772531.275 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 735872.7927 | 0 | 30193.2655 | 183172.4771 | 28180.3811 | 70450.9527 | 55029.975 | 236410.6258 | 17842.5 | 0 | 0 | 74065.7273 | 293857.4068 | 21509.0909 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-05 | 2225848.0345 |  |  | 740040.379 | 314165.6673 | 236700.4119 | 779405.4163 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 740040.379 | 0 | 30403.1291 | 184445.6498 | 28376.2538 | 70940.6345 | 58087.1958 | 236700.4119 | 17842.5 | 0 | 0 | 75886.1705 | 295381.1568 | 21981.8182 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-06 | 2239348.139 |  |  | 744207.9653 | 316334.2582 | 236990.1979 | 786279.5576 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 744207.9653 | 0 | 30612.9927 | 185718.8225 | 28572.1265 | 71430.3164 | 61144.4167 | 236990.1979 | 17842.5 | 0 | 0 | 77706.6136 | 296904.9068 | 22454.5455 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-07 | 2252848.2436 |  |  | 748375.5516 | 318502.8491 | 237279.984 | 793153.6989 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 748375.5516 | 0 | 30822.8564 | 186991.9953 | 28767.9993 | 71919.9982 | 64201.6375 | 237279.984 | 17842.5 | 0 | 0 | 79527.0568 | 298428.6568 | 22927.2727 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-08 | 2266348.3481 |  |  | 752543.1379 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 752543.1379 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-09 | 2267172.4508 |  |  | 753367.2406 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 753367.2406 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-10 | 2267996.5535 |  |  | 754191.3433 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 754191.3433 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-11 | 2268820.6562 |  |  | 755015.446 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 755015.446 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-12 | 2269644.7588 |  |  | 755839.5486 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 755839.5486 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-13 | 2270468.8615 |  |  | 756663.6513 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 756663.6513 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-14 | 2271292.9642 |  |  | 757487.754 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 757487.754 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-15 | 2272117.0669 |  |  | 758311.8567 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 758311.8567 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-16 | 2272941.1696 |  |  | 759135.9594 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 759135.9594 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-17 | 2273765.2722 |  |  | 759960.062 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 759960.062 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-18 | 2274589.3749 |  |  | 760784.1647 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 760784.1647 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-19 | 2275413.4776 |  |  | 761608.2674 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 761608.2674 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-20 | 2276237.5803 |  |  | 762432.3701 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 762432.3701 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-21 | 2277061.6829 |  |  | 763256.4728 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 763256.4728 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-22 | 2277885.7856 |  |  | 764080.5754 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 764080.5754 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-23 | 2278709.8883 |  |  | 764904.6781 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 764904.6781 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-24 | 2279533.991 |  |  | 765728.7808 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 765728.7808 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-25 | 2280358.0937 |  |  | 766552.8835 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 766552.8835 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-26 | 2281182.1963 |  |  | 767376.9861 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 767376.9861 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-27 | 2282006.299 |  |  | 768201.0888 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 768201.0888 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-28 | 2282830.4017 |  |  | 769025.1915 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 769025.1915 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-29 | 2283654.5044 |  |  | 769849.2942 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 769849.2942 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-09-30 | 2284478.6071 |  |  | 770673.3969 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 770673.3969 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-01 | 2285302.7097 |  |  | 771497.4995 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 771497.4995 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-02 | 2286126.8124 |  |  | 772321.6022 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 772321.6022 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-03 | 2286950.9151 |  |  | 773145.7049 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 773145.7049 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-04 | 2287775.0178 |  |  | 773969.8076 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 773969.8076 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-05 | 2288599.1204 |  |  | 774793.9103 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 774793.9103 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-06 | 2289423.2231 |  |  | 775618.0129 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 775618.0129 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-07 | 2290247.3258 |  |  | 776442.1156 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 776442.1156 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-08 | 2291071.4285 |  |  | 777266.2183 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 777266.2183 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-09 | 2291895.5312 |  |  | 778090.321 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 778090.321 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-10 | 2292719.6338 |  |  | 778914.4236 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 778914.4236 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-11 | 2293543.7365 |  |  | 779738.5263 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 779738.5263 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-12 | 2294367.8392 |  |  | 780562.629 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 780562.629 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Cost Sum
Date | Planned Total Cost (Cumulative) | Actual Total Cost (Cumulative) | Planned Labor (Cumulative) | Actual Labor (Cumulative) | Planned Travel&perdiem (Cumulative) | Actual Travel&perdiem (Cumulative) | Planned Parts&materials (Cumulative) | Actual Parts&materials (Cumulative) | Planned Outsource (Cumulative) | Actual Outsource (Cumulative) | Planned Equipment (Cumulative) | Actual Equipment (Cumulative) | Planned Total Cost (Daily) | Actual Total Cost (Daily) | Planned Labor (Daily) | Actual Labor (Daily) | Planned Travel&perdiem (Daily) | Actual Travel&perdiem (Daily) | Planned Parts&materials (Daily) | Actual Parts&materials (Daily) | Planned Outsource (Daily) | Actual Outsource (Daily) | Planned Equipment (Daily) | Actual Equipment (Daily)
2025-04-01 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-02 | 2593.9167 | 0 | 2593.9167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 3890.875 | 0 | 3890.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 5187.8333 | 0 | 5187.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 6484.7917 | 0 | 6484.7917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 7781.75 | 0 | 7781.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 9078.7083 | 2614.5 | 9078.7083 | 2614.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 2614.5 | 1296.9583 | 2614.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 10375.6667 | 5229 | 10375.6667 | 5229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 2614.5 | 1296.9583 | 2614.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 11672.625 | 7843.5 | 11672.625 | 7843.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 2614.5 | 1296.9583 | 2614.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 12969.5833 | 10458 | 12969.5833 | 10458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 2614.5 | 1296.9583 | 2614.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 14266.5417 | 13072.5 | 14266.5417 | 13072.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 2614.5 | 1296.9583 | 2614.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 15563.5 | 13072.5 | 15563.5 | 13072.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 16860.4583 | 13072.5 | 16860.4583 | 13072.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 18157.4167 | 13340.5 | 18157.4167 | 13340.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 268 | 1296.9583 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 19454.375 | 13608.5 | 19454.375 | 13608.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 268 | 1296.9583 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 20751.3333 | 13910.22 | 20751.3333 | 13876.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 301.72 | 1296.9583 | 268 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0
2025-04-17 | 22048.2917 | 14178.22 | 22048.2917 | 14144.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 268 | 1296.9583 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 23345.25 | 14446.22 | 23345.25 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 268 | 1296.9583 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 24642.2083 | 14446.22 | 24642.2083 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 25939.1667 | 14446.22 | 25939.1667 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 27236.125 | 14446.22 | 27236.125 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 28533.0833 | 14446.22 | 28533.0833 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 29830.0417 | 14446.22 | 29830.0417 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 31127 | 14446.22 | 31127 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 32423.9583 | 14446.22 | 32423.9583 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 33720.9167 | 14446.22 | 33720.9167 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 35017.875 | 14446.22 | 35017.875 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 36314.8333 | 14446.22 | 36314.8333 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 37611.7917 | 14446.22 | 37611.7917 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 38908.75 | 14446.22 | 38908.75 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 40205.7083 | 14446.22 | 40205.7083 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 41502.6667 | 14446.22 | 41502.6667 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 42799.625 | 14446.22 | 42799.625 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 44096.5833 | 14446.22 | 44096.5833 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 45393.5417 | 14446.22 | 45393.5417 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 46690.5 | 14446.22 | 46690.5 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 47987.4583 | 14446.22 | 47987.4583 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 49284.4167 | 14446.22 | 49284.4167 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 50581.375 | 14446.22 | 50581.375 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 51878.3333 | 14446.22 | 51878.3333 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 53175.2917 | 14446.22 | 53175.2917 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 54472.25 | 14446.22 | 54472.25 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 55769.2083 | 14446.22 | 55769.2083 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 57066.1667 | 14446.22 | 57066.1667 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 58363.125 | 14446.22 | 58363.125 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 59660.0833 | 14446.22 | 59660.0833 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 60957.0417 | 14446.22 | 60957.0417 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 62254 | 14446.22 | 62254 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 63550.9583 | 15123.17 | 63550.9583 | 15089.45 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 676.95 | 1296.9583 | 676.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 64847.9167 | 15800.12 | 64847.9167 | 15766.4 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 676.95 | 1296.9583 | 676.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 66144.875 | 16477.07 | 66144.875 | 16443.35 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 676.95 | 1296.9583 | 676.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 67441.8333 | 17154.02 | 67441.8333 | 17120.3 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 676.95 | 1296.9583 | 676.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 68738.7917 | 17830.97 | 68738.7917 | 17797.25 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 676.95 | 1296.9583 | 676.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 70035.75 | 17830.97 | 70035.75 | 17797.25 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 71332.7083 | 17830.97 | 71332.7083 | 17797.25 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 72629.6667 | 17830.97 | 72629.6667 | 17797.25 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 73926.625 | 17830.97 | 73926.625 | 17797.25 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 75223.5833 | 17830.97 | 75223.5833 | 17797.25 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 76520.5417 | 17830.97 | 76520.5417 | 17797.25 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 77817.5 | 17830.97 | 77817.5 | 17797.25 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 82127.8205 | 17830.97 | 77938.5843 | 17797.25 | 80.6747 | 0 | 1261.7398 | 33.72 | 1405.3373 | 0 | 1441.4843 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-02 | 86438.141 | 17830.97 | 78059.6687 | 17797.25 | 161.3494 | 0 | 2523.4795 | 33.72 | 2810.6747 | 0 | 2882.9687 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-03 | 90748.4614 | 17830.97 | 78180.753 | 17797.25 | 242.0241 | 0 | 3785.2193 | 33.72 | 4216.012 | 0 | 4324.453 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-04 | 95058.7819 | 17850.89 | 78301.8373 | 17797.25 | 322.6988 | 0 | 5046.959 | 53.64 | 5621.3494 | 0 | 5765.9373 | 0 | 4310.3205 | 19.92 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 19.92 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-05 | 99369.1024 | 43489.57 | 78422.9217 | 17797.25 | 403.3735 | 0 | 6308.6988 | 25692.32 | 7026.6867 | 0 | 7207.4217 | 0 | 4310.3205 | 25638.68 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 25638.68 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-06 | 103679.4229 | 43489.57 | 78544.006 | 17797.25 | 484.0482 | 0 | 7570.4386 | 25692.32 | 8432.0241 | 0 | 8648.906 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-07 | 107989.7434 | 43489.57 | 78665.0904 | 17797.25 | 564.7229 | 0 | 8832.1783 | 25692.32 | 9837.3614 | 0 | 10090.3904 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-08 | 112300.0639 | 43489.57 | 78786.1747 | 17797.25 | 645.3976 | 0 | 10093.9181 | 25692.32 | 11242.6988 | 0 | 11531.8747 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-09 | 116610.3843 | 43925.32 | 78907.259 | 18233 | 726.0723 | 0 | 11355.6578 | 25692.32 | 12648.0361 | 0 | 12973.359 | 0 | 4310.3205 | 435.75 | 121.0843 | 435.75 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-10 | 120920.7048 | 44361.07 | 79028.3434 | 18668.75 | 806.747 | 0 | 12617.3976 | 25692.32 | 14053.3735 | 0 | 14414.8434 | 0 | 4310.3205 | 435.75 | 121.0843 | 435.75 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-11 | 125231.0253 | 44796.82 | 79149.4277 | 19104.5 | 887.4217 | 0 | 13879.1373 | 25692.32 | 15458.7108 | 0 | 15856.3277 | 0 | 4310.3205 | 435.75 | 121.0843 | 435.75 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-12 | 129541.3458 | 45232.57 | 79270.512 | 19540.25 | 968.0964 | 0 | 15140.8771 | 25692.32 | 16864.0482 | 0 | 17297.812 | 0 | 4310.3205 | 435.75 | 121.0843 | 435.75 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-13 | 133851.6663 | 45668.32 | 79391.5964 | 19976 | 1048.7711 | 0 | 16402.6169 | 25692.32 | 18269.3855 | 0 | 18739.2964 | 0 | 4310.3205 | 435.75 | 121.0843 | 435.75 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-14 | 138161.9867 | 45668.32 | 79512.6807 | 19976 | 1129.4458 | 0 | 17664.3566 | 25692.32 | 19674.7229 | 0 | 20180.7807 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-15 | 142472.3072 | 45668.32 | 79633.7651 | 19976 | 1210.1205 | 0 | 18926.0964 | 25692.32 | 21080.0602 | 0 | 21622.2651 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-16 | 146782.6277 | 45936.32 | 79754.8494 | 20244 | 1290.7952 | 0 | 20187.8361 | 25692.32 | 22485.3976 | 0 | 23063.7494 | 0 | 4310.3205 | 268 | 121.0843 | 268 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-17 | 151092.9482 | 46204.32 | 79875.9337 | 20512 | 1371.4699 | 0 | 21449.5759 | 25692.32 | 23890.7349 | 0 | 24505.2337 | 0 | 4310.3205 | 268 | 121.0843 | 268 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-18 | 155403.2687 | 46472.32 | 79997.0181 | 20780 | 1452.1446 | 0 | 22711.3157 | 25692.32 | 25296.0723 | 0 | 25946.7181 | 0 | 4310.3205 | 268 | 121.0843 | 268 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-19 | 159713.5892 | 46740.32 | 80118.1024 | 21048 | 1532.8193 | 0 | 23973.0554 | 25692.32 | 26701.4096 | 0 | 27388.2024 | 0 | 4310.3205 | 268 | 121.0843 | 268 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-20 | 164023.9096 | 47590.82 | 80239.1867 | 21316 | 1613.494 | 0 | 25234.7952 | 25692.32 | 28106.747 | 582.5 | 28829.6867 | 0 | 4310.3205 | 850.5 | 121.0843 | 268 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 582.5 | 1441.4843 | 0
2025-06-21 | 168334.2301 | 47590.82 | 80360.2711 | 21316 | 1694.1687 | 0 | 26496.5349 | 25692.32 | 29512.0843 | 582.5 | 30271.1711 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-22 | 172644.5506 | 47590.82 | 80481.3554 | 21316 | 1774.8434 | 0 | 27758.2747 | 25692.32 | 30917.4217 | 582.5 | 31712.6554 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-23 | 176954.8711 | 47590.82 | 80602.4398 | 21316 | 1855.5181 | 0 | 29020.0145 | 25692.32 | 32322.759 | 582.5 | 33154.1398 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-24 | 181265.1916 | 48517.68 | 80723.5241 | 21316 | 1936.1928 | 679.86 | 30281.7542 | 25939.32 | 33728.0964 | 582.5 | 34595.6241 | 0 | 4310.3205 | 926.86 | 121.0843 | 0 | 80.6747 | 679.86 | 1261.7398 | 247 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-25 | 185575.512 | 48906.08 | 80844.6084 | 21316 | 2016.8675 | 679.86 | 31543.494 | 26327.72 | 35133.4337 | 582.5 | 36037.1084 | 0 | 4310.3205 | 388.4 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 388.4 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-26 | 189885.8325 | 48906.08 | 80965.6928 | 21316 | 2097.5422 | 679.86 | 32805.2337 | 26327.72 | 36538.7711 | 582.5 | 37478.5928 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-27 | 194196.153 | 48906.08 | 81086.7771 | 21316 | 2178.2169 | 679.86 | 34066.9735 | 26327.72 | 37944.1084 | 582.5 | 38920.0771 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-28 | 198506.4735 | 49018.35 | 81207.8614 | 21316 | 2258.8916 | 792.13 | 35328.7133 | 26327.72 | 39349.4458 | 582.5 | 40361.5614 | 0 | 4310.3205 | 112.27 | 121.0843 | 0 | 80.6747 | 112.27 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-29 | 202816.794 | 49167.1 | 81328.9458 | 21316 | 2339.5663 | 940.88 | 36590.453 | 26327.72 | 40754.7831 | 582.5 | 41803.0458 | 0 | 4310.3205 | 148.75 | 121.0843 | 0 | 80.6747 | 148.75 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-30 | 207127.1145 | 50151.03 | 81450.0301 | 22180.55 | 2420.241 | 1060.26 | 37852.1928 | 26327.72 | 42160.1205 | 582.5 | 43244.5301 | 0 | 4310.3205 | 983.93 | 121.0843 | 864.55 | 80.6747 | 119.38 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-01 | 211437.4349 | 89726.4 | 81571.1145 | 23045.1 | 2500.9157 | 1060.26 | 39113.9325 | 65038.54 | 43565.4578 | 582.5 | 44686.0145 | 0 | 4310.3205 | 39575.37 | 121.0843 | 864.55 | 80.6747 | 0 | 1261.7398 | 38710.82 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-02 | 215747.7554 | 91045.1 | 81692.1988 | 23909.65 | 2581.5904 | 1060.26 | 40375.6723 | 65038.54 | 44970.7952 | 1036.65 | 46127.4988 | 0 | 4310.3205 | 1318.7 | 121.0843 | 864.55 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 454.15 | 1441.4843 | 0
2025-07-03 | 220058.0759 | 91992.23 | 81813.2831 | 24774.2 | 2662.2651 | 1060.26 | 41637.412 | 65121.12 | 46376.1325 | 1036.65 | 47568.9831 | 0 | 4310.3205 | 947.13 | 121.0843 | 864.55 | 80.6747 | 0 | 1261.7398 | 82.58 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-04 | 224368.3964 | 93593.4 | 81934.3675 | 25638.75 | 2742.9398 | 1060.26 | 42899.1518 | 65407.74 | 47781.4699 | 1486.65 | 49010.4675 | 0 | 4310.3205 | 1601.17 | 121.0843 | 864.55 | 80.6747 | 0 | 1261.7398 | 286.62 | 1405.3373 | 450 | 1441.4843 | 0
2025-07-05 | 228678.7169 | 93643.65 | 82055.4518 | 25638.75 | 2823.6145 | 1060.26 | 44160.8916 | 65457.99 | 49186.8072 | 1486.65 | 50451.9518 | 0 | 4310.3205 | 50.25 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 50.25 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-06 | 232989.0373 | 93643.65 | 82176.5361 | 25638.75 | 2904.2892 | 1060.26 | 45422.6313 | 65457.99 | 50592.1446 | 1486.65 | 51893.4361 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-07 | 237299.3578 | 94545.75 | 82297.6205 | 26359.75 | 2984.9639 | 1241.36 | 46684.3711 | 65457.99 | 51997.4819 | 1486.65 | 53334.9205 | 0 | 4310.3205 | 902.1 | 121.0843 | 721 | 80.6747 | 181.1 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-08 | 241609.6783 | 96428.08 | 82418.7048 | 27080.75 | 3065.6386 | 1741.36 | 47946.1108 | 66119.32 | 53402.8193 | 1486.65 | 54776.4048 | 0 | 4310.3205 | 1882.33 | 121.0843 | 721 | 80.6747 | 500 | 1261.7398 | 661.33 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-09 | 245919.9988 | 97241.78 | 82539.7892 | 27801.75 | 3146.3133 | 1741.36 | 49207.8506 | 66119.32 | 54808.1566 | 1579.35 | 56217.8892 | 0 | 4310.3205 | 813.7 | 121.0843 | 721 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 92.7 | 1441.4843 | 0
2025-07-10 | 250230.3193 | 98020.67 | 82660.8735 | 28522.75 | 3226.988 | 1799.25 | 50469.5904 | 66119.32 | 56213.494 | 1579.35 | 57659.3735 | 0 | 4310.3205 | 778.89 | 121.0843 | 721 | 80.6747 | 57.89 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-11 | 254540.6398 | 100630.9 | 82781.9578 | 29243.75 | 3307.6627 | 2100.37 | 51731.3301 | 67449.13 | 57618.8313 | 1837.65 | 59100.8578 | 0 | 4310.3205 | 2610.23 | 121.0843 | 721 | 80.6747 | 301.12 | 1261.7398 | 1329.81 | 1405.3373 | 258.3 | 1441.4843 | 0
2025-07-12 | 258850.9602 | 101065.02 | 82903.0422 | 29243.75 | 3388.3373 | 2534.49 | 52993.0699 | 67449.13 | 59024.1687 | 1837.65 | 60542.3422 | 0 | 4310.3205 | 434.12 | 121.0843 | 0 | 80.6747 | 434.12 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-13 | 263161.2807 | 106212.83 | 83024.1265 | 29243.75 | 3469.012 | 7516.12 | 54254.8096 | 67449.13 | 60429.506 | 2003.83 | 61983.8265 | 0 | 4310.3205 | 5147.81 | 121.0843 | 0 | 80.6747 | 4981.63 | 1261.7398 | 0 | 1405.3373 | 166.18 | 1441.4843 | 0
2025-07-14 | 267471.6012 | 118057.76 | 83145.2108 | 30919.15 | 3549.6867 | 12432.37 | 55516.5494 | 72702.41 | 61834.8434 | 2003.83 | 63425.3108 | 0 | 4310.3205 | 11844.93 | 121.0843 | 1675.4 | 80.6747 | 4916.25 | 1261.7398 | 5253.28 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-15 | 271781.9217 | 123809.72 | 83266.2952 | 32594.55 | 3630.3614 | 14964.72 | 56778.2892 | 74124.67 | 63240.1807 | 2125.78 | 64866.7952 | 0 | 4310.3205 | 5751.96 | 121.0843 | 1675.4 | 80.6747 | 2532.35 | 1261.7398 | 1422.26 | 1405.3373 | 121.95 | 1441.4843 | 0
2025-07-16 | 276092.2422 | 132952.67 | 83387.3795 | 34269.95 | 3711.0361 | 15314.72 | 58040.0289 | 74942.22 | 64645.5181 | 8425.78 | 66308.2795 | 0 | 4310.3205 | 9142.95 | 121.0843 | 1675.4 | 80.6747 | 350 | 1261.7398 | 817.55 | 1405.3373 | 6300 | 1441.4843 | 0
2025-07-17 | 280402.5627 | 135204.38 | 83508.4639 | 35945.35 | 3791.7108 | 15589.91 | 59301.7687 | 75243.34 | 66050.8554 | 8688.27 | 67749.7639 | 0 | 4310.3205 | 2251.71 | 121.0843 | 1675.4 | 80.6747 | 275.19 | 1261.7398 | 301.12 | 1405.3373 | 262.49 | 1441.4843 | 0
2025-07-18 | 284712.8831 | 145421.51 | 83629.5482 | 37620.75 | 3872.3855 | 17749.91 | 60563.5084 | 81175.07 | 67456.1928 | 9179.36 | 69191.2482 | 0 | 4310.3205 | 10217.13 | 121.0843 | 1675.4 | 80.6747 | 2160 | 1261.7398 | 5931.73 | 1405.3373 | 491.09 | 1441.4843 | 0
2025-07-19 | 289023.2036 | 146256.5 | 83750.6325 | 37620.75 | 3953.0602 | 17793.21 | 61825.2482 | 81966.76 | 68861.5301 | 9179.36 | 70632.7325 | 0 | 4310.3205 | 834.99 | 121.0843 | 0 | 80.6747 | 43.3 | 1261.7398 | 791.69 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-20 | 293333.5241 | 146256.5 | 83871.7169 | 37620.75 | 4033.7349 | 17793.21 | 63086.988 | 81966.76 | 70266.8675 | 9179.36 | 72074.2169 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-21 | 309238.0738 | 149275.9 | 85072.9989 | 39350.15 | 4659.4329 | 19083.21 | 65426.4488 | 81966.76 | 80563.492 | 9179.36 | 73515.7012 | 0 | 15904.5497 | 3019.4 | 1201.282 | 1729.4 | 625.698 | 1290 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-07-22 | 325142.6235 | 166695.05 | 86274.2809 | 41079.55 | 5285.1308 | 19370.03 | 67765.9096 | 97369.69 | 90860.1166 | 9179.36 | 74957.1855 | 0 | 15904.5497 | 17419.15 | 1201.282 | 1729.4 | 625.698 | 286.82 | 2339.4608 | 15402.93 | 10296.6246 | 0 | 1441.4843 | 0
2025-07-23 | 341047.1732 | 171297.37 | 87475.5629 | 42808.95 | 5910.8288 | 19370.03 | 70105.3704 | 100242.61 | 101156.7412 | 9179.36 | 76398.6699 | 0 | 15904.5497 | 4602.32 | 1201.282 | 1729.4 | 625.698 | 0 | 2339.4608 | 2872.92 | 10296.6246 | 0 | 1441.4843 | 0
2025-07-24 | 356951.7228 | 173341.15 | 88676.8449 | 44538.35 | 6536.5268 | 19489.92 | 72444.8312 | 100437.1 | 111453.3657 | 9239.36 | 77840.1542 | 0 | 15904.5497 | 2043.78 | 1201.282 | 1729.4 | 625.698 | 119.89 | 2339.4608 | 194.49 | 10296.6246 | 60 | 1441.4843 | 0
2025-07-25 | 372856.2725 | 176585.32 | 89878.1269 | 46267.75 | 7162.2247 | 20639.92 | 74784.292 | 100801.87 | 121749.9903 | 9239.36 | 79281.6386 | 0 | 15904.5497 | 3244.17 | 1201.282 | 1729.4 | 625.698 | 1150 | 2339.4608 | 364.77 | 10296.6246 | 0 | 1441.4843 | 0
2025-07-26 | 388760.8222 | 176601.45 | 91079.4089 | 46267.75 | 7787.9227 | 20639.92 | 77123.7528 | 100818 | 132046.6149 | 9253.98 | 80723.1229 | 0 | 15904.5497 | 16.13 | 1201.282 | 0 | 625.698 | 0 | 2339.4608 | 16.13 | 10296.6246 | 14.62 | 1441.4843 | 0
2025-07-27 | 404665.3719 | 176693.89 | 92280.6909 | 46267.75 | 8413.6206 | 20732.36 | 79463.2137 | 100818 | 142343.2394 | 9253.98 | 82164.6072 | 0 | 15904.5497 | 92.44 | 1201.282 | 0 | 625.698 | 92.44 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-07-28 | 420569.9216 | 178691.69 | 93481.973 | 48265.55 | 9039.3186 | 20732.36 | 81802.6745 | 100818 | 152639.864 | 9253.98 | 83606.0916 | 0 | 15904.5497 | 1997.8 | 1201.282 | 1997.8 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-07-29 | 436474.4713 | 180749.49 | 94683.255 | 50263.35 | 9665.0165 | 20792.36 | 84142.1353 | 100818 | 162936.4886 | 9253.98 | 85047.5759 | 0 | 15904.5497 | 2057.8 | 1201.282 | 1997.8 | 625.698 | 60 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-07-30 | 452379.021 | 189839.53 | 95884.537 | 52261.15 | 10290.7145 | 20792.36 | 86481.5961 | 102239.06 | 173233.1131 | 14925.16 | 86489.0602 | 0 | 15904.5497 | 9090.04 | 1201.282 | 1997.8 | 625.698 | 0 | 2339.4608 | 1421.06 | 10296.6246 | 5671.18 | 1441.4843 | 0
2025-07-31 | 468283.5707 | 218199.31 | 97085.819 | 54258.95 | 10916.4124 | 21213.52 | 88821.0569 | 102534.46 | 183529.7377 | 40570.58 | 87930.5446 | 0 | 15904.5497 | 28359.78 | 1201.282 | 1997.8 | 625.698 | 421.16 | 2339.4608 | 295.4 | 10296.6246 | 25645.42 | 1441.4843 | 0
2025-08-01 | 484188.1203 | 227567.29 | 98287.101 | 56256.75 | 11542.1104 | 24073.89 | 91160.5177 | 106898.67 | 193826.3623 | 40716.18 | 89372.0289 | 0 | 15904.5497 | 9367.98 | 1201.282 | 1997.8 | 625.698 | 2860.37 | 2339.4608 | 4364.21 | 10296.6246 | 145.6 | 1441.4843 | 0
2025-08-02 | 500092.67 | 228643.89 | 99488.383 | 56256.75 | 12167.8083 | 25150.49 | 93499.9786 | 106898.67 | 204122.9868 | 40716.18 | 90813.5133 | 0 | 15904.5497 | 1076.6 | 1201.282 | 0 | 625.698 | 1076.6 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-03 | 515997.2197 | 230675.44 | 100689.665 | 56256.75 | 12793.5063 | 27182.04 | 95839.4394 | 106898.67 | 214419.6114 | 40716.18 | 92254.9976 | 0 | 15904.5497 | 2031.55 | 1201.282 | 0 | 625.698 | 2031.55 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-04 | 531901.7694 | 232754.79 | 101890.947 | 58253.75 | 13419.2043 | 27182.04 | 98178.9002 | 106981.02 | 224716.236 | 40716.18 | 93696.4819 | 0 | 15904.5497 | 2079.35 | 1201.282 | 1997 | 625.698 | 0 | 2339.4608 | 82.35 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-05 | 547806.3191 | 237856.02 | 103092.2291 | 60250.75 | 14044.9022 | 27182.04 | 100518.361 | 106981.02 | 235012.8605 | 43820.41 | 95137.9663 | 0 | 15904.5497 | 5101.23 | 1201.282 | 1997 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 3104.23 | 1441.4843 | 0
2025-08-06 | 563710.8688 | 244760.46 | 104293.5111 | 62247.75 | 14670.6002 | 27182.04 | 102857.8218 | 106981.02 | 245309.4851 | 48727.85 | 96579.4506 | 0 | 15904.5497 | 6904.44 | 1201.282 | 1997 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 4907.44 | 1441.4843 | 0
2025-08-07 | 579615.4185 | 246757.46 | 105494.7931 | 64244.75 | 15296.2981 | 27182.04 | 105197.2826 | 106981.02 | 255606.1097 | 48727.85 | 98020.9349 | 0 | 15904.5497 | 1997 | 1201.282 | 1997 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-08 | 595519.9681 | 250504.46 | 106696.0751 | 66241.75 | 15921.9961 | 28932.04 | 107536.7435 | 106981.02 | 265902.7343 | 48727.85 | 99462.4193 | 0 | 15904.5497 | 3747 | 1201.282 | 1997 | 625.698 | 1750 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-09 | 611424.5178 | 250504.46 | 107897.3571 | 66241.75 | 16547.694 | 28932.04 | 109876.2043 | 106981.02 | 276199.3588 | 48727.85 | 100903.9036 | 0 | 15904.5497 | 0 | 1201.282 | 0 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-10 | 627329.0675 | 251427.94 | 109098.6391 | 66241.75 | 17173.392 | 29855.52 | 112215.6651 | 106981.02 | 286495.9834 | 48727.85 | 102345.388 | 0 | 15904.5497 | 923.48 | 1201.282 | 0 | 625.698 | 923.48 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-11 | 643233.6172 | 254941.84 | 110299.9211 | 68909.75 | 17799.0899 | 30701.42 | 114555.1259 | 106981.02 | 296792.608 | 48727.85 | 103786.8723 | 0 | 15904.5497 | 3513.9 | 1201.282 | 2668 | 625.698 | 845.9 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-12 | 659138.1669 | 259317.46 | 111501.2031 | 71577.75 | 18424.7879 | 30701.42 | 116894.5867 | 106981.02 | 307089.2325 | 50435.47 | 105228.3566 | 0 | 15904.5497 | 4375.62 | 1201.282 | 2668 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 1707.62 | 1441.4843 | 0
2025-08-13 | 675042.7166 | 261985.46 | 112702.4851 | 74245.75 | 19050.4859 | 30701.42 | 119234.0475 | 106981.02 | 317385.8571 | 50435.47 | 106669.841 | 0 | 15904.5497 | 2668 | 1201.282 | 2668 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-14 | 690947.2663 | 266065.41 | 113903.7672 | 76913.75 | 19676.1838 | 30701.42 | 121573.5083 | 107092.97 | 327682.4817 | 51735.47 | 108111.3253 | 0 | 15904.5497 | 4079.95 | 1201.282 | 2668 | 625.698 | 0 | 2339.4608 | 111.95 | 10296.6246 | 1300 | 1441.4843 | 0
2025-08-15 | 706851.816 | 271662.32 | 115105.0492 | 79581.75 | 20301.8818 | 32451.42 | 123912.9692 | 107175.96 | 337979.1062 | 52831.39 | 109552.8096 | 0 | 15904.5497 | 5596.91 | 1201.282 | 2668 | 625.698 | 1750 | 2339.4608 | 82.99 | 10296.6246 | 1095.92 | 1441.4843 | 0
2025-08-16 | 722756.3656 | 272892.72 | 116306.3312 | 79581.75 | 20927.5797 | 33681.82 | 126252.43 | 107175.96 | 348275.7308 | 52831.39 | 110994.294 | 0 | 15904.5497 | 1230.4 | 1201.282 | 0 | 625.698 | 1230.4 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-17 | 738660.9153 | 273969.32 | 117507.6132 | 79581.75 | 21553.2777 | 34758.42 | 128591.8908 | 107175.96 | 358572.3554 | 52831.39 | 112435.7783 | 0 | 15904.5497 | 1076.6 | 1201.282 | 0 | 625.698 | 1076.6 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-18 | 754565.465 | 276637.32 | 118708.8952 | 82249.75 | 22178.9756 | 34758.42 | 130931.3516 | 107175.96 | 368868.9799 | 52831.39 | 113877.2627 | 0 | 15904.5497 | 2668 | 1201.282 | 2668 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-19 | 770470.0147 | 281864.38 | 119910.1772 | 84917.75 | 22804.6736 | 34758.42 | 133270.8124 | 109735.02 | 379165.6045 | 52831.39 | 115318.747 | 0 | 15904.5497 | 5227.06 | 1201.282 | 2668 | 625.698 | 0 | 2339.4608 | 2559.06 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-20 | 786374.5644 | 288723.17 | 121111.4592 | 87585.75 | 23430.3715 | 35142.92 | 135610.2732 | 109735.02 | 389462.2291 | 56637.68 | 116760.2313 | 0 | 15904.5497 | 6858.79 | 1201.282 | 2668 | 625.698 | 384.5 | 2339.4608 | 0 | 10296.6246 | 3806.29 | 1441.4843 | 0
2025-08-21 | 802279.1141 | 294774.36 | 122312.7412 | 90253.75 | 24056.0695 | 35142.92 | 137949.7341 | 113118.21 | 399758.8536 | 56637.68 | 118201.7157 | 0 | 15904.5497 | 6051.19 | 1201.282 | 2668 | 625.698 | 0 | 2339.4608 | 3383.19 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-22 | 818183.6638 | 312532.85 | 123514.0233 | 92921.75 | 24681.7674 | 37300.22 | 140289.1949 | 126051.4 | 410055.4782 | 56637.68 | 119643.2 | 0 | 15904.5497 | 17758.49 | 1201.282 | 2668 | 625.698 | 2157.3 | 2339.4608 | 12933.19 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-23 | 829777.893 | 312532.85 | 124594.2209 | 92921.75 | 25226.7907 | 37300.22 | 141366.9159 | 126051.4 | 418946.7654 | 56637.68 | 119643.2 | 0 | 11594.2292 | 0 | 1080.1977 | 0 | 545.0233 | 0 | 1077.7211 | 0 | 8891.2872 | 0 | 0 | 0
2025-08-24 | 841372.1222 | 313882.51 | 125674.4186 | 92921.75 | 25771.814 | 38649.88 | 142444.637 | 126051.4 | 427838.0526 | 56637.68 | 119643.2 | 0 | 11594.2292 | 1349.66 | 1080.1977 | 0 | 545.0233 | 1349.66 | 1077.7211 | 0 | 8891.2872 | 0 | 0 | 0
2025-08-25 | 852966.3514 | 381334.84 | 126754.6163 | 95147.35 | 26316.8372 | 42648.87 | 143522.358 | 127036.64 | 436729.3398 | 116880.18 | 119643.2 | 0 | 11594.2292 | 67452.33 | 1080.1977 | 2225.6 | 545.0233 | 3998.99 | 1077.7211 | 985.24 | 8891.2872 | 60242.5 | 0 | 0
2025-08-26 | 864560.5806 | 391692.13 | 127834.814 | 97372.95 | 26861.8605 | 42648.87 | 144600.0791 | 135168.33 | 445620.6271 | 116880.18 | 119643.2 | 0 | 11594.2292 | 10357.29 | 1080.1977 | 2225.6 | 545.0233 | 0 | 1077.7211 | 8131.69 | 8891.2872 | 0 | 0 | 0
2025-08-27 | 876154.8098 | 402697.58 | 128915.0116 | 99598.55 | 27406.8837 | 43034.05 | 145677.8002 | 135883.46 | 454511.9143 | 124559.72 | 119643.2 | 0 | 11594.2292 | 11005.45 | 1080.1977 | 2225.6 | 545.0233 | 385.18 | 1077.7211 | 715.13 | 8891.2872 | 7679.54 | 0 | 0
2025-08-28 | 887749.039 | 404923.18 | 129995.2093 | 101824.15 | 27951.907 | 43034.05 | 146755.5212 | 135883.46 | 463403.2015 | 124559.72 | 119643.2 | 0 | 11594.2292 | 2225.6 | 1080.1977 | 2225.6 | 545.0233 | 0 | 1077.7211 | 0 | 8891.2872 | 0 | 0 | 0
2025-08-29 | 899343.2682 | 410371.01 | 131075.407 | 104049.75 | 28496.9302 | 43384.05 | 147833.2423 | 136177.01 | 472294.4887 | 127138.4 | 119643.2 | 0 | 11594.2292 | 5447.83 | 1080.1977 | 2225.6 | 545.0233 | 350 | 1077.7211 | 293.55 | 8891.2872 | 2578.68 | 0 | 0
2025-08-30 | 910937.4974 | 411140.01 | 132155.6047 | 104049.75 | 29041.9535 | 44153.05 | 148910.9633 | 136177.01 | 481185.7759 | 127138.4 | 119643.2 | 0 | 11594.2292 | 769 | 1080.1977 | 0 | 545.0233 | 769 | 1077.7211 | 0 | 8891.2872 | 0 | 0 | 0
2025-08-31 | 922531.7266 | 427226.88 | 133235.8023 | 104049.75 | 29586.9767 | 44153.05 | 149988.6844 | 137459.01 | 490077.0632 | 141943.27 | 119643.2 | 0 | 11594.2292 | 16086.87 | 1080.1977 | 0 | 545.0233 | 0 | 1077.7211 | 1282 | 8891.2872 | 14804.87 | 0 | 0
2025-09-01 | 934125.9558 | 428767.68 | 134316 | 105282.95 | 30132 | 44460.65 | 151066.4054 | 137459.01 | 498968.3504 | 141943.27 | 119643.2 | 0 | 11594.2292 | 1540.8 | 1080.1977 | 1233.2 | 545.0233 | 307.6 | 1077.7211 | 0 | 8891.2872 | 0 | 0 | 0
2025-09-02 | 935589.1068 | 432954.08 | 134951.6376 | 106516.15 | 30502.7517 | 44460.65 | 151246.1068 | 137739.18 | 499245.4108 | 144616.3 | 119643.2 | 0 | 1463.151 | 4186.4 | 635.6376 | 1233.2 | 370.7517 | 0 | 179.7013 | 280.17 | 277.0604 | 2673.03 | 0 | 0
2025-09-03 | 937052.2578 | 691873.4 | 135587.2752 | 107749.35 | 30873.5034 | 44530.65 | 151425.8081 | 141922.8 | 499522.4711 | 398048.8 | 119643.2 | 0 | 1463.151 | 258919.32 | 635.6376 | 1233.2 | 370.7517 | 70 | 179.7013 | 4183.62 | 277.0604 | 253432.5 | 0 | 0
2025-09-04 | 938515.4088 | 693113.59 | 136222.9128 | 108982.55 | 31244.255 | 44530.65 | 151605.5095 | 141929.79 | 499799.5315 | 398048.8 | 119643.2 | 0 | 1463.151 | 1240.19 | 635.6376 | 1233.2 | 370.7517 | 0 | 179.7013 | 6.99 | 277.0604 | 0 | 0 | 0
2025-09-05 | 939978.5597 | 699447.63 | 136858.5503 | 110215.75 | 31615.0067 | 47076.82 | 151785.2108 | 141929.79 | 500076.5919 | 400603.47 | 119643.2 | 0 | 1463.151 | 6334.04 | 635.6376 | 1233.2 | 370.7517 | 2546.17 | 179.7013 | 0 | 277.0604 | 2554.67 | 0 | 0
2025-09-06 | 941441.7107 | 700697.63 | 137494.1879 | 110215.75 | 31985.7584 | 48326.82 | 151964.9122 | 141929.79 | 500353.6523 | 400603.47 | 119643.2 | 0 | 1463.151 | 1250 | 635.6376 | 0 | 370.7517 | 1250 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-09-07 | 942904.8617 | 700780.79 | 138129.8255 | 110215.75 | 32356.5101 | 48409.98 | 152144.6135 | 141929.79 | 500630.7126 | 400603.47 | 119643.2 | 0 | 1463.151 | 83.16 | 635.6376 | 0 | 370.7517 | 83.16 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-09-08 | 944368.0127 | 705824.89 | 138765.4631 | 112468.15 | 32727.2617 | 48488.22 | 152324.3148 | 141929.79 | 500907.773 | 403316.93 | 119643.2 | 0 | 1463.151 | 5044.1 | 635.6376 | 2252.4 | 370.7517 | 78.24 | 179.7013 | 0 | 277.0604 | 2713.46 | 0 | 0
2025-09-09 | 945831.1637 | 710432.45 | 139401.1007 | 114720.55 | 33098.0134 | 48528.22 | 152504.0162 | 141929.79 | 501184.8334 | 405632.09 | 119643.2 | 0 | 1463.151 | 4607.56 | 635.6376 | 2252.4 | 370.7517 | 40 | 179.7013 | 0 | 277.0604 | 2315.16 | 0 | 0
2025-09-10 | 947294.3146 | 717361.6 | 140036.7383 | 116972.95 | 33468.7651 | 53144.37 | 152683.7175 | 141990.39 | 501461.8938 | 405632.09 | 119643.2 | 0 | 1463.151 | 6929.15 | 635.6376 | 2252.4 | 370.7517 | 4616.15 | 179.7013 | 60.6 | 277.0604 | 0 | 0 | 0
2025-09-11 | 948757.4656 | 721693.31 | 140672.3758 | 119225.35 | 33839.5168 | 53840.97 | 152863.4189 | 142253.08 | 501738.9541 | 406752.11 | 119643.2 | 0 | 1463.151 | 4331.71 | 635.6376 | 2252.4 | 370.7517 | 696.6 | 179.7013 | 262.69 | 277.0604 | 1120.02 | 0 | 0
2025-09-12 | 950220.6166 | 724078.94 | 141308.0134 | 121477.75 | 34210.2685 | 53840.97 | 153043.1202 | 142386.31 | 502016.0145 | 406752.11 | 119643.2 | 0 | 1463.151 | 2385.63 | 635.6376 | 2252.4 | 370.7517 | 0 | 179.7013 | 133.23 | 277.0604 | 0 | 0 | 0
2025-09-13 | 951683.7676 | 724159.64 | 141943.651 | 121477.75 | 34581.0201 | 53921.67 | 153222.8215 | 142386.31 | 502293.0749 | 406752.11 | 119643.2 | 0 | 1463.151 | 80.7 | 635.6376 | 0 | 370.7517 | 80.7 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-09-14 | 953146.9186 | 724596.84 | 142579.2886 | 121477.75 | 34951.7718 | 54276.99 | 153402.5229 | 142468.19 | 502570.1353 | 406752.11 | 119643.2 | 0 | 1463.151 | 437.2 | 635.6376 | 0 | 370.7517 | 355.32 | 179.7013 | 81.88 | 277.0604 | 0 | 0 | 0
2025-09-15 | 954610.0695 | 736977.555 | 143214.9262 | 125315.025 | 35322.5235 | 57385.5 | 153582.2242 | 142761.74 | 502847.1957 | 411893.49 | 119643.2 | 0 | 1463.151 | 12380.715 | 635.6376 | 3837.275 | 370.7517 | 3108.51 | 179.7013 | 293.55 | 277.0604 | 5141.38 | 0 | 0
2025-09-16 | 956073.2205 | 742152.87 | 143850.5638 | 129152.3 | 35693.2752 | 58622.15 | 153761.9256 | 142863.13 | 503124.256 | 411893.49 | 119643.2 | 0 | 1463.151 | 5175.315 | 635.6376 | 3837.275 | 370.7517 | 1236.65 | 179.7013 | 101.39 | 277.0604 | 0 | 0 | 0
2025-09-17 | 957536.3715 | 746049.355 | 144486.2013 | 132989.575 | 36064.0268 | 58681.36 | 153941.6269 | 142863.13 | 503401.3164 | 411893.49 | 119643.2 | 0 | 1463.151 | 3896.485 | 635.6376 | 3837.275 | 370.7517 | 59.21 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-09-18 | 958999.5225 | 750699.35 | 145121.8389 | 136826.85 | 36434.7785 | 59487.08 | 154121.3283 | 142870.13 | 503678.3768 | 411893.49 | 119643.2 | 0 | 1463.151 | 4649.995 | 635.6376 | 3837.275 | 370.7517 | 805.72 | 179.7013 | 7 | 277.0604 | 0 | 0 | 0
2025-09-19 | 960462.6735 | 755522.855 | 145757.4765 | 140664.125 | 36805.5302 | 59591.96 | 154301.0296 | 143751.48 | 503955.4372 | 411893.49 | 119643.2 | 0 | 1463.151 | 4823.505 | 635.6376 | 3837.275 | 370.7517 | 104.88 | 179.7013 | 881.35 | 277.0604 | 0 | 0 | 0
2025-09-20 | 961925.8245 | 756129.685 | 146393.1141 | 140664.125 | 37176.2819 | 59656.96 | 154480.7309 | 144293.31 | 504232.4975 | 411893.49 | 119643.2 | 0 | 1463.151 | 606.83 | 635.6376 | 0 | 370.7517 | 65 | 179.7013 | 541.83 | 277.0604 | 0 | 0 | 0
2025-09-21 | 963388.9754 | 756696.795 | 147028.7517 | 140664.125 | 37547.0336 | 60224.07 | 154660.4323 | 144293.31 | 504509.5579 | 411893.49 | 119643.2 | 0 | 1463.151 | 567.11 | 635.6376 | 0 | 370.7517 | 567.11 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-09-22 | 964852.1264 | 761482.295 | 147664.3893 | 142895.775 | 37917.7852 | 62777.92 | 154840.1336 | 144293.31 | 504786.6183 | 411893.49 | 119643.2 | 0 | 1463.151 | 4785.5 | 635.6376 | 2231.65 | 370.7517 | 2553.85 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-09-23 | 966315.2774 | 767389.605 | 148300.0268 | 145127.425 | 38288.5369 | 62812.74 | 155019.835 | 145355.47 | 505063.6787 | 414472.17 | 119643.2 | 0 | 1463.151 | 5907.31 | 635.6376 | 2231.65 | 370.7517 | 34.82 | 179.7013 | 1062.16 | 277.0604 | 2578.68 | 0 | 0
2025-09-24 | 967778.4284 | 779568.245 | 148935.6644 | 147359.075 | 38659.2886 | 62866.7 | 155199.5363 | 147474.61 | 505340.739 | 422286.98 | 119643.2 | 0 | 1463.151 | 12178.64 | 635.6376 | 2231.65 | 370.7517 | 53.96 | 179.7013 | 2119.14 | 277.0604 | 7814.81 | 0 | 0
2025-09-25 | 969241.5794 | 792122.375 | 149571.302 | 149590.725 | 39030.0403 | 62928.52 | 155379.2377 | 147474.61 | 505617.7994 | 432547.64 | 119643.2 | 0 | 1463.151 | 12554.13 | 635.6376 | 2231.65 | 370.7517 | 61.82 | 179.7013 | 0 | 277.0604 | 10260.66 | 0 | 0
2025-09-26 | 970704.7303 | 802248.185 | 150206.9396 | 151822.375 | 39400.7919 | 63415.61 | 155558.939 | 149184.02 | 505894.8598 | 438245.3 | 119643.2 | 0 | 1463.151 | 10125.81 | 635.6376 | 2231.65 | 370.7517 | 487.09 | 179.7013 | 1709.41 | 277.0604 | 5697.66 | 0 | 0
2025-09-27 | 972167.8813 | 802861.735 | 150842.5772 | 151822.375 | 39771.5436 | 63667.11 | 155738.6403 | 149546.07 | 506171.9202 | 438245.3 | 119643.2 | 0 | 1463.151 | 613.55 | 635.6376 | 0 | 370.7517 | 251.5 | 179.7013 | 362.05 | 277.0604 | 0 | 0 | 0
2025-09-28 | 973631.0323 | 802861.735 | 151478.2148 | 151822.375 | 40142.2953 | 63667.11 | 155918.3417 | 149546.07 | 506448.9806 | 438245.3 | 119643.2 | 0 | 1463.151 | 0 | 635.6376 | 0 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-09-29 | 975094.1833 | 828070.05 | 152113.8523 | 154412.35 | 40513.047 | 71016.08 | 156098.043 | 149723.19 | 506726.0409 | 453337.55 | 119643.2 | 0 | 1463.151 | 25208.315 | 635.6376 | 2589.975 | 370.7517 | 7348.97 | 179.7013 | 177.12 | 277.0604 | 15092.25 | 0 | 0
2025-09-30 | 976557.3343 | 837742.385 | 152749.4899 | 157002.325 | 40883.7987 | 72479.29 | 156277.7444 | 150183.06 | 507003.1013 | 458496.83 | 119643.2 | 0 | 1463.151 | 9672.335 | 635.6376 | 2589.975 | 370.7517 | 1463.21 | 179.7013 | 459.87 | 277.0604 | 5159.28 | 0 | 0
2025-10-01 | 978020.4852 | 843569.57 | 153385.1275 | 159592.3 | 41254.5503 | 72622.32 | 156457.4457 | 153263.91 | 507280.1617 | 458606.74 | 119643.2 | 0 | 1463.151 | 5827.185 | 635.6376 | 2589.975 | 370.7517 | 143.03 | 179.7013 | 3080.85 | 277.0604 | 109.91 | 0 | 0
2025-10-02 | 979483.6362 | 848460.045 | 154020.7651 | 162182.275 | 41625.302 | 73480.3 | 156637.147 | 154706.43 | 507557.2221 | 458606.74 | 119643.2 | 0 | 1463.151 | 4890.475 | 635.6376 | 2589.975 | 370.7517 | 857.98 | 179.7013 | 1442.52 | 277.0604 | 0 | 0 | 0
2025-10-03 | 980946.7872 | 853218.41 | 154656.4027 | 164772.25 | 41996.0537 | 75648.69 | 156816.8484 | 154706.43 | 507834.2824 | 458606.74 | 119643.2 | 0 | 1463.151 | 4758.365 | 635.6376 | 2589.975 | 370.7517 | 2168.39 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-10-04 | 982409.9382 | 858265.89 | 155292.0403 | 164772.25 | 42366.8054 | 76070.17 | 156996.5497 | 155329.54 | 508111.3428 | 462609.63 | 119643.2 | 0 | 1463.151 | 5047.48 | 635.6376 | 0 | 370.7517 | 421.48 | 179.7013 | 623.11 | 277.0604 | 4002.89 | 0 | 0
2025-10-05 | 983873.0892 | 858480.82 | 155927.6779 | 164772.25 | 42737.557 | 76285.1 | 157176.2511 | 155329.54 | 508388.4032 | 462609.63 | 119643.2 | 0 | 1463.151 | 214.93 | 635.6376 | 0 | 370.7517 | 214.93 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-10-06 | 985336.2401 | 863560.245 | 156563.3154 | 165794.425 | 43108.3087 | 79895.59 | 157355.9524 | 155517.92 | 508665.4636 | 462935.23 | 119643.2 | 0 | 1463.151 | 5079.425 | 635.6376 | 1022.175 | 370.7517 | 3610.49 | 179.7013 | 188.38 | 277.0604 | 325.6 | 0 | 0
2025-10-07 | 986799.3911 | 866080.87 | 157198.953 | 166816.6 | 43479.0604 | 79971.45 | 157535.6538 | 155517.92 | 508942.5239 | 464357.82 | 119643.2 | 0 | 1463.151 | 2520.625 | 635.6376 | 1022.175 | 370.7517 | 75.86 | 179.7013 | 0 | 277.0604 | 1422.59 | 0 | 0
2025-10-08 | 988262.5421 | 868019.945 | 157834.5906 | 167838.775 | 43849.8121 | 80888.35 | 157715.3551 | 155517.92 | 509219.5843 | 464357.82 | 119643.2 | 0 | 1463.151 | 1939.075 | 635.6376 | 1022.175 | 370.7517 | 916.9 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-10-09 | 989725.6931 | 869315.36 | 158470.2282 | 168860.95 | 44220.5638 | 81161.59 | 157895.0564 | 155517.92 | 509496.6447 | 464357.82 | 119643.2 | 0 | 1463.151 | 1295.415 | 635.6376 | 1022.175 | 370.7517 | 273.24 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-10-10 | 991188.8441 | 870814.655 | 159105.8658 | 169883.125 | 44591.3154 | 81564.46 | 158074.7578 | 155592.17 | 509773.7051 | 464357.82 | 119643.2 | 0 | 1463.151 | 1499.295 | 635.6376 | 1022.175 | 370.7517 | 402.87 | 179.7013 | 74.25 | 277.0604 | 0 | 0 | 0
2025-10-11 | 992651.9951 | 870839.165 | 159741.5034 | 169883.125 | 44962.0671 | 81564.46 | 158254.4591 | 155616.68 | 510050.7655 | 464357.82 | 119643.2 | 0 | 1463.151 | 24.51 | 635.6376 | 0 | 370.7517 | 0 | 179.7013 | 24.51 | 277.0604 | 0 | 0 | 0
2025-10-12 | 994115.146 | 870910.775 | 160377.1409 | 169883.125 | 45332.8188 | 81636.07 | 158434.1605 | 155616.68 | 510327.8258 | 464357.82 | 119643.2 | 0 | 1463.151 | 71.61 | 635.6376 | 0 | 370.7517 | 71.61 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-10-13 | 995578.297 | 875014.25 | 161012.7785 | 171910.3 | 45703.5705 | 83712.37 | 158613.8618 | 155616.68 | 510604.8862 | 464357.82 | 119643.2 | 0 | 1463.151 | 4103.475 | 635.6376 | 2027.175 | 370.7517 | 2076.3 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-10-14 | 997041.448 | 878888.575 | 161648.4161 | 173937.475 | 46074.3221 | 84498.37 | 158793.5632 | 155709.2 | 510881.9466 | 465326.45 | 119643.2 | 0 | 1463.151 | 3874.325 | 635.6376 | 2027.175 | 370.7517 | 786 | 179.7013 | 92.52 | 277.0604 | 968.63 | 0 | 0
2025-10-15 | 998504.599 | 881748.04 | 162284.0537 | 175964.65 | 46445.0738 | 85254.57 | 158973.2645 | 155754.89 | 511159.007 | 465356.85 | 119643.2 | 0 | 1463.151 | 2859.465 | 635.6376 | 2027.175 | 370.7517 | 756.2 | 179.7013 | 45.69 | 277.0604 | 30.4 | 0 | 0
2025-10-16 | 999967.75 | 885395.045 | 162919.6913 | 177991.825 | 46815.8255 | 86625.01 | 159152.9658 | 156004.28 | 511436.0673 | 465356.85 | 119643.2 | 0 | 1463.151 | 3647.005 | 635.6376 | 2027.175 | 370.7517 | 1370.44 | 179.7013 | 249.39 | 277.0604 | 0 | 0 | 0
2025-10-17 | 1001430.9009 | 889848.12 | 163555.3289 | 180019 | 47186.5772 | 88989.52 | 159332.6672 | 156065.67 | 511713.1277 | 465356.85 | 119643.2 | 0 | 1463.151 | 4453.075 | 635.6376 | 2027.175 | 370.7517 | 2364.51 | 179.7013 | 61.39 | 277.0604 | 0 | 0 | 0
2025-10-18 | 1002894.0519 | 892020.02 | 164190.9664 | 180019 | 47557.3289 | 89021.28 | 159512.3685 | 157749.86 | 511990.1881 | 465812.8 | 119643.2 | 0 | 1463.151 | 2171.9 | 635.6376 | 0 | 370.7517 | 31.76 | 179.7013 | 1684.19 | 277.0604 | 455.95 | 0 | 0
2025-10-19 | 1004357.2029 | 892657.99 | 164826.604 | 180019 | 47928.0805 | 89529.62 | 159692.0699 | 157808.37 | 512267.2485 | 466009.66 | 119643.2 | 0 | 1463.151 | 637.97 | 635.6376 | 0 | 370.7517 | 508.34 | 179.7013 | 58.51 | 277.0604 | 196.86 | 0 | 0
2025-10-20 | 1005820.3539 | 902174.8 | 165462.2416 | 182968.2 | 48298.8322 | 89902.23 | 159871.7712 | 157808.37 | 512544.3088 | 472204.66 | 119643.2 | 0 | 1463.151 | 9516.81 | 635.6376 | 2949.2 | 370.7517 | 372.61 | 179.7013 | 0 | 277.0604 | 6195 | 0 | 0
2025-10-21 | 1007283.5049 | 907346.88 | 166097.8792 | 185917.4 | 48669.5839 | 91602.01 | 160051.4726 | 158217.07 | 512821.3692 | 472319.06 | 119643.2 | 0 | 1463.151 | 5172.08 | 635.6376 | 2949.2 | 370.7517 | 1699.78 | 179.7013 | 408.7 | 277.0604 | 114.4 | 0 | 0
2025-10-22 | 1008746.6558 | 917072.65 | 166733.5168 | 188866.6 | 49040.3356 | 91686.43 | 160231.1739 | 158217.07 | 513098.4296 | 479011.21 | 119643.2 | 0 | 1463.151 | 9725.77 | 635.6376 | 2949.2 | 370.7517 | 84.42 | 179.7013 | 0 | 277.0604 | 6692.15 | 0 | 0
2025-10-23 | 1010209.8068 | 923967.24 | 167369.1544 | 191815.8 | 49411.0872 | 94987.73 | 160410.8752 | 158669.77 | 513375.49 | 479253.83 | 119643.2 | 0 | 1463.151 | 6894.59 | 635.6376 | 2949.2 | 370.7517 | 3301.3 | 179.7013 | 452.7 | 277.0604 | 242.62 | 0 | 0
2025-10-24 | 1011672.9578 | 931901.67 | 168004.7919 | 194765 | 49781.8389 | 99972.96 | 160590.5766 | 158669.77 | 513652.5504 | 479253.83 | 119643.2 | 0 | 1463.151 | 7934.43 | 635.6376 | 2949.2 | 370.7517 | 4985.23 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-10-25 | 1013136.1088 | 932988.57 | 168640.4295 | 194765 | 50152.5906 | 100658.31 | 160770.2779 | 159071.32 | 513929.6107 | 479253.83 | 119643.2 | 0 | 1463.151 | 1086.9 | 635.6376 | 0 | 370.7517 | 685.35 | 179.7013 | 401.55 | 277.0604 | 0 | 0 | 0
2025-10-26 | 1014599.2598 | 933171.8 | 169276.0671 | 194765 | 50523.3423 | 100841.54 | 160949.9793 | 159071.32 | 514206.6711 | 479253.83 | 119643.2 | 0 | 1463.151 | 183.23 | 635.6376 | 0 | 370.7517 | 183.23 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-10-27 | 1016062.4107 | 937061.51 | 169911.7047 | 196708.4 | 50894.094 | 101562.85 | 161129.6806 | 160296.32 | 514483.7315 | 479253.83 | 119643.2 | 0 | 1463.151 | 3889.71 | 635.6376 | 1943.4 | 370.7517 | 721.31 | 179.7013 | 1225 | 277.0604 | 0 | 0 | 0
2025-10-28 | 1017525.5617 | 945324.18 | 170547.3423 | 198651.8 | 51264.8456 | 104613.9 | 161309.3819 | 160655.3 | 514760.7919 | 482163.07 | 119643.2 | 0 | 1463.151 | 8262.67 | 635.6376 | 1943.4 | 370.7517 | 3051.05 | 179.7013 | 358.98 | 277.0604 | 2909.24 | 0 | 0
2025-10-29 | 1018988.7127 | 951796.31 | 171182.9799 | 200595.2 | 51635.5973 | 104713.9 | 161489.0833 | 161370.54 | 515037.8522 | 485876.56 | 119643.2 | 0 | 1463.151 | 6472.13 | 635.6376 | 1943.4 | 370.7517 | 100 | 179.7013 | 715.24 | 277.0604 | 3713.49 | 0 | 0
2025-10-30 | 1020451.8637 | 1018929.65 | 171818.6174 | 202538.6 | 52006.349 | 104810.99 | 161668.7846 | 163416.74 | 515314.9126 | 548923.21 | 119643.2 | 0 | 1463.151 | 67133.34 | 635.6376 | 1943.4 | 370.7517 | 97.09 | 179.7013 | 2046.2 | 277.0604 | 63046.65 | 0 | 0
2025-10-31 | 1021915.0147 | 1021873.05 | 172454.255 | 204482 | 52377.1007 | 105810.99 | 161848.486 | 163416.74 | 515591.973 | 548923.21 | 119643.2 | 0 | 1463.151 | 2943.4 | 635.6376 | 1943.4 | 370.7517 | 1000 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-11-01 | 1023378.1657 | 1022003.78 | 173089.8926 | 204482 | 52747.8523 | 105941.72 | 162028.1873 | 163416.74 | 515869.0334 | 548923.21 | 119643.2 | 0 | 1463.151 | 130.73 | 635.6376 | 0 | 370.7517 | 130.73 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-11-02 | 1024841.3166 | 1022021.01 | 173725.5302 | 204482 | 53118.604 | 105958.95 | 162207.8887 | 163416.74 | 516146.0937 | 548923.21 | 119643.2 | 0 | 1463.151 | 17.23 | 635.6376 | 0 | 370.7517 | 17.23 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-11-03 | 1026304.4676 | 1023120.21 | 174361.1678 | 205581.2 | 53489.3557 | 105958.95 | 162387.59 | 163416.74 | 516423.1541 | 548923.21 | 119643.2 | 0 | 1463.151 | 1099.2 | 635.6376 | 1099.2 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-11-04 | 1027767.6186 | 1024482.38 | 174996.8054 | 206680.4 | 53860.1074 | 106221.92 | 162567.2913 | 163416.74 | 516700.2145 | 548923.21 | 119643.2 | 0 | 1463.151 | 1362.17 | 635.6376 | 1099.2 | 370.7517 | 262.97 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-11-05 | 1029230.7696 | 1026089.51 | 175632.443 | 207779.6 | 54230.8591 | 106675.26 | 162746.9927 | 163471.33 | 516977.2749 | 548923.21 | 119643.2 | 0 | 1463.151 | 1607.13 | 635.6376 | 1099.2 | 370.7517 | 453.34 | 179.7013 | 54.59 | 277.0604 | 0 | 0 | 0
2025-11-06 | 1030693.9206 | 1031780.32 | 176268.0805 | 208878.8 | 54601.6107 | 107020.03 | 162926.694 | 167702.15 | 517254.3352 | 548939.23 | 119643.2 | 0 | 1463.151 | 5690.81 | 635.6376 | 1099.2 | 370.7517 | 344.77 | 179.7013 | 4230.82 | 277.0604 | 16.02 | 0 | 0
2025-11-07 | 1032157.0715 | 1038057.32 | 176903.7181 | 209978 | 54972.3624 | 109925.4 | 163106.3954 | 169974.58 | 517531.3956 | 548939.23 | 119643.2 | 0 | 1463.151 | 6277 | 635.6376 | 1099.2 | 370.7517 | 2905.37 | 179.7013 | 2272.43 | 277.0604 | 0 | 0 | 0
2025-11-08 | 1033620.2225 | 1039791.23 | 177539.3557 | 209978 | 55343.1141 | 110334.05 | 163286.0967 | 171299.84 | 517808.456 | 548939.23 | 119643.2 | 0 | 1463.151 | 1733.91 | 635.6376 | 0 | 370.7517 | 408.65 | 179.7013 | 1325.26 | 277.0604 | 0 | 0 | 0
2025-11-09 | 1035083.3735 | 1040498.94 | 178174.9933 | 209978 | 55713.8658 | 110632.04 | 163465.7981 | 171709.56 | 518085.5164 | 548939.23 | 119643.2 | 0 | 1463.151 | 707.71 | 635.6376 | 0 | 370.7517 | 297.99 | 179.7013 | 409.72 | 277.0604 | 0 | 0 | 0
2025-11-10 | 1036546.5245 | 1045777.88 | 178810.6309 | 211827.2 | 56084.6174 | 111072.23 | 163645.4994 | 174368.36 | 518362.5768 | 549269.98 | 119643.2 | 0 | 1463.151 | 5278.94 | 635.6376 | 1849.2 | 370.7517 | 440.19 | 179.7013 | 2658.8 | 277.0604 | 330.75 | 0 | 0
2025-11-11 | 1038009.6755 | 1050759.83 | 179446.2685 | 213676.4 | 56455.3691 | 111144.61 | 163825.2007 | 174464.42 | 518639.6371 | 552234.29 | 119643.2 | 0 | 1463.151 | 4981.95 | 635.6376 | 1849.2 | 370.7517 | 72.38 | 179.7013 | 96.06 | 277.0604 | 2964.31 | 0 | 0
2025-11-12 | 1039472.8264 | 1054099.41 | 180081.906 | 215525.6 | 56826.1208 | 111194.99 | 164004.9021 | 175904.42 | 518916.6975 | 552234.29 | 119643.2 | 0 | 1463.151 | 3339.58 | 635.6376 | 1849.2 | 370.7517 | 50.38 | 179.7013 | 1440 | 277.0604 | 0 | 0 | 0
2025-11-13 | 1040935.9774 | 1056637.58 | 180717.5436 | 217374.8 | 57196.8725 | 111495.82 | 164184.6034 | 176292.56 | 519193.7579 | 552234.29 | 119643.2 | 0 | 1463.151 | 2538.17 | 635.6376 | 1849.2 | 370.7517 | 300.83 | 179.7013 | 388.14 | 277.0604 | 0 | 0 | 0
2025-11-14 | 1042399.1284 | 1061967.93 | 181353.1812 | 219224 | 57567.6242 | 112951 | 164364.3048 | 178318.53 | 519470.8183 | 552234.29 | 119643.2 | 0 | 1463.151 | 5330.35 | 635.6376 | 1849.2 | 370.7517 | 1455.18 | 179.7013 | 2025.97 | 277.0604 | 0 | 0 | 0
2025-11-15 | 1043862.2794 | 1064234.97 | 181988.8188 | 219224 | 57938.3758 | 113293.18 | 164544.0061 | 180243.39 | 519747.8786 | 552234.29 | 119643.2 | 0 | 1463.151 | 2267.04 | 635.6376 | 0 | 370.7517 | 342.18 | 179.7013 | 1924.86 | 277.0604 | 0 | 0 | 0
2025-11-16 | 1045325.4304 | 1065410 | 182624.4564 | 219224 | 58309.1275 | 114421.94 | 164723.7075 | 180289.66 | 520024.939 | 552234.29 | 119643.2 | 0 | 1463.151 | 1175.03 | 635.6376 | 0 | 370.7517 | 1128.76 | 179.7013 | 46.27 | 277.0604 | 0 | 0 | 0
2025-11-17 | 1046788.5813 | 1067688.38 | 183260.094 | 221193.8 | 58679.8792 | 114501.94 | 164903.4088 | 180518.24 | 520301.9994 | 552234.29 | 119643.2 | 0 | 1463.151 | 2278.38 | 635.6376 | 1969.8 | 370.7517 | 80 | 179.7013 | 228.58 | 277.0604 | 0 | 0 | 0
2025-11-18 | 1048251.7323 | 1070007.29 | 183895.7315 | 223163.6 | 59050.6309 | 114796.14 | 165083.1101 | 180573.15 | 520579.0598 | 552234.29 | 119643.2 | 0 | 1463.151 | 2318.91 | 635.6376 | 1969.8 | 370.7517 | 294.2 | 179.7013 | 54.91 | 277.0604 | 0 | 0 | 0
2025-11-19 | 1049714.8833 | 1077214.8 | 184531.3691 | 225133.4 | 59421.3826 | 114898.79 | 165262.8115 | 180607.35 | 520856.1201 | 557335.15 | 119643.2 | 0 | 1463.151 | 7207.51 | 635.6376 | 1969.8 | 370.7517 | 102.65 | 179.7013 | 34.2 | 277.0604 | 5100.86 | 0 | 0
2025-11-20 | 1051178.0343 | 1080588.65 | 185167.0067 | 227103.2 | 59792.1342 | 115961.24 | 165442.5128 | 180948.95 | 521133.1805 | 557335.15 | 119643.2 | 0 | 1463.151 | 3373.85 | 635.6376 | 1969.8 | 370.7517 | 1062.45 | 179.7013 | 341.6 | 277.0604 | 0 | 0 | 0
2025-11-21 | 1052641.1853 | 1091405.4 | 185802.6443 | 229073 | 60162.8859 | 124763.67 | 165622.2142 | 180993.47 | 521410.2409 | 557335.15 | 119643.2 | 0 | 1463.151 | 10816.75 | 635.6376 | 1969.8 | 370.7517 | 8802.43 | 179.7013 | 44.52 | 277.0604 | 0 | 0 | 0
2025-11-22 | 1054104.3362 | 1091768.26 | 186438.2819 | 229073 | 60533.6376 | 125126.53 | 165801.9155 | 180993.47 | 521687.3013 | 557335.15 | 119643.2 | 0 | 1463.151 | 362.86 | 635.6376 | 0 | 370.7517 | 362.86 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-11-23 | 1055567.4872 | 1091822.68 | 187073.9195 | 229073 | 60904.3893 | 125180.95 | 165981.6168 | 180993.47 | 521964.3617 | 557335.15 | 119643.2 | 0 | 1463.151 | 54.42 | 635.6376 | 0 | 370.7517 | 54.42 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-11-24 | 1057030.6382 | 1097764.92 | 187709.557 | 229300.8 | 61275.1409 | 125180.95 | 166161.3182 | 180993.47 | 522241.422 | 563049.59 | 119643.2 | 0 | 1463.151 | 5942.24 | 635.6376 | 227.8 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 5714.44 | 0 | 0
2025-11-25 | 1058493.7892 | 1098342.96 | 188345.1946 | 229528.6 | 61645.8926 | 125180.95 | 166341.0195 | 181343.71 | 522518.4824 | 563049.59 | 119643.2 | 0 | 1463.151 | 578.04 | 635.6376 | 227.8 | 370.7517 | 0 | 179.7013 | 350.24 | 277.0604 | 0 | 0 | 0
2025-11-26 | 1059956.9402 | 1111000.76 | 188980.8322 | 229756.4 | 62016.6443 | 125180.95 | 166520.7209 | 181343.71 | 522795.5428 | 575479.59 | 119643.2 | 0 | 1463.151 | 12657.8 | 635.6376 | 227.8 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 12430 | 0 | 0
2025-11-27 | 1061420.0912 | 1112654.13 | 189616.4698 | 229984.2 | 62387.396 | 126606.52 | 166700.4222 | 181343.71 | 523072.6032 | 575479.59 | 119643.2 | 0 | 1463.151 | 1653.37 | 635.6376 | 227.8 | 370.7517 | 1425.57 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-11-28 | 1062883.2421 | 1113788.77 | 190252.1074 | 230212 | 62758.1477 | 127513.36 | 166880.1236 | 181343.71 | 523349.6635 | 575479.59 | 119643.2 | 0 | 1463.151 | 1134.64 | 635.6376 | 227.8 | 370.7517 | 906.84 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-11-29 | 1064346.3931 | 1113872.86 | 190887.745 | 230212 | 63128.8993 | 127597.45 | 167059.8249 | 181343.71 | 523626.7239 | 575479.59 | 119643.2 | 0 | 1463.151 | 84.09 | 635.6376 | 0 | 370.7517 | 84.09 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-11-30 | 1065809.5441 | 1114235.53 | 191523.3826 | 230212 | 63499.651 | 127960.12 | 167239.5262 | 181343.71 | 523903.7843 | 575479.59 | 119643.2 | 0 | 1463.151 | 362.67 | 635.6376 | 0 | 370.7517 | 362.67 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-12-01 | 1067272.6951 | 1116235.77 | 192159.0201 | 232155.4 | 63870.4027 | 128016.96 | 167419.2276 | 181343.71 | 524180.8447 | 575479.59 | 119643.2 | 0 | 1463.151 | 2000.24 | 635.6376 | 1943.4 | 370.7517 | 56.84 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-12-02 | 1068735.8461 | 1118179.17 | 192794.6577 | 234098.8 | 64241.1544 | 128016.96 | 167598.9289 | 181343.71 | 524457.905 | 575479.59 | 119643.2 | 0 | 1463.151 | 1943.4 | 635.6376 | 1943.4 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-12-03 | 1070198.997 | 1120509.39 | 193430.2953 | 236042.2 | 64611.906 | 128016.96 | 167778.6303 | 181343.71 | 524734.9654 | 575479.59 | 119643.2 | 386.82 | 1463.151 | 2330.22 | 635.6376 | 1943.4 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 386.82
2025-12-04 | 1071662.148 | 1122528.92 | 194065.9329 | 237985.6 | 64982.6577 | 128093.09 | 167958.3316 | 181343.71 | 525012.0258 | 575479.59 | 119643.2 | 386.82 | 1463.151 | 2019.53 | 635.6376 | 1943.4 | 370.7517 | 76.13 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-12-05 | 1073125.299 | 1129195.52 | 194701.5705 | 239929 | 65353.4094 | 130720.84 | 168138.033 | 183285.65 | 525289.0862 | 575633.1 | 119643.2 | 386.82 | 1463.151 | 6666.6 | 635.6376 | 1943.4 | 370.7517 | 2627.75 | 179.7013 | 1941.94 | 277.0604 | 153.51 | 0 | 0
2025-12-06 | 1074588.45 | 1129233.8 | 195337.2081 | 239929 | 65724.1611 | 130759.12 | 168317.7343 | 183285.65 | 525566.1466 | 575633.1 | 119643.2 | 386.82 | 1463.151 | 38.28 | 635.6376 | 0 | 370.7517 | 38.28 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-12-07 | 1076051.601 | 1129233.8 | 195972.8456 | 239929 | 66094.9128 | 130759.12 | 168497.4356 | 183285.65 | 525843.2069 | 575633.1 | 119643.2 | 386.82 | 1463.151 | 0 | 635.6376 | 0 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-12-08 | 1077514.7519 | 1134382.88 | 196608.4832 | 242999 | 66465.6644 | 130826.66 | 168677.137 | 183547.19 | 526120.2673 | 577383.1 | 119643.2 | 386.82 | 1463.151 | 5149.08 | 635.6376 | 3070 | 370.7517 | 67.54 | 179.7013 | 261.54 | 277.0604 | 1750 | 0 | 0
2025-12-09 | 1078977.9029 | 1145307.02 | 197244.1208 | 246069 | 66836.4161 | 130966.66 | 168856.8383 | 185971.18 | 526397.3277 | 582673.25 | 119643.2 | 386.82 | 1463.151 | 10924.14 | 635.6376 | 3070 | 370.7517 | 140 | 179.7013 | 2423.99 | 277.0604 | 5290.15 | 0 | 0
2025-12-10 | 1080441.0539 | 1148636.57 | 197879.7584 | 249139 | 67207.1678 | 130966.66 | 169036.5397 | 186230.73 | 526674.3881 | 582673.25 | 119643.2 | 386.82 | 1463.151 | 3329.55 | 635.6376 | 3070 | 370.7517 | 0 | 179.7013 | 259.55 | 277.0604 | 0 | 0 | 0
2025-12-11 | 1081904.2049 | 1151803.46 | 198515.396 | 252209 | 67577.9195 | 131063.55 | 169216.241 | 186230.73 | 526951.4484 | 582673.25 | 119643.2 | 386.82 | 1463.151 | 3166.89 | 635.6376 | 3070 | 370.7517 | 96.89 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-12-12 | 1083367.3559 | 1158661.68 | 199151.0336 | 255279 | 67948.6711 | 134357.9 | 169395.9424 | 186230.73 | 527228.5088 | 583167.12 | 119643.2 | 386.82 | 1463.151 | 6858.22 | 635.6376 | 3070 | 370.7517 | 3294.35 | 179.7013 | 0 | 277.0604 | 493.87 | 0 | 0
2025-12-13 | 1084830.5068 | 1158661.68 | 199786.6711 | 255279 | 68319.4228 | 134357.9 | 169575.6437 | 186230.73 | 527505.5692 | 583167.12 | 119643.2 | 386.82 | 1463.151 | 0 | 635.6376 | 0 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-12-14 | 1086293.6578 | 1158661.68 | 200422.3087 | 255279 | 68690.1745 | 134357.9 | 169755.345 | 186230.73 | 527782.6296 | 583167.12 | 119643.2 | 386.82 | 1463.151 | 0 | 635.6376 | 0 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-12-15 | 1087756.8088 | 1162781.13 | 201057.9463 | 258885 | 69060.9262 | 134753.09 | 169935.0464 | 186338.31 | 528059.6899 | 583177.8 | 119643.2 | 386.82 | 1463.151 | 4119.45 | 635.6376 | 3606 | 370.7517 | 395.19 | 179.7013 | 107.58 | 277.0604 | 10.68 | 0 | 0
2025-12-16 | 1089219.9598 | 1167051.38 | 201693.5839 | 262491 | 69431.6779 | 135283.22 | 170114.7477 | 186472.43 | 528336.7503 | 583177.8 | 119643.2 | 386.82 | 1463.151 | 4270.25 | 635.6376 | 3606 | 370.7517 | 530.13 | 179.7013 | 134.12 | 277.0604 | 0 | 0 | 0
2025-12-17 | 1090683.1108 | 1177167.87 | 202329.2215 | 266097 | 69802.4295 | 135831.4 | 170294.4491 | 187333.88 | 528613.8107 | 588278.66 | 119643.2 | 386.82 | 1463.151 | 10116.49 | 635.6376 | 3606 | 370.7517 | 548.18 | 179.7013 | 861.45 | 277.0604 | 5100.86 | 0 | 0
2025-12-18 | 1092146.2618 | 1180773.87 | 202964.8591 | 269703 | 70173.1812 | 135831.4 | 170474.1504 | 187333.88 | 528890.8711 | 588278.66 | 119643.2 | 386.82 | 1463.151 | 3606 | 635.6376 | 3606 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-12-19 | 1093609.4127 | 1190062.54 | 203600.4966 | 273309 | 70543.9329 | 141514.07 | 170653.8517 | 187333.88 | 529167.9315 | 588278.66 | 119643.2 | 386.82 | 1463.151 | 9288.67 | 635.6376 | 3606 | 370.7517 | 5682.67 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-12-20 | 1095072.5637 | 1194753.9 | 204236.1342 | 273309 | 70914.6846 | 146205.43 | 170833.5531 | 187333.88 | 529444.9918 | 588278.66 | 119643.2 | 386.82 | 1463.151 | 4691.36 | 635.6376 | 0 | 370.7517 | 4691.36 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-12-21 | 1096535.7147 | 1195197.75 | 204871.7718 | 273309 | 71285.4362 | 146649.28 | 171013.2544 | 187333.88 | 529722.0522 | 588278.66 | 119643.2 | 386.82 | 1463.151 | 443.85 | 635.6376 | 0 | 370.7517 | 443.85 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-12-22 | 1097998.8657 | 1195974.9 | 205507.4094 | 273630.6 | 71656.1879 | 146649.28 | 171192.9558 | 187789.43 | 529999.1126 | 588278.66 | 119643.2 | 386.82 | 1463.151 | 777.15 | 635.6376 | 321.6 | 370.7517 | 0 | 179.7013 | 455.55 | 277.0604 | 0 | 0 | 0
2025-12-23 | 1099462.0167 | 1196296.5 | 206143.047 | 273952.2 | 72026.9396 | 146649.28 | 171372.6571 | 187789.43 | 530276.173 | 588278.66 | 119643.2 | 386.82 | 1463.151 | 321.6 | 635.6376 | 321.6 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-12-24 | 1100925.1676 | 1196618.1 | 206778.6846 | 274273.8 | 72397.6913 | 146649.28 | 171552.3585 | 187789.43 | 530553.2333 | 588278.66 | 119643.2 | 386.82 | 1463.151 | 321.6 | 635.6376 | 321.6 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-12-25 | 1102388.3186 | 1197644.91 | 207414.3221 | 274595.4 | 72768.443 | 147012.73 | 171732.0598 | 187789.43 | 530830.2937 | 588620.42 | 119643.2 | 386.82 | 1463.151 | 1026.81 | 635.6376 | 321.6 | 370.7517 | 363.45 | 179.7013 | 0 | 277.0604 | 341.76 | 0 | 0
2025-12-26 | 1103851.4696 | 1197966.51 | 208049.9597 | 274917 | 73139.1946 | 147012.73 | 171911.7611 | 187789.43 | 531107.3541 | 588620.42 | 119643.2 | 386.82 | 1463.151 | 321.6 | 635.6376 | 321.6 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-12-27 | 1105314.6206 | 1197966.51 | 208685.5973 | 274917 | 73509.9463 | 147012.73 | 172091.4625 | 187789.43 | 531384.4145 | 588620.42 | 119643.2 | 386.82 | 1463.151 | 0 | 635.6376 | 0 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-12-28 | 1106777.7716 | 1197966.51 | 209321.2349 | 274917 | 73880.698 | 147012.73 | 172271.1638 | 187789.43 | 531661.4748 | 588620.42 | 119643.2 | 386.82 | 1463.151 | 0 | 635.6376 | 0 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-12-29 | 1108240.9225 | 1198164.91 | 209956.8725 | 275115.4 | 74251.4497 | 147012.73 | 172450.8652 | 187789.43 | 531938.5352 | 588620.42 | 119643.2 | 386.82 | 1463.151 | 198.4 | 635.6376 | 198.4 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2025-12-30 | 1109704.0735 | 1201363.31 | 210592.5101 | 275313.8 | 74622.2013 | 147312.73 | 172630.5665 | 187789.43 | 532215.5956 | 591320.42 | 119643.2 | 386.82 | 1463.151 | 3198.4 | 635.6376 | 198.4 | 370.7517 | 300 | 179.7013 | 0 | 277.0604 | 2700 | 0 | 0
2025-12-31 | 1111167.2245 | 1201561.71 | 211228.1477 | 275512.2 | 74992.953 | 147312.73 | 172810.2679 | 187789.43 | 532492.656 | 591320.42 | 119643.2 | 386.82 | 1463.151 | 198.4 | 635.6376 | 198.4 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2026-01-01 | 1112630.3755 | 1201760.11 | 211863.7852 | 275710.6 | 75363.7047 | 147312.73 | 172989.9692 | 187789.43 | 532769.7164 | 591320.42 | 119643.2 | 386.82 | 1463.151 | 198.4 | 635.6376 | 198.4 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2026-01-02 | 1114093.5265 | 1201958.51 | 212499.4228 | 275909 | 75734.4564 | 147312.73 | 173169.6705 | 187789.43 | 533046.7767 | 591320.42 | 119643.2 | 386.82 | 1463.151 | 198.4 | 635.6376 | 198.4 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2026-01-03 | 1115556.6774 | 1203883.37 | 213135.0604 | 275909 | 76105.2081 | 149237.59 | 173349.3719 | 187789.43 | 533323.8371 | 591320.42 | 119643.2 | 386.82 | 1463.151 | 1924.86 | 635.6376 | 0 | 370.7517 | 1924.86 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2026-01-04 | 1117019.8284 | 1203930.04 | 213770.698 | 275909 | 76475.9597 | 149284.26 | 173529.0732 | 187789.43 | 533600.8975 | 591320.42 | 119643.2 | 386.82 | 1463.151 | 46.67 | 635.6376 | 0 | 370.7517 | 46.67 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2026-01-05 | 1118482.9794 | 1207566.98 | 214406.3356 | 278241.8 | 76846.7114 | 150283.65 | 173708.7746 | 187789.43 | 533877.9579 | 591625.17 | 119643.2 | 386.82 | 1463.151 | 3636.94 | 635.6376 | 2332.8 | 370.7517 | 999.39 | 179.7013 | 0 | 277.0604 | 304.75 | 0 | 0
2026-01-06 | 1119946.1304 | 1218416.01 | 215041.9732 | 280574.6 | 77217.4631 | 152558.72 | 173888.4759 | 188700.98 | 534155.0182 | 596954.78 | 119643.2 | 386.82 | 1463.151 | 10849.03 | 635.6376 | 2332.8 | 370.7517 | 2275.07 | 179.7013 | 911.55 | 277.0604 | 5329.61 | 0 | 0
2026-01-07 | 1121409.2814 | 1221059.53 | 215677.6107 | 282907.4 | 77588.2148 | 152558.72 | 174068.1773 | 189011.7 | 534432.0786 | 596954.78 | 119643.2 | 386.82 | 1463.151 | 2643.52 | 635.6376 | 2332.8 | 370.7517 | 0 | 179.7013 | 310.72 | 277.0604 | 0 | 0 | 0
2026-01-08 | 1122872.4324 | 1224776.19 | 216313.2483 | 285240.2 | 77958.9664 | 152558.72 | 174247.8786 | 190395.56 | 534709.139 | 596954.78 | 119643.2 | 386.82 | 1463.151 | 3716.66 | 635.6376 | 2332.8 | 370.7517 | 0 | 179.7013 | 1383.86 | 277.0604 | 0 | 0 | 0
2026-01-09 | 1124335.5833 | 1227280.03 | 216948.8859 | 287573 | 78329.7181 | 152614.64 | 174427.5799 | 190510.68 | 534986.1994 | 596954.78 | 119643.2 | 386.82 | 1463.151 | 2503.84 | 635.6376 | 2332.8 | 370.7517 | 55.92 | 179.7013 | 115.12 | 277.0604 | 0 | 0 | 0
2026-01-10 | 1125798.7343 | 1227280.03 | 217584.5235 | 287573 | 78700.4698 | 152614.64 | 174607.2813 | 190510.68 | 535263.2597 | 596954.78 | 119643.2 | 386.82 | 1463.151 | 0 | 635.6376 | 0 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2026-01-11 | 1127261.8853 | 1227325.12 | 218220.1611 | 287573 | 79071.2215 | 152659.73 | 174786.9826 | 190510.68 | 535540.3201 | 596954.78 | 119643.2 | 386.82 | 1463.151 | 45.09 | 635.6376 | 0 | 370.7517 | 45.09 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2026-01-12 | 1128725.0363 | 1229653.2 | 218855.7987 | 289839 | 79441.9732 | 152721.81 | 174966.684 | 190510.68 | 535817.3805 | 596954.78 | 119643.2 | 386.82 | 1463.151 | 2328.08 | 635.6376 | 2266 | 370.7517 | 62.08 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2026-01-13 | 1130188.1873 | 1231919.2 | 219491.4362 | 292105 | 79812.7248 | 152721.81 | 175146.3853 | 190510.68 | 536094.4409 | 596954.78 | 119643.2 | 386.82 | 1463.151 | 2266 | 635.6376 | 2266 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2026-01-14 | 1131651.3382 | 1236148.51 | 220127.0738 | 294371 | 80183.4765 | 154660.21 | 175326.0866 | 190535.59 | 536371.5013 | 596954.78 | 119643.2 | 386.82 | 1463.151 | 4229.31 | 635.6376 | 2266 | 370.7517 | 1938.4 | 179.7013 | 24.91 | 277.0604 | 0 | 0 | 0
2026-01-15 | 1133114.4892 | 1238444.01 | 220762.7114 | 296637 | 80554.2282 | 154689.71 | 175505.788 | 190535.59 | 536648.5616 | 596954.78 | 119643.2 | 386.82 | 1463.151 | 2295.5 | 635.6376 | 2266 | 370.7517 | 29.5 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2026-01-16 | 1134577.6402 | 1245145.59 | 221398.349 | 298903 | 80924.9799 | 158739.71 | 175685.4893 | 190891.17 | 536925.622 | 596984.78 | 119643.2 | 386.82 | 1463.151 | 6701.58 | 635.6376 | 2266 | 370.7517 | 4050 | 179.7013 | 355.58 | 277.0604 | 30 | 0 | 0
2026-01-17 | 1136040.7912 | 1245145.59 | 222033.9866 | 298903 | 81295.7315 | 158739.71 | 175865.1907 | 190891.17 | 537202.6824 | 596984.78 | 119643.2 | 386.82 | 1463.151 | 0 | 635.6376 | 0 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2026-01-18 | 1137503.9422 | 1245145.59 | 222669.6242 | 298903 | 81666.4832 | 158739.71 | 176044.892 | 190891.17 | 537479.7428 | 596984.78 | 119643.2 | 386.82 | 1463.151 | 0 | 635.6376 | 0 | 370.7517 | 0 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2026-01-19 | 1138967.0931 | 1247483.55 | 223305.2617 | 301102 | 82037.2349 | 158739.71 | 176224.5934 | 191030.13 | 537756.8031 | 596984.78 | 119643.2 | 386.82 | 1463.151 | 2337.96 | 635.6376 | 2199 | 370.7517 | 0 | 179.7013 | 138.96 | 277.0604 | 0 | 0 | 0
2026-01-20 | 1140430.2441 | 1251515.13 | 223940.8993 | 303301 | 82407.9866 | 159474.41 | 176404.2947 | 192128.01 | 538033.8635 | 596984.78 | 119643.2 | 386.82 | 1463.151 | 4031.58 | 635.6376 | 2199 | 370.7517 | 734.7 | 179.7013 | 1097.88 | 277.0604 | 0 | 0 | 0
2026-01-21 | 1141893.3951 | 1253792.58 | 224576.5369 | 305500 | 82778.7383 | 159474.41 | 176583.996 | 192206.46 | 538310.9239 | 596984.78 | 119643.2 | 386.82 | 1463.151 | 2277.45 | 635.6376 | 2199 | 370.7517 | 0 | 179.7013 | 78.45 | 277.0604 | 0 | 0 | 0
2026-01-22 | 1143356.5461 | 1256068.3 | 225212.1745 | 307699 | 83149.4899 | 159474.41 | 176763.6974 | 192266.84 | 538587.9843 | 597001.12 | 119643.2 | 386.82 | 1463.151 | 2275.72 | 635.6376 | 2199 | 370.7517 | 0 | 179.7013 | 60.38 | 277.0604 | 16.34 | 0 | 0
2026-01-23 | 1144819.6971 | 1262236.41 | 225847.8121 | 309898 | 83520.2416 | 161463.36 | 176943.3987 | 192266.84 | 538865.0446 | 598981.28 | 119643.2 | 386.82 | 1463.151 | 6168.11 | 635.6376 | 2199 | 370.7517 | 1988.95 | 179.7013 | 0 | 277.0604 | 1980.16 | 0 | 0
2026-01-24 | 1146282.848 | 1262371.59 | 226483.4497 | 309898 | 83890.9933 | 161598.54 | 177123.1001 | 192266.84 | 539142.105 | 598981.28 | 119643.2 | 386.82 | 1463.151 | 135.18 | 635.6376 | 0 | 370.7517 | 135.18 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2026-01-25 | 1147745.999 | 1262839.87 | 227119.0872 | 309898 | 84261.745 | 162066.82 | 177302.8014 | 192266.84 | 539419.1654 | 598981.28 | 119643.2 | 386.82 | 1463.151 | 468.28 | 635.6376 | 0 | 370.7517 | 468.28 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2026-01-26 | 1149209.15 | 1265814.7 | 227754.7248 | 312164 | 84632.4966 | 162066.82 | 177482.5028 | 192945.67 | 539696.2258 | 599011.28 | 119643.2 | 386.82 | 1463.151 | 2974.83 | 635.6376 | 2266 | 370.7517 | 0 | 179.7013 | 678.83 | 277.0604 | 30 | 0 | 0
2026-01-27 | 1150672.301 | 1270844.14 | 228390.3624 | 314430 | 85003.2483 | 162130.26 | 177662.2041 | 192945.67 | 539973.2862 | 601711.28 | 119643.2 | 386.82 | 1463.151 | 5029.44 | 635.6376 | 2266 | 370.7517 | 63.44 | 179.7013 | 0 | 277.0604 | 2700 | 0 | 0
2026-01-28 | 1152135.452 | 1273505.34 | 229026 | 316696 | 85374 | 162525.46 | 177841.9054 | 192945.67 | 540250.3465 | 601711.28 | 119643.2 | 386.82 | 1463.151 | 2661.2 | 635.6376 | 2266 | 370.7517 | 395.2 | 179.7013 | 0 | 277.0604 | 0 | 0 | 0
2026-01-29 | 1154322.7591 | 1275984.93 | 230328.4857 | 318962 | 86038.9798 | 162582.68 | 177841.9054 | 193084.78 | 540470.1882 | 601728.54 | 119643.2 | 386.82 | 2187.3071 | 2479.59 | 1302.4857 | 2266 | 664.9798 | 57.22 | 0 | 139.11 | 219.8417 | 17.26 | 0 | 0
2026-01-30 | 1156510.0662 | 1283608.36 | 231630.9714 | 321228 | 86703.9595 | 167671.1 | 177841.9054 | 193353.79 | 540690.0299 | 601728.54 | 119643.2 | 386.82 | 2187.3071 | 7623.43 | 1302.4857 | 2266 | 664.9798 | 5088.42 | 0 | 269.01 | 219.8417 | 0 | 0 | 0
2026-01-31 | 1158697.3733 | 1287106.53 | 232933.4571 | 321228 | 87368.9393 | 167737.45 | 177841.9054 | 193353.79 | 540909.8715 | 605160.36 | 119643.2 | 386.82 | 2187.3071 | 3498.17 | 1302.4857 | 0 | 664.9798 | 66.35 | 0 | 0 | 219.8417 | 3431.82 | 0 | 0
2026-02-01 | 1160884.6805 | 1287158.85 | 234235.9428 | 321228 | 88033.919 | 167789.77 | 177841.9054 | 193353.79 | 541129.7132 | 605160.36 | 119643.2 | 386.82 | 2187.3071 | 52.32 | 1302.4857 | 0 | 664.9798 | 52.32 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-02-02 | 1163071.9876 | 1293397.87 | 235538.4285 | 322501.4 | 88698.8988 | 170834.67 | 177841.9054 | 195263.15 | 541349.5549 | 605171.72 | 119643.2 | 386.82 | 2187.3071 | 6239.02 | 1302.4857 | 1273.4 | 664.9798 | 3044.9 | 0 | 1909.36 | 219.8417 | 11.36 | 0 | 0
2026-02-03 | 1165259.2947 | 1295692.92 | 236840.9142 | 323774.8 | 89363.8786 | 171179.87 | 177841.9054 | 195263.15 | 541569.3965 | 605848.17 | 119643.2 | 386.82 | 2187.3071 | 2295.05 | 1302.4857 | 1273.4 | 664.9798 | 345.2 | 0 | 0 | 219.8417 | 676.45 | 0 | 0
2026-02-04 | 1167446.6019 | 1297100.54 | 238143.3999 | 325048.2 | 90028.8583 | 171280.18 | 177841.9054 | 195286.28 | 541789.2382 | 605858.95 | 119643.2 | 386.82 | 2187.3071 | 1407.62 | 1302.4857 | 1273.4 | 664.9798 | 100.31 | 0 | 23.13 | 219.8417 | 10.78 | 0 | 0
2026-02-05 | 1169633.909 | 1298402.34 | 239445.8856 | 326321.6 | 90693.8381 | 171280.18 | 177841.9054 | 195299.68 | 542009.0799 | 605873.95 | 119643.2 | 386.82 | 2187.3071 | 1301.8 | 1302.4857 | 1273.4 | 664.9798 | 0 | 0 | 13.4 | 219.8417 | 15 | 0 | 0
2026-02-06 | 1171821.2161 | 1302355.18 | 240748.3713 | 327595 | 91358.8178 | 173614.82 | 177841.9054 | 195644.48 | 542228.9215 | 605873.95 | 119643.2 | 386.82 | 2187.3071 | 3952.84 | 1302.4857 | 1273.4 | 664.9798 | 2334.64 | 0 | 344.8 | 219.8417 | 0 | 0 | 0
2026-02-07 | 1174008.5232 | 1302355.18 | 242050.857 | 327595 | 92023.7976 | 173614.82 | 177841.9054 | 195644.48 | 542448.7632 | 605873.95 | 119643.2 | 386.82 | 2187.3071 | 0 | 1302.4857 | 0 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-02-08 | 1176195.8304 | 1302355.18 | 243353.3427 | 327595 | 92688.7774 | 173614.82 | 177841.9054 | 195644.48 | 542668.6049 | 605873.95 | 119643.2 | 386.82 | 2187.3071 | 0 | 1302.4857 | 0 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-02-09 | 1178383.1375 | 1310183 | 244655.8284 | 328732.95 | 93353.7571 | 176594.69 | 177841.9054 | 195644.48 | 542888.4465 | 609583.95 | 119643.2 | 386.82 | 2187.3071 | 7827.82 | 1302.4857 | 1137.95 | 664.9798 | 2979.87 | 0 | 0 | 219.8417 | 3710 | 0 | 0
2026-02-10 | 1180570.4446 | 1311320.95 | 245958.3141 | 329870.9 | 94018.7369 | 176594.69 | 177841.9054 | 195644.48 | 543108.2882 | 609583.95 | 119643.2 | 386.82 | 2187.3071 | 1137.95 | 1302.4857 | 1137.95 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-02-11 | 1182757.7517 | 1312497.41 | 247260.7998 | 331008.85 | 94683.7166 | 176623.5 | 177841.9054 | 195654.18 | 543328.1299 | 609583.95 | 119643.2 | 386.82 | 2187.3071 | 1176.46 | 1302.4857 | 1137.95 | 664.9798 | 28.81 | 0 | 9.7 | 219.8417 | 0 | 0 | 0
2026-02-12 | 1184945.0589 | 1313985.36 | 248563.2855 | 332146.8 | 95348.6964 | 176973.5 | 177841.9054 | 195654.18 | 543547.9715 | 609583.95 | 119643.2 | 386.82 | 2187.3071 | 1487.95 | 1302.4857 | 1137.95 | 664.9798 | 350 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-02-13 | 1187132.366 | 1316366.17 | 249865.7712 | 333284.75 | 96013.6762 | 177583.8 | 177841.9054 | 195654.18 | 543767.8132 | 610216.51 | 119643.2 | 386.82 | 2187.3071 | 2380.81 | 1302.4857 | 1137.95 | 664.9798 | 610.3 | 0 | 0 | 219.8417 | 632.56 | 0 | 0
2026-02-14 | 1189319.6731 | 1316366.17 | 251168.2569 | 333284.75 | 96678.6559 | 177583.8 | 177841.9054 | 195654.18 | 543987.6549 | 610216.51 | 119643.2 | 386.82 | 2187.3071 | 0 | 1302.4857 | 0 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-02-15 | 1191506.9802 | 1316366.17 | 252470.7426 | 333284.75 | 97343.6357 | 177583.8 | 177841.9054 | 195654.18 | 544207.4965 | 610216.51 | 119643.2 | 386.82 | 2187.3071 | 0 | 1302.4857 | 0 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-02-16 | 1193694.2874 | 1318796.455 | 253773.2283 | 333924.775 | 98008.6154 | 177583.8 | 177841.9054 | 195654.18 | 544427.3382 | 612006.77 | 119643.2 | 386.82 | 2187.3071 | 2430.285 | 1302.4857 | 640.025 | 664.9798 | 0 | 0 | 0 | 219.8417 | 1790.26 | 0 | 0
2026-02-17 | 1195881.5945 | 1322848.13 | 255075.714 | 334564.8 | 98673.5952 | 178022 | 177841.9054 | 195654.18 | 544647.1799 | 614980.22 | 119643.2 | 386.82 | 2187.3071 | 4051.675 | 1302.4857 | 640.025 | 664.9798 | 438.2 | 0 | 0 | 219.8417 | 2973.45 | 0 | 0
2026-02-18 | 1198068.9016 | 1323488.155 | 256378.1997 | 335204.825 | 99338.575 | 178022 | 177841.9054 | 195654.18 | 544867.0215 | 614980.22 | 119643.2 | 386.82 | 2187.3071 | 640.025 | 1302.4857 | 640.025 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-02-19 | 1200256.2088 | 1324508.57 | 257680.6854 | 335844.85 | 100003.5547 | 178402.39 | 177841.9054 | 195654.18 | 545086.8632 | 614980.22 | 119643.2 | 386.82 | 2187.3071 | 1020.415 | 1302.4857 | 640.025 | 664.9798 | 380.39 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-02-20 | 1202443.5159 | 1327155.175 | 258983.1711 | 336484.875 | 100668.5345 | 180408.97 | 177841.9054 | 195654.18 | 545306.7049 | 614980.22 | 119643.2 | 386.82 | 2187.3071 | 2646.605 | 1302.4857 | 640.025 | 664.9798 | 2006.58 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-02-21 | 1204630.823 | 1327155.175 | 260285.6568 | 336484.875 | 101333.5142 | 180408.97 | 177841.9054 | 195654.18 | 545526.5465 | 614980.22 | 119643.2 | 386.82 | 2187.3071 | 0 | 1302.4857 | 0 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-02-22 | 1206818.1301 | 1327155.175 | 261588.1425 | 336484.875 | 101998.494 | 180408.97 | 177841.9054 | 195654.18 | 545746.3882 | 614980.22 | 119643.2 | 386.82 | 2187.3071 | 0 | 1302.4857 | 0 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-02-23 | 1209005.4373 | 1327339.7 | 262890.6282 | 336669.4 | 102663.4738 | 180408.97 | 177841.9054 | 195654.18 | 545966.2299 | 614980.22 | 119643.2 | 386.82 | 2187.3071 | 184.525 | 1302.4857 | 184.525 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-02-24 | 1211192.7444 | 1329384.075 | 264193.1139 | 336853.925 | 103328.4535 | 182268.82 | 177841.9054 | 195654.18 | 546186.0715 | 614980.22 | 119643.2 | 386.82 | 2187.3071 | 2044.375 | 1302.4857 | 184.525 | 664.9798 | 1859.85 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-02-25 | 1213380.0515 | 1330208.4 | 265495.5996 | 337038.45 | 103993.4333 | 182908.62 | 177841.9054 | 195654.18 | 546405.9132 | 614980.22 | 119643.2 | 386.82 | 2187.3071 | 824.325 | 1302.4857 | 184.525 | 664.9798 | 639.8 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-02-26 | 1215567.3586 | 1330392.925 | 266798.0853 | 337222.975 | 104658.413 | 182908.62 | 177841.9054 | 195654.18 | 546625.7549 | 614980.22 | 119643.2 | 386.82 | 2187.3071 | 184.525 | 1302.4857 | 184.525 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-02-27 | 1217754.6658 | 1331895.22 | 268100.571 | 337407.5 | 105323.3928 | 184008.62 | 177841.9054 | 195801.95 | 546845.5965 | 615050.22 | 119643.2 | 386.82 | 2187.3071 | 1502.295 | 1302.4857 | 184.525 | 664.9798 | 1100 | 0 | 147.77 | 219.8417 | 70 | 0 | 0
2026-02-28 | 1219941.9729 | 1334595.22 | 269403.0567 | 337407.5 | 105988.3726 | 184008.62 | 177841.9054 | 195801.95 | 547065.4382 | 617750.22 | 119643.2 | 386.82 | 2187.3071 | 2700 | 1302.4857 | 0 | 664.9798 | 0 | 0 | 0 | 219.8417 | 2700 | 0 | 0
2026-03-01 | 1222129.28 | 1334595.22 | 270705.5424 | 337407.5 | 106653.3523 | 184008.62 | 177841.9054 | 195801.95 | 547285.2799 | 617750.22 | 119643.2 | 386.82 | 2187.3071 | 0 | 1302.4857 | 0 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-02 | 1224316.5871 | 1336994.035 | 272008.0281 | 337841.525 | 107318.3321 | 185973.41 | 177841.9054 | 195801.95 | 547505.1215 | 617750.22 | 119643.2 | 386.82 | 2187.3071 | 2398.815 | 1302.4857 | 434.025 | 664.9798 | 1964.79 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-03 | 1226503.8943 | 1338104.51 | 273310.5138 | 338275.55 | 107983.3118 | 185973.41 | 177841.9054 | 195801.95 | 547724.9632 | 618426.67 | 119643.2 | 386.82 | 2187.3071 | 1110.475 | 1302.4857 | 434.025 | 664.9798 | 0 | 0 | 0 | 219.8417 | 676.45 | 0 | 0
2026-03-04 | 1228691.2014 | 1345042.055 | 274612.9995 | 338709.575 | 108648.2916 | 185973.41 | 177841.9054 | 195801.95 | 547944.8049 | 624930.19 | 119643.2 | 386.82 | 2187.3071 | 6937.545 | 1302.4857 | 434.025 | 664.9798 | 0 | 0 | 0 | 219.8417 | 6503.52 | 0 | 0
2026-03-05 | 1230878.5085 | 1345476.08 | 275915.4852 | 339143.6 | 109313.2714 | 185973.41 | 177841.9054 | 195801.95 | 548164.6465 | 624930.19 | 119643.2 | 386.82 | 2187.3071 | 434.025 | 1302.4857 | 434.025 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-06 | 1233065.8157 | 1347997.985 | 277217.9709 | 339577.625 | 109978.2511 | 188061.29 | 177841.9054 | 195801.95 | 548384.4882 | 624930.19 | 119643.2 | 386.82 | 2187.3071 | 2521.905 | 1302.4857 | 434.025 | 664.9798 | 2087.88 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-07 | 1235253.1228 | 1347997.985 | 278520.4566 | 339577.625 | 110643.2309 | 188061.29 | 177841.9054 | 195801.95 | 548604.3299 | 624930.19 | 119643.2 | 386.82 | 2187.3071 | 0 | 1302.4857 | 0 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-08 | 1237440.4299 | 1347997.985 | 279822.9423 | 339577.625 | 111308.2106 | 188061.29 | 177841.9054 | 195801.95 | 548824.1715 | 624930.19 | 119643.2 | 386.82 | 2187.3071 | 0 | 1302.4857 | 0 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-09 | 1239627.737 | 1348621.735 | 281125.428 | 340201.375 | 111973.1904 | 188061.29 | 177841.9054 | 195801.95 | 549044.0132 | 624930.19 | 119643.2 | 386.82 | 2187.3071 | 623.75 | 1302.4857 | 623.75 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-10 | 1241815.0442 | 1349245.485 | 282427.9137 | 340825.125 | 112638.1702 | 188061.29 | 177841.9054 | 195801.95 | 549263.8549 | 624930.19 | 119643.2 | 386.82 | 2187.3071 | 623.75 | 1302.4857 | 623.75 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-11 | 1244002.3513 | 1349869.235 | 283730.3994 | 341448.875 | 113303.1499 | 188061.29 | 177841.9054 | 195801.95 | 549483.6965 | 624930.19 | 119643.2 | 386.82 | 2187.3071 | 623.75 | 1302.4857 | 623.75 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-12 | 1246189.6584 | 1350492.985 | 285032.8851 | 342072.625 | 113968.1297 | 188061.29 | 177841.9054 | 195801.95 | 549703.5382 | 624930.19 | 119643.2 | 386.82 | 2187.3071 | 623.75 | 1302.4857 | 623.75 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-13 | 1248376.9655 | 1352706.635 | 286335.3708 | 342696.375 | 114633.1094 | 189651.19 | 177841.9054 | 195801.95 | 549923.3799 | 624930.19 | 119643.2 | 386.82 | 2187.3071 | 2213.65 | 1302.4857 | 623.75 | 664.9798 | 1589.9 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-14 | 1250564.2727 | 1352706.635 | 287637.8565 | 342696.375 | 115298.0892 | 189651.19 | 177841.9054 | 195801.95 | 550143.2215 | 624930.19 | 119643.2 | 386.82 | 2187.3071 | 0 | 1302.4857 | 0 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-15 | 1252751.5798 | 1352706.635 | 288940.3422 | 342696.375 | 115963.069 | 189651.19 | 177841.9054 | 195801.95 | 550363.0632 | 624930.19 | 119643.2 | 386.82 | 2187.3071 | 0 | 1302.4857 | 0 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-16 | 1254938.8869 | 1353414.26 | 290242.8279 | 343404 | 116628.0487 | 189651.19 | 177841.9054 | 195801.95 | 550582.9049 | 624930.19 | 119643.2 | 386.82 | 2187.3071 | 707.625 | 1302.4857 | 707.625 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-17 | 1257126.194 | 1354121.885 | 291545.3136 | 344111.625 | 117293.0285 | 189651.19 | 177841.9054 | 195801.95 | 550802.7465 | 624930.19 | 119643.2 | 386.82 | 2187.3071 | 707.625 | 1302.4857 | 707.625 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-18 | 1259313.5012 | 1354829.51 | 292847.7993 | 344819.25 | 117958.0082 | 189651.19 | 177841.9054 | 195801.95 | 551022.5882 | 624930.19 | 119643.2 | 386.82 | 2187.3071 | 707.625 | 1302.4857 | 707.625 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-19 | 1261500.8083 | 1355537.135 | 294150.285 | 345526.875 | 118622.988 | 189651.19 | 177841.9054 | 195801.95 | 551242.4299 | 624930.19 | 119643.2 | 386.82 | 2187.3071 | 707.625 | 1302.4857 | 707.625 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-20 | 1263688.1154 | 1356244.76 | 295452.7707 | 346234.5 | 119287.9678 | 189651.19 | 177841.9054 | 195801.95 | 551462.2715 | 624930.19 | 119643.2 | 386.82 | 2187.3071 | 707.625 | 1302.4857 | 707.625 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-21 | 1265875.4226 | 1356244.76 | 296755.2564 | 346234.5 | 119952.9475 | 189651.19 | 177841.9054 | 195801.95 | 551682.1132 | 624930.19 | 119643.2 | 386.82 | 2187.3071 | 0 | 1302.4857 | 0 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-22 | 1268062.7297 | 1356244.76 | 298057.7421 | 346234.5 | 120617.9273 | 189651.19 | 177841.9054 | 195801.95 | 551901.9549 | 624930.19 | 119643.2 | 386.82 | 2187.3071 | 0 | 1302.4857 | 0 | 664.9798 | 0 | 0 | 0 | 219.8417 | 0 | 0 | 0
2026-03-23 | 1270250.0368 |  | 299360.2278 |  | 121282.907 |  | 177841.9054 |  | 552121.7965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-24 | 1272437.3439 |  | 300662.7135 |  | 121947.8868 |  | 177841.9054 |  | 552341.6382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-25 | 1274624.6511 |  | 301965.1992 |  | 122612.8666 |  | 177841.9054 |  | 552561.4799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-26 | 1276811.9582 |  | 303267.6849 |  | 123277.8463 |  | 177841.9054 |  | 552781.3215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-27 | 1278999.2653 |  | 304570.1706 |  | 123942.8261 |  | 177841.9054 |  | 553001.1632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-28 | 1281186.5724 |  | 305872.6563 |  | 124607.8058 |  | 177841.9054 |  | 553221.0049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-29 | 1283373.8796 |  | 307175.142 |  | 125272.7856 |  | 177841.9054 |  | 553440.8465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-30 | 1285561.1867 |  | 308477.6277 |  | 125937.7654 |  | 177841.9054 |  | 553660.6882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-31 | 1287748.4938 |  | 309780.1134 |  | 126602.7451 |  | 177841.9054 |  | 553880.5299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-01 | 1289935.8009 |  | 311082.5991 |  | 127267.7249 |  | 177841.9054 |  | 554100.3715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-02 | 1292123.1081 |  | 312385.0848 |  | 127932.7046 |  | 177841.9054 |  | 554320.2132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-03 | 1294310.4152 |  | 313687.5705 |  | 128597.6844 |  | 177841.9054 |  | 554540.0549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-04 | 1296497.7223 |  | 314990.0562 |  | 129262.6642 |  | 177841.9054 |  | 554759.8965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-05 | 1298685.0295 |  | 316292.5419 |  | 129927.6439 |  | 177841.9054 |  | 554979.7382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-06 | 1300872.3366 |  | 317595.0276 |  | 130592.6237 |  | 177841.9054 |  | 555199.5799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-07 | 1303059.6437 |  | 318897.5133 |  | 131257.6034 |  | 177841.9054 |  | 555419.4215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-08 | 1305246.9508 |  | 320199.999 |  | 131922.5832 |  | 177841.9054 |  | 555639.2632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-09 | 1307434.258 |  | 321502.4847 |  | 132587.563 |  | 177841.9054 |  | 555859.1049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-10 | 1309621.5651 |  | 322804.9704 |  | 133252.5427 |  | 177841.9054 |  | 556078.9465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-11 | 1311808.8722 |  | 324107.4561 |  | 133917.5225 |  | 177841.9054 |  | 556298.7882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-12 | 1313996.1793 |  | 325409.9418 |  | 134582.5022 |  | 177841.9054 |  | 556518.6299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-13 | 1316183.4865 |  | 326712.4275 |  | 135247.482 |  | 177841.9054 |  | 556738.4715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-14 | 1318370.7936 |  | 328014.9132 |  | 135912.4618 |  | 177841.9054 |  | 556958.3132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-15 | 1320558.1007 |  | 329317.3989 |  | 136577.4415 |  | 177841.9054 |  | 557178.1549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-16 | 1322745.4078 |  | 330619.8846 |  | 137242.4213 |  | 177841.9054 |  | 557397.9965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-17 | 1324932.715 |  | 331922.3703 |  | 137907.401 |  | 177841.9054 |  | 557617.8382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-18 | 1327120.0221 |  | 333224.856 |  | 138572.3808 |  | 177841.9054 |  | 557837.6799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-19 | 1329307.3292 |  | 334527.3417 |  | 139237.3606 |  | 177841.9054 |  | 558057.5215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-20 | 1331494.6364 |  | 335829.8274 |  | 139902.3403 |  | 177841.9054 |  | 558277.3632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-21 | 1333681.9435 |  | 337132.3131 |  | 140567.3201 |  | 177841.9054 |  | 558497.2049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-22 | 1335869.2506 |  | 338434.7988 |  | 141232.2998 |  | 177841.9054 |  | 558717.0465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-23 | 1338056.5577 |  | 339737.2845 |  | 141897.2796 |  | 177841.9054 |  | 558936.8882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-24 | 1340243.8649 |  | 341039.7702 |  | 142562.2594 |  | 177841.9054 |  | 559156.7299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-25 | 1342431.172 |  | 342342.2559 |  | 143227.2391 |  | 177841.9054 |  | 559376.5715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-26 | 1344618.4791 |  | 343644.7416 |  | 143892.2189 |  | 177841.9054 |  | 559596.4132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-27 | 1346805.7862 |  | 344947.2273 |  | 144557.1986 |  | 177841.9054 |  | 559816.2549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-28 | 1348993.0934 |  | 346249.713 |  | 145222.1784 |  | 177841.9054 |  | 560036.0965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-29 | 1351180.4005 |  | 347552.1987 |  | 145887.1582 |  | 177841.9054 |  | 560255.9382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-30 | 1353367.7076 |  | 348854.6844 |  | 146552.1379 |  | 177841.9054 |  | 560475.7799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-01 | 1355555.0147 |  | 350157.1701 |  | 147217.1177 |  | 177841.9054 |  | 560695.6215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-02 | 1357742.3219 |  | 351459.6558 |  | 147882.0974 |  | 177841.9054 |  | 560915.4632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-03 | 1359929.629 |  | 352762.1415 |  | 148547.0772 |  | 177841.9054 |  | 561135.3049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-04 | 1362116.9361 |  | 354064.6272 |  | 149212.057 |  | 177841.9054 |  | 561355.1465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-05 | 1364304.2433 |  | 355367.1129 |  | 149877.0367 |  | 177841.9054 |  | 561574.9882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-06 | 1366491.5504 |  | 356669.5986 |  | 150542.0165 |  | 177841.9054 |  | 561794.8299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-07 | 1368678.8575 |  | 357972.0843 |  | 151206.9962 |  | 177841.9054 |  | 562014.6715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-08 | 1370866.1646 |  | 359274.57 |  | 151871.976 |  | 177841.9054 |  | 562234.5132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-09 | 1373053.4718 |  | 360577.0557 |  | 152536.9558 |  | 177841.9054 |  | 562454.3549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-10 | 1375240.7789 |  | 361879.5414 |  | 153201.9355 |  | 177841.9054 |  | 562674.1965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-11 | 1377428.086 |  | 363182.0271 |  | 153866.9153 |  | 177841.9054 |  | 562894.0382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-12 | 1379615.3931 |  | 364484.5128 |  | 154531.895 |  | 177841.9054 |  | 563113.8799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-13 | 1381802.7003 |  | 365786.9985 |  | 155196.8748 |  | 177841.9054 |  | 563333.7215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-14 | 1383990.0074 |  | 367089.4842 |  | 155861.8546 |  | 177841.9054 |  | 563553.5632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-15 | 1386177.3145 |  | 368391.9699 |  | 156526.8343 |  | 177841.9054 |  | 563773.4049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-16 | 1388364.6216 |  | 369694.4556 |  | 157191.8141 |  | 177841.9054 |  | 563993.2465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-17 | 1390551.9288 |  | 370996.9413 |  | 157856.7938 |  | 177841.9054 |  | 564213.0882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-18 | 1392739.2359 |  | 372299.427 |  | 158521.7736 |  | 177841.9054 |  | 564432.9299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-19 | 1394926.543 |  | 373601.9127 |  | 159186.7534 |  | 177841.9054 |  | 564652.7715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-20 | 1397113.8502 |  | 374904.3984 |  | 159851.7331 |  | 177841.9054 |  | 564872.6132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-21 | 1399301.1573 |  | 376206.8841 |  | 160516.7129 |  | 177841.9054 |  | 565092.4549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-22 | 1401488.4644 |  | 377509.3698 |  | 161181.6926 |  | 177841.9054 |  | 565312.2965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-23 | 1403675.7715 |  | 378811.8555 |  | 161846.6724 |  | 177841.9054 |  | 565532.1382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-24 | 1405863.0787 |  | 380114.3412 |  | 162511.6522 |  | 177841.9054 |  | 565751.9799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-25 | 1408050.3858 |  | 381416.8269 |  | 163176.6319 |  | 177841.9054 |  | 565971.8215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-26 | 1410237.6929 |  | 382719.3126 |  | 163841.6117 |  | 177841.9054 |  | 566191.6632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-27 | 1412425 |  | 384021.7983 |  | 164506.5914 |  | 177841.9054 |  | 566411.5049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-28 | 1414612.3072 |  | 385324.284 |  | 165171.5712 |  | 177841.9054 |  | 566631.3465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-29 | 1416799.6143 |  | 386626.7697 |  | 165836.551 |  | 177841.9054 |  | 566851.1882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-30 | 1418986.9214 |  | 387929.2554 |  | 166501.5307 |  | 177841.9054 |  | 567071.0299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-31 | 1421174.2285 |  | 389231.7411 |  | 167166.5105 |  | 177841.9054 |  | 567290.8715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-01 | 1423361.5357 |  | 390534.2268 |  | 167831.4902 |  | 177841.9054 |  | 567510.7132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-02 | 1425548.8428 |  | 391836.7125 |  | 168496.47 |  | 177841.9054 |  | 567730.5549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-03 | 1427736.1499 |  | 393139.1982 |  | 169161.4498 |  | 177841.9054 |  | 567950.3965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-04 | 1429923.4571 |  | 394441.6839 |  | 169826.4295 |  | 177841.9054 |  | 568170.2382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-05 | 1432110.7642 |  | 395744.1696 |  | 170491.4093 |  | 177841.9054 |  | 568390.0799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-06 | 1434298.0713 |  | 397046.6553 |  | 171156.389 |  | 177841.9054 |  | 568609.9215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-07 | 1436485.3784 |  | 398349.141 |  | 171821.3688 |  | 177841.9054 |  | 568829.7632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-08 | 1438672.6856 |  | 399651.6267 |  | 172486.3486 |  | 177841.9054 |  | 569049.6049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-09 | 1440859.9927 |  | 400954.1124 |  | 173151.3283 |  | 177841.9054 |  | 569269.4465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-10 | 1443047.2998 |  | 402256.5981 |  | 173816.3081 |  | 177841.9054 |  | 569489.2882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-11 | 1445234.6069 |  | 403559.0838 |  | 174481.2878 |  | 177841.9054 |  | 569709.1299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-12 | 1447421.9141 |  | 404861.5695 |  | 175146.2676 |  | 177841.9054 |  | 569928.9715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-13 | 1449609.2212 |  | 406164.0552 |  | 175811.2474 |  | 177841.9054 |  | 570148.8132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-14 | 1451796.5283 |  | 407466.5409 |  | 176476.2271 |  | 177841.9054 |  | 570368.6549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-15 | 1453983.8354 |  | 408769.0266 |  | 177141.2069 |  | 177841.9054 |  | 570588.4965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-16 | 1456171.1426 |  | 410071.5123 |  | 177806.1866 |  | 177841.9054 |  | 570808.3382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-17 | 1458358.4497 |  | 411373.998 |  | 178471.1664 |  | 177841.9054 |  | 571028.1799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-18 | 1460545.7568 |  | 412676.4837 |  | 179136.1462 |  | 177841.9054 |  | 571248.0215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-19 | 1462733.064 |  | 413978.9694 |  | 179801.1259 |  | 177841.9054 |  | 571467.8632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-20 | 1464920.3711 |  | 415281.4551 |  | 180466.1057 |  | 177841.9054 |  | 571687.7049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-21 | 1467107.6782 |  | 416583.9408 |  | 181131.0854 |  | 177841.9054 |  | 571907.5465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-22 | 1469294.9853 |  | 417886.4265 |  | 181796.0652 |  | 177841.9054 |  | 572127.3882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-23 | 1471482.2925 |  | 419188.9122 |  | 182461.045 |  | 177841.9054 |  | 572347.2299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-24 | 1473669.5996 |  | 420491.3979 |  | 183126.0247 |  | 177841.9054 |  | 572567.0715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-25 | 1475856.9067 |  | 421793.8836 |  | 183791.0045 |  | 177841.9054 |  | 572786.9132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-26 | 1478044.2138 |  | 423096.3693 |  | 184455.9842 |  | 177841.9054 |  | 573006.7549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-27 | 1480231.521 |  | 424398.855 |  | 185120.964 |  | 177841.9054 |  | 573226.5965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-28 | 1482418.8281 |  | 425701.3407 |  | 185785.9438 |  | 177841.9054 |  | 573446.4382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-29 | 1484606.1352 |  | 427003.8264 |  | 186450.9235 |  | 177841.9054 |  | 573666.2799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-06-30 | 1486793.4423 |  | 428306.3121 |  | 187115.9033 |  | 177841.9054 |  | 573886.1215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-01 | 1488980.7495 |  | 429608.7978 |  | 187780.883 |  | 177841.9054 |  | 574105.9632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-02 | 1491168.0566 |  | 430911.2835 |  | 188445.8628 |  | 177841.9054 |  | 574325.8049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-03 | 1493355.3637 |  | 432213.7692 |  | 189110.8426 |  | 177841.9054 |  | 574545.6465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-04 | 1495542.6709 |  | 433516.2549 |  | 189775.8223 |  | 177841.9054 |  | 574765.4882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-05 | 1497729.978 |  | 434818.7406 |  | 190440.8021 |  | 177841.9054 |  | 574985.3299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-06 | 1499917.2851 |  | 436121.2263 |  | 191105.7818 |  | 177841.9054 |  | 575205.1715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-07 | 1502104.5922 |  | 437423.712 |  | 191770.7616 |  | 177841.9054 |  | 575425.0132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-08 | 1504291.8994 |  | 438726.1977 |  | 192435.7414 |  | 177841.9054 |  | 575644.8549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-09 | 1506479.2065 |  | 440028.6834 |  | 193100.7211 |  | 177841.9054 |  | 575864.6965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-10 | 1508666.5136 |  | 441331.1691 |  | 193765.7009 |  | 177841.9054 |  | 576084.5382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-11 | 1510853.8207 |  | 442633.6548 |  | 194430.6806 |  | 177841.9054 |  | 576304.3799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-12 | 1513041.1279 |  | 443936.1405 |  | 195095.6604 |  | 177841.9054 |  | 576524.2215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-13 | 1515228.435 |  | 445238.6262 |  | 195760.6402 |  | 177841.9054 |  | 576744.0632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-14 | 1517415.7421 |  | 446541.1119 |  | 196425.6199 |  | 177841.9054 |  | 576963.9049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-15 | 1519603.0492 |  | 447843.5976 |  | 197090.5997 |  | 177841.9054 |  | 577183.7465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-16 | 1521790.3564 |  | 449146.0833 |  | 197755.5794 |  | 177841.9054 |  | 577403.5882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-17 | 1523977.6635 |  | 450448.569 |  | 198420.5592 |  | 177841.9054 |  | 577623.4299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-18 | 1526164.9706 |  | 451751.0547 |  | 199085.539 |  | 177841.9054 |  | 577843.2715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-19 | 1528352.2778 |  | 453053.5404 |  | 199750.5187 |  | 177841.9054 |  | 578063.1132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-20 | 1530539.5849 |  | 454356.0261 |  | 200415.4985 |  | 177841.9054 |  | 578282.9549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-21 | 1532726.892 |  | 455658.5118 |  | 201080.4782 |  | 177841.9054 |  | 578502.7965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-22 | 1534914.1991 |  | 456960.9975 |  | 201745.458 |  | 177841.9054 |  | 578722.6382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-23 | 1537101.5063 |  | 458263.4832 |  | 202410.4378 |  | 177841.9054 |  | 578942.4799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-24 | 1539288.8134 |  | 459565.9689 |  | 203075.4175 |  | 177841.9054 |  | 579162.3215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-25 | 1541476.1205 |  | 460868.4546 |  | 203740.3973 |  | 177841.9054 |  | 579382.1632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-26 | 1543663.4276 |  | 462170.9403 |  | 204405.377 |  | 177841.9054 |  | 579602.0049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-27 | 1545850.7348 |  | 463473.426 |  | 205070.3568 |  | 177841.9054 |  | 579821.8465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-28 | 1548038.0419 |  | 464775.9117 |  | 205735.3366 |  | 177841.9054 |  | 580041.6882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-29 | 1550225.349 |  | 466078.3974 |  | 206400.3163 |  | 177841.9054 |  | 580261.5299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-30 | 1552412.6561 |  | 467380.8831 |  | 207065.2961 |  | 177841.9054 |  | 580481.3715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-07-31 | 1554599.9633 |  | 468683.3688 |  | 207730.2758 |  | 177841.9054 |  | 580701.2132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-08-01 | 1556787.2704 |  | 469985.8545 |  | 208395.2556 |  | 177841.9054 |  | 580921.0549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-08-02 | 1558974.5775 |  | 471288.3402 |  | 209060.2354 |  | 177841.9054 |  | 581140.8965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-08-03 | 1561161.8847 |  | 472590.8259 |  | 209725.2151 |  | 177841.9054 |  | 581360.7382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-08-04 | 1563349.1918 |  | 473893.3116 |  | 210390.1949 |  | 177841.9054 |  | 581580.5799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-08-05 | 1565536.4989 |  | 475195.7973 |  | 211055.1746 |  | 177841.9054 |  | 581800.4215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-08-06 | 1567723.806 |  | 476498.283 |  | 211720.1544 |  | 177841.9054 |  | 582020.2632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-08-07 | 1569911.1132 |  | 477800.7687 |  | 212385.1342 |  | 177841.9054 |  | 582240.1049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-08-08 | 1572098.4203 |  | 479103.2544 |  | 213050.1139 |  | 177841.9054 |  | 582459.9465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-08-09 | 1574285.7274 |  | 480405.7401 |  | 213715.0937 |  | 177841.9054 |  | 582679.7882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-08-10 | 1576473.0345 |  | 481708.2258 |  | 214380.0734 |  | 177841.9054 |  | 582899.6299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-08-11 | 1578660.3417 |  | 483010.7115 |  | 215045.0532 |  | 177841.9054 |  | 583119.4715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-08-12 | 1580847.6488 |  | 484313.1972 |  | 215710.033 |  | 177841.9054 |  | 583339.3132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-08-13 | 1583034.9559 |  | 485615.6829 |  | 216375.0127 |  | 177841.9054 |  | 583559.1549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-08-14 | 1585222.263 |  | 486918.1686 |  | 217039.9925 |  | 177841.9054 |  | 583778.9965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-08-15 | 1587409.5702 |  | 488220.6543 |  | 217704.9722 |  | 177841.9054 |  | 583998.8382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-08-16 | 1589596.8773 |  | 489523.14 |  | 218369.952 |  | 177841.9054 |  | 584218.6799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-08-18 | 1598818.4717 |  | 492610.241 |  | 220104.8247 |  | 178064.8178 |  | 588395.3882 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-08-19 | 1608040.0661 |  | 495697.3419 |  | 221839.6975 |  | 178287.7301 |  | 592572.0965 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-08-20 | 1617261.6604 |  | 498784.4429 |  | 223574.5702 |  | 178510.6425 |  | 596748.8049 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-08-21 | 1626483.2548 |  | 501871.5439 |  | 225309.4429 |  | 178733.5548 |  | 600925.5132 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-08-22 | 1635704.8492 |  | 504958.6449 |  | 227044.3156 |  | 178956.4671 |  | 605102.2215 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-08-23 | 1644926.4436 |  | 508045.7458 |  | 228779.1884 |  | 179179.3795 |  | 609278.9299 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-08-24 | 1654148.0379 |  | 511132.8468 |  | 230514.0611 |  | 179402.2918 |  | 613455.6382 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-08-25 | 1663369.6323 |  | 514219.9478 |  | 232248.9338 |  | 179625.2042 |  | 617632.3465 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-08-26 | 1672591.2267 |  | 517307.0488 |  | 233983.8065 |  | 179848.1165 |  | 621809.0549 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-08-27 | 1681812.8211 |  | 520394.1497 |  | 235718.6793 |  | 180071.0288 |  | 625985.7632 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-08-28 | 1691034.4154 |  | 523481.2507 |  | 237453.552 |  | 180293.9412 |  | 630162.4715 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-08-29 | 1700256.0098 |  | 526568.3517 |  | 239188.4247 |  | 180516.8535 |  | 634339.1799 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-08-30 | 1709477.6042 |  | 529655.4527 |  | 240923.2975 |  | 180739.7659 |  | 638515.8882 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-08-31 | 1718699.1986 |  | 532742.5536 |  | 242658.1702 |  | 180962.6782 |  | 642692.5965 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-09-01 | 1727920.7929 |  | 535829.6546 |  | 244393.0429 |  | 181185.5906 |  | 646869.3049 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-09-02 | 1737142.3873 |  | 538916.7556 |  | 246127.9156 |  | 181408.5029 |  | 651046.0132 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-09-03 | 1746363.9817 |  | 542003.8566 |  | 247862.7884 |  | 181631.4152 |  | 655222.7215 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-09-04 | 1755585.5761 |  | 545090.9575 |  | 249597.6611 |  | 181854.3276 |  | 659399.4299 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-09-05 | 1764807.1704 |  | 548178.0585 |  | 251332.5338 |  | 182077.2399 |  | 663576.1382 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-09-06 | 1774028.7648 |  | 551265.1595 |  | 253067.4065 |  | 182300.1523 |  | 667752.8465 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-09-07 | 1783250.3592 |  | 554352.2605 |  | 254802.2793 |  | 182523.0646 |  | 671929.5549 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-09-08 | 1792471.9536 |  | 557439.3614 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-09-09 | 1793082.4 |  | 558049.8079 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-10 | 1793692.8464 |  | 558660.2543 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-11 | 1794303.2928 |  | 559270.7007 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-12 | 1794913.7393 |  | 559881.1471 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-13 | 1795524.1857 |  | 560491.5936 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-14 | 1796134.6321 |  | 561102.04 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-15 | 1796745.0786 |  | 561712.4864 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-16 | 1797355.525 |  | 562322.9329 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-17 | 1797965.9714 |  | 562933.3793 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-18 | 1798576.4178 |  | 563543.8257 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-19 | 1799186.8643 |  | 564154.2721 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-20 | 1799797.3107 |  | 564764.7186 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-21 | 1800407.7571 |  | 565375.165 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-22 | 1801018.2036 |  | 565985.6114 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-23 | 1801628.65 |  | 566596.0579 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-24 | 1802239.0964 |  | 567206.5043 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-25 | 1802849.5428 |  | 567816.9507 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-26 | 1803459.9893 |  | 568427.3971 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-27 | 1804070.4357 |  | 569037.8436 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-28 | 1804680.8821 |  | 569648.29 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-29 | 1805291.3286 |  | 570258.7364 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-09-30 | 1805901.775 |  | 570869.1829 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-10-01 | 1806512.2214 |  | 571479.6293 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-10-02 | 1807122.6678 |  | 572090.0757 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-10-03 | 1807733.1143 |  | 572700.5221 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-10-04 | 1808343.5607 |  | 573310.9686 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-10-05 | 1808954.0071 |  | 573921.415 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-10-06 | 1809564.4536 |  | 574531.8614 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-10-07 | 1810174.9 |  | 575142.3079 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-10-08 | 1810785.3464 |  | 575752.7543 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-10-09 | 1811395.7928 |  | 576363.2007 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-10-10 | 1812006.2393 |  | 576973.6471 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-10-11 | 1812616.6857 |  | 577584.0936 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-10-12 | 1813227.1321 |  | 578194.54 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0

## Labor Cost
Date | Planned Labor (Cumulative) | Actual Labor (Cumulative) | Planned 5101 · Salary and wages (Direct) (Cumulative) | Actual 5101 · Salary and wages (Direct) (Cumulative) | Planned 5102 · Payroll taxes (Direct) (Cumulative) | Actual 5102 · Payroll taxes (Direct) (Cumulative)
2025-04-01 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0
2025-04-02 | 2593.9167 | 0 | 2593.9167 | 0 | 0 | 0
2025-04-03 | 3890.875 | 0 | 3890.875 | 0 | 0 | 0
2025-04-04 | 5187.8333 | 0 | 5187.8333 | 0 | 0 | 0
2025-04-05 | 6484.7917 | 0 | 6484.7917 | 0 | 0 | 0
2025-04-06 | 7781.75 | 0 | 7781.75 | 0 | 0 | 0
2025-04-07 | 9078.7083 | 2614.5 | 9078.7083 | 2614.5 | 0 | 2614.5
2025-04-08 | 10375.6667 | 5229 | 10375.6667 | 5229 | 0 | 5229
2025-04-09 | 11672.625 | 7843.5 | 11672.625 | 7843.5 | 0 | 7843.5
2025-04-10 | 12969.5833 | 10458 | 12969.5833 | 10458 | 0 | 10458
2025-04-11 | 14266.5417 | 13072.5 | 14266.5417 | 13072.5 | 0 | 13072.5
2025-04-12 | 15563.5 | 13072.5 | 15563.5 | 13072.5 | 0 | 13072.5
2025-04-13 | 16860.4583 | 13072.5 | 16860.4583 | 13072.5 | 0 | 13072.5
2025-04-14 | 18157.4167 | 13340.5 | 18157.4167 | 13340.5 | 0 | 13340.5
2025-04-15 | 19454.375 | 13608.5 | 19454.375 | 13608.5 | 0 | 13608.5
2025-04-16 | 20751.3333 | 13876.5 | 20751.3333 | 13876.5 | 0 | 13876.5
2025-04-17 | 22048.2917 | 14144.5 | 22048.2917 | 14144.5 | 0 | 14144.5
2025-04-18 | 23345.25 | 14412.5 | 23345.25 | 14412.5 | 0 | 14412.5
2025-04-19 | 24642.2083 | 14412.5 | 24642.2083 | 14412.5 | 0 | 14412.5
2025-04-20 | 25939.1667 | 14412.5 | 25939.1667 | 14412.5 | 0 | 14412.5
2025-04-21 | 27236.125 | 14412.5 | 27236.125 | 14412.5 | 0 | 14412.5
2025-04-22 | 28533.0833 | 14412.5 | 28533.0833 | 14412.5 | 0 | 14412.5
2025-04-23 | 29830.0417 | 14412.5 | 29830.0417 | 14412.5 | 0 | 14412.5
2025-04-24 | 31127 | 14412.5 | 31127 | 14412.5 | 0 | 14412.5
2025-04-25 | 32423.9583 | 14412.5 | 32423.9583 | 14412.5 | 0 | 14412.5
2025-04-26 | 33720.9167 | 14412.5 | 33720.9167 | 14412.5 | 0 | 14412.5
2025-04-27 | 35017.875 | 14412.5 | 35017.875 | 14412.5 | 0 | 14412.5
2025-04-28 | 36314.8333 | 14412.5 | 36314.8333 | 14412.5 | 0 | 14412.5
2025-04-29 | 37611.7917 | 14412.5 | 37611.7917 | 14412.5 | 0 | 14412.5
2025-04-30 | 38908.75 | 14412.5 | 38908.75 | 14412.5 | 0 | 14412.5
2025-05-01 | 40205.7083 | 14412.5 | 40205.7083 | 14412.5 | 0 | 14412.5
2025-05-02 | 41502.6667 | 14412.5 | 41502.6667 | 14412.5 | 0 | 14412.5
2025-05-03 | 42799.625 | 14412.5 | 42799.625 | 14412.5 | 0 | 14412.5
2025-05-04 | 44096.5833 | 14412.5 | 44096.5833 | 14412.5 | 0 | 14412.5
2025-05-05 | 45393.5417 | 14412.5 | 45393.5417 | 14412.5 | 0 | 14412.5
2025-05-06 | 46690.5 | 14412.5 | 46690.5 | 14412.5 | 0 | 14412.5
2025-05-07 | 47987.4583 | 14412.5 | 47987.4583 | 14412.5 | 0 | 14412.5
2025-05-08 | 49284.4167 | 14412.5 | 49284.4167 | 14412.5 | 0 | 14412.5
2025-05-09 | 50581.375 | 14412.5 | 50581.375 | 14412.5 | 0 | 14412.5
2025-05-10 | 51878.3333 | 14412.5 | 51878.3333 | 14412.5 | 0 | 14412.5
2025-05-11 | 53175.2917 | 14412.5 | 53175.2917 | 14412.5 | 0 | 14412.5
2025-05-12 | 54472.25 | 14412.5 | 54472.25 | 14412.5 | 0 | 14412.5
2025-05-13 | 55769.2083 | 14412.5 | 55769.2083 | 14412.5 | 0 | 14412.5
2025-05-14 | 57066.1667 | 14412.5 | 57066.1667 | 14412.5 | 0 | 14412.5
2025-05-15 | 58363.125 | 14412.5 | 58363.125 | 14412.5 | 0 | 14412.5
2025-05-16 | 59660.0833 | 14412.5 | 59660.0833 | 14412.5 | 0 | 14412.5
2025-05-17 | 60957.0417 | 14412.5 | 60957.0417 | 14412.5 | 0 | 14412.5
2025-05-18 | 62254 | 14412.5 | 62254 | 14412.5 | 0 | 14412.5
2025-05-19 | 63550.9583 | 15089.45 | 63550.9583 | 15089.45 | 0 | 15089.45
2025-05-20 | 64847.9167 | 15766.4 | 64847.9167 | 15766.4 | 0 | 15766.4
2025-05-21 | 66144.875 | 16443.35 | 66144.875 | 16443.35 | 0 | 16443.35
2025-05-22 | 67441.8333 | 17120.3 | 67441.8333 | 17120.3 | 0 | 17120.3
2025-05-23 | 68738.7917 | 17797.25 | 68738.7917 | 17797.25 | 0 | 17797.25
2025-05-24 | 70035.75 | 17797.25 | 70035.75 | 17797.25 | 0 | 17797.25
2025-05-25 | 71332.7083 | 17797.25 | 71332.7083 | 17797.25 | 0 | 17797.25
2025-05-26 | 72629.6667 | 17797.25 | 72629.6667 | 17797.25 | 0 | 17797.25
2025-05-27 | 73926.625 | 17797.25 | 73926.625 | 17797.25 | 0 | 17797.25
2025-05-28 | 75223.5833 | 17797.25 | 75223.5833 | 17797.25 | 0 | 17797.25
2025-05-29 | 76520.5417 | 17797.25 | 76520.5417 | 17797.25 | 0 | 17797.25
2025-05-30 | 77817.5 | 17797.25 | 77817.5 | 17797.25 | 0 | 17797.25
2025-06-01 | 77938.5843 | 17797.25 | 77938.5843 | 17797.25 | 0 | 17797.25
2025-06-02 | 78059.6687 | 17797.25 | 78059.6687 | 17797.25 | 0 | 17797.25
2025-06-03 | 78180.753 | 17797.25 | 78180.753 | 17797.25 | 0 | 17797.25
2025-06-04 | 78301.8373 | 17797.25 | 78301.8373 | 17797.25 | 0 | 17797.25
2025-06-05 | 78422.9217 | 17797.25 | 78422.9217 | 17797.25 | 0 | 17797.25
2025-06-06 | 78544.006 | 17797.25 | 78544.006 | 17797.25 | 0 | 17797.25
2025-06-07 | 78665.0904 | 17797.25 | 78665.0904 | 17797.25 | 0 | 17797.25
2025-06-08 | 78786.1747 | 17797.25 | 78786.1747 | 17797.25 | 0 | 17797.25
2025-06-09 | 78907.259 | 18233 | 78907.259 | 18233 | 0 | 18233
2025-06-10 | 79028.3434 | 18668.75 | 79028.3434 | 18668.75 | 0 | 18668.75
2025-06-11 | 79149.4277 | 19104.5 | 79149.4277 | 19104.5 | 0 | 19104.5
2025-06-12 | 79270.512 | 19540.25 | 79270.512 | 19540.25 | 0 | 19540.25
2025-06-13 | 79391.5964 | 19976 | 79391.5964 | 19976 | 0 | 19976
2025-06-14 | 79512.6807 | 19976 | 79512.6807 | 19976 | 0 | 19976
2025-06-15 | 79633.7651 | 19976 | 79633.7651 | 19976 | 0 | 19976
2025-06-16 | 79754.8494 | 20244 | 79754.8494 | 20244 | 0 | 20244
2025-06-17 | 79875.9337 | 20512 | 79875.9337 | 20512 | 0 | 20512
2025-06-18 | 79997.0181 | 20780 | 79997.0181 | 20780 | 0 | 20780
2025-06-19 | 80118.1024 | 21048 | 80118.1024 | 21048 | 0 | 21048
2025-06-20 | 80239.1867 | 21316 | 80239.1867 | 21316 | 0 | 21316
2025-06-21 | 80360.2711 | 21316 | 80360.2711 | 21316 | 0 | 21316
2025-06-22 | 80481.3554 | 21316 | 80481.3554 | 21316 | 0 | 21316
2025-06-23 | 80602.4398 | 21316 | 80602.4398 | 21316 | 0 | 21316
2025-06-24 | 80723.5241 | 21316 | 80723.5241 | 21316 | 0 | 21316
2025-06-25 | 80844.6084 | 21316 | 80844.6084 | 21316 | 0 | 21316
2025-06-26 | 80965.6928 | 21316 | 80965.6928 | 21316 | 0 | 21316
2025-06-27 | 81086.7771 | 21316 | 81086.7771 | 21316 | 0 | 21316
2025-06-28 | 81207.8614 | 21316 | 81207.8614 | 21316 | 0 | 21316
2025-06-29 | 81328.9458 | 21316 | 81328.9458 | 21316 | 0 | 21316
2025-06-30 | 81450.0301 | 22180.55 | 81450.0301 | 22180.55 | 0 | 22180.55
2025-07-01 | 81571.1145 | 23045.1 | 81571.1145 | 23045.1 | 0 | 23045.1
2025-07-02 | 81692.1988 | 23909.65 | 81692.1988 | 23909.65 | 0 | 23909.65
2025-07-03 | 81813.2831 | 24774.2 | 81813.2831 | 24774.2 | 0 | 24774.2
2025-07-04 | 81934.3675 | 25638.75 | 81934.3675 | 25638.75 | 0 | 25638.75
2025-07-05 | 82055.4518 | 25638.75 | 82055.4518 | 25638.75 | 0 | 25638.75
2025-07-06 | 82176.5361 | 25638.75 | 82176.5361 | 25638.75 | 0 | 25638.75
2025-07-07 | 82297.6205 | 26359.75 | 82297.6205 | 26359.75 | 0 | 26359.75
2025-07-08 | 82418.7048 | 27080.75 | 82418.7048 | 27080.75 | 0 | 27080.75
2025-07-09 | 82539.7892 | 27801.75 | 82539.7892 | 27801.75 | 0 | 27801.75
2025-07-10 | 82660.8735 | 28522.75 | 82660.8735 | 28522.75 | 0 | 28522.75
2025-07-11 | 82781.9578 | 29243.75 | 82781.9578 | 29243.75 | 0 | 29243.75
2025-07-12 | 82903.0422 | 29243.75 | 82903.0422 | 29243.75 | 0 | 29243.75
2025-07-13 | 83024.1265 | 29243.75 | 83024.1265 | 29243.75 | 0 | 29243.75
2025-07-14 | 83145.2108 | 30919.15 | 83145.2108 | 30919.15 | 0 | 30919.15
2025-07-15 | 83266.2952 | 32594.55 | 83266.2952 | 32594.55 | 0 | 32594.55
2025-07-16 | 83387.3795 | 34269.95 | 83387.3795 | 34269.95 | 0 | 34269.95
2025-07-17 | 83508.4639 | 35945.35 | 83508.4639 | 35945.35 | 0 | 35945.35
2025-07-18 | 83629.5482 | 37620.75 | 83629.5482 | 37620.75 | 0 | 37620.75
2025-07-19 | 83750.6325 | 37620.75 | 83750.6325 | 37620.75 | 0 | 37620.75
2025-07-20 | 83871.7169 | 37620.75 | 83871.7169 | 37620.75 | 0 | 37620.75
2025-07-21 | 85072.9989 | 39350.15 | 85072.9989 | 39350.15 | 0 | 39350.15
2025-07-22 | 86274.2809 | 41079.55 | 86274.2809 | 41079.55 | 0 | 41079.55
2025-07-23 | 87475.5629 | 42808.95 | 87475.5629 | 42808.95 | 0 | 42808.95
2025-07-24 | 88676.8449 | 44538.35 | 88676.8449 | 44538.35 | 0 | 44538.35
2025-07-25 | 89878.1269 | 46267.75 | 89878.1269 | 46267.75 | 0 | 46267.75
2025-07-26 | 91079.4089 | 46267.75 | 91079.4089 | 46267.75 | 0 | 46267.75
2025-07-27 | 92280.6909 | 46267.75 | 92280.6909 | 46267.75 | 0 | 46267.75
2025-07-28 | 93481.973 | 48265.55 | 93481.973 | 48265.55 | 0 | 48265.55
2025-07-29 | 94683.255 | 50263.35 | 94683.255 | 50263.35 | 0 | 50263.35
2025-07-30 | 95884.537 | 52261.15 | 95884.537 | 52261.15 | 0 | 52261.15
2025-07-31 | 97085.819 | 54258.95 | 97085.819 | 54258.95 | 0 | 54258.95
2025-08-01 | 98287.101 | 56256.75 | 98287.101 | 56256.75 | 0 | 56256.75
2025-08-02 | 99488.383 | 56256.75 | 99488.383 | 56256.75 | 0 | 56256.75
2025-08-03 | 100689.665 | 56256.75 | 100689.665 | 56256.75 | 0 | 56256.75
2025-08-04 | 101890.947 | 58253.75 | 101890.947 | 58253.75 | 0 | 58253.75
2025-08-05 | 103092.2291 | 60250.75 | 103092.2291 | 60250.75 | 0 | 60250.75
2025-08-06 | 104293.5111 | 62247.75 | 104293.5111 | 62247.75 | 0 | 62247.75
2025-08-07 | 105494.7931 | 64244.75 | 105494.7931 | 64244.75 | 0 | 64244.75
2025-08-08 | 106696.0751 | 66241.75 | 106696.0751 | 66241.75 | 0 | 66241.75
2025-08-09 | 107897.3571 | 66241.75 | 107897.3571 | 66241.75 | 0 | 66241.75
2025-08-10 | 109098.6391 | 66241.75 | 109098.6391 | 66241.75 | 0 | 66241.75
2025-08-11 | 110299.9211 | 68909.75 | 110299.9211 | 68909.75 | 0 | 68909.75
2025-08-12 | 111501.2031 | 71577.75 | 111501.2031 | 71577.75 | 0 | 71577.75
2025-08-13 | 112702.4851 | 74245.75 | 112702.4851 | 74245.75 | 0 | 74245.75
2025-08-14 | 113903.7672 | 76913.75 | 113903.7672 | 76913.75 | 0 | 76913.75
2025-08-15 | 115105.0492 | 79581.75 | 115105.0492 | 79581.75 | 0 | 79581.75
2025-08-16 | 116306.3312 | 79581.75 | 116306.3312 | 79581.75 | 0 | 79581.75
2025-08-17 | 117507.6132 | 79581.75 | 117507.6132 | 79581.75 | 0 | 79581.75
2025-08-18 | 118708.8952 | 82249.75 | 118708.8952 | 82249.75 | 0 | 82249.75
2025-08-19 | 119910.1772 | 84917.75 | 119910.1772 | 84917.75 | 0 | 84917.75
2025-08-20 | 121111.4592 | 87585.75 | 121111.4592 | 87585.75 | 0 | 87585.75
2025-08-21 | 122312.7412 | 90253.75 | 122312.7412 | 90253.75 | 0 | 90253.75
2025-08-22 | 123514.0233 | 92921.75 | 123514.0233 | 92921.75 | 0 | 92921.75
2025-08-23 | 124594.2209 | 92921.75 | 124594.2209 | 92921.75 | 0 | 92921.75
2025-08-24 | 125674.4186 | 92921.75 | 125674.4186 | 92921.75 | 0 | 92921.75
2025-08-25 | 126754.6163 | 95147.35 | 126754.6163 | 95147.35 | 0 | 95147.35
2025-08-26 | 127834.814 | 97372.95 | 127834.814 | 97372.95 | 0 | 97372.95
2025-08-27 | 128915.0116 | 99598.55 | 128915.0116 | 99598.55 | 0 | 99598.55
2025-08-28 | 129995.2093 | 101824.15 | 129995.2093 | 101824.15 | 0 | 101824.15
2025-08-29 | 131075.407 | 104049.75 | 131075.407 | 104049.75 | 0 | 104049.75
2025-08-30 | 132155.6047 | 104049.75 | 132155.6047 | 104049.75 | 0 | 104049.75
2025-08-31 | 133235.8023 | 104049.75 | 133235.8023 | 104049.75 | 0 | 104049.75
2025-09-01 | 134316 | 105282.95 | 134316 | 105282.95 | 0 | 105282.95
2025-09-02 | 134951.6376 | 106516.15 | 134951.6376 | 106516.15 | 0 | 106516.15
2025-09-03 | 135587.2752 | 107749.35 | 135587.2752 | 107749.35 | 0 | 107749.35
2025-09-04 | 136222.9128 | 108982.55 | 136222.9128 | 108982.55 | 0 | 108982.55
2025-09-05 | 136858.5503 | 110215.75 | 136858.5503 | 110215.75 | 0 | 110215.75
2025-09-06 | 137494.1879 | 110215.75 | 137494.1879 | 110215.75 | 0 | 110215.75
2025-09-07 | 138129.8255 | 110215.75 | 138129.8255 | 110215.75 | 0 | 110215.75
2025-09-08 | 138765.4631 | 112468.15 | 138765.4631 | 112468.15 | 0 | 112468.15
2025-09-09 | 139401.1007 | 114720.55 | 139401.1007 | 114720.55 | 0 | 114720.55
2025-09-10 | 140036.7383 | 116972.95 | 140036.7383 | 116972.95 | 0 | 116972.95
2025-09-11 | 140672.3758 | 119225.35 | 140672.3758 | 119225.35 | 0 | 119225.35
2025-09-12 | 141308.0134 | 121477.75 | 141308.0134 | 121477.75 | 0 | 121477.75
2025-09-13 | 141943.651 | 121477.75 | 141943.651 | 121477.75 | 0 | 121477.75
2025-09-14 | 142579.2886 | 121477.75 | 142579.2886 | 121477.75 | 0 | 121477.75
2025-09-15 | 143214.9262 | 125315.025 | 143214.9262 | 125315.025 | 0 | 125315.025
2025-09-16 | 143850.5638 | 129152.3 | 143850.5638 | 129152.3 | 0 | 129152.3
2025-09-17 | 144486.2013 | 132989.575 | 144486.2013 | 132989.575 | 0 | 132989.575
2025-09-18 | 145121.8389 | 136826.85 | 145121.8389 | 136826.85 | 0 | 136826.85
2025-09-19 | 145757.4765 | 140664.125 | 145757.4765 | 140664.125 | 0 | 140664.125
2025-09-20 | 146393.1141 | 140664.125 | 146393.1141 | 140664.125 | 0 | 140664.125
2025-09-21 | 147028.7517 | 140664.125 | 147028.7517 | 140664.125 | 0 | 140664.125
2025-09-22 | 147664.3893 | 142895.775 | 147664.3893 | 142895.775 | 0 | 142895.775
2025-09-23 | 148300.0268 | 145127.425 | 148300.0268 | 145127.425 | 0 | 145127.425
2025-09-24 | 148935.6644 | 147359.075 | 148935.6644 | 147359.075 | 0 | 147359.075
2025-09-25 | 149571.302 | 149590.725 | 149571.302 | 149590.725 | 0 | 149590.725
2025-09-26 | 150206.9396 | 151822.375 | 150206.9396 | 151822.375 | 0 | 151822.375
2025-09-27 | 150842.5772 | 151822.375 | 150842.5772 | 151822.375 | 0 | 151822.375
2025-09-28 | 151478.2148 | 151822.375 | 151478.2148 | 151822.375 | 0 | 151822.375
2025-09-29 | 152113.8523 | 154412.35 | 152113.8523 | 154412.35 | 0 | 154412.35
2025-09-30 | 152749.4899 | 157002.325 | 152749.4899 | 157002.325 | 0 | 157002.325
2025-10-01 | 153385.1275 | 159592.3 | 153385.1275 | 159592.3 | 0 | 159592.3
2025-10-02 | 154020.7651 | 162182.275 | 154020.7651 | 162182.275 | 0 | 162182.275
2025-10-03 | 154656.4027 | 164772.25 | 154656.4027 | 164772.25 | 0 | 164772.25
2025-10-04 | 155292.0403 | 164772.25 | 155292.0403 | 164772.25 | 0 | 164772.25
2025-10-05 | 155927.6779 | 164772.25 | 155927.6779 | 164772.25 | 0 | 164772.25
2025-10-06 | 156563.3154 | 165794.425 | 156563.3154 | 165794.425 | 0 | 165794.425
2025-10-07 | 157198.953 | 166816.6 | 157198.953 | 166816.6 | 0 | 166816.6
2025-10-08 | 157834.5906 | 167838.775 | 157834.5906 | 167838.775 | 0 | 167838.775
2025-10-09 | 158470.2282 | 168860.95 | 158470.2282 | 168860.95 | 0 | 168860.95
2025-10-10 | 159105.8658 | 169883.125 | 159105.8658 | 169883.125 | 0 | 169883.125
2025-10-11 | 159741.5034 | 169883.125 | 159741.5034 | 169883.125 | 0 | 169883.125
2025-10-12 | 160377.1409 | 169883.125 | 160377.1409 | 169883.125 | 0 | 169883.125
2025-10-13 | 161012.7785 | 171910.3 | 161012.7785 | 171910.3 | 0 | 171910.3
2025-10-14 | 161648.4161 | 173937.475 | 161648.4161 | 173937.475 | 0 | 173937.475
2025-10-15 | 162284.0537 | 175964.65 | 162284.0537 | 175964.65 | 0 | 175964.65
2025-10-16 | 162919.6913 | 177991.825 | 162919.6913 | 177991.825 | 0 | 177991.825
2025-10-17 | 163555.3289 | 180019 | 163555.3289 | 180019 | 0 | 180019
2025-10-18 | 164190.9664 | 180019 | 164190.9664 | 180019 | 0 | 180019
2025-10-19 | 164826.604 | 180019 | 164826.604 | 180019 | 0 | 180019
2025-10-20 | 165462.2416 | 182968.2 | 165462.2416 | 182968.2 | 0 | 182968.2
2025-10-21 | 166097.8792 | 185917.4 | 166097.8792 | 185917.4 | 0 | 185917.4
2025-10-22 | 166733.5168 | 188866.6 | 166733.5168 | 188866.6 | 0 | 188866.6
2025-10-23 | 167369.1544 | 191815.8 | 167369.1544 | 191815.8 | 0 | 191815.8
2025-10-24 | 168004.7919 | 194765 | 168004.7919 | 194765 | 0 | 194765
2025-10-25 | 168640.4295 | 194765 | 168640.4295 | 194765 | 0 | 194765
2025-10-26 | 169276.0671 | 194765 | 169276.0671 | 194765 | 0 | 194765
2025-10-27 | 169911.7047 | 196708.4 | 169911.7047 | 196708.4 | 0 | 196708.4
2025-10-28 | 170547.3423 | 198651.8 | 170547.3423 | 198651.8 | 0 | 198651.8
2025-10-29 | 171182.9799 | 200595.2 | 171182.9799 | 200595.2 | 0 | 200595.2
2025-10-30 | 171818.6174 | 202538.6 | 171818.6174 | 202538.6 | 0 | 202538.6
2025-10-31 | 172454.255 | 204482 | 172454.255 | 204482 | 0 | 204482
2025-11-01 | 173089.8926 | 204482 | 173089.8926 | 204482 | 0 | 204482
2025-11-02 | 173725.5302 | 204482 | 173725.5302 | 204482 | 0 | 204482
2025-11-03 | 174361.1678 | 205581.2 | 174361.1678 | 205581.2 | 0 | 205581.2
2025-11-04 | 174996.8054 | 206680.4 | 174996.8054 | 206680.4 | 0 | 206680.4
2025-11-05 | 175632.443 | 207779.6 | 175632.443 | 207779.6 | 0 | 207779.6
2025-11-06 | 176268.0805 | 208878.8 | 176268.0805 | 208878.8 | 0 | 208878.8
2025-11-07 | 176903.7181 | 209978 | 176903.7181 | 209978 | 0 | 209978
2025-11-08 | 177539.3557 | 209978 | 177539.3557 | 209978 | 0 | 209978
2025-11-09 | 178174.9933 | 209978 | 178174.9933 | 209978 | 0 | 209978
2025-11-10 | 178810.6309 | 211827.2 | 178810.6309 | 211827.2 | 0 | 211827.2
2025-11-11 | 179446.2685 | 213676.4 | 179446.2685 | 213676.4 | 0 | 213676.4
2025-11-12 | 180081.906 | 215525.6 | 180081.906 | 215525.6 | 0 | 215525.6
2025-11-13 | 180717.5436 | 217374.8 | 180717.5436 | 217374.8 | 0 | 217374.8
2025-11-14 | 181353.1812 | 219224 | 181353.1812 | 219224 | 0 | 219224
2025-11-15 | 181988.8188 | 219224 | 181988.8188 | 219224 | 0 | 219224
2025-11-16 | 182624.4564 | 219224 | 182624.4564 | 219224 | 0 | 219224
2025-11-17 | 183260.094 | 221193.8 | 183260.094 | 221193.8 | 0 | 221193.8
2025-11-18 | 183895.7315 | 223163.6 | 183895.7315 | 223163.6 | 0 | 223163.6
2025-11-19 | 184531.3691 | 225133.4 | 184531.3691 | 225133.4 | 0 | 225133.4
2025-11-20 | 185167.0067 | 227103.2 | 185167.0067 | 227103.2 | 0 | 227103.2
2025-11-21 | 185802.6443 | 229073 | 185802.6443 | 229073 | 0 | 229073
2025-11-22 | 186438.2819 | 229073 | 186438.2819 | 229073 | 0 | 229073
2025-11-23 | 187073.9195 | 229073 | 187073.9195 | 229073 | 0 | 229073
2025-11-24 | 187709.557 | 229300.8 | 187709.557 | 229300.8 | 0 | 229300.8
2025-11-25 | 188345.1946 | 229528.6 | 188345.1946 | 229528.6 | 0 | 229528.6
2025-11-26 | 188980.8322 | 229756.4 | 188980.8322 | 229756.4 | 0 | 229756.4
2025-11-27 | 189616.4698 | 229984.2 | 189616.4698 | 229984.2 | 0 | 229984.2
2025-11-28 | 190252.1074 | 230212 | 190252.1074 | 230212 | 0 | 230212
2025-11-29 | 190887.745 | 230212 | 190887.745 | 230212 | 0 | 230212
2025-11-30 | 191523.3826 | 230212 | 191523.3826 | 230212 | 0 | 230212
2025-12-01 | 192159.0201 | 232155.4 | 192159.0201 | 232155.4 | 0 | 232155.4
2025-12-02 | 192794.6577 | 234098.8 | 192794.6577 | 234098.8 | 0 | 234098.8
2025-12-03 | 193430.2953 | 236042.2 | 193430.2953 | 236042.2 | 0 | 236042.2
2025-12-04 | 194065.9329 | 237985.6 | 194065.9329 | 237985.6 | 0 | 237985.6
2025-12-05 | 194701.5705 | 239929 | 194701.5705 | 239929 | 0 | 239929
2025-12-06 | 195337.2081 | 239929 | 195337.2081 | 239929 | 0 | 239929
2025-12-07 | 195972.8456 | 239929 | 195972.8456 | 239929 | 0 | 239929
2025-12-08 | 196608.4832 | 242999 | 196608.4832 | 242999 | 0 | 242999
2025-12-09 | 197244.1208 | 246069 | 197244.1208 | 246069 | 0 | 246069
2025-12-10 | 197879.7584 | 249139 | 197879.7584 | 249139 | 0 | 249139
2025-12-11 | 198515.396 | 252209 | 198515.396 | 252209 | 0 | 252209
2025-12-12 | 199151.0336 | 255279 | 199151.0336 | 255279 | 0 | 255279
2025-12-13 | 199786.6711 | 255279 | 199786.6711 | 255279 | 0 | 255279
2025-12-14 | 200422.3087 | 255279 | 200422.3087 | 255279 | 0 | 255279
2025-12-15 | 201057.9463 | 258885 | 201057.9463 | 258885 | 0 | 258885
2025-12-16 | 201693.5839 | 262491 | 201693.5839 | 262491 | 0 | 262491
2025-12-17 | 202329.2215 | 266097 | 202329.2215 | 266097 | 0 | 266097
2025-12-18 | 202964.8591 | 269703 | 202964.8591 | 269703 | 0 | 269703
2025-12-19 | 203600.4966 | 273309 | 203600.4966 | 273309 | 0 | 273309
2025-12-20 | 204236.1342 | 273309 | 204236.1342 | 273309 | 0 | 273309
2025-12-21 | 204871.7718 | 273309 | 204871.7718 | 273309 | 0 | 273309
2025-12-22 | 205507.4094 | 273630.6 | 205507.4094 | 273630.6 | 0 | 273630.6
2025-12-23 | 206143.047 | 273952.2 | 206143.047 | 273952.2 | 0 | 273952.2
2025-12-24 | 206778.6846 | 274273.8 | 206778.6846 | 274273.8 | 0 | 274273.8
2025-12-25 | 207414.3221 | 274595.4 | 207414.3221 | 274595.4 | 0 | 274595.4
2025-12-26 | 208049.9597 | 274917 | 208049.9597 | 274917 | 0 | 274917
2025-12-27 | 208685.5973 | 274917 | 208685.5973 | 274917 | 0 | 274917
2025-12-28 | 209321.2349 | 274917 | 209321.2349 | 274917 | 0 | 274917
2025-12-29 | 209956.8725 | 275115.4 | 209956.8725 | 275115.4 | 0 | 275115.4
2025-12-30 | 210592.5101 | 275313.8 | 210592.5101 | 275313.8 | 0 | 275313.8
2025-12-31 | 211228.1477 | 275512.2 | 211228.1477 | 275512.2 | 0 | 275512.2
2026-01-01 | 211863.7852 | 275710.6 | 211863.7852 | 275710.6 | 0 | 275710.6
2026-01-02 | 212499.4228 | 275909 | 212499.4228 | 275909 | 0 | 275909
2026-01-03 | 213135.0604 | 275909 | 213135.0604 | 275909 | 0 | 275909
2026-01-04 | 213770.698 | 275909 | 213770.698 | 275909 | 0 | 275909
2026-01-05 | 214406.3356 | 278241.8 | 214406.3356 | 278241.8 | 0 | 278241.8
2026-01-06 | 215041.9732 | 280574.6 | 215041.9732 | 280574.6 | 0 | 280574.6
2026-01-07 | 215677.6107 | 282907.4 | 215677.6107 | 282907.4 | 0 | 282907.4
2026-01-08 | 216313.2483 | 285240.2 | 216313.2483 | 285240.2 | 0 | 285240.2
2026-01-09 | 216948.8859 | 287573 | 216948.8859 | 287573 | 0 | 287573
2026-01-10 | 217584.5235 | 287573 | 217584.5235 | 287573 | 0 | 287573
2026-01-11 | 218220.1611 | 287573 | 218220.1611 | 287573 | 0 | 287573
2026-01-12 | 218855.7987 | 289839 | 218855.7987 | 289839 | 0 | 289839
2026-01-13 | 219491.4362 | 292105 | 219491.4362 | 292105 | 0 | 292105
2026-01-14 | 220127.0738 | 294371 | 220127.0738 | 294371 | 0 | 294371
2026-01-15 | 220762.7114 | 296637 | 220762.7114 | 296637 | 0 | 296637
2026-01-16 | 221398.349 | 298903 | 221398.349 | 298903 | 0 | 298903
2026-01-17 | 222033.9866 | 298903 | 222033.9866 | 298903 | 0 | 298903
2026-01-18 | 222669.6242 | 298903 | 222669.6242 | 298903 | 0 | 298903
2026-01-19 | 223305.2617 | 301102 | 223305.2617 | 301102 | 0 | 301102
2026-01-20 | 223940.8993 | 303301 | 223940.8993 | 303301 | 0 | 303301
2026-01-21 | 224576.5369 | 305500 | 224576.5369 | 305500 | 0 | 305500
2026-01-22 | 225212.1745 | 307699 | 225212.1745 | 307699 | 0 | 307699
2026-01-23 | 225847.8121 | 309898 | 225847.8121 | 309898 | 0 | 309898
2026-01-24 | 226483.4497 | 309898 | 226483.4497 | 309898 | 0 | 309898
2026-01-25 | 227119.0872 | 309898 | 227119.0872 | 309898 | 0 | 309898
2026-01-26 | 227754.7248 | 312164 | 227754.7248 | 312164 | 0 | 312164
2026-01-27 | 228390.3624 | 314430 | 228390.3624 | 314430 | 0 | 314430
2026-01-28 | 229026 | 316696 | 229026 | 316696 | 0 | 316696
2026-01-29 | 230328.4857 | 318962 | 230328.4857 | 318962 | 0 | 318962
2026-01-30 | 231630.9714 | 321228 | 231630.9714 | 321228 | 0 | 321228
2026-01-31 | 232933.4571 | 321228 | 232933.4571 | 321228 | 0 | 321228
2026-02-01 | 234235.9428 | 321228 | 234235.9428 | 321228 | 0 | 321228
2026-02-02 | 235538.4285 | 322501.4 | 235538.4285 | 322501.4 | 0 | 322501.4
2026-02-03 | 236840.9142 | 323774.8 | 236840.9142 | 323774.8 | 0 | 323774.8
2026-02-04 | 238143.3999 | 325048.2 | 238143.3999 | 325048.2 | 0 | 325048.2
2026-02-05 | 239445.8856 | 326321.6 | 239445.8856 | 326321.6 | 0 | 326321.6
2026-02-06 | 240748.3713 | 327595 | 240748.3713 | 327595 | 0 | 327595
2026-02-07 | 242050.857 | 327595 | 242050.857 | 327595 | 0 | 327595
2026-02-08 | 243353.3427 | 327595 | 243353.3427 | 327595 | 0 | 327595
2026-02-09 | 244655.8284 | 328732.95 | 244655.8284 | 328732.95 | 0 | 328732.95
2026-02-10 | 245958.3141 | 329870.9 | 245958.3141 | 329870.9 | 0 | 329870.9
2026-02-11 | 247260.7998 | 331008.85 | 247260.7998 | 331008.85 | 0 | 331008.85
2026-02-12 | 248563.2855 | 332146.8 | 248563.2855 | 332146.8 | 0 | 332146.8
2026-02-13 | 249865.7712 | 333284.75 | 249865.7712 | 333284.75 | 0 | 333284.75
2026-02-14 | 251168.2569 | 333284.75 | 251168.2569 | 333284.75 | 0 | 333284.75
2026-02-15 | 252470.7426 | 333284.75 | 252470.7426 | 333284.75 | 0 | 333284.75
2026-02-16 | 253773.2283 | 333924.775 | 253773.2283 | 333924.775 | 0 | 333924.775
2026-02-17 | 255075.714 | 334564.8 | 255075.714 | 334564.8 | 0 | 334564.8
2026-02-18 | 256378.1997 | 335204.825 | 256378.1997 | 335204.825 | 0 | 335204.825
2026-02-19 | 257680.6854 | 335844.85 | 257680.6854 | 335844.85 | 0 | 335844.85
2026-02-20 | 258983.1711 | 336484.875 | 258983.1711 | 336484.875 | 0 | 336484.875
2026-02-21 | 260285.6568 | 336484.875 | 260285.6568 | 336484.875 | 0 | 336484.875
2026-02-22 | 261588.1425 | 336484.875 | 261588.1425 | 336484.875 | 0 | 336484.875
2026-02-23 | 262890.6282 | 336669.4 | 262890.6282 | 336669.4 | 0 | 336669.4
2026-02-24 | 264193.1139 | 336853.925 | 264193.1139 | 336853.925 | 0 | 336853.925
2026-02-25 | 265495.5996 | 337038.45 | 265495.5996 | 337038.45 | 0 | 337038.45
2026-02-26 | 266798.0853 | 337222.975 | 266798.0853 | 337222.975 | 0 | 337222.975
2026-02-27 | 268100.571 | 337407.5 | 268100.571 | 337407.5 | 0 | 337407.5
2026-02-28 | 269403.0567 | 337407.5 | 269403.0567 | 337407.5 | 0 | 337407.5
2026-03-01 | 270705.5424 | 337407.5 | 270705.5424 | 337407.5 | 0 | 337407.5
2026-03-02 | 272008.0281 | 337841.525 | 272008.0281 | 337841.525 | 0 | 337841.525
2026-03-03 | 273310.5138 | 338275.55 | 273310.5138 | 338275.55 | 0 | 338275.55
2026-03-04 | 274612.9995 | 338709.575 | 274612.9995 | 338709.575 | 0 | 338709.575
2026-03-05 | 275915.4852 | 339143.6 | 275915.4852 | 339143.6 | 0 | 339143.6
2026-03-06 | 277217.9709 | 339577.625 | 277217.9709 | 339577.625 | 0 | 339577.625
2026-03-07 | 278520.4566 | 339577.625 | 278520.4566 | 339577.625 | 0 | 339577.625
2026-03-08 | 279822.9423 | 339577.625 | 279822.9423 | 339577.625 | 0 | 339577.625
2026-03-09 | 281125.428 | 340201.375 | 281125.428 | 340201.375 | 0 | 340201.375
2026-03-10 | 282427.9137 | 340825.125 | 282427.9137 | 340825.125 | 0 | 340825.125
2026-03-11 | 283730.3994 | 341448.875 | 283730.3994 | 341448.875 | 0 | 341448.875
2026-03-12 | 285032.8851 | 342072.625 | 285032.8851 | 342072.625 | 0 | 342072.625
2026-03-13 | 286335.3708 | 342696.375 | 286335.3708 | 342696.375 | 0 | 342696.375
2026-03-14 | 287637.8565 | 342696.375 | 287637.8565 | 342696.375 | 0 | 342696.375
2026-03-15 | 288940.3422 | 342696.375 | 288940.3422 | 342696.375 | 0 | 342696.375
2026-03-16 | 290242.8279 | 343404 | 290242.8279 | 343404 | 0 | 343404
2026-03-17 | 291545.3136 | 344111.625 | 291545.3136 | 344111.625 | 0 | 344111.625
2026-03-18 | 292847.7993 | 344819.25 | 292847.7993 | 344819.25 | 0 | 344819.25
2026-03-19 | 294150.285 | 345526.875 | 294150.285 | 345526.875 | 0 | 345526.875
2026-03-20 | 295452.7707 | 346234.5 | 295452.7707 | 346234.5 | 0 | 346234.5
2026-03-21 | 296755.2564 | 346234.5 | 296755.2564 | 346234.5 | 0 | 346234.5
2026-03-22 | 298057.7421 | 346234.5 | 298057.7421 | 346234.5 | 0 | 346234.5
2026-03-23 | 299360.2278 |  | 299360.2278 |  | 0
2026-03-24 | 300662.7135 |  | 300662.7135 |  | 0
2026-03-25 | 301965.1992 |  | 301965.1992 |  | 0
2026-03-26 | 303267.6849 |  | 303267.6849 |  | 0
2026-03-27 | 304570.1706 |  | 304570.1706 |  | 0
2026-03-28 | 305872.6563 |  | 305872.6563 |  | 0
2026-03-29 | 307175.142 |  | 307175.142 |  | 0
2026-03-30 | 308477.6277 |  | 308477.6277 |  | 0
2026-03-31 | 309780.1134 |  | 309780.1134 |  | 0
2026-04-01 | 311082.5991 |  | 311082.5991 |  | 0
2026-04-02 | 312385.0848 |  | 312385.0848 |  | 0
2026-04-03 | 313687.5705 |  | 313687.5705 |  | 0
2026-04-04 | 314990.0562 |  | 314990.0562 |  | 0
2026-04-05 | 316292.5419 |  | 316292.5419 |  | 0
2026-04-06 | 317595.0276 |  | 317595.0276 |  | 0
2026-04-07 | 318897.5133 |  | 318897.5133 |  | 0
2026-04-08 | 320199.999 |  | 320199.999 |  | 0
2026-04-09 | 321502.4847 |  | 321502.4847 |  | 0
2026-04-10 | 322804.9704 |  | 322804.9704 |  | 0
2026-04-11 | 324107.4561 |  | 324107.4561 |  | 0
2026-04-12 | 325409.9418 |  | 325409.9418 |  | 0
2026-04-13 | 326712.4275 |  | 326712.4275 |  | 0
2026-04-14 | 328014.9132 |  | 328014.9132 |  | 0
2026-04-15 | 329317.3989 |  | 329317.3989 |  | 0
2026-04-16 | 330619.8846 |  | 330619.8846 |  | 0
2026-04-17 | 331922.3703 |  | 331922.3703 |  | 0
2026-04-18 | 333224.856 |  | 333224.856 |  | 0
2026-04-19 | 334527.3417 |  | 334527.3417 |  | 0
2026-04-20 | 335829.8274 |  | 335829.8274 |  | 0
2026-04-21 | 337132.3131 |  | 337132.3131 |  | 0
2026-04-22 | 338434.7988 |  | 338434.7988 |  | 0
2026-04-23 | 339737.2845 |  | 339737.2845 |  | 0
2026-04-24 | 341039.7702 |  | 341039.7702 |  | 0
2026-04-25 | 342342.2559 |  | 342342.2559 |  | 0
2026-04-26 | 343644.7416 |  | 343644.7416 |  | 0
2026-04-27 | 344947.2273 |  | 344947.2273 |  | 0
2026-04-28 | 346249.713 |  | 346249.713 |  | 0
2026-04-29 | 347552.1987 |  | 347552.1987 |  | 0
2026-04-30 | 348854.6844 |  | 348854.6844 |  | 0
2026-05-01 | 350157.1701 |  | 350157.1701 |  | 0
2026-05-02 | 351459.6558 |  | 351459.6558 |  | 0
2026-05-03 | 352762.1415 |  | 352762.1415 |  | 0
2026-05-04 | 354064.6272 |  | 354064.6272 |  | 0
2026-05-05 | 355367.1129 |  | 355367.1129 |  | 0
2026-05-06 | 356669.5986 |  | 356669.5986 |  | 0
2026-05-07 | 357972.0843 |  | 357972.0843 |  | 0
2026-05-08 | 359274.57 |  | 359274.57 |  | 0
2026-05-09 | 360577.0557 |  | 360577.0557 |  | 0
2026-05-10 | 361879.5414 |  | 361879.5414 |  | 0
2026-05-11 | 363182.0271 |  | 363182.0271 |  | 0
2026-05-12 | 364484.5128 |  | 364484.5128 |  | 0
2026-05-13 | 365786.9985 |  | 365786.9985 |  | 0
2026-05-14 | 367089.4842 |  | 367089.4842 |  | 0
2026-05-15 | 368391.9699 |  | 368391.9699 |  | 0
2026-05-16 | 369694.4556 |  | 369694.4556 |  | 0
2026-05-17 | 370996.9413 |  | 370996.9413 |  | 0
2026-05-18 | 372299.427 |  | 372299.427 |  | 0
2026-05-19 | 373601.9127 |  | 373601.9127 |  | 0
2026-05-20 | 374904.3984 |  | 374904.3984 |  | 0
2026-05-21 | 376206.8841 |  | 376206.8841 |  | 0
2026-05-22 | 377509.3698 |  | 377509.3698 |  | 0
2026-05-23 | 378811.8555 |  | 378811.8555 |  | 0
2026-05-24 | 380114.3412 |  | 380114.3412 |  | 0
2026-05-25 | 381416.8269 |  | 381416.8269 |  | 0
2026-05-26 | 382719.3126 |  | 382719.3126 |  | 0
2026-05-27 | 384021.7983 |  | 384021.7983 |  | 0
2026-05-28 | 385324.284 |  | 385324.284 |  | 0
2026-05-29 | 386626.7697 |  | 386626.7697 |  | 0
2026-05-30 | 387929.2554 |  | 387929.2554 |  | 0
2026-05-31 | 389231.7411 |  | 389231.7411 |  | 0
2026-06-01 | 390534.2268 |  | 390534.2268 |  | 0
2026-06-02 | 391836.7125 |  | 391836.7125 |  | 0
2026-06-03 | 393139.1982 |  | 393139.1982 |  | 0
2026-06-04 | 394441.6839 |  | 394441.6839 |  | 0
2026-06-05 | 395744.1696 |  | 395744.1696 |  | 0
2026-06-06 | 397046.6553 |  | 397046.6553 |  | 0
2026-06-07 | 398349.141 |  | 398349.141 |  | 0
2026-06-08 | 399651.6267 |  | 399651.6267 |  | 0
2026-06-09 | 400954.1124 |  | 400954.1124 |  | 0
2026-06-10 | 402256.5981 |  | 402256.5981 |  | 0
2026-06-11 | 403559.0838 |  | 403559.0838 |  | 0
2026-06-12 | 404861.5695 |  | 404861.5695 |  | 0
2026-06-13 | 406164.0552 |  | 406164.0552 |  | 0
2026-06-14 | 407466.5409 |  | 407466.5409 |  | 0
2026-06-15 | 408769.0266 |  | 408769.0266 |  | 0
2026-06-16 | 410071.5123 |  | 410071.5123 |  | 0
2026-06-17 | 411373.998 |  | 411373.998 |  | 0
2026-06-18 | 412676.4837 |  | 412676.4837 |  | 0
2026-06-19 | 413978.9694 |  | 413978.9694 |  | 0
2026-06-20 | 415281.4551 |  | 415281.4551 |  | 0
2026-06-21 | 416583.9408 |  | 416583.9408 |  | 0
2026-06-22 | 417886.4265 |  | 417886.4265 |  | 0
2026-06-23 | 419188.9122 |  | 419188.9122 |  | 0
2026-06-24 | 420491.3979 |  | 420491.3979 |  | 0
2026-06-25 | 421793.8836 |  | 421793.8836 |  | 0
2026-06-26 | 423096.3693 |  | 423096.3693 |  | 0
2026-06-27 | 424398.855 |  | 424398.855 |  | 0
2026-06-28 | 425701.3407 |  | 425701.3407 |  | 0
2026-06-29 | 427003.8264 |  | 427003.8264 |  | 0
2026-06-30 | 428306.3121 |  | 428306.3121 |  | 0
2026-07-01 | 429608.7978 |  | 429608.7978 |  | 0
2026-07-02 | 430911.2835 |  | 430911.2835 |  | 0
2026-07-03 | 432213.7692 |  | 432213.7692 |  | 0
2026-07-04 | 433516.2549 |  | 433516.2549 |  | 0
2026-07-05 | 434818.7406 |  | 434818.7406 |  | 0
2026-07-06 | 436121.2263 |  | 436121.2263 |  | 0
2026-07-07 | 437423.712 |  | 437423.712 |  | 0
2026-07-08 | 438726.1977 |  | 438726.1977 |  | 0
2026-07-09 | 440028.6834 |  | 440028.6834 |  | 0
2026-07-10 | 441331.1691 |  | 441331.1691 |  | 0
2026-07-11 | 442633.6548 |  | 442633.6548 |  | 0
2026-07-12 | 443936.1405 |  | 443936.1405 |  | 0
2026-07-13 | 445238.6262 |  | 445238.6262 |  | 0
2026-07-14 | 446541.1119 |  | 446541.1119 |  | 0
2026-07-15 | 447843.5976 |  | 447843.5976 |  | 0
2026-07-16 | 449146.0833 |  | 449146.0833 |  | 0
2026-07-17 | 450448.569 |  | 450448.569 |  | 0
2026-07-18 | 451751.0547 |  | 451751.0547 |  | 0
2026-07-19 | 453053.5404 |  | 453053.5404 |  | 0
2026-07-20 | 454356.0261 |  | 454356.0261 |  | 0
2026-07-21 | 455658.5118 |  | 455658.5118 |  | 0
2026-07-22 | 456960.9975 |  | 456960.9975 |  | 0
2026-07-23 | 458263.4832 |  | 458263.4832 |  | 0
2026-07-24 | 459565.9689 |  | 459565.9689 |  | 0
2026-07-25 | 460868.4546 |  | 460868.4546 |  | 0
2026-07-26 | 462170.9403 |  | 462170.9403 |  | 0
2026-07-27 | 463473.426 |  | 463473.426 |  | 0
2026-07-28 | 464775.9117 |  | 464775.9117 |  | 0
2026-07-29 | 466078.3974 |  | 466078.3974 |  | 0
2026-07-30 | 467380.8831 |  | 467380.8831 |  | 0
2026-07-31 | 468683.3688 |  | 468683.3688 |  | 0
2026-08-01 | 469985.8545 |  | 469985.8545 |  | 0
2026-08-02 | 471288.3402 |  | 471288.3402 |  | 0
2026-08-03 | 472590.8259 |  | 472590.8259 |  | 0
2026-08-04 | 473893.3116 |  | 473893.3116 |  | 0
2026-08-05 | 475195.7973 |  | 475195.7973 |  | 0
2026-08-06 | 476498.283 |  | 476498.283 |  | 0
2026-08-07 | 477800.7687 |  | 477800.7687 |  | 0
2026-08-08 | 479103.2544 |  | 479103.2544 |  | 0
2026-08-09 | 480405.7401 |  | 480405.7401 |  | 0
2026-08-10 | 481708.2258 |  | 481708.2258 |  | 0
2026-08-11 | 483010.7115 |  | 483010.7115 |  | 0
2026-08-12 | 484313.1972 |  | 484313.1972 |  | 0
2026-08-13 | 485615.6829 |  | 485615.6829 |  | 0
2026-08-14 | 486918.1686 |  | 486918.1686 |  | 0
2026-08-15 | 488220.6543 |  | 488220.6543 |  | 0
2026-08-16 | 489523.14 |  | 489523.14 |  | 0
2026-08-18 | 492610.241 |  | 492610.241 |  | 0
2026-08-19 | 495697.3419 |  | 495697.3419 |  | 0
2026-08-20 | 498784.4429 |  | 498784.4429 |  | 0
2026-08-21 | 501871.5439 |  | 501871.5439 |  | 0
2026-08-22 | 504958.6449 |  | 504958.6449 |  | 0
2026-08-23 | 508045.7458 |  | 508045.7458 |  | 0
2026-08-24 | 511132.8468 |  | 511132.8468 |  | 0
2026-08-25 | 514219.9478 |  | 514219.9478 |  | 0
2026-08-26 | 517307.0488 |  | 517307.0488 |  | 0
2026-08-27 | 520394.1497 |  | 520394.1497 |  | 0
2026-08-28 | 523481.2507 |  | 523481.2507 |  | 0
2026-08-29 | 526568.3517 |  | 526568.3517 |  | 0
2026-08-30 | 529655.4527 |  | 529655.4527 |  | 0
2026-08-31 | 532742.5536 |  | 532742.5536 |  | 0
2026-09-01 | 535829.6546 |  | 535829.6546 |  | 0
2026-09-02 | 538916.7556 |  | 538916.7556 |  | 0
2026-09-03 | 542003.8566 |  | 542003.8566 |  | 0
2026-09-04 | 545090.9575 |  | 545090.9575 |  | 0
2026-09-05 | 548178.0585 |  | 548178.0585 |  | 0
2026-09-06 | 551265.1595 |  | 551265.1595 |  | 0
2026-09-07 | 554352.2605 |  | 554352.2605 |  | 0
2026-09-08 | 557439.3614 |  | 557439.3614 |  | 0
2026-09-09 | 558049.8079 |  | 558049.8079 |  | 0
2026-09-10 | 558660.2543 |  | 558660.2543 |  | 0
2026-09-11 | 559270.7007 |  | 559270.7007 |  | 0
2026-09-12 | 559881.1471 |  | 559881.1471 |  | 0
2026-09-13 | 560491.5936 |  | 560491.5936 |  | 0
2026-09-14 | 561102.04 |  | 561102.04 |  | 0
2026-09-15 | 561712.4864 |  | 561712.4864 |  | 0
2026-09-16 | 562322.9329 |  | 562322.9329 |  | 0
2026-09-17 | 562933.3793 |  | 562933.3793 |  | 0
2026-09-18 | 563543.8257 |  | 563543.8257 |  | 0
2026-09-19 | 564154.2721 |  | 564154.2721 |  | 0
2026-09-20 | 564764.7186 |  | 564764.7186 |  | 0
2026-09-21 | 565375.165 |  | 565375.165 |  | 0
2026-09-22 | 565985.6114 |  | 565985.6114 |  | 0
2026-09-23 | 566596.0579 |  | 566596.0579 |  | 0
2026-09-24 | 567206.5043 |  | 567206.5043 |  | 0
2026-09-25 | 567816.9507 |  | 567816.9507 |  | 0
2026-09-26 | 568427.3971 |  | 568427.3971 |  | 0
2026-09-27 | 569037.8436 |  | 569037.8436 |  | 0
2026-09-28 | 569648.29 |  | 569648.29 |  | 0
2026-09-29 | 570258.7364 |  | 570258.7364 |  | 0
2026-09-30 | 570869.1829 |  | 570869.1829 |  | 0
2026-10-01 | 571479.6293 |  | 571479.6293 |  | 0
2026-10-02 | 572090.0757 |  | 572090.0757 |  | 0
2026-10-03 | 572700.5221 |  | 572700.5221 |  | 0
2026-10-04 | 573310.9686 |  | 573310.9686 |  | 0
2026-10-05 | 573921.415 |  | 573921.415 |  | 0
2026-10-06 | 574531.8614 |  | 574531.8614 |  | 0
2026-10-07 | 575142.3079 |  | 575142.3079 |  | 0
2026-10-08 | 575752.7543 |  | 575752.7543 |  | 0
2026-10-09 | 576363.2007 |  | 576363.2007 |  | 0
2026-10-10 | 576973.6471 |  | 576973.6471 |  | 0
2026-10-11 | 577584.0936 |  | 577584.0936 |  | 0
2026-10-12 | 578194.54 |  | 578194.54 |  | 0

## Travel&perdiem (Direct Cost)
Date | Planned Travel&perdiem (Cumulative) | Actual Travel&perdiem (Cumulative) | Planned 5105 · Travel - Airfare (Direct) (Cumulative) | Actual 5105 · Travel - Airfare (Direct) (Cumulative) | Planned 5106 · Travel - Hotel (Direct) (Cumulative) | Actual 5106 · Travel - Hotel (Direct) (Cumulative) | Planned 5107 · Travel - Other (Direct) (Cumulative) | Actual 5107 · Travel - Other (Direct) (Cumulative) | Planned 5108 · Meals & entertainment (Direct) (Cumulative) | Actual 5108 · Meals & entertainment (Direct) (Cumulative) | Planned 5122 · Motor vehicle exp (Direct) (Cumulative) | Actual 5122 · Motor vehicle exp (Direct) (Cumulative) | Planned 5123 · Auto fuel (Direct) (Cumulative) | Actual 5123 · Auto fuel (Direct) (Cumulative)
2025-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 80.6747 | 0 | 13.4458 | 0 | 13.4458 | 0 | 13.4458 | 0 | 13.4458 | 0 | 13.4458 | 0 | 13.4458 | 0
2025-06-02 | 161.3494 | 0 | 26.8916 | 0 | 26.8916 | 0 | 26.8916 | 0 | 26.8916 | 0 | 26.8916 | 0 | 26.8916 | 0
2025-06-03 | 242.0241 | 0 | 40.3373 | 0 | 40.3373 | 0 | 40.3373 | 0 | 40.3373 | 0 | 40.3373 | 0 | 40.3373 | 0
2025-06-04 | 322.6988 | 0 | 53.7831 | 0 | 53.7831 | 0 | 53.7831 | 0 | 53.7831 | 0 | 53.7831 | 0 | 53.7831 | 0
2025-06-05 | 403.3735 | 0 | 67.2289 | 0 | 67.2289 | 0 | 67.2289 | 0 | 67.2289 | 0 | 67.2289 | 0 | 67.2289 | 0
2025-06-06 | 484.0482 | 0 | 80.6747 | 0 | 80.6747 | 0 | 80.6747 | 0 | 80.6747 | 0 | 80.6747 | 0 | 80.6747 | 0
2025-06-07 | 564.7229 | 0 | 94.1205 | 0 | 94.1205 | 0 | 94.1205 | 0 | 94.1205 | 0 | 94.1205 | 0 | 94.1205 | 0
2025-06-08 | 645.3976 | 0 | 107.5663 | 0 | 107.5663 | 0 | 107.5663 | 0 | 107.5663 | 0 | 107.5663 | 0 | 107.5663 | 0
2025-06-09 | 726.0723 | 0 | 121.012 | 0 | 121.012 | 0 | 121.012 | 0 | 121.012 | 0 | 121.012 | 0 | 121.012 | 0
2025-06-10 | 806.747 | 0 | 134.4578 | 0 | 134.4578 | 0 | 134.4578 | 0 | 134.4578 | 0 | 134.4578 | 0 | 134.4578 | 0
2025-06-11 | 887.4217 | 0 | 147.9036 | 0 | 147.9036 | 0 | 147.9036 | 0 | 147.9036 | 0 | 147.9036 | 0 | 147.9036 | 0
2025-06-12 | 968.0964 | 0 | 161.3494 | 0 | 161.3494 | 0 | 161.3494 | 0 | 161.3494 | 0 | 161.3494 | 0 | 161.3494 | 0
2025-06-13 | 1048.7711 | 0 | 174.7952 | 0 | 174.7952 | 0 | 174.7952 | 0 | 174.7952 | 0 | 174.7952 | 0 | 174.7952 | 0
2025-06-14 | 1129.4458 | 0 | 188.241 | 0 | 188.241 | 0 | 188.241 | 0 | 188.241 | 0 | 188.241 | 0 | 188.241 | 0
2025-06-15 | 1210.1205 | 0 | 201.6867 | 0 | 201.6867 | 0 | 201.6867 | 0 | 201.6867 | 0 | 201.6867 | 0 | 201.6867 | 0
2025-06-16 | 1290.7952 | 0 | 215.1325 | 0 | 215.1325 | 0 | 215.1325 | 0 | 215.1325 | 0 | 215.1325 | 0 | 215.1325 | 0
2025-06-17 | 1371.4699 | 0 | 228.5783 | 0 | 228.5783 | 0 | 228.5783 | 0 | 228.5783 | 0 | 228.5783 | 0 | 228.5783 | 0
2025-06-18 | 1452.1446 | 0 | 242.0241 | 0 | 242.0241 | 0 | 242.0241 | 0 | 242.0241 | 0 | 242.0241 | 0 | 242.0241 | 0
2025-06-19 | 1532.8193 | 0 | 255.4699 | 0 | 255.4699 | 0 | 255.4699 | 0 | 255.4699 | 0 | 255.4699 | 0 | 255.4699 | 0
2025-06-20 | 1613.494 | 0 | 268.9157 | 0 | 268.9157 | 0 | 268.9157 | 0 | 268.9157 | 0 | 268.9157 | 0 | 268.9157 | 0
2025-06-21 | 1694.1687 | 0 | 282.3614 | 0 | 282.3614 | 0 | 282.3614 | 0 | 282.3614 | 0 | 282.3614 | 0 | 282.3614 | 0
2025-06-22 | 1774.8434 | 0 | 295.8072 | 0 | 295.8072 | 0 | 295.8072 | 0 | 295.8072 | 0 | 295.8072 | 0 | 295.8072 | 0
2025-06-23 | 1855.5181 | 0 | 309.253 | 0 | 309.253 | 0 | 309.253 | 0 | 309.253 | 0 | 309.253 | 0 | 309.253 | 0
2025-06-24 | 1936.1928 | 679.86 | 322.6988 | 0 | 322.6988 | 0 | 322.6988 | 312.76 | 322.6988 | 0 | 322.6988 | 367.1 | 322.6988 | 0
2025-06-25 | 2016.8675 | 679.86 | 336.1446 | 0 | 336.1446 | 0 | 336.1446 | 312.76 | 336.1446 | 0 | 336.1446 | 367.1 | 336.1446 | 0
2025-06-26 | 2097.5422 | 679.86 | 349.5904 | 0 | 349.5904 | 0 | 349.5904 | 312.76 | 349.5904 | 0 | 349.5904 | 367.1 | 349.5904 | 0
2025-06-27 | 2178.2169 | 679.86 | 363.0361 | 0 | 363.0361 | 0 | 363.0361 | 312.76 | 363.0361 | 0 | 363.0361 | 367.1 | 363.0361 | 0
2025-06-28 | 2258.8916 | 792.13 | 376.4819 | 0 | 376.4819 | 0 | 376.4819 | 425.03 | 376.4819 | 0 | 376.4819 | 367.1 | 376.4819 | 0
2025-06-29 | 2339.5663 | 940.88 | 389.9277 | 0 | 389.9277 | 148.75 | 389.9277 | 425.03 | 389.9277 | 0 | 389.9277 | 367.1 | 389.9277 | 0
2025-06-30 | 2420.241 | 1060.26 | 403.3735 | 0 | 403.3735 | 148.75 | 403.3735 | 425.03 | 403.3735 | 0 | 403.3735 | 367.1 | 403.3735 | 119.38
2025-07-01 | 2500.9157 | 1060.26 | 416.8193 | 0 | 416.8193 | 148.75 | 416.8193 | 425.03 | 416.8193 | 0 | 416.8193 | 367.1 | 416.8193 | 119.38
2025-07-02 | 2581.5904 | 1060.26 | 430.2651 | 0 | 430.2651 | 148.75 | 430.2651 | 425.03 | 430.2651 | 0 | 430.2651 | 367.1 | 430.2651 | 119.38
2025-07-03 | 2662.2651 | 1060.26 | 443.7108 | 0 | 443.7108 | 148.75 | 443.7108 | 425.03 | 443.7108 | 0 | 443.7108 | 367.1 | 443.7108 | 119.38
2025-07-04 | 2742.9398 | 1060.26 | 457.1566 | 0 | 457.1566 | 148.75 | 457.1566 | 425.03 | 457.1566 | 0 | 457.1566 | 367.1 | 457.1566 | 119.38
2025-07-05 | 2823.6145 | 1060.26 | 470.6024 | 0 | 470.6024 | 148.75 | 470.6024 | 425.03 | 470.6024 | 0 | 470.6024 | 367.1 | 470.6024 | 119.38
2025-07-06 | 2904.2892 | 1060.26 | 484.0482 | 0 | 484.0482 | 148.75 | 484.0482 | 425.03 | 484.0482 | 0 | 484.0482 | 367.1 | 484.0482 | 119.38
2025-07-07 | 2984.9639 | 1241.36 | 497.494 | 0 | 497.494 | 148.75 | 497.494 | 425.03 | 497.494 | 0 | 497.494 | 479.66 | 497.494 | 187.92
2025-07-08 | 3065.6386 | 1741.36 | 510.9398 | 0 | 510.9398 | 148.75 | 510.9398 | 425.03 | 510.9398 | 500 | 510.9398 | 479.66 | 510.9398 | 187.92
2025-07-09 | 3146.3133 | 1741.36 | 524.3855 | 0 | 524.3855 | 148.75 | 524.3855 | 425.03 | 524.3855 | 500 | 524.3855 | 479.66 | 524.3855 | 187.92
2025-07-10 | 3226.988 | 1799.25 | 537.8313 | 0 | 537.8313 | 148.75 | 537.8313 | 425.03 | 537.8313 | 500 | 537.8313 | 479.66 | 537.8313 | 245.81
2025-07-11 | 3307.6627 | 2100.37 | 551.2771 | 0 | 551.2771 | 449.87 | 551.2771 | 425.03 | 551.2771 | 500 | 551.2771 | 479.66 | 551.2771 | 245.81
2025-07-12 | 3388.3373 | 2534.49 | 564.7229 | 0 | 564.7229 | 654.71 | 564.7229 | 425.03 | 564.7229 | 500 | 564.7229 | 479.66 | 564.7229 | 475.09
2025-07-13 | 3469.012 | 7516.12 | 578.1687 | 0 | 578.1687 | 5636.34 | 578.1687 | 425.03 | 578.1687 | 500 | 578.1687 | 479.66 | 578.1687 | 475.09
2025-07-14 | 3549.6867 | 12432.37 | 591.6145 | 0 | 591.6145 | 10482.45 | 591.6145 | 425.03 | 591.6145 | 500 | 591.6145 | 479.66 | 591.6145 | 545.23
2025-07-15 | 3630.3614 | 14964.72 | 605.0602 | 0 | 605.0602 | 13014.8 | 605.0602 | 425.03 | 605.0602 | 500 | 605.0602 | 479.66 | 605.0602 | 545.23
2025-07-16 | 3711.0361 | 15314.72 | 618.506 | 0 | 618.506 | 13014.8 | 618.506 | 425.03 | 618.506 | 850 | 618.506 | 479.66 | 618.506 | 545.23
2025-07-17 | 3791.7108 | 15589.91 | 631.9518 | 185.57 | 631.9518 | 13014.8 | 631.9518 | 425.03 | 631.9518 | 850 | 631.9518 | 479.66 | 631.9518 | 634.85
2025-07-18 | 3872.3855 | 17749.91 | 645.3976 | 185.57 | 645.3976 | 13374.8 | 645.3976 | 425.03 | 645.3976 | 2650 | 645.3976 | 479.66 | 645.3976 | 634.85
2025-07-19 | 3953.0602 | 17793.21 | 658.8434 | 228.87 | 658.8434 | 13374.8 | 658.8434 | 425.03 | 658.8434 | 2650 | 658.8434 | 479.66 | 658.8434 | 634.85
2025-07-20 | 4033.7349 | 17793.21 | 672.2892 | 228.87 | 672.2892 | 13374.8 | 672.2892 | 425.03 | 672.2892 | 2650 | 672.2892 | 479.66 | 672.2892 | 634.85
2025-07-21 | 4659.4329 | 19083.21 | 776.5721 | 228.87 | 776.5721 | 14624.8 | 776.5721 | 425.03 | 776.5721 | 2650 | 776.5721 | 479.66 | 776.5721 | 674.85
2025-07-22 | 5285.1308 | 19370.03 | 880.8551 | 414.44 | 880.8551 | 14624.8 | 880.8551 | 425.03 | 880.8551 | 2650 | 880.8551 | 580.91 | 880.8551 | 674.85
2025-07-23 | 5910.8288 | 19370.03 | 985.1381 | 414.44 | 985.1381 | 14624.8 | 985.1381 | 425.03 | 985.1381 | 2650 | 985.1381 | 580.91 | 985.1381 | 674.85
2025-07-24 | 6536.5268 | 19489.92 | 1089.4211 | 414.44 | 1089.4211 | 14624.8 | 1089.4211 | 425.03 | 1089.4211 | 2650 | 1089.4211 | 580.91 | 1089.4211 | 794.74
2025-07-25 | 7162.2247 | 20639.92 | 1193.7041 | 414.44 | 1193.7041 | 14624.8 | 1193.7041 | 425.03 | 1193.7041 | 3800 | 1193.7041 | 580.91 | 1193.7041 | 794.74
2025-07-26 | 7787.9227 | 20639.92 | 1297.9871 | 414.44 | 1297.9871 | 14624.8 | 1297.9871 | 425.03 | 1297.9871 | 3800 | 1297.9871 | 580.91 | 1297.9871 | 794.74
2025-07-27 | 8413.6206 | 20732.36 | 1402.2701 | 414.44 | 1402.2701 | 14624.8 | 1402.2701 | 440.44 | 1402.2701 | 3800 | 1402.2701 | 580.91 | 1402.2701 | 871.77
2025-07-28 | 9039.3186 | 20732.36 | 1506.5531 | 414.44 | 1506.5531 | 14624.8 | 1506.5531 | 440.44 | 1506.5531 | 3800 | 1506.5531 | 580.91 | 1506.5531 | 871.77
2025-07-29 | 9665.0165 | 20792.36 | 1610.8361 | 414.44 | 1610.8361 | 14624.8 | 1610.8361 | 440.44 | 1610.8361 | 3800 | 1610.8361 | 580.91 | 1610.8361 | 931.77
2025-07-30 | 10290.7145 | 20792.36 | 1715.1191 | 414.44 | 1715.1191 | 14624.8 | 1715.1191 | 440.44 | 1715.1191 | 3800 | 1715.1191 | 580.91 | 1715.1191 | 931.77
2025-07-31 | 10916.4124 | 21213.52 | 1819.4021 | 414.44 | 1819.4021 | 15045.96 | 1819.4021 | 440.44 | 1819.4021 | 3800 | 1819.4021 | 580.91 | 1819.4021 | 931.77
2025-08-01 | 11542.1104 | 24073.89 | 1923.6851 | 414.44 | 1923.6851 | 15045.96 | 1923.6851 | 644.44 | 1923.6851 | 4850 | 1923.6851 | 923.74 | 1923.6851 | 1882.44
2025-08-02 | 12167.8083 | 25150.49 | 2027.9681 | 414.44 | 2027.9681 | 16122.56 | 2027.9681 | 644.44 | 2027.9681 | 4850 | 2027.9681 | 923.74 | 2027.9681 | 1882.44
2025-08-03 | 12793.5063 | 27182.04 | 2132.2511 | 414.44 | 2132.2511 | 18154.11 | 2132.2511 | 644.44 | 2132.2511 | 4850 | 2132.2511 | 923.74 | 2132.2511 | 1882.44
2025-08-04 | 13419.2043 | 27182.04 | 2236.534 | 414.44 | 2236.534 | 18154.11 | 2236.534 | 644.44 | 2236.534 | 4850 | 2236.534 | 923.74 | 2236.534 | 1882.44
2025-08-05 | 14044.9022 | 27182.04 | 2340.817 | 414.44 | 2340.817 | 18154.11 | 2340.817 | 644.44 | 2340.817 | 4850 | 2340.817 | 923.74 | 2340.817 | 1882.44
2025-08-06 | 14670.6002 | 27182.04 | 2445.1 | 414.44 | 2445.1 | 18154.11 | 2445.1 | 644.44 | 2445.1 | 4850 | 2445.1 | 923.74 | 2445.1 | 1882.44
2025-08-07 | 15296.2981 | 27182.04 | 2549.383 | 414.44 | 2549.383 | 18154.11 | 2549.383 | 644.44 | 2549.383 | 4850 | 2549.383 | 923.74 | 2549.383 | 1882.44
2025-08-08 | 15921.9961 | 28932.04 | 2653.666 | 414.44 | 2653.666 | 18154.11 | 2653.666 | 644.44 | 2653.666 | 6600 | 2653.666 | 923.74 | 2653.666 | 1882.44
2025-08-09 | 16547.694 | 28932.04 | 2757.949 | 414.44 | 2757.949 | 18154.11 | 2757.949 | 644.44 | 2757.949 | 6600 | 2757.949 | 923.74 | 2757.949 | 1882.44
2025-08-10 | 17173.392 | 29855.52 | 2862.232 | 799.62 | 2862.232 | 18692.41 | 2862.232 | 644.44 | 2862.232 | 6600 | 2862.232 | 923.74 | 2862.232 | 1882.44
2025-08-11 | 17799.0899 | 30701.42 | 2966.515 | 799.62 | 2966.515 | 19538.31 | 2966.515 | 644.44 | 2966.515 | 6600 | 2966.515 | 923.74 | 2966.515 | 1882.44
2025-08-12 | 18424.7879 | 30701.42 | 3070.798 | 799.62 | 3070.798 | 19538.31 | 3070.798 | 644.44 | 3070.798 | 6600 | 3070.798 | 923.74 | 3070.798 | 1882.44
2025-08-13 | 19050.4859 | 30701.42 | 3175.081 | 799.62 | 3175.081 | 19538.31 | 3175.081 | 644.44 | 3175.081 | 6600 | 3175.081 | 923.74 | 3175.081 | 1882.44
2025-08-14 | 19676.1838 | 30701.42 | 3279.364 | 799.62 | 3279.364 | 19538.31 | 3279.364 | 644.44 | 3279.364 | 6600 | 3279.364 | 923.74 | 3279.364 | 1882.44
2025-08-15 | 20301.8818 | 32451.42 | 3383.647 | 799.62 | 3383.647 | 19538.31 | 3383.647 | 644.44 | 3383.647 | 8350 | 3383.647 | 923.74 | 3383.647 | 1882.44
2025-08-16 | 20927.5797 | 33681.82 | 3487.93 | 799.62 | 3487.93 | 20768.71 | 3487.93 | 644.44 | 3487.93 | 8350 | 3487.93 | 923.74 | 3487.93 | 1882.44
2025-08-17 | 21553.2777 | 34758.42 | 3592.2129 | 799.62 | 3592.2129 | 21845.31 | 3592.2129 | 644.44 | 3592.2129 | 8350 | 3592.2129 | 923.74 | 3592.2129 | 1882.44
2025-08-18 | 22178.9756 | 34758.42 | 3696.4959 | 799.62 | 3696.4959 | 21845.31 | 3696.4959 | 644.44 | 3696.4959 | 8350 | 3696.4959 | 923.74 | 3696.4959 | 1882.44
2025-08-19 | 22804.6736 | 34758.42 | 3800.7789 | 799.62 | 3800.7789 | 21845.31 | 3800.7789 | 644.44 | 3800.7789 | 8350 | 3800.7789 | 923.74 | 3800.7789 | 1882.44
2025-08-20 | 23430.3715 | 35142.92 | 3905.0619 | 799.62 | 3905.0619 | 22229.81 | 3905.0619 | 644.44 | 3905.0619 | 8350 | 3905.0619 | 923.74 | 3905.0619 | 1882.44
2025-08-21 | 24056.0695 | 35142.92 | 4009.3449 | 799.62 | 4009.3449 | 22229.81 | 4009.3449 | 644.44 | 4009.3449 | 8350 | 4009.3449 | 923.74 | 4009.3449 | 1882.44
2025-08-22 | 24681.7674 | 37300.22 | 4113.6279 | 799.62 | 4113.6279 | 23537.11 | 4113.6279 | 644.44 | 4113.6279 | 9200 | 4113.6279 | 923.74 | 4113.6279 | 1882.44
2025-08-23 | 25226.7907 | 37300.22 | 4204.4651 | 799.62 | 4204.4651 | 23537.11 | 4204.4651 | 644.44 | 4204.4651 | 9200 | 4204.4651 | 923.74 | 4204.4651 | 1882.44
2025-08-24 | 25771.814 | 38649.88 | 4295.3023 | 799.62 | 4295.3023 | 24886.77 | 4295.3023 | 644.44 | 4295.3023 | 9200 | 4295.3023 | 923.74 | 4295.3023 | 1882.44
2025-08-25 | 26316.8372 | 42648.87 | 4386.1395 | 799.62 | 4386.1395 | 24886.77 | 4386.1395 | 644.44 | 4386.1395 | 9200 | 4386.1395 | 4922.73 | 4386.1395 | 1882.44
2025-08-26 | 26861.8605 | 42648.87 | 4476.9767 | 799.62 | 4476.9767 | 24886.77 | 4476.9767 | 644.44 | 4476.9767 | 9200 | 4476.9767 | 4922.73 | 4476.9767 | 1882.44
2025-08-27 | 27406.8837 | 43034.05 | 4567.814 | 1184.8 | 4567.814 | 24886.77 | 4567.814 | 644.44 | 4567.814 | 9200 | 4567.814 | 4922.73 | 4567.814 | 1882.44
2025-08-28 | 27951.907 | 43034.05 | 4658.6512 | 1184.8 | 4658.6512 | 24886.77 | 4658.6512 | 644.44 | 4658.6512 | 9200 | 4658.6512 | 4922.73 | 4658.6512 | 1882.44
2025-08-29 | 28496.9302 | 43384.05 | 4749.4884 | 1184.8 | 4749.4884 | 24886.77 | 4749.4884 | 644.44 | 4749.4884 | 9550 | 4749.4884 | 4922.73 | 4749.4884 | 1882.44
2025-08-30 | 29041.9535 | 44153.05 | 4840.3256 | 1184.8 | 4840.3256 | 25655.77 | 4840.3256 | 644.44 | 4840.3256 | 9550 | 4840.3256 | 4922.73 | 4840.3256 | 1882.44
2025-08-31 | 29586.9767 | 44153.05 | 4931.1628 | 1184.8 | 4931.1628 | 25655.77 | 4931.1628 | 644.44 | 4931.1628 | 9550 | 4931.1628 | 4922.73 | 4931.1628 | 1882.44
2025-09-01 | 30132 | 44460.65 | 5022 | 1184.8 | 5022 | 25963.37 | 5022 | 644.44 | 5022 | 9550 | 5022 | 4922.73 | 5022 | 1882.44
2025-09-02 | 30502.7517 | 44460.65 | 5083.7919 | 1184.8 | 5083.7919 | 25963.37 | 5083.7919 | 644.44 | 5083.7919 | 9550 | 5083.7919 | 4922.73 | 5083.7919 | 1882.44
2025-09-03 | 30873.5034 | 44530.65 | 5145.5839 | 1184.8 | 5145.5839 | 25963.37 | 5145.5839 | 644.44 | 5145.5839 | 9550 | 5145.5839 | 4922.73 | 5145.5839 | 1952.44
2025-09-04 | 31244.255 | 44530.65 | 5207.3758 | 1184.8 | 5207.3758 | 25963.37 | 5207.3758 | 644.44 | 5207.3758 | 9550 | 5207.3758 | 4922.73 | 5207.3758 | 1952.44
2025-09-05 | 31615.0067 | 47076.82 | 5269.1678 | 1184.8 | 5269.1678 | 27655.17 | 5269.1678 | 1148.81 | 5269.1678 | 9900 | 5269.1678 | 4922.73 | 5269.1678 | 1952.44
2025-09-06 | 31985.7584 | 48326.82 | 5330.9597 | 1184.8 | 5330.9597 | 28905.17 | 5330.9597 | 1148.81 | 5330.9597 | 9900 | 5330.9597 | 4922.73 | 5330.9597 | 1952.44
2025-09-07 | 32356.5101 | 48409.98 | 5392.7517 | 1184.8 | 5392.7517 | 28905.17 | 5392.7517 | 1148.81 | 5392.7517 | 9900 | 5392.7517 | 4922.73 | 5392.7517 | 2035.6
2025-09-08 | 32727.2617 | 48488.22 | 5454.5436 | 1184.8 | 5454.5436 | 28905.17 | 5454.5436 | 1148.81 | 5454.5436 | 9900 | 5454.5436 | 4922.73 | 5454.5436 | 2113.84
2025-09-09 | 33098.0134 | 48528.22 | 5516.3356 | 1184.8 | 5516.3356 | 28905.17 | 5516.3356 | 1188.81 | 5516.3356 | 9900 | 5516.3356 | 4922.73 | 5516.3356 | 2113.84
2025-09-10 | 33468.7651 | 53144.37 | 5578.1275 | 1504.98 | 5578.1275 | 33134.67 | 5578.1275 | 1188.81 | 5578.1275 | 9966.47 | 5578.1275 | 4922.73 | 5578.1275 | 2113.84
2025-09-11 | 33839.5168 | 53840.97 | 5639.9195 | 1504.98 | 5639.9195 | 33134.67 | 5639.9195 | 1188.81 | 5639.9195 | 9966.47 | 5639.9195 | 5619.33 | 5639.9195 | 2113.84
2025-09-12 | 34210.2685 | 53840.97 | 5701.7114 | 1504.98 | 5701.7114 | 33134.67 | 5701.7114 | 1188.81 | 5701.7114 | 9966.47 | 5701.7114 | 5619.33 | 5701.7114 | 2113.84
2025-09-13 | 34581.0201 | 53921.67 | 5763.5034 | 1504.98 | 5763.5034 | 33134.67 | 5763.5034 | 1188.81 | 5763.5034 | 9966.47 | 5763.5034 | 5619.33 | 5763.5034 | 2194.54
2025-09-14 | 34951.7718 | 54276.99 | 5825.2953 | 1504.98 | 5825.2953 | 33148.16 | 5825.2953 | 1188.81 | 5825.2953 | 9966.47 | 5825.2953 | 5643.11 | 5825.2953 | 2512.59
2025-09-15 | 35322.5235 | 57385.5 | 5887.0872 | 1504.98 | 5887.0872 | 34498.16 | 5887.0872 | 1497.32 | 5887.0872 | 11416.47 | 5887.0872 | 5643.11 | 5887.0872 | 2512.59
2025-09-16 | 35693.2752 | 58622.15 | 5948.8792 | 1504.98 | 5948.8792 | 35003.76 | 5948.8792 | 1762.12 | 5948.8792 | 11416.47 | 5948.8792 | 5789.3 | 5948.8792 | 2832.65
2025-09-17 | 36064.0268 | 58681.36 | 6010.6711 | 1504.98 | 6010.6711 | 35003.76 | 6010.6711 | 1762.12 | 6010.6711 | 11416.47 | 6010.6711 | 5789.3 | 6010.6711 | 2891.86
2025-09-18 | 36434.7785 | 59487.08 | 6072.4631 | 2090.35 | 6072.4631 | 35003.76 | 6072.4631 | 1832.2 | 6072.4631 | 11416.47 | 6072.4631 | 5789.3 | 6072.4631 | 3042.13
2025-09-19 | 36805.5302 | 59591.96 | 6134.255 | 2090.35 | 6134.255 | 35003.76 | 6134.255 | 1832.2 | 6134.255 | 11416.47 | 6134.255 | 5789.3 | 6134.255 | 3147.01
2025-09-20 | 37176.2819 | 59656.96 | 6196.047 | 2090.35 | 6196.047 | 35003.76 | 6196.047 | 1882.2 | 6196.047 | 11416.47 | 6196.047 | 5789.3 | 6196.047 | 3162.01
2025-09-21 | 37547.0336 | 60224.07 | 6257.8389 | 2090.35 | 6257.8389 | 35003.76 | 6257.8389 | 2345.63 | 6257.8389 | 11416.47 | 6257.8389 | 5789.3 | 6257.8389 | 3265.69
2025-09-22 | 37917.7852 | 62777.92 | 6319.6309 | 2090.35 | 6319.6309 | 35003.76 | 6319.6309 | 2345.63 | 6319.6309 | 13216.47 | 6319.6309 | 6328.44 | 6319.6309 | 3480.4
2025-09-23 | 38288.5369 | 62812.74 | 6381.4228 | 2090.35 | 6381.4228 | 35003.76 | 6381.4228 | 2345.63 | 6381.4228 | 13216.47 | 6381.4228 | 6340.51 | 6381.4228 | 3503.15
2025-09-24 | 38659.2886 | 62866.7 | 6443.2148 | 2090.35 | 6443.2148 | 35003.76 | 6443.2148 | 2345.63 | 6443.2148 | 13216.47 | 6443.2148 | 6394.47 | 6443.2148 | 3503.15
2025-09-25 | 39030.0403 | 62928.52 | 6505.0067 | 2090.35 | 6505.0067 | 35003.76 | 6505.0067 | 2345.63 | 6505.0067 | 13216.47 | 6505.0067 | 6394.47 | 6505.0067 | 3564.97
2025-09-26 | 39400.7919 | 63415.61 | 6566.7987 | 2090.35 | 6566.7987 | 35003.76 | 6566.7987 | 2740.82 | 6566.7987 | 13216.47 | 6566.7987 | 6394.47 | 6566.7987 | 3656.87
2025-09-27 | 39771.5436 | 63667.11 | 6628.5906 | 2090.35 | 6628.5906 | 35003.76 | 6628.5906 | 2740.82 | 6628.5906 | 13216.47 | 6628.5906 | 6394.47 | 6628.5906 | 3908.37
2025-09-28 | 40142.2953 | 63667.11 | 6690.3826 | 2090.35 | 6690.3826 | 35003.76 | 6690.3826 | 2740.82 | 6690.3826 | 13216.47 | 6690.3826 | 6394.47 | 6690.3826 | 3908.37
2025-09-29 | 40513.047 | 71016.08 | 6752.1745 | 2090.35 | 6752.1745 | 39463.96 | 6752.1745 | 2740.82 | 6752.1745 | 16016.47 | 6752.1745 | 6394.47 | 6752.1745 | 3997.14
2025-09-30 | 40883.7987 | 72479.29 | 6813.9664 | 2090.35 | 6813.9664 | 40617.46 | 6813.9664 | 2825.82 | 6813.9664 | 16016.47 | 6813.9664 | 6394.47 | 6813.9664 | 4221.85
2025-10-01 | 41254.5503 | 72622.32 | 6875.7584 | 2090.35 | 6875.7584 | 40617.46 | 6875.7584 | 2907.57 | 6875.7584 | 16016.47 | 6875.7584 | 6394.47 | 6875.7584 | 4283.13
2025-10-02 | 41625.302 | 73480.3 | 6937.5503 | 2798.73 | 6937.5503 | 40694.36 | 6937.5503 | 2943.35 | 6937.5503 | 16016.47 | 6937.5503 | 6394.47 | 6937.5503 | 4320.05
2025-10-03 | 41996.0537 | 75648.69 | 6999.3423 | 2839.73 | 6999.3423 | 40694.36 | 6999.3423 | 2943.35 | 6999.3423 | 18066.47 | 6999.3423 | 6394.47 | 6999.3423 | 4397.44
2025-10-04 | 42366.8054 | 76070.17 | 7061.1342 | 2839.73 | 7061.1342 | 40694.36 | 7061.1342 | 2943.35 | 7061.1342 | 18066.47 | 7061.1342 | 6394.47 | 7061.1342 | 4818.92
2025-10-05 | 42737.557 | 76285.1 | 7122.9262 | 2839.73 | 7122.9262 | 40694.36 | 7122.9262 | 3107.84 | 7122.9262 | 18066.47 | 7122.9262 | 6394.47 | 7122.9262 | 4869.36
2025-10-06 | 43108.3087 | 79895.59 | 7184.7181 | 2839.73 | 7184.7181 | 44154.86 | 7184.7181 | 3194.55 | 7184.7181 | 18066.47 | 7184.7181 | 6394.47 | 7184.7181 | 4932.64
2025-10-07 | 43479.0604 | 79971.45 | 7246.5101 | 2839.73 | 7246.5101 | 44154.86 | 7246.5101 | 3194.55 | 7246.5101 | 18066.47 | 7246.5101 | 6394.47 | 7246.5101 | 5008.5
2025-10-08 | 43849.8121 | 80888.35 | 7308.302 | 2839.73 | 7308.302 | 44154.86 | 7308.302 | 3928.92 | 7308.302 | 18066.47 | 7308.302 | 6394.47 | 7308.302 | 5191.03
2025-10-09 | 44220.5638 | 81161.59 | 7370.094 | 2839.73 | 7370.094 | 44414.02 | 7370.094 | 3928.92 | 7370.094 | 18066.47 | 7370.094 | 6394.47 | 7370.094 | 5205.11
2025-10-10 | 44591.3154 | 81564.46 | 7431.8859 | 2839.73 | 7431.8859 | 44414.02 | 7431.8859 | 3928.92 | 7431.8859 | 18066.47 | 7431.8859 | 6797.34 | 7431.8859 | 5205.11
2025-10-11 | 44962.0671 | 81564.46 | 7493.6779 | 2839.73 | 7493.6779 | 44414.02 | 7493.6779 | 3928.92 | 7493.6779 | 18066.47 | 7493.6779 | 6797.34 | 7493.6779 | 5205.11
2025-10-12 | 45332.8188 | 81636.07 | 7555.4698 | 2839.73 | 7555.4698 | 44414.02 | 7555.4698 | 3928.92 | 7555.4698 | 18066.47 | 7555.4698 | 6797.34 | 7555.4698 | 5276.72
2025-10-13 | 45703.5705 | 83712.37 | 7617.2617 | 2839.73 | 7617.2617 | 46490.32 | 7617.2617 | 3928.92 | 7617.2617 | 18066.47 | 7617.2617 | 6797.34 | 7617.2617 | 5276.72
2025-10-14 | 46074.3221 | 84498.37 | 7679.0537 | 2839.73 | 7679.0537 | 46490.32 | 7679.0537 | 4014.92 | 7679.0537 | 18766.47 | 7679.0537 | 6797.34 | 7679.0537 | 5276.72
2025-10-15 | 46445.0738 | 85254.57 | 7740.8456 | 2839.73 | 7740.8456 | 46886.2 | 7740.8456 | 4014.92 | 7740.8456 | 18766.47 | 7740.8456 | 6797.34 | 7740.8456 | 5637.04
2025-10-16 | 46815.8255 | 86625.01 | 7802.6376 | 2839.73 | 7802.6376 | 48206.4 | 7802.6376 | 4014.92 | 7802.6376 | 18766.47 | 7802.6376 | 6797.34 | 7802.6376 | 5687.28
2025-10-17 | 47186.5772 | 88989.52 | 7864.4295 | 2839.73 | 7864.4295 | 49513.7 | 7864.4295 | 4026.4 | 7864.4295 | 19766.47 | 7864.4295 | 6797.34 | 7864.4295 | 5733.01
2025-10-18 | 47557.3289 | 89021.28 | 7926.2215 | 2839.73 | 7926.2215 | 49513.7 | 7926.2215 | 4026.4 | 7926.2215 | 19766.47 | 7926.2215 | 6797.34 | 7926.2215 | 5764.77
2025-10-19 | 47928.0805 | 89529.62 | 7988.0134 | 3234.92 | 7988.0134 | 49513.7 | 7988.0134 | 4026.4 | 7988.0134 | 19766.47 | 7988.0134 | 6797.34 | 7988.0134 | 5877.92
2025-10-20 | 48298.8322 | 89902.23 | 8049.8054 | 3234.92 | 8049.8054 | 49744.4 | 8049.8054 | 4118.7 | 8049.8054 | 19766.47 | 8049.8054 | 6797.34 | 8049.8054 | 5927.53
2025-10-21 | 48669.5839 | 91602.01 | 8111.5973 | 4071.45 | 8111.5973 | 50513.4 | 8111.5973 | 4153.7 | 8111.5973 | 19766.47 | 8111.5973 | 6797.34 | 8111.5973 | 5986.78
2025-10-22 | 49040.3356 | 91686.43 | 8173.3893 | 4071.45 | 8173.3893 | 50513.4 | 8173.3893 | 4153.7 | 8173.3893 | 19766.47 | 8173.3893 | 6797.34 | 8173.3893 | 6071.2
2025-10-23 | 49411.0872 | 94987.73 | 8235.1812 | 4071.45 | 8235.1812 | 53572.44 | 8235.1812 | 4153.7 | 8235.1812 | 19766.47 | 8235.1812 | 6797.34 | 8235.1812 | 6313.46
2025-10-24 | 49781.8389 | 99972.96 | 8296.9732 | 4471.64 | 8296.9732 | 53572.44 | 8296.9732 | 4153.7 | 8296.9732 | 22019.47 | 8296.9732 | 9099.43 | 8296.9732 | 6343.41
2025-10-25 | 50152.5906 | 100658.31 | 8358.7651 | 4471.64 | 8358.7651 | 53642.68 | 8358.7651 | 4153.7 | 8358.7651 | 22019.47 | 8358.7651 | 9620.11 | 8358.7651 | 6437.84
2025-10-26 | 50523.3423 | 100841.54 | 8420.557 | 4506.64 | 8420.557 | 53642.68 | 8420.557 | 4153.7 | 8420.557 | 22019.47 | 8420.557 | 9620.11 | 8420.557 | 6586.07
2025-10-27 | 50894.094 | 101562.85 | 8482.349 | 4506.64 | 8482.349 | 54189.8 | 8482.349 | 4153.7 | 8482.349 | 22019.47 | 8482.349 | 9620.11 | 8482.349 | 6760.26
2025-10-28 | 51264.8456 | 104613.9 | 8544.1409 | 4506.64 | 8544.1409 | 56936.5 | 8544.1409 | 4173.7 | 8544.1409 | 22029.07 | 8544.1409 | 9808.48 | 8544.1409 | 6846.64
2025-10-29 | 51635.5973 | 104713.9 | 8605.9329 | 4506.64 | 8605.9329 | 56936.5 | 8605.9329 | 4173.7 | 8605.9329 | 22029.07 | 8605.9329 | 9808.48 | 8605.9329 | 6946.64
2025-10-30 | 52006.349 | 104810.99 | 8667.7248 | 4506.64 | 8667.7248 | 56936.5 | 8667.7248 | 4173.7 | 8667.7248 | 22029.07 | 8667.7248 | 9808.48 | 8667.7248 | 7043.73
2025-10-31 | 52377.1007 | 105810.99 | 8729.5168 | 4506.64 | 8729.5168 | 56936.5 | 8729.5168 | 4173.7 | 8729.5168 | 23029.07 | 8729.5168 | 9808.48 | 8729.5168 | 7043.73
2025-11-01 | 52747.8523 | 105941.72 | 8791.3087 | 4506.64 | 8791.3087 | 56936.5 | 8791.3087 | 4173.7 | 8791.3087 | 23029.07 | 8791.3087 | 9808.48 | 8791.3087 | 7174.46
2025-11-02 | 53118.604 | 105958.95 | 8853.1007 | 4506.64 | 8853.1007 | 56936.5 | 8853.1007 | 4190.93 | 8853.1007 | 23029.07 | 8853.1007 | 9808.48 | 8853.1007 | 7174.46
2025-11-03 | 53489.3557 | 105958.95 | 8914.8926 | 4506.64 | 8914.8926 | 56936.5 | 8914.8926 | 4190.93 | 8914.8926 | 23029.07 | 8914.8926 | 9808.48 | 8914.8926 | 7174.46
2025-11-04 | 53860.1074 | 106221.92 | 8976.6846 | 4506.64 | 8976.6846 | 56936.5 | 8976.6846 | 4190.93 | 8976.6846 | 23029.07 | 8976.6846 | 9978.33 | 8976.6846 | 7267.58
2025-11-05 | 54230.8591 | 106675.26 | 9038.4765 | 4506.64 | 9038.4765 | 56936.5 | 9038.4765 | 4190.93 | 9038.4765 | 23029.07 | 9038.4765 | 10431.67 | 9038.4765 | 7267.58
2025-11-06 | 54601.6107 | 107020.03 | 9100.2685 | 4506.64 | 9100.2685 | 57006.74 | 9100.2685 | 4190.93 | 9100.2685 | 23029.07 | 9100.2685 | 10431.67 | 9100.2685 | 7542.11
2025-11-07 | 54972.3624 | 109925.4 | 9162.0604 | 5269.01 | 9162.0604 | 57222.2 | 9162.0604 | 4204.93 | 9162.0604 | 24829.07 | 9162.0604 | 10431.67 | 9162.0604 | 7655.65
2025-11-08 | 55343.1141 | 110334.05 | 9223.8523 | 5269.01 | 9223.8523 | 57351.88 | 9223.8523 | 4204.93 | 9223.8523 | 24829.07 | 9223.8523 | 10484.11 | 9223.8523 | 7882.18
2025-11-09 | 55713.8658 | 110632.04 | 9285.6443 | 5269.01 | 9285.6443 | 57351.88 | 9285.6443 | 4204.93 | 9285.6443 | 24829.07 | 9285.6443 | 10484.11 | 9285.6443 | 8180.17
2025-11-10 | 56084.6174 | 111072.23 | 9347.4362 | 5269.01 | 9347.4362 | 57792.07 | 9347.4362 | 4204.93 | 9347.4362 | 24829.07 | 9347.4362 | 10484.11 | 9347.4362 | 8180.17
2025-11-11 | 56455.3691 | 111144.61 | 9409.2282 | 5269.01 | 9409.2282 | 57792.07 | 9409.2282 | 4242.55 | 9409.2282 | 24829.07 | 9409.2282 | 10484.11 | 9409.2282 | 8214.93
2025-11-12 | 56826.1208 | 111194.99 | 9471.0201 | 5319.39 | 9471.0201 | 57792.07 | 9471.0201 | 4242.55 | 9471.0201 | 24829.07 | 9471.0201 | 10484.11 | 9471.0201 | 8214.93
2025-11-13 | 57196.8725 | 111495.82 | 9532.8121 | 5319.39 | 9532.8121 | 57792.07 | 9532.8121 | 4501.54 | 9532.8121 | 24829.07 | 9532.8121 | 10484.11 | 9532.8121 | 8256.77
2025-11-14 | 57567.6242 | 112951 | 9594.604 | 5319.39 | 9594.604 | 57792.07 | 9594.604 | 4501.54 | 9594.604 | 26229.07 | 9594.604 | 10484.11 | 9594.604 | 8311.95
2025-11-15 | 57938.3758 | 113293.18 | 9656.396 | 5654.57 | 9656.396 | 57792.07 | 9656.396 | 4501.54 | 9656.396 | 26229.07 | 9656.396 | 10484.11 | 9656.396 | 8318.95
2025-11-16 | 58309.1275 | 114421.94 | 9718.1879 | 5654.57 | 9718.1879 | 58835.92 | 9718.1879 | 4501.54 | 9718.1879 | 26229.07 | 9718.1879 | 10484.11 | 9718.1879 | 8403.86
2025-11-17 | 58679.8792 | 114501.94 | 9779.9799 | 5654.57 | 9779.9799 | 58835.92 | 9779.9799 | 4501.54 | 9779.9799 | 26229.07 | 9779.9799 | 10484.11 | 9779.9799 | 8483.86
2025-11-18 | 59050.6309 | 114796.14 | 9841.7718 | 5654.57 | 9841.7718 | 58835.92 | 9841.7718 | 4769.73 | 9841.7718 | 26229.07 | 9841.7718 | 10484.11 | 9841.7718 | 8509.87
2025-11-19 | 59421.3826 | 114898.79 | 9903.5638 | 5654.57 | 9903.5638 | 58835.92 | 9903.5638 | 4872.38 | 9903.5638 | 26229.07 | 9903.5638 | 10484.11 | 9903.5638 | 8509.87
2025-11-20 | 59792.1342 | 115961.24 | 9965.3557 | 5654.57 | 9965.3557 | 59771.15 | 9965.3557 | 4879.38 | 9965.3557 | 26229.07 | 9965.3557 | 10591.35 | 9965.3557 | 8522.85
2025-11-21 | 60162.8859 | 124763.67 | 10027.1477 | 5654.57 | 10027.1477 | 68013.77 | 10027.1477 | 4879.38 | 10027.1477 | 26229.07 | 10027.1477 | 10591.35 | 10027.1477 | 8522.85
2025-11-22 | 60533.6376 | 125126.53 | 10088.9396 | 5654.57 | 10088.9396 | 68013.77 | 10088.9396 | 5017.76 | 10088.9396 | 26229.07 | 10088.9396 | 10591.35 | 10088.9396 | 8747.33
2025-11-23 | 60904.3893 | 125180.95 | 10150.7315 | 5654.57 | 10150.7315 | 68013.77 | 10150.7315 | 5017.76 | 10150.7315 | 26229.07 | 10150.7315 | 10591.35 | 10150.7315 | 8801.75
2025-11-24 | 61275.1409 | 125180.95 | 10212.5235 | 5654.57 | 10212.5235 | 68013.77 | 10212.5235 | 5017.76 | 10212.5235 | 26229.07 | 10212.5235 | 10591.35 | 10212.5235 | 8801.75
2025-11-25 | 61645.8926 | 125180.95 | 10274.3154 | 5654.57 | 10274.3154 | 68013.77 | 10274.3154 | 5017.76 | 10274.3154 | 26229.07 | 10274.3154 | 10591.35 | 10274.3154 | 8801.75
2025-11-26 | 62016.6443 | 125180.95 | 10336.1074 | 5654.57 | 10336.1074 | 68013.77 | 10336.1074 | 5017.76 | 10336.1074 | 26229.07 | 10336.1074 | 10591.35 | 10336.1074 | 8801.75
2025-11-27 | 62387.396 | 126606.52 | 10397.8993 | 7080.14 | 10397.8993 | 68013.77 | 10397.8993 | 5017.76 | 10397.8993 | 26229.07 | 10397.8993 | 10591.35 | 10397.8993 | 8801.75
2025-11-28 | 62758.1477 | 127513.36 | 10459.6913 | 7080.14 | 10459.6913 | 68013.77 | 10459.6913 | 5017.76 | 10459.6913 | 26929.07 | 10459.6913 | 10591.35 | 10459.6913 | 9008.59
2025-11-29 | 63128.8993 | 127597.45 | 10521.4832 | 7080.14 | 10521.4832 | 68013.77 | 10521.4832 | 5017.76 | 10521.4832 | 26929.07 | 10521.4832 | 10591.35 | 10521.4832 | 9092.68
2025-11-30 | 63499.651 | 127960.12 | 10583.2752 | 7080.14 | 10583.2752 | 68145.53 | 10583.2752 | 5017.76 | 10583.2752 | 26929.07 | 10583.2752 | 10745.3 | 10583.2752 | 9169.64
2025-12-01 | 63870.4027 | 128016.96 | 10645.0671 | 7080.14 | 10645.0671 | 68145.53 | 10645.0671 | 5017.76 | 10645.0671 | 26929.07 | 10645.0671 | 10745.3 | 10645.0671 | 9226.48
2025-12-02 | 64241.1544 | 128016.96 | 10706.8591 | 7080.14 | 10706.8591 | 68145.53 | 10706.8591 | 5017.76 | 10706.8591 | 26929.07 | 10706.8591 | 10745.3 | 10706.8591 | 9226.48
2025-12-03 | 64611.906 | 128016.96 | 10768.651 | 7080.14 | 10768.651 | 68145.53 | 10768.651 | 5017.76 | 10768.651 | 26929.07 | 10768.651 | 10745.3 | 10768.651 | 9226.48
2025-12-04 | 64982.6577 | 128093.09 | 10830.443 | 7080.14 | 10830.443 | 68145.53 | 10830.443 | 5017.76 | 10830.443 | 26929.07 | 10830.443 | 10745.3 | 10830.443 | 9302.61
2025-12-05 | 65353.4094 | 130720.84 | 10892.2349 | 7080.14 | 10892.2349 | 68145.53 | 10892.2349 | 6245.51 | 10892.2349 | 28329.07 | 10892.2349 | 10745.3 | 10892.2349 | 9302.61
2025-12-06 | 65724.1611 | 130759.12 | 10954.0268 | 7080.14 | 10954.0268 | 68145.53 | 10954.0268 | 6245.51 | 10954.0268 | 28329.07 | 10954.0268 | 10745.3 | 10954.0268 | 9340.89
2025-12-07 | 66094.9128 | 130759.12 | 11015.8188 | 7080.14 | 11015.8188 | 68145.53 | 11015.8188 | 6245.51 | 11015.8188 | 28329.07 | 11015.8188 | 10745.3 | 11015.8188 | 9340.89
2025-12-08 | 66465.6644 | 130826.66 | 11077.6107 | 7080.14 | 11077.6107 | 68145.53 | 11077.6107 | 6245.51 | 11077.6107 | 28329.07 | 11077.6107 | 10745.3 | 11077.6107 | 9408.43
2025-12-09 | 66836.4161 | 130966.66 | 11139.4027 | 7080.14 | 11139.4027 | 68145.53 | 11139.4027 | 6385.51 | 11139.4027 | 28329.07 | 11139.4027 | 10745.3 | 11139.4027 | 9408.43
2025-12-10 | 67207.1678 | 130966.66 | 11201.1946 | 7080.14 | 11201.1946 | 68145.53 | 11201.1946 | 6385.51 | 11201.1946 | 28329.07 | 11201.1946 | 10745.3 | 11201.1946 | 9408.43
2025-12-11 | 67577.9195 | 131063.55 | 11262.9866 | 7080.14 | 11262.9866 | 68145.53 | 11262.9866 | 6385.51 | 11262.9866 | 28329.07 | 11262.9866 | 10745.3 | 11262.9866 | 9505.32
2025-12-12 | 67948.6711 | 134357.9 | 11324.7785 | 7080.14 | 11324.7785 | 68145.53 | 11324.7785 | 6385.51 | 11324.7785 | 31579.07 | 11324.7785 | 10745.3 | 11324.7785 | 9549.67
2025-12-13 | 68319.4228 | 134357.9 | 11386.5705 | 7080.14 | 11386.5705 | 68145.53 | 11386.5705 | 6385.51 | 11386.5705 | 31579.07 | 11386.5705 | 10745.3 | 11386.5705 | 9549.67
2025-12-14 | 68690.1745 | 134357.9 | 11448.3624 | 7080.14 | 11448.3624 | 68145.53 | 11448.3624 | 6385.51 | 11448.3624 | 31579.07 | 11448.3624 | 10745.3 | 11448.3624 | 9549.67
2025-12-15 | 69060.9262 | 134753.09 | 11510.1544 | 7080.14 | 11510.1544 | 68145.53 | 11510.1544 | 6780.7 | 11510.1544 | 31579.07 | 11510.1544 | 10745.3 | 11510.1544 | 9549.67
2025-12-16 | 69431.6779 | 135283.22 | 11571.9463 | 7080.14 | 11571.9463 | 68675.66 | 11571.9463 | 6780.7 | 11571.9463 | 31579.07 | 11571.9463 | 10745.3 | 11571.9463 | 9549.67
2025-12-17 | 69802.4295 | 135831.4 | 11633.7383 | 7628.32 | 11633.7383 | 68675.66 | 11633.7383 | 6780.7 | 11633.7383 | 31579.07 | 11633.7383 | 10745.3 | 11633.7383 | 9549.67
2025-12-18 | 70173.1812 | 135831.4 | 11695.5302 | 7628.32 | 11695.5302 | 68675.66 | 11695.5302 | 6780.7 | 11695.5302 | 31579.07 | 11695.5302 | 10745.3 | 11695.5302 | 9549.67
2025-12-19 | 70543.9329 | 141514.07 | 11757.3221 | 7628.32 | 11757.3221 | 73165.4 | 11757.3221 | 6780.7 | 11757.3221 | 31729.07 | 11757.3221 | 10745.3 | 11757.3221 | 9549.67
2025-12-20 | 70914.6846 | 146205.43 | 11819.1141 | 7628.32 | 11819.1141 | 77856.76 | 11819.1141 | 6780.7 | 11819.1141 | 31729.07 | 11819.1141 | 10745.3 | 11819.1141 | 9549.67
2025-12-21 | 71285.4362 | 146649.28 | 11880.906 | 7628.32 | 11880.906 | 78300.61 | 11880.906 | 6780.7 | 11880.906 | 31729.07 | 11880.906 | 10745.3 | 11880.906 | 9549.67
2025-12-22 | 71656.1879 | 146649.28 | 11942.698 | 7628.32 | 11942.698 | 78300.61 | 11942.698 | 6780.7 | 11942.698 | 31729.07 | 11942.698 | 10745.3 | 11942.698 | 9549.67
2025-12-23 | 72026.9396 | 146649.28 | 12004.4899 | 7628.32 | 12004.4899 | 78300.61 | 12004.4899 | 6780.7 | 12004.4899 | 31729.07 | 12004.4899 | 10745.3 | 12004.4899 | 9549.67
2025-12-24 | 72397.6913 | 146649.28 | 12066.2819 | 7628.32 | 12066.2819 | 78300.61 | 12066.2819 | 6780.7 | 12066.2819 | 31729.07 | 12066.2819 | 10745.3 | 12066.2819 | 9549.67
2025-12-25 | 72768.443 | 147012.73 | 12128.0738 | 7991.77 | 12128.0738 | 78300.61 | 12128.0738 | 6780.7 | 12128.0738 | 31729.07 | 12128.0738 | 10745.3 | 12128.0738 | 9549.67
2025-12-26 | 73139.1946 | 147012.73 | 12189.8658 | 7991.77 | 12189.8658 | 78300.61 | 12189.8658 | 6780.7 | 12189.8658 | 31729.07 | 12189.8658 | 10745.3 | 12189.8658 | 9549.67
2025-12-27 | 73509.9463 | 147012.73 | 12251.6577 | 7991.77 | 12251.6577 | 78300.61 | 12251.6577 | 6780.7 | 12251.6577 | 31729.07 | 12251.6577 | 10745.3 | 12251.6577 | 9549.67
2025-12-28 | 73880.698 | 147012.73 | 12313.4497 | 7991.77 | 12313.4497 | 78300.61 | 12313.4497 | 6780.7 | 12313.4497 | 31729.07 | 12313.4497 | 10745.3 | 12313.4497 | 9549.67
2025-12-29 | 74251.4497 | 147012.73 | 12375.2416 | 7991.77 | 12375.2416 | 78300.61 | 12375.2416 | 6780.7 | 12375.2416 | 31729.07 | 12375.2416 | 10745.3 | 12375.2416 | 9549.67
2025-12-30 | 74622.2013 | 147312.73 | 12437.0336 | 7991.77 | 12437.0336 | 78300.61 | 12437.0336 | 6780.7 | 12437.0336 | 32029.07 | 12437.0336 | 10745.3 | 12437.0336 | 9549.67
2025-12-31 | 74992.953 | 147312.73 | 12498.8255 | 7991.77 | 12498.8255 | 78300.61 | 12498.8255 | 6780.7 | 12498.8255 | 32029.07 | 12498.8255 | 10745.3 | 12498.8255 | 9549.67
2026-01-01 | 75363.7047 | 147312.73 | 12560.6174 | 7991.77 | 12560.6174 | 78300.61 | 12560.6174 | 6780.7 | 12560.6174 | 32029.07 | 12560.6174 | 10745.3 | 12560.6174 | 9549.67
2026-01-02 | 75734.4564 | 147312.73 | 12622.4094 | 7991.77 | 12622.4094 | 78300.61 | 12622.4094 | 6780.7 | 12622.4094 | 32029.07 | 12622.4094 | 10745.3 | 12622.4094 | 9549.67
2026-01-03 | 76105.2081 | 149237.59 | 12684.2013 | 7991.77 | 12684.2013 | 80225.47 | 12684.2013 | 6780.7 | 12684.2013 | 32029.07 | 12684.2013 | 10745.3 | 12684.2013 | 9549.67
2026-01-04 | 76475.9597 | 149284.26 | 12745.9933 | 7991.77 | 12745.9933 | 80225.47 | 12745.9933 | 6780.7 | 12745.9933 | 32029.07 | 12745.9933 | 10745.3 | 12745.9933 | 9596.34
2026-01-05 | 76846.7114 | 150283.65 | 12807.7852 | 7991.77 | 12807.7852 | 80225.47 | 12807.7852 | 7780.09 | 12807.7852 | 32029.07 | 12807.7852 | 10745.3 | 12807.7852 | 9596.34
2026-01-06 | 77217.4631 | 152558.72 | 12869.5772 | 8525.07 | 12869.5772 | 80225.47 | 12869.5772 | 7780.09 | 12869.5772 | 33629.07 | 12869.5772 | 10745.3 | 12869.5772 | 9738.11
2026-01-07 | 77588.2148 | 152558.72 | 12931.3691 | 8525.07 | 12931.3691 | 80225.47 | 12931.3691 | 7780.09 | 12931.3691 | 33629.07 | 12931.3691 | 10745.3 | 12931.3691 | 9738.11
2026-01-08 | 77958.9664 | 152558.72 | 12993.1611 | 8525.07 | 12993.1611 | 80225.47 | 12993.1611 | 7780.09 | 12993.1611 | 33629.07 | 12993.1611 | 10745.3 | 12993.1611 | 9738.11
2026-01-09 | 78329.7181 | 152614.64 | 13054.953 | 8525.07 | 13054.953 | 80225.47 | 13054.953 | 7780.09 | 13054.953 | 33629.07 | 13054.953 | 10745.3 | 13054.953 | 9794.03
2026-01-10 | 78700.4698 | 152614.64 | 13116.745 | 8525.07 | 13116.745 | 80225.47 | 13116.745 | 7780.09 | 13116.745 | 33629.07 | 13116.745 | 10745.3 | 13116.745 | 9794.03
2026-01-11 | 79071.2215 | 152659.73 | 13178.5369 | 8525.07 | 13178.5369 | 80225.47 | 13178.5369 | 7780.09 | 13178.5369 | 33629.07 | 13178.5369 | 10745.3 | 13178.5369 | 9839.12
2026-01-12 | 79441.9732 | 152721.81 | 13240.3289 | 8525.07 | 13240.3289 | 80287.55 | 13240.3289 | 7780.09 | 13240.3289 | 33629.07 | 13240.3289 | 10745.3 | 13240.3289 | 9839.12
2026-01-13 | 79812.7248 | 152721.81 | 13302.1208 | 8525.07 | 13302.1208 | 80287.55 | 13302.1208 | 7780.09 | 13302.1208 | 33629.07 | 13302.1208 | 10745.3 | 13302.1208 | 9839.12
2026-01-14 | 80183.4765 | 154660.21 | 13363.9128 | 8525.07 | 13363.9128 | 82225.95 | 13363.9128 | 7780.09 | 13363.9128 | 33629.07 | 13363.9128 | 10745.3 | 13363.9128 | 9839.12
2026-01-15 | 80554.2282 | 154689.71 | 13425.7047 | 8525.07 | 13425.7047 | 82225.95 | 13425.7047 | 7780.09 | 13425.7047 | 33629.07 | 13425.7047 | 10745.3 | 13425.7047 | 9868.62
2026-01-16 | 80924.9799 | 158739.71 | 13487.4966 | 8525.07 | 13487.4966 | 82225.95 | 13487.4966 | 7780.09 | 13487.4966 | 37679.07 | 13487.4966 | 10745.3 | 13487.4966 | 9868.62
2026-01-17 | 81295.7315 | 158739.71 | 13549.2886 | 8525.07 | 13549.2886 | 82225.95 | 13549.2886 | 7780.09 | 13549.2886 | 37679.07 | 13549.2886 | 10745.3 | 13549.2886 | 9868.62
2026-01-18 | 81666.4832 | 158739.71 | 13611.0805 | 8525.07 | 13611.0805 | 82225.95 | 13611.0805 | 7780.09 | 13611.0805 | 37679.07 | 13611.0805 | 10745.3 | 13611.0805 | 9868.62
2026-01-19 | 82037.2349 | 158739.71 | 13672.8725 | 8525.07 | 13672.8725 | 82225.95 | 13672.8725 | 7780.09 | 13672.8725 | 37679.07 | 13672.8725 | 10745.3 | 13672.8725 | 9868.62
2026-01-20 | 82407.9866 | 159474.41 | 13734.6644 | 9222.25 | 13734.6644 | 82225.95 | 13734.6644 | 7780.09 | 13734.6644 | 37679.07 | 13734.6644 | 10745.3 | 13734.6644 | 9906.14
2026-01-21 | 82778.7383 | 159474.41 | 13796.4564 | 9222.25 | 13796.4564 | 82225.95 | 13796.4564 | 7780.09 | 13796.4564 | 37679.07 | 13796.4564 | 10745.3 | 13796.4564 | 9906.14
2026-01-22 | 83149.4899 | 159474.41 | 13858.2483 | 9222.25 | 13858.2483 | 82225.95 | 13858.2483 | 7780.09 | 13858.2483 | 37679.07 | 13858.2483 | 10745.3 | 13858.2483 | 9906.14
2026-01-23 | 83520.2416 | 161463.36 | 13920.0403 | 9811.2 | 13920.0403 | 82225.95 | 13920.0403 | 7780.09 | 13920.0403 | 39079.07 | 13920.0403 | 10745.3 | 13920.0403 | 9906.14
2026-01-24 | 83890.9933 | 161598.54 | 13981.8322 | 9811.2 | 13981.8322 | 82225.95 | 13981.8322 | 7780.09 | 13981.8322 | 39079.07 | 13981.8322 | 10745.3 | 13981.8322 | 10041.32
2026-01-25 | 84261.745 | 162066.82 | 14043.6242 | 9811.2 | 14043.6242 | 82225.95 | 14043.6242 | 7780.09 | 14043.6242 | 39547.35 | 14043.6242 | 10745.3 | 14043.6242 | 10041.32
2026-01-26 | 84632.4966 | 162066.82 | 14105.4161 | 9811.2 | 14105.4161 | 82225.95 | 14105.4161 | 7780.09 | 14105.4161 | 39547.35 | 14105.4161 | 10745.3 | 14105.4161 | 10041.32
2026-01-27 | 85003.2483 | 162130.26 | 14167.2081 | 9811.2 | 14167.2081 | 82225.95 | 14167.2081 | 7780.09 | 14167.2081 | 39547.35 | 14167.2081 | 10745.3 | 14167.2081 | 10104.76
2026-01-28 | 85374 | 162525.46 | 14229 | 9811.2 | 14229 | 82225.95 | 14229 | 8175.29 | 14229 | 39547.35 | 14229 | 10745.3 | 14229 | 10104.76
2026-01-29 | 86038.9798 | 162582.68 | 14339.83 | 9811.2 | 14339.83 | 82225.95 | 14339.83 | 8175.29 | 14339.83 | 39547.35 | 14339.83 | 10745.3 | 14339.83 | 10161.98
2026-01-30 | 86703.9595 | 167671.1 | 14450.6599 | 9811.2 | 14450.6599 | 87314.37 | 14450.6599 | 8175.29 | 14450.6599 | 39547.35 | 14450.6599 | 10745.3 | 14450.6599 | 10161.98
2026-01-31 | 87368.9393 | 167737.45 | 14561.4899 | 9811.2 | 14561.4899 | 87314.37 | 14561.4899 | 8175.29 | 14561.4899 | 39547.35 | 14561.4899 | 10745.3 | 14561.4899 | 10228.33
2026-02-01 | 88033.919 | 167789.77 | 14672.3198 | 9811.2 | 14672.3198 | 87314.37 | 14672.3198 | 8175.29 | 14672.3198 | 39547.35 | 14672.3198 | 10745.3 | 14672.3198 | 10280.65
2026-02-02 | 88698.8988 | 170834.67 | 14783.1498 | 9811.2 | 14783.1498 | 89309.27 | 14783.1498 | 8175.29 | 14783.1498 | 40597.35 | 14783.1498 | 10745.3 | 14783.1498 | 10280.65
2026-02-03 | 89363.8786 | 171179.87 | 14893.9798 | 9811.2 | 14893.9798 | 89309.27 | 14893.9798 | 8520.49 | 14893.9798 | 40597.35 | 14893.9798 | 10745.3 | 14893.9798 | 10280.65
2026-02-04 | 90028.8583 | 171280.18 | 15004.8097 | 9811.2 | 15004.8097 | 89309.27 | 15004.8097 | 8520.49 | 15004.8097 | 40597.35 | 15004.8097 | 10745.3 | 15004.8097 | 10380.96
2026-02-05 | 90693.8381 | 171280.18 | 15115.6397 | 9811.2 | 15115.6397 | 89309.27 | 15115.6397 | 8520.49 | 15115.6397 | 40597.35 | 15115.6397 | 10745.3 | 15115.6397 | 10380.96
2026-02-06 | 91358.8178 | 173614.82 | 15226.4696 | 9811.2 | 15226.4696 | 90673.16 | 15226.4696 | 8520.49 | 15226.4696 | 41497.35 | 15226.4696 | 10745.3 | 15226.4696 | 10451.71
2026-02-07 | 92023.7976 | 173614.82 | 15337.2996 | 9811.2 | 15337.2996 | 90673.16 | 15337.2996 | 8520.49 | 15337.2996 | 41497.35 | 15337.2996 | 10745.3 | 15337.2996 | 10451.71
2026-02-08 | 92688.7774 | 173614.82 | 15448.1296 | 9811.2 | 15448.1296 | 90673.16 | 15448.1296 | 8520.49 | 15448.1296 | 41497.35 | 15448.1296 | 10745.3 | 15448.1296 | 10451.71
2026-02-09 | 93353.7571 | 176594.69 | 15558.9595 | 9811.2 | 15558.9595 | 90673.16 | 15558.9595 | 8665.43 | 15558.9595 | 42217.35 | 15558.9595 | 10745.3 | 15558.9595 | 10560.3
2026-02-10 | 94018.7369 | 176594.69 | 15669.7895 | 9811.2 | 15669.7895 | 90673.16 | 15669.7895 | 8665.43 | 15669.7895 | 42217.35 | 15669.7895 | 10745.3 | 15669.7895 | 10560.3
2026-02-11 | 94683.7166 | 176623.5 | 15780.6194 | 9811.2 | 15780.6194 | 90673.16 | 15780.6194 | 8665.43 | 15780.6194 | 42217.35 | 15780.6194 | 10745.3 | 15780.6194 | 10589.11
2026-02-12 | 95348.6964 | 176973.5 | 15891.4494 | 9811.2 | 15891.4494 | 90673.16 | 15891.4494 | 8665.43 | 15891.4494 | 42567.35 | 15891.4494 | 10745.3 | 15891.4494 | 10589.11
2026-02-13 | 96013.6762 | 177583.8 | 16002.2794 | 10421.5 | 16002.2794 | 90673.16 | 16002.2794 | 8665.43 | 16002.2794 | 42567.35 | 16002.2794 | 10745.3 | 16002.2794 | 10589.11
2026-02-14 | 96678.6559 | 177583.8 | 16113.1093 | 10421.5 | 16113.1093 | 90673.16 | 16113.1093 | 8665.43 | 16113.1093 | 42567.35 | 16113.1093 | 10745.3 | 16113.1093 | 10589.11
2026-02-15 | 97343.6357 | 177583.8 | 16223.9393 | 10421.5 | 16223.9393 | 90673.16 | 16223.9393 | 8665.43 | 16223.9393 | 42567.35 | 16223.9393 | 10745.3 | 16223.9393 | 10589.11
2026-02-16 | 98008.6154 | 177583.8 | 16334.7692 | 10421.5 | 16334.7692 | 90673.16 | 16334.7692 | 8665.43 | 16334.7692 | 42567.35 | 16334.7692 | 10745.3 | 16334.7692 | 10589.11
2026-02-17 | 98673.5952 | 178022 | 16445.5992 | 10859.7 | 16445.5992 | 90673.16 | 16445.5992 | 8665.43 | 16445.5992 | 42567.35 | 16445.5992 | 10745.3 | 16445.5992 | 10589.11
2026-02-18 | 99338.575 | 178022 | 16556.4292 | 10859.7 | 16556.4292 | 90673.16 | 16556.4292 | 8665.43 | 16556.4292 | 42567.35 | 16556.4292 | 10745.3 | 16556.4292 | 10589.11
2026-02-19 | 100003.5547 | 178402.39 | 16667.2591 | 10859.7 | 16667.2591 | 90673.16 | 16667.2591 | 9045.82 | 16667.2591 | 42567.35 | 16667.2591 | 10745.3 | 16667.2591 | 10589.11
2026-02-20 | 100668.5345 | 180408.97 | 16778.0891 | 10859.7 | 16778.0891 | 92679.74 | 16778.0891 | 9045.82 | 16778.0891 | 42567.35 | 16778.0891 | 10745.3 | 16778.0891 | 10589.11
2026-02-21 | 101333.5142 | 180408.97 | 16888.919 | 10859.7 | 16888.919 | 92679.74 | 16888.919 | 9045.82 | 16888.919 | 42567.35 | 16888.919 | 10745.3 | 16888.919 | 10589.11
2026-02-22 | 101998.494 | 180408.97 | 16999.749 | 10859.7 | 16999.749 | 92679.74 | 16999.749 | 9045.82 | 16999.749 | 42567.35 | 16999.749 | 10745.3 | 16999.749 | 10589.11
2026-02-23 | 102663.4738 | 180408.97 | 17110.579 | 10859.7 | 17110.579 | 92679.74 | 17110.579 | 9045.82 | 17110.579 | 42567.35 | 17110.579 | 10745.3 | 17110.579 | 10589.11
2026-02-24 | 103328.4535 | 182268.82 | 17221.4089 | 10859.7 | 17221.4089 | 94539.59 | 17221.4089 | 9045.82 | 17221.4089 | 42567.35 | 17221.4089 | 10745.3 | 17221.4089 | 10589.11
2026-02-25 | 103993.4333 | 182908.62 | 17332.2389 | 10859.7 | 17332.2389 | 94539.59 | 17332.2389 | 9685.62 | 17332.2389 | 42567.35 | 17332.2389 | 10745.3 | 17332.2389 | 10589.11
2026-02-26 | 104658.413 | 182908.62 | 17443.0688 | 10859.7 | 17443.0688 | 94539.59 | 17443.0688 | 9685.62 | 17443.0688 | 42567.35 | 17443.0688 | 10745.3 | 17443.0688 | 10589.11
2026-02-27 | 105323.3928 | 184008.62 | 17553.8988 | 10859.7 | 17553.8988 | 94539.59 | 17553.8988 | 9685.62 | 17553.8988 | 43667.35 | 17553.8988 | 10745.3 | 17553.8988 | 10589.11
2026-02-28 | 105988.3726 | 184008.62 | 17664.7288 | 10859.7 | 17664.7288 | 94539.59 | 17664.7288 | 9685.62 | 17664.7288 | 43667.35 | 17664.7288 | 10745.3 | 17664.7288 | 10589.11
2026-03-01 | 106653.3523 | 184008.62 | 17775.5587 | 10859.7 | 17775.5587 | 94539.59 | 17775.5587 | 9685.62 | 17775.5587 | 43667.35 | 17775.5587 | 10745.3 | 17775.5587 | 10589.11
2026-03-02 | 107318.3321 | 185973.41 | 17886.3887 | 10859.7 | 17886.3887 | 96504.38 | 17886.3887 | 9685.62 | 17886.3887 | 43667.35 | 17886.3887 | 10745.3 | 17886.3887 | 10589.11
2026-03-03 | 107983.3118 | 185973.41 | 17997.2186 | 10859.7 | 17997.2186 | 96504.38 | 17997.2186 | 9685.62 | 17997.2186 | 43667.35 | 17997.2186 | 10745.3 | 17997.2186 | 10589.11
2026-03-04 | 108648.2916 | 185973.41 | 18108.0486 | 10859.7 | 18108.0486 | 96504.38 | 18108.0486 | 9685.62 | 18108.0486 | 43667.35 | 18108.0486 | 10745.3 | 18108.0486 | 10589.11
2026-03-05 | 109313.2714 | 185973.41 | 18218.8786 | 10859.7 | 18218.8786 | 96504.38 | 18218.8786 | 9685.62 | 18218.8786 | 43667.35 | 18218.8786 | 10745.3 | 18218.8786 | 10589.11
2026-03-06 | 109978.2511 | 188061.29 | 18329.7085 | 10859.7 | 18329.7085 | 97992.26 | 18329.7085 | 9685.62 | 18329.7085 | 44267.35 | 18329.7085 | 10745.3 | 18329.7085 | 10589.11
2026-03-07 | 110643.2309 | 188061.29 | 18440.5385 | 10859.7 | 18440.5385 | 97992.26 | 18440.5385 | 9685.62 | 18440.5385 | 44267.35 | 18440.5385 | 10745.3 | 18440.5385 | 10589.11
2026-03-08 | 111308.2106 | 188061.29 | 18551.3684 | 10859.7 | 18551.3684 | 97992.26 | 18551.3684 | 9685.62 | 18551.3684 | 44267.35 | 18551.3684 | 10745.3 | 18551.3684 | 10589.11
2026-03-09 | 111973.1904 | 188061.29 | 18662.1984 | 10859.7 | 18662.1984 | 97992.26 | 18662.1984 | 9685.62 | 18662.1984 | 44267.35 | 18662.1984 | 10745.3 | 18662.1984 | 10589.11
2026-03-10 | 112638.1702 | 188061.29 | 18773.0284 | 10859.7 | 18773.0284 | 97992.26 | 18773.0284 | 9685.62 | 18773.0284 | 44267.35 | 18773.0284 | 10745.3 | 18773.0284 | 10589.11
2026-03-11 | 113303.1499 | 188061.29 | 18883.8583 | 10859.7 | 18883.8583 | 97992.26 | 18883.8583 | 9685.62 | 18883.8583 | 44267.35 | 18883.8583 | 10745.3 | 18883.8583 | 10589.11
2026-03-12 | 113968.1297 | 188061.29 | 18994.6883 | 10859.7 | 18994.6883 | 97992.26 | 18994.6883 | 9685.62 | 18994.6883 | 44267.35 | 18994.6883 | 10745.3 | 18994.6883 | 10589.11
2026-03-13 | 114633.1094 | 189651.19 | 19105.5182 | 10859.7 | 19105.5182 | 99232.16 | 19105.5182 | 9685.62 | 19105.5182 | 44617.35 | 19105.5182 | 10745.3 | 19105.5182 | 10589.11
2026-03-14 | 115298.0892 | 189651.19 | 19216.3482 | 10859.7 | 19216.3482 | 99232.16 | 19216.3482 | 9685.62 | 19216.3482 | 44617.35 | 19216.3482 | 10745.3 | 19216.3482 | 10589.11
2026-03-15 | 115963.069 | 189651.19 | 19327.1782 | 10859.7 | 19327.1782 | 99232.16 | 19327.1782 | 9685.62 | 19327.1782 | 44617.35 | 19327.1782 | 10745.3 | 19327.1782 | 10589.11
2026-03-16 | 116628.0487 | 189651.19 | 19438.0081 | 10859.7 | 19438.0081 | 99232.16 | 19438.0081 | 9685.62 | 19438.0081 | 44617.35 | 19438.0081 | 10745.3 | 19438.0081 | 10589.11
2026-03-17 | 117293.0285 | 189651.19 | 19548.8381 | 10859.7 | 19548.8381 | 99232.16 | 19548.8381 | 9685.62 | 19548.8381 | 44617.35 | 19548.8381 | 10745.3 | 19548.8381 | 10589.11
2026-03-18 | 117958.0082 | 189651.19 | 19659.668 | 10859.7 | 19659.668 | 99232.16 | 19659.668 | 9685.62 | 19659.668 | 44617.35 | 19659.668 | 10745.3 | 19659.668 | 10589.11
2026-03-19 | 118622.988 | 189651.19 | 19770.498 | 10859.7 | 19770.498 | 99232.16 | 19770.498 | 9685.62 | 19770.498 | 44617.35 | 19770.498 | 10745.3 | 19770.498 | 10589.11
2026-03-20 | 119287.9678 | 189651.19 | 19881.328 | 10859.7 | 19881.328 | 99232.16 | 19881.328 | 9685.62 | 19881.328 | 44617.35 | 19881.328 | 10745.3 | 19881.328 | 10589.11
2026-03-21 | 119952.9475 | 189651.19 | 19992.1579 | 10859.7 | 19992.1579 | 99232.16 | 19992.1579 | 9685.62 | 19992.1579 | 44617.35 | 19992.1579 | 10745.3 | 19992.1579 | 10589.11
2026-03-22 | 120617.9273 | 189651.19 | 20102.9879 | 10859.7 | 20102.9879 | 99232.16 | 20102.9879 | 9685.62 | 20102.9879 | 44617.35 | 20102.9879 | 10745.3 | 20102.9879 | 10589.11
2026-03-23 | 121282.907 |  | 20213.8178 |  | 20213.8178 |  | 20213.8178 |  | 20213.8178 |  | 20213.8178 |  | 20213.8178
2026-03-24 | 121947.8868 |  | 20324.6478 |  | 20324.6478 |  | 20324.6478 |  | 20324.6478 |  | 20324.6478 |  | 20324.6478
2026-03-25 | 122612.8666 |  | 20435.4778 |  | 20435.4778 |  | 20435.4778 |  | 20435.4778 |  | 20435.4778 |  | 20435.4778
2026-03-26 | 123277.8463 |  | 20546.3077 |  | 20546.3077 |  | 20546.3077 |  | 20546.3077 |  | 20546.3077 |  | 20546.3077
2026-03-27 | 123942.8261 |  | 20657.1377 |  | 20657.1377 |  | 20657.1377 |  | 20657.1377 |  | 20657.1377 |  | 20657.1377
2026-03-28 | 124607.8058 |  | 20767.9676 |  | 20767.9676 |  | 20767.9676 |  | 20767.9676 |  | 20767.9676 |  | 20767.9676
2026-03-29 | 125272.7856 |  | 20878.7976 |  | 20878.7976 |  | 20878.7976 |  | 20878.7976 |  | 20878.7976 |  | 20878.7976
2026-03-30 | 125937.7654 |  | 20989.6276 |  | 20989.6276 |  | 20989.6276 |  | 20989.6276 |  | 20989.6276 |  | 20989.6276
2026-03-31 | 126602.7451 |  | 21100.4575 |  | 21100.4575 |  | 21100.4575 |  | 21100.4575 |  | 21100.4575 |  | 21100.4575
2026-04-01 | 127267.7249 |  | 21211.2875 |  | 21211.2875 |  | 21211.2875 |  | 21211.2875 |  | 21211.2875 |  | 21211.2875
2026-04-02 | 127932.7046 |  | 21322.1174 |  | 21322.1174 |  | 21322.1174 |  | 21322.1174 |  | 21322.1174 |  | 21322.1174
2026-04-03 | 128597.6844 |  | 21432.9474 |  | 21432.9474 |  | 21432.9474 |  | 21432.9474 |  | 21432.9474 |  | 21432.9474
2026-04-04 | 129262.6642 |  | 21543.7774 |  | 21543.7774 |  | 21543.7774 |  | 21543.7774 |  | 21543.7774 |  | 21543.7774
2026-04-05 | 129927.6439 |  | 21654.6073 |  | 21654.6073 |  | 21654.6073 |  | 21654.6073 |  | 21654.6073 |  | 21654.6073
2026-04-06 | 130592.6237 |  | 21765.4373 |  | 21765.4373 |  | 21765.4373 |  | 21765.4373 |  | 21765.4373 |  | 21765.4373
2026-04-07 | 131257.6034 |  | 21876.2672 |  | 21876.2672 |  | 21876.2672 |  | 21876.2672 |  | 21876.2672 |  | 21876.2672
2026-04-08 | 131922.5832 |  | 21987.0972 |  | 21987.0972 |  | 21987.0972 |  | 21987.0972 |  | 21987.0972 |  | 21987.0972
2026-04-09 | 132587.563 |  | 22097.9272 |  | 22097.9272 |  | 22097.9272 |  | 22097.9272 |  | 22097.9272 |  | 22097.9272
2026-04-10 | 133252.5427 |  | 22208.7571 |  | 22208.7571 |  | 22208.7571 |  | 22208.7571 |  | 22208.7571 |  | 22208.7571
2026-04-11 | 133917.5225 |  | 22319.5871 |  | 22319.5871 |  | 22319.5871 |  | 22319.5871 |  | 22319.5871 |  | 22319.5871
2026-04-12 | 134582.5022 |  | 22430.417 |  | 22430.417 |  | 22430.417 |  | 22430.417 |  | 22430.417 |  | 22430.417
2026-04-13 | 135247.482 |  | 22541.247 |  | 22541.247 |  | 22541.247 |  | 22541.247 |  | 22541.247 |  | 22541.247
2026-04-14 | 135912.4618 |  | 22652.077 |  | 22652.077 |  | 22652.077 |  | 22652.077 |  | 22652.077 |  | 22652.077
2026-04-15 | 136577.4415 |  | 22762.9069 |  | 22762.9069 |  | 22762.9069 |  | 22762.9069 |  | 22762.9069 |  | 22762.9069
2026-04-16 | 137242.4213 |  | 22873.7369 |  | 22873.7369 |  | 22873.7369 |  | 22873.7369 |  | 22873.7369 |  | 22873.7369
2026-04-17 | 137907.401 |  | 22984.5668 |  | 22984.5668 |  | 22984.5668 |  | 22984.5668 |  | 22984.5668 |  | 22984.5668
2026-04-18 | 138572.3808 |  | 23095.3968 |  | 23095.3968 |  | 23095.3968 |  | 23095.3968 |  | 23095.3968 |  | 23095.3968
2026-04-19 | 139237.3606 |  | 23206.2268 |  | 23206.2268 |  | 23206.2268 |  | 23206.2268 |  | 23206.2268 |  | 23206.2268
2026-04-20 | 139902.3403 |  | 23317.0567 |  | 23317.0567 |  | 23317.0567 |  | 23317.0567 |  | 23317.0567 |  | 23317.0567
2026-04-21 | 140567.3201 |  | 23427.8867 |  | 23427.8867 |  | 23427.8867 |  | 23427.8867 |  | 23427.8867 |  | 23427.8867
2026-04-22 | 141232.2998 |  | 23538.7166 |  | 23538.7166 |  | 23538.7166 |  | 23538.7166 |  | 23538.7166 |  | 23538.7166
2026-04-23 | 141897.2796 |  | 23649.5466 |  | 23649.5466 |  | 23649.5466 |  | 23649.5466 |  | 23649.5466 |  | 23649.5466
2026-04-24 | 142562.2594 |  | 23760.3766 |  | 23760.3766 |  | 23760.3766 |  | 23760.3766 |  | 23760.3766 |  | 23760.3766
2026-04-25 | 143227.2391 |  | 23871.2065 |  | 23871.2065 |  | 23871.2065 |  | 23871.2065 |  | 23871.2065 |  | 23871.2065
2026-04-26 | 143892.2189 |  | 23982.0365 |  | 23982.0365 |  | 23982.0365 |  | 23982.0365 |  | 23982.0365 |  | 23982.0365
2026-04-27 | 144557.1986 |  | 24092.8664 |  | 24092.8664 |  | 24092.8664 |  | 24092.8664 |  | 24092.8664 |  | 24092.8664
2026-04-28 | 145222.1784 |  | 24203.6964 |  | 24203.6964 |  | 24203.6964 |  | 24203.6964 |  | 24203.6964 |  | 24203.6964
2026-04-29 | 145887.1582 |  | 24314.5264 |  | 24314.5264 |  | 24314.5264 |  | 24314.5264 |  | 24314.5264 |  | 24314.5264
2026-04-30 | 146552.1379 |  | 24425.3563 |  | 24425.3563 |  | 24425.3563 |  | 24425.3563 |  | 24425.3563 |  | 24425.3563
2026-05-01 | 147217.1177 |  | 24536.1863 |  | 24536.1863 |  | 24536.1863 |  | 24536.1863 |  | 24536.1863 |  | 24536.1863
2026-05-02 | 147882.0974 |  | 24647.0162 |  | 24647.0162 |  | 24647.0162 |  | 24647.0162 |  | 24647.0162 |  | 24647.0162
2026-05-03 | 148547.0772 |  | 24757.8462 |  | 24757.8462 |  | 24757.8462 |  | 24757.8462 |  | 24757.8462 |  | 24757.8462
2026-05-04 | 149212.057 |  | 24868.6762 |  | 24868.6762 |  | 24868.6762 |  | 24868.6762 |  | 24868.6762 |  | 24868.6762
2026-05-05 | 149877.0367 |  | 24979.5061 |  | 24979.5061 |  | 24979.5061 |  | 24979.5061 |  | 24979.5061 |  | 24979.5061
2026-05-06 | 150542.0165 |  | 25090.3361 |  | 25090.3361 |  | 25090.3361 |  | 25090.3361 |  | 25090.3361 |  | 25090.3361
2026-05-07 | 151206.9962 |  | 25201.166 |  | 25201.166 |  | 25201.166 |  | 25201.166 |  | 25201.166 |  | 25201.166
2026-05-08 | 151871.976 |  | 25311.996 |  | 25311.996 |  | 25311.996 |  | 25311.996 |  | 25311.996 |  | 25311.996
2026-05-09 | 152536.9558 |  | 25422.826 |  | 25422.826 |  | 25422.826 |  | 25422.826 |  | 25422.826 |  | 25422.826
2026-05-10 | 153201.9355 |  | 25533.6559 |  | 25533.6559 |  | 25533.6559 |  | 25533.6559 |  | 25533.6559 |  | 25533.6559
2026-05-11 | 153866.9153 |  | 25644.4859 |  | 25644.4859 |  | 25644.4859 |  | 25644.4859 |  | 25644.4859 |  | 25644.4859
2026-05-12 | 154531.895 |  | 25755.3158 |  | 25755.3158 |  | 25755.3158 |  | 25755.3158 |  | 25755.3158 |  | 25755.3158
2026-05-13 | 155196.8748 |  | 25866.1458 |  | 25866.1458 |  | 25866.1458 |  | 25866.1458 |  | 25866.1458 |  | 25866.1458
2026-05-14 | 155861.8546 |  | 25976.9758 |  | 25976.9758 |  | 25976.9758 |  | 25976.9758 |  | 25976.9758 |  | 25976.9758
2026-05-15 | 156526.8343 |  | 26087.8057 |  | 26087.8057 |  | 26087.8057 |  | 26087.8057 |  | 26087.8057 |  | 26087.8057
2026-05-16 | 157191.8141 |  | 26198.6357 |  | 26198.6357 |  | 26198.6357 |  | 26198.6357 |  | 26198.6357 |  | 26198.6357
2026-05-17 | 157856.7938 |  | 26309.4656 |  | 26309.4656 |  | 26309.4656 |  | 26309.4656 |  | 26309.4656 |  | 26309.4656
2026-05-18 | 158521.7736 |  | 26420.2956 |  | 26420.2956 |  | 26420.2956 |  | 26420.2956 |  | 26420.2956 |  | 26420.2956
2026-05-19 | 159186.7534 |  | 26531.1256 |  | 26531.1256 |  | 26531.1256 |  | 26531.1256 |  | 26531.1256 |  | 26531.1256
2026-05-20 | 159851.7331 |  | 26641.9555 |  | 26641.9555 |  | 26641.9555 |  | 26641.9555 |  | 26641.9555 |  | 26641.9555
2026-05-21 | 160516.7129 |  | 26752.7855 |  | 26752.7855 |  | 26752.7855 |  | 26752.7855 |  | 26752.7855 |  | 26752.7855
2026-05-22 | 161181.6926 |  | 26863.6154 |  | 26863.6154 |  | 26863.6154 |  | 26863.6154 |  | 26863.6154 |  | 26863.6154
2026-05-23 | 161846.6724 |  | 26974.4454 |  | 26974.4454 |  | 26974.4454 |  | 26974.4454 |  | 26974.4454 |  | 26974.4454
2026-05-24 | 162511.6522 |  | 27085.2754 |  | 27085.2754 |  | 27085.2754 |  | 27085.2754 |  | 27085.2754 |  | 27085.2754
2026-05-25 | 163176.6319 |  | 27196.1053 |  | 27196.1053 |  | 27196.1053 |  | 27196.1053 |  | 27196.1053 |  | 27196.1053
2026-05-26 | 163841.6117 |  | 27306.9353 |  | 27306.9353 |  | 27306.9353 |  | 27306.9353 |  | 27306.9353 |  | 27306.9353
2026-05-27 | 164506.5914 |  | 27417.7652 |  | 27417.7652 |  | 27417.7652 |  | 27417.7652 |  | 27417.7652 |  | 27417.7652
2026-05-28 | 165171.5712 |  | 27528.5952 |  | 27528.5952 |  | 27528.5952 |  | 27528.5952 |  | 27528.5952 |  | 27528.5952
2026-05-29 | 165836.551 |  | 27639.4252 |  | 27639.4252 |  | 27639.4252 |  | 27639.4252 |  | 27639.4252 |  | 27639.4252
2026-05-30 | 166501.5307 |  | 27750.2551 |  | 27750.2551 |  | 27750.2551 |  | 27750.2551 |  | 27750.2551 |  | 27750.2551
2026-05-31 | 167166.5105 |  | 27861.0851 |  | 27861.0851 |  | 27861.0851 |  | 27861.0851 |  | 27861.0851 |  | 27861.0851
2026-06-01 | 167831.4902 |  | 27971.915 |  | 27971.915 |  | 27971.915 |  | 27971.915 |  | 27971.915 |  | 27971.915
2026-06-02 | 168496.47 |  | 28082.745 |  | 28082.745 |  | 28082.745 |  | 28082.745 |  | 28082.745 |  | 28082.745
2026-06-03 | 169161.4498 |  | 28193.575 |  | 28193.575 |  | 28193.575 |  | 28193.575 |  | 28193.575 |  | 28193.575
2026-06-04 | 169826.4295 |  | 28304.4049 |  | 28304.4049 |  | 28304.4049 |  | 28304.4049 |  | 28304.4049 |  | 28304.4049
2026-06-05 | 170491.4093 |  | 28415.2349 |  | 28415.2349 |  | 28415.2349 |  | 28415.2349 |  | 28415.2349 |  | 28415.2349
2026-06-06 | 171156.389 |  | 28526.0648 |  | 28526.0648 |  | 28526.0648 |  | 28526.0648 |  | 28526.0648 |  | 28526.0648
2026-06-07 | 171821.3688 |  | 28636.8948 |  | 28636.8948 |  | 28636.8948 |  | 28636.8948 |  | 28636.8948 |  | 28636.8948
2026-06-08 | 172486.3486 |  | 28747.7248 |  | 28747.7248 |  | 28747.7248 |  | 28747.7248 |  | 28747.7248 |  | 28747.7248
2026-06-09 | 173151.3283 |  | 28858.5547 |  | 28858.5547 |  | 28858.5547 |  | 28858.5547 |  | 28858.5547 |  | 28858.5547
2026-06-10 | 173816.3081 |  | 28969.3847 |  | 28969.3847 |  | 28969.3847 |  | 28969.3847 |  | 28969.3847 |  | 28969.3847
2026-06-11 | 174481.2878 |  | 29080.2146 |  | 29080.2146 |  | 29080.2146 |  | 29080.2146 |  | 29080.2146 |  | 29080.2146
2026-06-12 | 175146.2676 |  | 29191.0446 |  | 29191.0446 |  | 29191.0446 |  | 29191.0446 |  | 29191.0446 |  | 29191.0446
2026-06-13 | 175811.2474 |  | 29301.8746 |  | 29301.8746 |  | 29301.8746 |  | 29301.8746 |  | 29301.8746 |  | 29301.8746
2026-06-14 | 176476.2271 |  | 29412.7045 |  | 29412.7045 |  | 29412.7045 |  | 29412.7045 |  | 29412.7045 |  | 29412.7045
2026-06-15 | 177141.2069 |  | 29523.5345 |  | 29523.5345 |  | 29523.5345 |  | 29523.5345 |  | 29523.5345 |  | 29523.5345
2026-06-16 | 177806.1866 |  | 29634.3644 |  | 29634.3644 |  | 29634.3644 |  | 29634.3644 |  | 29634.3644 |  | 29634.3644
2026-06-17 | 178471.1664 |  | 29745.1944 |  | 29745.1944 |  | 29745.1944 |  | 29745.1944 |  | 29745.1944 |  | 29745.1944
2026-06-18 | 179136.1462 |  | 29856.0244 |  | 29856.0244 |  | 29856.0244 |  | 29856.0244 |  | 29856.0244 |  | 29856.0244
2026-06-19 | 179801.1259 |  | 29966.8543 |  | 29966.8543 |  | 29966.8543 |  | 29966.8543 |  | 29966.8543 |  | 29966.8543
2026-06-20 | 180466.1057 |  | 30077.6843 |  | 30077.6843 |  | 30077.6843 |  | 30077.6843 |  | 30077.6843 |  | 30077.6843
2026-06-21 | 181131.0854 |  | 30188.5142 |  | 30188.5142 |  | 30188.5142 |  | 30188.5142 |  | 30188.5142 |  | 30188.5142
2026-06-22 | 181796.0652 |  | 30299.3442 |  | 30299.3442 |  | 30299.3442 |  | 30299.3442 |  | 30299.3442 |  | 30299.3442
2026-06-23 | 182461.045 |  | 30410.1742 |  | 30410.1742 |  | 30410.1742 |  | 30410.1742 |  | 30410.1742 |  | 30410.1742
2026-06-24 | 183126.0247 |  | 30521.0041 |  | 30521.0041 |  | 30521.0041 |  | 30521.0041 |  | 30521.0041 |  | 30521.0041
2026-06-25 | 183791.0045 |  | 30631.8341 |  | 30631.8341 |  | 30631.8341 |  | 30631.8341 |  | 30631.8341 |  | 30631.8341
2026-06-26 | 184455.9842 |  | 30742.664 |  | 30742.664 |  | 30742.664 |  | 30742.664 |  | 30742.664 |  | 30742.664
2026-06-27 | 185120.964 |  | 30853.494 |  | 30853.494 |  | 30853.494 |  | 30853.494 |  | 30853.494 |  | 30853.494
2026-06-28 | 185785.9438 |  | 30964.324 |  | 30964.324 |  | 30964.324 |  | 30964.324 |  | 30964.324 |  | 30964.324
2026-06-29 | 186450.9235 |  | 31075.1539 |  | 31075.1539 |  | 31075.1539 |  | 31075.1539 |  | 31075.1539 |  | 31075.1539
2026-06-30 | 187115.9033 |  | 31185.9839 |  | 31185.9839 |  | 31185.9839 |  | 31185.9839 |  | 31185.9839 |  | 31185.9839
2026-07-01 | 187780.883 |  | 31296.8138 |  | 31296.8138 |  | 31296.8138 |  | 31296.8138 |  | 31296.8138 |  | 31296.8138
2026-07-02 | 188445.8628 |  | 31407.6438 |  | 31407.6438 |  | 31407.6438 |  | 31407.6438 |  | 31407.6438 |  | 31407.6438
2026-07-03 | 189110.8426 |  | 31518.4738 |  | 31518.4738 |  | 31518.4738 |  | 31518.4738 |  | 31518.4738 |  | 31518.4738
2026-07-04 | 189775.8223 |  | 31629.3037 |  | 31629.3037 |  | 31629.3037 |  | 31629.3037 |  | 31629.3037 |  | 31629.3037
2026-07-05 | 190440.8021 |  | 31740.1337 |  | 31740.1337 |  | 31740.1337 |  | 31740.1337 |  | 31740.1337 |  | 31740.1337
2026-07-06 | 191105.7818 |  | 31850.9636 |  | 31850.9636 |  | 31850.9636 |  | 31850.9636 |  | 31850.9636 |  | 31850.9636
2026-07-07 | 191770.7616 |  | 31961.7936 |  | 31961.7936 |  | 31961.7936 |  | 31961.7936 |  | 31961.7936 |  | 31961.7936
2026-07-08 | 192435.7414 |  | 32072.6236 |  | 32072.6236 |  | 32072.6236 |  | 32072.6236 |  | 32072.6236 |  | 32072.6236
2026-07-09 | 193100.7211 |  | 32183.4535 |  | 32183.4535 |  | 32183.4535 |  | 32183.4535 |  | 32183.4535 |  | 32183.4535
2026-07-10 | 193765.7009 |  | 32294.2835 |  | 32294.2835 |  | 32294.2835 |  | 32294.2835 |  | 32294.2835 |  | 32294.2835
2026-07-11 | 194430.6806 |  | 32405.1134 |  | 32405.1134 |  | 32405.1134 |  | 32405.1134 |  | 32405.1134 |  | 32405.1134
2026-07-12 | 195095.6604 |  | 32515.9434 |  | 32515.9434 |  | 32515.9434 |  | 32515.9434 |  | 32515.9434 |  | 32515.9434
2026-07-13 | 195760.6402 |  | 32626.7734 |  | 32626.7734 |  | 32626.7734 |  | 32626.7734 |  | 32626.7734 |  | 32626.7734
2026-07-14 | 196425.6199 |  | 32737.6033 |  | 32737.6033 |  | 32737.6033 |  | 32737.6033 |  | 32737.6033 |  | 32737.6033
2026-07-15 | 197090.5997 |  | 32848.4333 |  | 32848.4333 |  | 32848.4333 |  | 32848.4333 |  | 32848.4333 |  | 32848.4333
2026-07-16 | 197755.5794 |  | 32959.2632 |  | 32959.2632 |  | 32959.2632 |  | 32959.2632 |  | 32959.2632 |  | 32959.2632
2026-07-17 | 198420.5592 |  | 33070.0932 |  | 33070.0932 |  | 33070.0932 |  | 33070.0932 |  | 33070.0932 |  | 33070.0932
2026-07-18 | 199085.539 |  | 33180.9232 |  | 33180.9232 |  | 33180.9232 |  | 33180.9232 |  | 33180.9232 |  | 33180.9232
2026-07-19 | 199750.5187 |  | 33291.7531 |  | 33291.7531 |  | 33291.7531 |  | 33291.7531 |  | 33291.7531 |  | 33291.7531
2026-07-20 | 200415.4985 |  | 33402.5831 |  | 33402.5831 |  | 33402.5831 |  | 33402.5831 |  | 33402.5831 |  | 33402.5831
2026-07-21 | 201080.4782 |  | 33513.413 |  | 33513.413 |  | 33513.413 |  | 33513.413 |  | 33513.413 |  | 33513.413
2026-07-22 | 201745.458 |  | 33624.243 |  | 33624.243 |  | 33624.243 |  | 33624.243 |  | 33624.243 |  | 33624.243
2026-07-23 | 202410.4378 |  | 33735.073 |  | 33735.073 |  | 33735.073 |  | 33735.073 |  | 33735.073 |  | 33735.073
2026-07-24 | 203075.4175 |  | 33845.9029 |  | 33845.9029 |  | 33845.9029 |  | 33845.9029 |  | 33845.9029 |  | 33845.9029
2026-07-25 | 203740.3973 |  | 33956.7329 |  | 33956.7329 |  | 33956.7329 |  | 33956.7329 |  | 33956.7329 |  | 33956.7329
2026-07-26 | 204405.377 |  | 34067.5628 |  | 34067.5628 |  | 34067.5628 |  | 34067.5628 |  | 34067.5628 |  | 34067.5628
2026-07-27 | 205070.3568 |  | 34178.3928 |  | 34178.3928 |  | 34178.3928 |  | 34178.3928 |  | 34178.3928 |  | 34178.3928
2026-07-28 | 205735.3366 |  | 34289.2228 |  | 34289.2228 |  | 34289.2228 |  | 34289.2228 |  | 34289.2228 |  | 34289.2228
2026-07-29 | 206400.3163 |  | 34400.0527 |  | 34400.0527 |  | 34400.0527 |  | 34400.0527 |  | 34400.0527 |  | 34400.0527
2026-07-30 | 207065.2961 |  | 34510.8827 |  | 34510.8827 |  | 34510.8827 |  | 34510.8827 |  | 34510.8827 |  | 34510.8827
2026-07-31 | 207730.2758 |  | 34621.7126 |  | 34621.7126 |  | 34621.7126 |  | 34621.7126 |  | 34621.7126 |  | 34621.7126
2026-08-01 | 208395.2556 |  | 34732.5426 |  | 34732.5426 |  | 34732.5426 |  | 34732.5426 |  | 34732.5426 |  | 34732.5426
2026-08-02 | 209060.2354 |  | 34843.3726 |  | 34843.3726 |  | 34843.3726 |  | 34843.3726 |  | 34843.3726 |  | 34843.3726
2026-08-03 | 209725.2151 |  | 34954.2025 |  | 34954.2025 |  | 34954.2025 |  | 34954.2025 |  | 34954.2025 |  | 34954.2025
2026-08-04 | 210390.1949 |  | 35065.0325 |  | 35065.0325 |  | 35065.0325 |  | 35065.0325 |  | 35065.0325 |  | 35065.0325
2026-08-05 | 211055.1746 |  | 35175.8624 |  | 35175.8624 |  | 35175.8624 |  | 35175.8624 |  | 35175.8624 |  | 35175.8624
2026-08-06 | 211720.1544 |  | 35286.6924 |  | 35286.6924 |  | 35286.6924 |  | 35286.6924 |  | 35286.6924 |  | 35286.6924
2026-08-07 | 212385.1342 |  | 35397.5224 |  | 35397.5224 |  | 35397.5224 |  | 35397.5224 |  | 35397.5224 |  | 35397.5224
2026-08-08 | 213050.1139 |  | 35508.3523 |  | 35508.3523 |  | 35508.3523 |  | 35508.3523 |  | 35508.3523 |  | 35508.3523
2026-08-09 | 213715.0937 |  | 35619.1823 |  | 35619.1823 |  | 35619.1823 |  | 35619.1823 |  | 35619.1823 |  | 35619.1823
2026-08-10 | 214380.0734 |  | 35730.0122 |  | 35730.0122 |  | 35730.0122 |  | 35730.0122 |  | 35730.0122 |  | 35730.0122
2026-08-11 | 215045.0532 |  | 35840.8422 |  | 35840.8422 |  | 35840.8422 |  | 35840.8422 |  | 35840.8422 |  | 35840.8422
2026-08-12 | 215710.033 |  | 35951.6722 |  | 35951.6722 |  | 35951.6722 |  | 35951.6722 |  | 35951.6722 |  | 35951.6722
2026-08-13 | 216375.0127 |  | 36062.5021 |  | 36062.5021 |  | 36062.5021 |  | 36062.5021 |  | 36062.5021 |  | 36062.5021
2026-08-14 | 217039.9925 |  | 36173.3321 |  | 36173.3321 |  | 36173.3321 |  | 36173.3321 |  | 36173.3321 |  | 36173.3321
2026-08-15 | 217704.9722 |  | 36284.162 |  | 36284.162 |  | 36284.162 |  | 36284.162 |  | 36284.162 |  | 36284.162
2026-08-16 | 218369.952 |  | 36394.992 |  | 36394.992 |  | 36394.992 |  | 36394.992 |  | 36394.992 |  | 36394.992
2026-08-18 | 220104.8247 |  | 36684.1375 |  | 36684.1375 |  | 36684.1375 |  | 36684.1375 |  | 36684.1375 |  | 36684.1375
2026-08-19 | 221839.6975 |  | 36973.2829 |  | 36973.2829 |  | 36973.2829 |  | 36973.2829 |  | 36973.2829 |  | 36973.2829
2026-08-20 | 223574.5702 |  | 37262.4284 |  | 37262.4284 |  | 37262.4284 |  | 37262.4284 |  | 37262.4284 |  | 37262.4284
2026-08-21 | 225309.4429 |  | 37551.5738 |  | 37551.5738 |  | 37551.5738 |  | 37551.5738 |  | 37551.5738 |  | 37551.5738
2026-08-22 | 227044.3156 |  | 37840.7193 |  | 37840.7193 |  | 37840.7193 |  | 37840.7193 |  | 37840.7193 |  | 37840.7193
2026-08-23 | 228779.1884 |  | 38129.8647 |  | 38129.8647 |  | 38129.8647 |  | 38129.8647 |  | 38129.8647 |  | 38129.8647
2026-08-24 | 230514.0611 |  | 38419.0102 |  | 38419.0102 |  | 38419.0102 |  | 38419.0102 |  | 38419.0102 |  | 38419.0102
2026-08-25 | 232248.9338 |  | 38708.1556 |  | 38708.1556 |  | 38708.1556 |  | 38708.1556 |  | 38708.1556 |  | 38708.1556
2026-08-26 | 233983.8065 |  | 38997.3011 |  | 38997.3011 |  | 38997.3011 |  | 38997.3011 |  | 38997.3011 |  | 38997.3011
2026-08-27 | 235718.6793 |  | 39286.4465 |  | 39286.4465 |  | 39286.4465 |  | 39286.4465 |  | 39286.4465 |  | 39286.4465
2026-08-28 | 237453.552 |  | 39575.592 |  | 39575.592 |  | 39575.592 |  | 39575.592 |  | 39575.592 |  | 39575.592
2026-08-29 | 239188.4247 |  | 39864.7375 |  | 39864.7375 |  | 39864.7375 |  | 39864.7375 |  | 39864.7375 |  | 39864.7375
2026-08-30 | 240923.2975 |  | 40153.8829 |  | 40153.8829 |  | 40153.8829 |  | 40153.8829 |  | 40153.8829 |  | 40153.8829
2026-08-31 | 242658.1702 |  | 40443.0284 |  | 40443.0284 |  | 40443.0284 |  | 40443.0284 |  | 40443.0284 |  | 40443.0284
2026-09-01 | 244393.0429 |  | 40732.1738 |  | 40732.1738 |  | 40732.1738 |  | 40732.1738 |  | 40732.1738 |  | 40732.1738
2026-09-02 | 246127.9156 |  | 41021.3193 |  | 41021.3193 |  | 41021.3193 |  | 41021.3193 |  | 41021.3193 |  | 41021.3193
2026-09-03 | 247862.7884 |  | 41310.4647 |  | 41310.4647 |  | 41310.4647 |  | 41310.4647 |  | 41310.4647 |  | 41310.4647
2026-09-04 | 249597.6611 |  | 41599.6102 |  | 41599.6102 |  | 41599.6102 |  | 41599.6102 |  | 41599.6102 |  | 41599.6102
2026-09-05 | 251332.5338 |  | 41888.7556 |  | 41888.7556 |  | 41888.7556 |  | 41888.7556 |  | 41888.7556 |  | 41888.7556
2026-09-06 | 253067.4065 |  | 42177.9011 |  | 42177.9011 |  | 42177.9011 |  | 42177.9011 |  | 42177.9011 |  | 42177.9011
2026-09-07 | 254802.2793 |  | 42467.0465 |  | 42467.0465 |  | 42467.0465 |  | 42467.0465 |  | 42467.0465 |  | 42467.0465
2026-09-08 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-09 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-10 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-11 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-12 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-13 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-14 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-15 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-16 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-17 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-18 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-19 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-20 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-21 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-22 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-23 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-24 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-25 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-26 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-27 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-28 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-29 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-09-30 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-10-01 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-10-02 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-10-03 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-10-04 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-10-05 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-10-06 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-10-07 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-10-08 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-10-09 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-10-10 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-10-11 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-10-12 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192

## Parts&materials (Direct Cost)
Date | Planned Parts&materials (Cumulative) | Actual Parts&materials (Cumulative) | Planned 5004 · GTR Cost of Sales - Parts (Cumulative) | Actual 5004 · GTR Cost of Sales - Parts (Cumulative) | Planned 5111 · Parts & material costs (Direct) (Cumulative) | Actual 5111 · Parts & material costs (Direct) (Cumulative) | Planned 5128 · Health & Safety Equip (Direct) (Cumulative) | Actual 5128 · Health & Safety Equip (Direct) (Cumulative)
2025-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-17 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-18 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-19 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-20 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-21 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-22 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-23 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-24 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-25 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-26 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-27 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-28 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-29 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-30 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-01 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-02 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-03 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-04 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-05 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-06 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-07 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-08 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-09 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-10 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-11 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-12 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-13 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-14 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-15 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-16 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-17 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-18 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-19 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-20 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-21 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-22 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-23 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-24 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-25 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-26 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-27 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-28 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-29 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-30 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-06-01 | 1261.7398 | 33.72 | 420.5799 | 0 | 420.5799 | 33.72 | 420.5799 | 0
2025-06-02 | 2523.4795 | 33.72 | 841.1598 | 0 | 841.1598 | 33.72 | 841.1598 | 0
2025-06-03 | 3785.2193 | 33.72 | 1261.7398 | 0 | 1261.7398 | 33.72 | 1261.7398 | 0
2025-06-04 | 5046.959 | 53.64 | 1682.3197 | 0 | 1682.3197 | 53.64 | 1682.3197 | 0
2025-06-05 | 6308.6988 | 25692.32 | 2102.8996 | 0 | 2102.8996 | 25692.32 | 2102.8996 | 0
2025-06-06 | 7570.4386 | 25692.32 | 2523.4795 | 0 | 2523.4795 | 25692.32 | 2523.4795 | 0
2025-06-07 | 8832.1783 | 25692.32 | 2944.0594 | 0 | 2944.0594 | 25692.32 | 2944.0594 | 0
2025-06-08 | 10093.9181 | 25692.32 | 3364.6394 | 0 | 3364.6394 | 25692.32 | 3364.6394 | 0
2025-06-09 | 11355.6578 | 25692.32 | 3785.2193 | 0 | 3785.2193 | 25692.32 | 3785.2193 | 0
2025-06-10 | 12617.3976 | 25692.32 | 4205.7992 | 0 | 4205.7992 | 25692.32 | 4205.7992 | 0
2025-06-11 | 13879.1373 | 25692.32 | 4626.3791 | 0 | 4626.3791 | 25692.32 | 4626.3791 | 0
2025-06-12 | 15140.8771 | 25692.32 | 5046.959 | 0 | 5046.959 | 25692.32 | 5046.959 | 0
2025-06-13 | 16402.6169 | 25692.32 | 5467.539 | 0 | 5467.539 | 25692.32 | 5467.539 | 0
2025-06-14 | 17664.3566 | 25692.32 | 5888.1189 | 0 | 5888.1189 | 25692.32 | 5888.1189 | 0
2025-06-15 | 18926.0964 | 25692.32 | 6308.6988 | 0 | 6308.6988 | 25692.32 | 6308.6988 | 0
2025-06-16 | 20187.8361 | 25692.32 | 6729.2787 | 0 | 6729.2787 | 25692.32 | 6729.2787 | 0
2025-06-17 | 21449.5759 | 25692.32 | 7149.8586 | 0 | 7149.8586 | 25692.32 | 7149.8586 | 0
2025-06-18 | 22711.3157 | 25692.32 | 7570.4386 | 0 | 7570.4386 | 25692.32 | 7570.4386 | 0
2025-06-19 | 23973.0554 | 25692.32 | 7991.0185 | 0 | 7991.0185 | 25692.32 | 7991.0185 | 0
2025-06-20 | 25234.7952 | 25692.32 | 8411.5984 | 0 | 8411.5984 | 25692.32 | 8411.5984 | 0
2025-06-21 | 26496.5349 | 25692.32 | 8832.1783 | 0 | 8832.1783 | 25692.32 | 8832.1783 | 0
2025-06-22 | 27758.2747 | 25692.32 | 9252.7582 | 0 | 9252.7582 | 25692.32 | 9252.7582 | 0
2025-06-23 | 29020.0145 | 25692.32 | 9673.3382 | 0 | 9673.3382 | 25692.32 | 9673.3382 | 0
2025-06-24 | 30281.7542 | 25939.32 | 10093.9181 | 0 | 10093.9181 | 25939.32 | 10093.9181 | 0
2025-06-25 | 31543.494 | 26327.72 | 10514.498 | 0 | 10514.498 | 26327.72 | 10514.498 | 0
2025-06-26 | 32805.2337 | 26327.72 | 10935.0779 | 0 | 10935.0779 | 26327.72 | 10935.0779 | 0
2025-06-27 | 34066.9735 | 26327.72 | 11355.6578 | 0 | 11355.6578 | 26327.72 | 11355.6578 | 0
2025-06-28 | 35328.7133 | 26327.72 | 11776.2378 | 0 | 11776.2378 | 26327.72 | 11776.2378 | 0
2025-06-29 | 36590.453 | 26327.72 | 12196.8177 | 0 | 12196.8177 | 26327.72 | 12196.8177 | 0
2025-06-30 | 37852.1928 | 26327.72 | 12617.3976 | 0 | 12617.3976 | 26327.72 | 12617.3976 | 0
2025-07-01 | 39113.9325 | 65038.54 | 13037.9775 | 37227.57 | 13037.9775 | 27810.97 | 13037.9775 | 0
2025-07-02 | 40375.6723 | 65038.54 | 13458.5574 | 37227.57 | 13458.5574 | 27810.97 | 13458.5574 | 0
2025-07-03 | 41637.412 | 65121.12 | 13879.1373 | 37227.57 | 13879.1373 | 27893.55 | 13879.1373 | 0
2025-07-04 | 42899.1518 | 65407.74 | 14299.7173 | 37227.57 | 14299.7173 | 28180.17 | 14299.7173 | 0
2025-07-05 | 44160.8916 | 65457.99 | 14720.2972 | 37227.57 | 14720.2972 | 28230.42 | 14720.2972 | 0
2025-07-06 | 45422.6313 | 65457.99 | 15140.8771 | 37227.57 | 15140.8771 | 28230.42 | 15140.8771 | 0
2025-07-07 | 46684.3711 | 65457.99 | 15561.457 | 37227.57 | 15561.457 | 28230.42 | 15561.457 | 0
2025-07-08 | 47946.1108 | 66119.32 | 15982.0369 | 37227.57 | 15982.0369 | 28891.75 | 15982.0369 | 0
2025-07-09 | 49207.8506 | 66119.32 | 16402.6169 | 37227.57 | 16402.6169 | 28891.75 | 16402.6169 | 0
2025-07-10 | 50469.5904 | 66119.32 | 16823.1968 | 37227.57 | 16823.1968 | 28891.75 | 16823.1968 | 0
2025-07-11 | 51731.3301 | 67449.13 | 17243.7767 | 37227.57 | 17243.7767 | 30221.56 | 17243.7767 | 0
2025-07-12 | 52993.0699 | 67449.13 | 17664.3566 | 37227.57 | 17664.3566 | 30221.56 | 17664.3566 | 0
2025-07-13 | 54254.8096 | 67449.13 | 18084.9365 | 37227.57 | 18084.9365 | 30221.56 | 18084.9365 | 0
2025-07-14 | 55516.5494 | 72702.41 | 18505.5165 | 37227.57 | 18505.5165 | 35474.84 | 18505.5165 | 0
2025-07-15 | 56778.2892 | 74124.67 | 18926.0964 | 37227.57 | 18926.0964 | 36897.1 | 18926.0964 | 0
2025-07-16 | 58040.0289 | 74942.22 | 19346.6763 | 37227.57 | 19346.6763 | 37714.65 | 19346.6763 | 0
2025-07-17 | 59301.7687 | 75243.34 | 19767.2562 | 37227.57 | 19767.2562 | 38015.77 | 19767.2562 | 0
2025-07-18 | 60563.5084 | 81175.07 | 20187.8361 | 37227.57 | 20187.8361 | 43947.5 | 20187.8361 | 0
2025-07-19 | 61825.2482 | 81966.76 | 20608.4161 | 37227.57 | 20608.4161 | 44739.19 | 20608.4161 | 0
2025-07-20 | 63086.988 | 81966.76 | 21028.996 | 37227.57 | 21028.996 | 44739.19 | 21028.996 | 0
2025-07-21 | 65426.4488 | 81966.76 | 21808.8163 | 37227.57 | 21808.8163 | 44739.19 | 21808.8163 | 0
2025-07-22 | 67765.9096 | 97369.69 | 22588.6365 | 37227.57 | 22588.6365 | 60142.12 | 22588.6365 | 0
2025-07-23 | 70105.3704 | 100242.61 | 23368.4568 | 37227.57 | 23368.4568 | 63015.04 | 23368.4568 | 0
2025-07-24 | 72444.8312 | 100437.1 | 24148.2771 | 37227.57 | 24148.2771 | 63209.53 | 24148.2771 | 0
2025-07-25 | 74784.292 | 100801.87 | 24928.0973 | 37227.57 | 24928.0973 | 63574.3 | 24928.0973 | 0
2025-07-26 | 77123.7528 | 100818 | 25707.9176 | 37227.57 | 25707.9176 | 63590.43 | 25707.9176 | 0
2025-07-27 | 79463.2137 | 100818 | 26487.7379 | 37227.57 | 26487.7379 | 63590.43 | 26487.7379 | 0
2025-07-28 | 81802.6745 | 100818 | 27267.5582 | 37227.57 | 27267.5582 | 63590.43 | 27267.5582 | 0
2025-07-29 | 84142.1353 | 100818 | 28047.3784 | 37227.57 | 28047.3784 | 63590.43 | 28047.3784 | 0
2025-07-30 | 86481.5961 | 102239.06 | 28827.1987 | 37227.57 | 28827.1987 | 65011.49 | 28827.1987 | 0
2025-07-31 | 88821.0569 | 102534.46 | 29607.019 | 37227.57 | 29607.019 | 65011.49 | 29607.019 | 295.4
2025-08-01 | 91160.5177 | 106898.67 | 30386.8392 | 37227.57 | 30386.8392 | 69158.55 | 30386.8392 | 512.55
2025-08-02 | 93499.9786 | 106898.67 | 31166.6595 | 37227.57 | 31166.6595 | 69158.55 | 31166.6595 | 512.55
2025-08-03 | 95839.4394 | 106898.67 | 31946.4798 | 37227.57 | 31946.4798 | 69158.55 | 31946.4798 | 512.55
2025-08-04 | 98178.9002 | 106981.02 | 32726.3001 | 37227.57 | 32726.3001 | 69240.9 | 32726.3001 | 512.55
2025-08-05 | 100518.361 | 106981.02 | 33506.1203 | 37227.57 | 33506.1203 | 69240.9 | 33506.1203 | 512.55
2025-08-06 | 102857.8218 | 106981.02 | 34285.9406 | 37227.57 | 34285.9406 | 69240.9 | 34285.9406 | 512.55
2025-08-07 | 105197.2826 | 106981.02 | 35065.7609 | 37227.57 | 35065.7609 | 69240.9 | 35065.7609 | 512.55
2025-08-08 | 107536.7435 | 106981.02 | 35845.5812 | 37227.57 | 35845.5812 | 69240.9 | 35845.5812 | 512.55
2025-08-09 | 109876.2043 | 106981.02 | 36625.4014 | 37227.57 | 36625.4014 | 69240.9 | 36625.4014 | 512.55
2025-08-10 | 112215.6651 | 106981.02 | 37405.2217 | 37227.57 | 37405.2217 | 69240.9 | 37405.2217 | 512.55
2025-08-11 | 114555.1259 | 106981.02 | 38185.042 | 37227.57 | 38185.042 | 69240.9 | 38185.042 | 512.55
2025-08-12 | 116894.5867 | 106981.02 | 38964.8622 | 37227.57 | 38964.8622 | 69240.9 | 38964.8622 | 512.55
2025-08-13 | 119234.0475 | 106981.02 | 39744.6825 | 37227.57 | 39744.6825 | 69240.9 | 39744.6825 | 512.55
2025-08-14 | 121573.5083 | 107092.97 | 40524.5028 | 37227.57 | 40524.5028 | 69352.85 | 40524.5028 | 512.55
2025-08-15 | 123912.9692 | 107175.96 | 41304.3231 | 37227.57 | 41304.3231 | 69435.84 | 41304.3231 | 512.55
2025-08-16 | 126252.43 | 107175.96 | 42084.1433 | 37227.57 | 42084.1433 | 69435.84 | 42084.1433 | 512.55
2025-08-17 | 128591.8908 | 107175.96 | 42863.9636 | 37227.57 | 42863.9636 | 69435.84 | 42863.9636 | 512.55
2025-08-18 | 130931.3516 | 107175.96 | 43643.7839 | 37227.57 | 43643.7839 | 69435.84 | 43643.7839 | 512.55
2025-08-19 | 133270.8124 | 109735.02 | 44423.6041 | 37227.57 | 44423.6041 | 71994.9 | 44423.6041 | 512.55
2025-08-20 | 135610.2732 | 109735.02 | 45203.4244 | 37227.57 | 45203.4244 | 71994.9 | 45203.4244 | 512.55
2025-08-21 | 137949.7341 | 113118.21 | 45983.2447 | 37227.57 | 45983.2447 | 75378.09 | 45983.2447 | 512.55
2025-08-22 | 140289.1949 | 126051.4 | 46763.065 | 37227.57 | 46763.065 | 88311.28 | 46763.065 | 512.55
2025-08-23 | 141366.9159 | 126051.4 | 47122.3053 | 37227.57 | 47122.3053 | 88311.28 | 47122.3053 | 512.55
2025-08-24 | 142444.637 | 126051.4 | 47481.5457 | 37227.57 | 47481.5457 | 88311.28 | 47481.5457 | 512.55
2025-08-25 | 143522.358 | 127036.64 | 47840.786 | 37227.57 | 47840.786 | 89296.52 | 47840.786 | 512.55
2025-08-26 | 144600.0791 | 135168.33 | 48200.0264 | 37227.57 | 48200.0264 | 97428.21 | 48200.0264 | 512.55
2025-08-27 | 145677.8002 | 135883.46 | 48559.2667 | 37227.57 | 48559.2667 | 98143.34 | 48559.2667 | 512.55
2025-08-28 | 146755.5212 | 135883.46 | 48918.5071 | 37227.57 | 48918.5071 | 98143.34 | 48918.5071 | 512.55
2025-08-29 | 147833.2423 | 136177.01 | 49277.7474 | 37227.57 | 49277.7474 | 98436.89 | 49277.7474 | 512.55
2025-08-30 | 148910.9633 | 136177.01 | 49636.9878 | 37227.57 | 49636.9878 | 98436.89 | 49636.9878 | 512.55
2025-08-31 | 149988.6844 | 137459.01 | 49996.2281 | 37227.57 | 49996.2281 | 99718.89 | 49996.2281 | 512.55
2025-09-01 | 151066.4054 | 137459.01 | 50355.4685 | 37227.57 | 50355.4685 | 99718.89 | 50355.4685 | 512.55
2025-09-02 | 151246.1068 | 137739.18 | 50415.3689 | 37227.57 | 50415.3689 | 99999.06 | 50415.3689 | 512.55
2025-09-03 | 151425.8081 | 141922.8 | 50475.2694 | 37227.57 | 50475.2694 | 104182.68 | 50475.2694 | 512.55
2025-09-04 | 151605.5095 | 141929.79 | 50535.1698 | 37227.57 | 50535.1698 | 104182.68 | 50535.1698 | 519.54
2025-09-05 | 151785.2108 | 141929.79 | 50595.0703 | 37227.57 | 50595.0703 | 104182.68 | 50595.0703 | 519.54
2025-09-06 | 151964.9122 | 141929.79 | 50654.9707 | 37227.57 | 50654.9707 | 104182.68 | 50654.9707 | 519.54
2025-09-07 | 152144.6135 | 141929.79 | 50714.8712 | 37227.57 | 50714.8712 | 104182.68 | 50714.8712 | 519.54
2025-09-08 | 152324.3148 | 141929.79 | 50774.7716 | 37227.57 | 50774.7716 | 104182.68 | 50774.7716 | 519.54
2025-09-09 | 152504.0162 | 141929.79 | 50834.6721 | 37227.57 | 50834.6721 | 104182.68 | 50834.6721 | 519.54
2025-09-10 | 152683.7175 | 141990.39 | 50894.5725 | 37227.57 | 50894.5725 | 104236.28 | 50894.5725 | 526.54
2025-09-11 | 152863.4189 | 142253.08 | 50954.473 | 37227.57 | 50954.473 | 104498.97 | 50954.473 | 526.54
2025-09-12 | 153043.1202 | 142386.31 | 51014.3734 | 37227.57 | 51014.3734 | 104629.2 | 51014.3734 | 529.54
2025-09-13 | 153222.8215 | 142386.31 | 51074.2738 | 37227.57 | 51074.2738 | 104629.2 | 51074.2738 | 529.54
2025-09-14 | 153402.5229 | 142468.19 | 51134.1743 | 37227.57 | 51134.1743 | 104711.08 | 51134.1743 | 529.54
2025-09-15 | 153582.2242 | 142761.74 | 51194.0747 | 37227.57 | 51194.0747 | 105004.63 | 51194.0747 | 529.54
2025-09-16 | 153761.9256 | 142863.13 | 51253.9752 | 37227.57 | 51253.9752 | 105004.63 | 51253.9752 | 630.93
2025-09-17 | 153941.6269 | 142863.13 | 51313.8756 | 37227.57 | 51313.8756 | 105004.63 | 51313.8756 | 630.93
2025-09-18 | 154121.3283 | 142870.13 | 51373.7761 | 37227.57 | 51373.7761 | 105004.63 | 51373.7761 | 637.93
2025-09-19 | 154301.0296 | 143751.48 | 51433.6765 | 37227.57 | 51433.6765 | 105864.98 | 51433.6765 | 658.93
2025-09-20 | 154480.7309 | 144293.31 | 51493.577 | 37227.57 | 51493.577 | 106350.25 | 51493.577 | 715.49
2025-09-21 | 154660.4323 | 144293.31 | 51553.4774 | 37227.57 | 51553.4774 | 106350.25 | 51553.4774 | 715.49
2025-09-22 | 154840.1336 | 144293.31 | 51613.3779 | 37227.57 | 51613.3779 | 106350.25 | 51613.3779 | 715.49
2025-09-23 | 155019.835 | 145355.47 | 51673.2783 | 37227.57 | 51673.2783 | 107412.41 | 51673.2783 | 715.49
2025-09-24 | 155199.5363 | 147474.61 | 51733.1788 | 37227.57 | 51733.1788 | 109531.55 | 51733.1788 | 715.49
2025-09-25 | 155379.2377 | 147474.61 | 51793.0792 | 37227.57 | 51793.0792 | 109531.55 | 51793.0792 | 715.49
2025-09-26 | 155558.939 | 149184.02 | 51852.9797 | 37227.57 | 51852.9797 | 111222.84 | 51852.9797 | 733.61
2025-09-27 | 155738.6403 | 149546.07 | 51912.8801 | 37227.57 | 51912.8801 | 111584.89 | 51912.8801 | 733.61
2025-09-28 | 155918.3417 | 149546.07 | 51972.7806 | 37227.57 | 51972.7806 | 111584.89 | 51972.7806 | 733.61
2025-09-29 | 156098.043 | 149723.19 | 52032.681 | 37227.57 | 52032.681 | 111762.01 | 52032.681 | 733.61
2025-09-30 | 156277.7444 | 150183.06 | 52092.5815 | 37227.57 | 52092.5815 | 112221.88 | 52092.5815 | 733.61
2025-10-01 | 156457.4457 | 153263.91 | 52152.4819 | 37227.57 | 52152.4819 | 115302.73 | 52152.4819 | 733.61
2025-10-02 | 156637.147 | 154706.43 | 52212.3823 | 37227.57 | 52212.3823 | 116745.25 | 52212.3823 | 733.61
2025-10-03 | 156816.8484 | 154706.43 | 52272.2828 | 37227.57 | 52272.2828 | 116745.25 | 52272.2828 | 733.61
2025-10-04 | 156996.5497 | 155329.54 | 52332.1832 | 37227.57 | 52332.1832 | 117368.36 | 52332.1832 | 733.61
2025-10-05 | 157176.2511 | 155329.54 | 52392.0837 | 37227.57 | 52392.0837 | 117368.36 | 52392.0837 | 733.61
2025-10-06 | 157355.9524 | 155517.92 | 52451.9841 | 37227.57 | 52451.9841 | 117556.74 | 52451.9841 | 733.61
2025-10-07 | 157535.6538 | 155517.92 | 52511.8846 | 37227.57 | 52511.8846 | 117556.74 | 52511.8846 | 733.61
2025-10-08 | 157715.3551 | 155517.92 | 52571.785 | 37227.57 | 52571.785 | 117556.74 | 52571.785 | 733.61
2025-10-09 | 157895.0564 | 155517.92 | 52631.6855 | 37227.57 | 52631.6855 | 117556.74 | 52631.6855 | 733.61
2025-10-10 | 158074.7578 | 155592.17 | 52691.5859 | 37227.57 | 52691.5859 | 117630.99 | 52691.5859 | 733.61
2025-10-11 | 158254.4591 | 155616.68 | 52751.4864 | 37227.57 | 52751.4864 | 117655.5 | 52751.4864 | 733.61
2025-10-12 | 158434.1605 | 155616.68 | 52811.3868 | 37227.57 | 52811.3868 | 117655.5 | 52811.3868 | 733.61
2025-10-13 | 158613.8618 | 155616.68 | 52871.2873 | 37227.57 | 52871.2873 | 117655.5 | 52871.2873 | 733.61
2025-10-14 | 158793.5632 | 155709.2 | 52931.1877 | 37227.57 | 52931.1877 | 117655.5 | 52931.1877 | 826.13
2025-10-15 | 158973.2645 | 155754.89 | 52991.0882 | 37227.57 | 52991.0882 | 117701.19 | 52991.0882 | 826.13
2025-10-16 | 159152.9658 | 156004.28 | 53050.9886 | 37227.57 | 53050.9886 | 117950.58 | 53050.9886 | 826.13
2025-10-17 | 159332.6672 | 156065.67 | 53110.8891 | 37227.57 | 53110.8891 | 118011.97 | 53110.8891 | 826.13
2025-10-18 | 159512.3685 | 157749.86 | 53170.7895 | 37227.57 | 53170.7895 | 119696.16 | 53170.7895 | 826.13
2025-10-19 | 159692.0699 | 157808.37 | 53230.69 | 37227.57 | 53230.69 | 119754.67 | 53230.69 | 826.13
2025-10-20 | 159871.7712 | 157808.37 | 53290.5904 | 37227.57 | 53290.5904 | 119754.67 | 53290.5904 | 826.13
2025-10-21 | 160051.4726 | 158217.07 | 53350.4909 | 37227.57 | 53350.4909 | 120163.37 | 53350.4909 | 826.13
2025-10-22 | 160231.1739 | 158217.07 | 53410.3913 | 37227.57 | 53410.3913 | 120163.37 | 53410.3913 | 826.13
2025-10-23 | 160410.8752 | 158669.77 | 53470.2917 | 37227.57 | 53470.2917 | 120616.07 | 53470.2917 | 826.13
2025-10-24 | 160590.5766 | 158669.77 | 53530.1922 | 37227.57 | 53530.1922 | 120616.07 | 53530.1922 | 826.13
2025-10-25 | 160770.2779 | 159071.32 | 53590.0926 | 37227.57 | 53590.0926 | 121017.62 | 53590.0926 | 826.13
2025-10-26 | 160949.9793 | 159071.32 | 53649.9931 | 37227.57 | 53649.9931 | 121017.62 | 53649.9931 | 826.13
2025-10-27 | 161129.6806 | 160296.32 | 53709.8935 | 37227.57 | 53709.8935 | 122242.62 | 53709.8935 | 826.13
2025-10-28 | 161309.3819 | 160655.3 | 53769.794 | 37227.57 | 53769.794 | 122601.6 | 53769.794 | 826.13
2025-10-29 | 161489.0833 | 161370.54 | 53829.6944 | 37227.57 | 53829.6944 | 123316.84 | 53829.6944 | 826.13
2025-10-30 | 161668.7846 | 163416.74 | 53889.5949 | 37227.57 | 53889.5949 | 125363.04 | 53889.5949 | 826.13
2025-10-31 | 161848.486 | 163416.74 | 53949.4953 | 37227.57 | 53949.4953 | 125363.04 | 53949.4953 | 826.13
2025-11-01 | 162028.1873 | 163416.74 | 54009.3958 | 37227.57 | 54009.3958 | 125363.04 | 54009.3958 | 826.13
2025-11-02 | 162207.8887 | 163416.74 | 54069.2962 | 37227.57 | 54069.2962 | 125363.04 | 54069.2962 | 826.13
2025-11-03 | 162387.59 | 163416.74 | 54129.1967 | 37227.57 | 54129.1967 | 125363.04 | 54129.1967 | 826.13
2025-11-04 | 162567.2913 | 163416.74 | 54189.0971 | 37227.57 | 54189.0971 | 125363.04 | 54189.0971 | 826.13
2025-11-05 | 162746.9927 | 163471.33 | 54248.9976 | 37227.57 | 54248.9976 | 125417.63 | 54248.9976 | 826.13
2025-11-06 | 162926.694 | 167702.15 | 54308.898 | 37227.57 | 54308.898 | 129648.45 | 54308.898 | 826.13
2025-11-07 | 163106.3954 | 169974.58 | 54368.7985 | 37227.57 | 54368.7985 | 131920.88 | 54368.7985 | 826.13
2025-11-08 | 163286.0967 | 171299.84 | 54428.6989 | 37227.57 | 54428.6989 | 133246.14 | 54428.6989 | 826.13
2025-11-09 | 163465.7981 | 171709.56 | 54488.5994 | 37227.57 | 54488.5994 | 133655.86 | 54488.5994 | 826.13
2025-11-10 | 163645.4994 | 174368.36 | 54548.4998 | 37227.57 | 54548.4998 | 136314.66 | 54548.4998 | 826.13
2025-11-11 | 163825.2007 | 174464.42 | 54608.4002 | 37227.57 | 54608.4002 | 136410.72 | 54608.4002 | 826.13
2025-11-12 | 164004.9021 | 175904.42 | 54668.3007 | 37227.57 | 54668.3007 | 137850.72 | 54668.3007 | 826.13
2025-11-13 | 164184.6034 | 176292.56 | 54728.2011 | 37227.57 | 54728.2011 | 138238.86 | 54728.2011 | 826.13
2025-11-14 | 164364.3048 | 178318.53 | 54788.1016 | 37227.57 | 54788.1016 | 140264.83 | 54788.1016 | 826.13
2025-11-15 | 164544.0061 | 180243.39 | 54848.002 | 37227.57 | 54848.002 | 142189.69 | 54848.002 | 826.13
2025-11-16 | 164723.7075 | 180289.66 | 54907.9025 | 37227.57 | 54907.9025 | 142235.96 | 54907.9025 | 826.13
2025-11-17 | 164903.4088 | 180518.24 | 54967.8029 | 37227.57 | 54967.8029 | 142464.54 | 54967.8029 | 826.13
2025-11-18 | 165083.1101 | 180573.15 | 55027.7034 | 37227.57 | 55027.7034 | 142519.45 | 55027.7034 | 826.13
2025-11-19 | 165262.8115 | 180607.35 | 55087.6038 | 37227.57 | 55087.6038 | 142553.65 | 55087.6038 | 826.13
2025-11-20 | 165442.5128 | 180948.95 | 55147.5043 | 37227.57 | 55147.5043 | 142895.25 | 55147.5043 | 826.13
2025-11-21 | 165622.2142 | 180993.47 | 55207.4047 | 37227.57 | 55207.4047 | 142939.77 | 55207.4047 | 826.13
2025-11-22 | 165801.9155 | 180993.47 | 55267.3052 | 37227.57 | 55267.3052 | 142939.77 | 55267.3052 | 826.13
2025-11-23 | 165981.6168 | 180993.47 | 55327.2056 | 37227.57 | 55327.2056 | 142939.77 | 55327.2056 | 826.13
2025-11-24 | 166161.3182 | 180993.47 | 55387.1061 | 37227.57 | 55387.1061 | 142939.77 | 55387.1061 | 826.13
2025-11-25 | 166341.0195 | 181343.71 | 55447.0065 | 37227.57 | 55447.0065 | 142939.77 | 55447.0065 | 1176.37
2025-11-26 | 166520.7209 | 181343.71 | 55506.907 | 37227.57 | 55506.907 | 142939.77 | 55506.907 | 1176.37
2025-11-27 | 166700.4222 | 181343.71 | 55566.8074 | 37227.57 | 55566.8074 | 142939.77 | 55566.8074 | 1176.37
2025-11-28 | 166880.1236 | 181343.71 | 55626.7079 | 37227.57 | 55626.7079 | 142939.77 | 55626.7079 | 1176.37
2025-11-29 | 167059.8249 | 181343.71 | 55686.6083 | 37227.57 | 55686.6083 | 142939.77 | 55686.6083 | 1176.37
2025-11-30 | 167239.5262 | 181343.71 | 55746.5087 | 37227.57 | 55746.5087 | 142939.77 | 55746.5087 | 1176.37
2025-12-01 | 167419.2276 | 181343.71 | 55806.4092 | 37227.57 | 55806.4092 | 142939.77 | 55806.4092 | 1176.37
2025-12-02 | 167598.9289 | 181343.71 | 55866.3096 | 37227.57 | 55866.3096 | 142939.77 | 55866.3096 | 1176.37
2025-12-03 | 167778.6303 | 181343.71 | 55926.2101 | 37227.57 | 55926.2101 | 142939.77 | 55926.2101 | 1176.37
2025-12-04 | 167958.3316 | 181343.71 | 55986.1105 | 37227.57 | 55986.1105 | 142939.77 | 55986.1105 | 1176.37
2025-12-05 | 168138.033 | 183285.65 | 56046.011 | 37227.57 | 56046.011 | 144881.71 | 56046.011 | 1176.37
2025-12-06 | 168317.7343 | 183285.65 | 56105.9114 | 37227.57 | 56105.9114 | 144881.71 | 56105.9114 | 1176.37
2025-12-07 | 168497.4356 | 183285.65 | 56165.8119 | 37227.57 | 56165.8119 | 144881.71 | 56165.8119 | 1176.37
2025-12-08 | 168677.137 | 183547.19 | 56225.7123 | 37227.57 | 56225.7123 | 145143.25 | 56225.7123 | 1176.37
2025-12-09 | 168856.8383 | 185971.18 | 56285.6128 | 37227.57 | 56285.6128 | 147567.24 | 56285.6128 | 1176.37
2025-12-10 | 169036.5397 | 186230.73 | 56345.5132 | 37227.57 | 56345.5132 | 147826.79 | 56345.5132 | 1176.37
2025-12-11 | 169216.241 | 186230.73 | 56405.4137 | 37227.57 | 56405.4137 | 147826.79 | 56405.4137 | 1176.37
2025-12-12 | 169395.9424 | 186230.73 | 56465.3141 | 37227.57 | 56465.3141 | 147826.79 | 56465.3141 | 1176.37
2025-12-13 | 169575.6437 | 186230.73 | 56525.2146 | 37227.57 | 56525.2146 | 147826.79 | 56525.2146 | 1176.37
2025-12-14 | 169755.345 | 186230.73 | 56585.115 | 37227.57 | 56585.115 | 147826.79 | 56585.115 | 1176.37
2025-12-15 | 169935.0464 | 186338.31 | 56645.0155 | 37227.57 | 56645.0155 | 147934.37 | 56645.0155 | 1176.37
2025-12-16 | 170114.7477 | 186472.43 | 56704.9159 | 37227.57 | 56704.9159 | 148068.49 | 56704.9159 | 1176.37
2025-12-17 | 170294.4491 | 187333.88 | 56764.8164 | 37227.57 | 56764.8164 | 148929.94 | 56764.8164 | 1176.37
2025-12-18 | 170474.1504 | 187333.88 | 56824.7168 | 37227.57 | 56824.7168 | 148929.94 | 56824.7168 | 1176.37
2025-12-19 | 170653.8517 | 187333.88 | 56884.6172 | 37227.57 | 56884.6172 | 148929.94 | 56884.6172 | 1176.37
2025-12-20 | 170833.5531 | 187333.88 | 56944.5177 | 37227.57 | 56944.5177 | 148929.94 | 56944.5177 | 1176.37
2025-12-21 | 171013.2544 | 187333.88 | 57004.4181 | 37227.57 | 57004.4181 | 148929.94 | 57004.4181 | 1176.37
2025-12-22 | 171192.9558 | 187789.43 | 57064.3186 | 37227.57 | 57064.3186 | 149385.49 | 57064.3186 | 1176.37
2025-12-23 | 171372.6571 | 187789.43 | 57124.219 | 37227.57 | 57124.219 | 149385.49 | 57124.219 | 1176.37
2025-12-24 | 171552.3585 | 187789.43 | 57184.1195 | 37227.57 | 57184.1195 | 149385.49 | 57184.1195 | 1176.37
2025-12-25 | 171732.0598 | 187789.43 | 57244.0199 | 37227.57 | 57244.0199 | 149385.49 | 57244.0199 | 1176.37
2025-12-26 | 171911.7611 | 187789.43 | 57303.9204 | 37227.57 | 57303.9204 | 149385.49 | 57303.9204 | 1176.37
2025-12-27 | 172091.4625 | 187789.43 | 57363.8208 | 37227.57 | 57363.8208 | 149385.49 | 57363.8208 | 1176.37
2025-12-28 | 172271.1638 | 187789.43 | 57423.7213 | 37227.57 | 57423.7213 | 149385.49 | 57423.7213 | 1176.37
2025-12-29 | 172450.8652 | 187789.43 | 57483.6217 | 37227.57 | 57483.6217 | 149385.49 | 57483.6217 | 1176.37
2025-12-30 | 172630.5665 | 187789.43 | 57543.5222 | 37227.57 | 57543.5222 | 149385.49 | 57543.5222 | 1176.37
2025-12-31 | 172810.2679 | 187789.43 | 57603.4226 | 37227.57 | 57603.4226 | 149385.49 | 57603.4226 | 1176.37
2026-01-01 | 172989.9692 | 187789.43 | 57663.3231 | 37227.57 | 57663.3231 | 149385.49 | 57663.3231 | 1176.37
2026-01-02 | 173169.6705 | 187789.43 | 57723.2235 | 37227.57 | 57723.2235 | 149385.49 | 57723.2235 | 1176.37
2026-01-03 | 173349.3719 | 187789.43 | 57783.124 | 37227.57 | 57783.124 | 149385.49 | 57783.124 | 1176.37
2026-01-04 | 173529.0732 | 187789.43 | 57843.0244 | 37227.57 | 57843.0244 | 149385.49 | 57843.0244 | 1176.37
2026-01-05 | 173708.7746 | 187789.43 | 57902.9249 | 37227.57 | 57902.9249 | 149385.49 | 57902.9249 | 1176.37
2026-01-06 | 173888.4759 | 188700.98 | 57962.8253 | 37227.57 | 57962.8253 | 150297.04 | 57962.8253 | 1176.37
2026-01-07 | 174068.1773 | 189011.7 | 58022.7258 | 37227.57 | 58022.7258 | 150607.76 | 58022.7258 | 1176.37
2026-01-08 | 174247.8786 | 190395.56 | 58082.6262 | 37227.57 | 58082.6262 | 151991.62 | 58082.6262 | 1176.37
2026-01-09 | 174427.5799 | 190510.68 | 58142.5266 | 37227.57 | 58142.5266 | 152106.74 | 58142.5266 | 1176.37
2026-01-10 | 174607.2813 | 190510.68 | 58202.4271 | 37227.57 | 58202.4271 | 152106.74 | 58202.4271 | 1176.37
2026-01-11 | 174786.9826 | 190510.68 | 58262.3275 | 37227.57 | 58262.3275 | 152106.74 | 58262.3275 | 1176.37
2026-01-12 | 174966.684 | 190510.68 | 58322.228 | 37227.57 | 58322.228 | 152106.74 | 58322.228 | 1176.37
2026-01-13 | 175146.3853 | 190510.68 | 58382.1284 | 37227.57 | 58382.1284 | 152106.74 | 58382.1284 | 1176.37
2026-01-14 | 175326.0866 | 190535.59 | 58442.0289 | 37227.57 | 58442.0289 | 152131.65 | 58442.0289 | 1176.37
2026-01-15 | 175505.788 | 190535.59 | 58501.9293 | 37227.57 | 58501.9293 | 152131.65 | 58501.9293 | 1176.37
2026-01-16 | 175685.4893 | 190891.17 | 58561.8298 | 37227.57 | 58561.8298 | 152487.23 | 58561.8298 | 1176.37
2026-01-17 | 175865.1907 | 190891.17 | 58621.7302 | 37227.57 | 58621.7302 | 152487.23 | 58621.7302 | 1176.37
2026-01-18 | 176044.892 | 190891.17 | 58681.6307 | 37227.57 | 58681.6307 | 152487.23 | 58681.6307 | 1176.37
2026-01-19 | 176224.5934 | 191030.13 | 58741.5311 | 37227.57 | 58741.5311 | 152626.19 | 58741.5311 | 1176.37
2026-01-20 | 176404.2947 | 192128.01 | 58801.4316 | 37227.57 | 58801.4316 | 153673.15 | 58801.4316 | 1227.29
2026-01-21 | 176583.996 | 192206.46 | 58861.332 | 37227.57 | 58861.332 | 153751.6 | 58861.332 | 1227.29
2026-01-22 | 176763.6974 | 192266.84 | 58921.2325 | 37227.57 | 58921.2325 | 153811.98 | 58921.2325 | 1227.29
2026-01-23 | 176943.3987 | 192266.84 | 58981.1329 | 37227.57 | 58981.1329 | 153811.98 | 58981.1329 | 1227.29
2026-01-24 | 177123.1001 | 192266.84 | 59041.0334 | 37227.57 | 59041.0334 | 153811.98 | 59041.0334 | 1227.29
2026-01-25 | 177302.8014 | 192266.84 | 59100.9338 | 37227.57 | 59100.9338 | 153811.98 | 59100.9338 | 1227.29
2026-01-26 | 177482.5028 | 192945.67 | 59160.8343 | 37227.57 | 59160.8343 | 154490.81 | 59160.8343 | 1227.29
2026-01-27 | 177662.2041 | 192945.67 | 59220.7347 | 37227.57 | 59220.7347 | 154490.81 | 59220.7347 | 1227.29
2026-01-28 | 177841.9054 | 192945.67 | 59280.6351 | 37227.57 | 59280.6351 | 154490.81 | 59280.6351 | 1227.29
2026-01-29 | 177841.9054 | 193084.78 | 59280.6351 | 37227.57 | 59280.6351 | 154629.92 | 59280.6351 | 1227.29
2026-01-30 | 177841.9054 | 193353.79 | 59280.6351 | 37227.57 | 59280.6351 | 154898.93 | 59280.6351 | 1227.29
2026-01-31 | 177841.9054 | 193353.79 | 59280.6351 | 37227.57 | 59280.6351 | 154898.93 | 59280.6351 | 1227.29
2026-02-01 | 177841.9054 | 193353.79 | 59280.6351 | 37227.57 | 59280.6351 | 154898.93 | 59280.6351 | 1227.29
2026-02-02 | 177841.9054 | 195263.15 | 59280.6351 | 37227.57 | 59280.6351 | 156808.29 | 59280.6351 | 1227.29
2026-02-03 | 177841.9054 | 195263.15 | 59280.6351 | 37227.57 | 59280.6351 | 156808.29 | 59280.6351 | 1227.29
2026-02-04 | 177841.9054 | 195286.28 | 59280.6351 | 37227.57 | 59280.6351 | 156831.42 | 59280.6351 | 1227.29
2026-02-05 | 177841.9054 | 195299.68 | 59280.6351 | 37227.57 | 59280.6351 | 156844.82 | 59280.6351 | 1227.29
2026-02-06 | 177841.9054 | 195644.48 | 59280.6351 | 37227.57 | 59280.6351 | 157189.62 | 59280.6351 | 1227.29
2026-02-07 | 177841.9054 | 195644.48 | 59280.6351 | 37227.57 | 59280.6351 | 157189.62 | 59280.6351 | 1227.29
2026-02-08 | 177841.9054 | 195644.48 | 59280.6351 | 37227.57 | 59280.6351 | 157189.62 | 59280.6351 | 1227.29
2026-02-09 | 177841.9054 | 195644.48 | 59280.6351 | 37227.57 | 59280.6351 | 157189.62 | 59280.6351 | 1227.29
2026-02-10 | 177841.9054 | 195644.48 | 59280.6351 | 37227.57 | 59280.6351 | 157189.62 | 59280.6351 | 1227.29
2026-02-11 | 177841.9054 | 195654.18 | 59280.6351 | 37227.57 | 59280.6351 | 157199.32 | 59280.6351 | 1227.29
2026-02-12 | 177841.9054 | 195654.18 | 59280.6351 | 37227.57 | 59280.6351 | 157199.32 | 59280.6351 | 1227.29
2026-02-13 | 177841.9054 | 195654.18 | 59280.6351 | 37227.57 | 59280.6351 | 157199.32 | 59280.6351 | 1227.29
2026-02-14 | 177841.9054 | 195654.18 | 59280.6351 | 37227.57 | 59280.6351 | 157199.32 | 59280.6351 | 1227.29
2026-02-15 | 177841.9054 | 195654.18 | 59280.6351 | 37227.57 | 59280.6351 | 157199.32 | 59280.6351 | 1227.29
2026-02-16 | 177841.9054 | 195654.18 | 59280.6351 | 37227.57 | 59280.6351 | 157199.32 | 59280.6351 | 1227.29
2026-02-17 | 177841.9054 | 195654.18 | 59280.6351 | 37227.57 | 59280.6351 | 157199.32 | 59280.6351 | 1227.29
2026-02-18 | 177841.9054 | 195654.18 | 59280.6351 | 37227.57 | 59280.6351 | 157199.32 | 59280.6351 | 1227.29
2026-02-19 | 177841.9054 | 195654.18 | 59280.6351 | 37227.57 | 59280.6351 | 157199.32 | 59280.6351 | 1227.29
2026-02-20 | 177841.9054 | 195654.18 | 59280.6351 | 37227.57 | 59280.6351 | 157199.32 | 59280.6351 | 1227.29
2026-02-21 | 177841.9054 | 195654.18 | 59280.6351 | 37227.57 | 59280.6351 | 157199.32 | 59280.6351 | 1227.29
2026-02-22 | 177841.9054 | 195654.18 | 59280.6351 | 37227.57 | 59280.6351 | 157199.32 | 59280.6351 | 1227.29
2026-02-23 | 177841.9054 | 195654.18 | 59280.6351 | 37227.57 | 59280.6351 | 157199.32 | 59280.6351 | 1227.29
2026-02-24 | 177841.9054 | 195654.18 | 59280.6351 | 37227.57 | 59280.6351 | 157199.32 | 59280.6351 | 1227.29
2026-02-25 | 177841.9054 | 195654.18 | 59280.6351 | 37227.57 | 59280.6351 | 157199.32 | 59280.6351 | 1227.29
2026-02-26 | 177841.9054 | 195654.18 | 59280.6351 | 37227.57 | 59280.6351 | 157199.32 | 59280.6351 | 1227.29
2026-02-27 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-02-28 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-01 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-02 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-03 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-04 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-05 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-06 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-07 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-08 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-09 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-10 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-11 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-12 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-13 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-14 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-15 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-16 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-17 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-18 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-19 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-20 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-21 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-22 | 177841.9054 | 195801.95 | 59280.6351 | 37227.57 | 59280.6351 | 157347.09 | 59280.6351 | 1227.29
2026-03-23 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-24 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-25 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-26 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-27 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-28 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-29 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-30 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-31 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-01 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-02 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-03 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-04 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-05 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-06 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-07 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-08 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-09 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-10 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-11 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-12 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-13 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-14 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-15 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-16 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-17 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-18 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-19 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-20 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-21 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-22 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-23 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-24 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-25 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-26 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-27 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-28 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-29 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-30 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-01 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-02 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-03 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-04 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-05 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-06 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-07 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-08 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-09 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-10 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-11 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-12 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-13 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-14 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-15 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-16 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-17 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-18 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-19 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-20 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-21 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-22 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-23 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-24 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-25 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-26 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-27 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-28 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-29 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-30 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-31 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-01 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-02 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-03 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-04 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-05 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-06 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-07 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-08 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-09 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-10 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-11 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-12 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-13 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-14 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-15 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-16 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-17 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-18 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-19 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-20 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-21 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-22 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-23 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-24 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-25 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-26 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-27 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-28 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-29 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-06-30 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-01 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-02 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-03 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-04 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-05 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-06 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-07 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-08 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-09 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-10 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-11 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-12 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-13 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-14 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-15 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-16 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-17 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-18 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-19 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-20 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-21 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-22 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-23 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-24 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-25 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-26 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-27 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-28 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-29 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-30 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-07-31 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-08-01 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-08-02 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-08-03 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-08-04 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-08-05 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-08-06 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-08-07 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-08-08 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-08-09 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-08-10 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-08-11 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-08-12 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-08-13 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-08-14 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-08-15 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-08-16 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-08-18 | 178064.8178 |  | 59354.9393 |  | 59354.9393 |  | 59354.9393
2026-08-19 | 178287.7301 |  | 59429.2434 |  | 59429.2434 |  | 59429.2434
2026-08-20 | 178510.6425 |  | 59503.5475 |  | 59503.5475 |  | 59503.5475
2026-08-21 | 178733.5548 |  | 59577.8516 |  | 59577.8516 |  | 59577.8516
2026-08-22 | 178956.4671 |  | 59652.1557 |  | 59652.1557 |  | 59652.1557
2026-08-23 | 179179.3795 |  | 59726.4598 |  | 59726.4598 |  | 59726.4598
2026-08-24 | 179402.2918 |  | 59800.7639 |  | 59800.7639 |  | 59800.7639
2026-08-25 | 179625.2042 |  | 59875.0681 |  | 59875.0681 |  | 59875.0681
2026-08-26 | 179848.1165 |  | 59949.3722 |  | 59949.3722 |  | 59949.3722
2026-08-27 | 180071.0288 |  | 60023.6763 |  | 60023.6763 |  | 60023.6763
2026-08-28 | 180293.9412 |  | 60097.9804 |  | 60097.9804 |  | 60097.9804
2026-08-29 | 180516.8535 |  | 60172.2845 |  | 60172.2845 |  | 60172.2845
2026-08-30 | 180739.7659 |  | 60246.5886 |  | 60246.5886 |  | 60246.5886
2026-08-31 | 180962.6782 |  | 60320.8927 |  | 60320.8927 |  | 60320.8927
2026-09-01 | 181185.5906 |  | 60395.1969 |  | 60395.1969 |  | 60395.1969
2026-09-02 | 181408.5029 |  | 60469.501 |  | 60469.501 |  | 60469.501
2026-09-03 | 181631.4152 |  | 60543.8051 |  | 60543.8051 |  | 60543.8051
2026-09-04 | 181854.3276 |  | 60618.1092 |  | 60618.1092 |  | 60618.1092
2026-09-05 | 182077.2399 |  | 60692.4133 |  | 60692.4133 |  | 60692.4133
2026-09-06 | 182300.1523 |  | 60766.7174 |  | 60766.7174 |  | 60766.7174
2026-09-07 | 182523.0646 |  | 60841.0215 |  | 60841.0215 |  | 60841.0215
2026-09-08 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-09 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-10 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-11 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-12 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-13 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-14 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-15 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-16 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-17 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-18 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-19 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-20 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-21 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-22 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-23 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-24 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-25 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-26 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-27 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-28 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-29 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-09-30 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-10-01 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-10-02 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-10-03 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-10-04 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-10-05 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-10-06 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-10-07 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-10-08 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-10-09 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-10-10 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-10-11 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-10-12 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256

## Outsource (Direct Cost)
Date | Planned Outsource (Cumulative) | Actual Outsource (Cumulative) | Planned 5006 · Drilling Expense (Cumulative) | Actual 5006 · Drilling Expense (Cumulative) | Planned 5110 · Temporary labor (Direct) (Cumulative) | Actual 5110 · Temporary labor (Direct) (Cumulative) | Planned 5112 · Carbon & Lab Samplies (Driect) (Cumulative) | Actual 5112 · Carbon & Lab Samplies (Driect) (Cumulative) | Planned 5114 · Rent - Building (Direct) (Cumulative) | Actual 5114 · Rent - Building (Direct) (Cumulative) | Planned 5115 · Rent - Equipment (direct) (Cumulative) | Actual 5115 · Rent - Equipment (direct) (Cumulative) | Planned 5120 · Outside services (Direct) (Cumulative) | Actual 5120 · Outside services (Direct) (Cumulative) | Planned 5121 · Freight & Shipping (Direct) (Cumulative) | Actual 5121 · Freight & Shipping (Direct) (Cumulative) | Planned 5124 · License and permits (Direct) (Cumulative) | Actual 5124 · License and permits (Direct) (Cumulative) | Planned 5129 · Misc expenses (Direct) (Cumulative) | Actual 5129 · Misc expenses (Direct) (Cumulative) | Planned 5132 · Internet fee (Direct) (Cumulative) | Actual 5132 · Internet fee (Direct) (Cumulative)
2025-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 1405.3373 | 0 | 140.5337 | 0 | 140.5337 | 0 | 140.5337 | 0 | 140.5337 | 0 | 140.5337 | 0 | 140.5337 | 0 | 140.5337 | 0 | 140.5337 | 0 | 140.5337 | 0 | 140.5337 | 0
2025-06-02 | 2810.6747 | 0 | 281.0675 | 0 | 281.0675 | 0 | 281.0675 | 0 | 281.0675 | 0 | 281.0675 | 0 | 281.0675 | 0 | 281.0675 | 0 | 281.0675 | 0 | 281.0675 | 0 | 281.0675 | 0
2025-06-03 | 4216.012 | 0 | 421.6012 | 0 | 421.6012 | 0 | 421.6012 | 0 | 421.6012 | 0 | 421.6012 | 0 | 421.6012 | 0 | 421.6012 | 0 | 421.6012 | 0 | 421.6012 | 0 | 421.6012 | 0
2025-06-04 | 5621.3494 | 0 | 562.1349 | 0 | 562.1349 | 0 | 562.1349 | 0 | 562.1349 | 0 | 562.1349 | 0 | 562.1349 | 0 | 562.1349 | 0 | 562.1349 | 0 | 562.1349 | 0 | 562.1349 | 0
2025-06-05 | 7026.6867 | 0 | 702.6687 | 0 | 702.6687 | 0 | 702.6687 | 0 | 702.6687 | 0 | 702.6687 | 0 | 702.6687 | 0 | 702.6687 | 0 | 702.6687 | 0 | 702.6687 | 0 | 702.6687 | 0
2025-06-06 | 8432.0241 | 0 | 843.2024 | 0 | 843.2024 | 0 | 843.2024 | 0 | 843.2024 | 0 | 843.2024 | 0 | 843.2024 | 0 | 843.2024 | 0 | 843.2024 | 0 | 843.2024 | 0 | 843.2024 | 0
2025-06-07 | 9837.3614 | 0 | 983.7361 | 0 | 983.7361 | 0 | 983.7361 | 0 | 983.7361 | 0 | 983.7361 | 0 | 983.7361 | 0 | 983.7361 | 0 | 983.7361 | 0 | 983.7361 | 0 | 983.7361 | 0
2025-06-08 | 11242.6988 | 0 | 1124.2699 | 0 | 1124.2699 | 0 | 1124.2699 | 0 | 1124.2699 | 0 | 1124.2699 | 0 | 1124.2699 | 0 | 1124.2699 | 0 | 1124.2699 | 0 | 1124.2699 | 0 | 1124.2699 | 0
2025-06-09 | 12648.0361 | 0 | 1264.8036 | 0 | 1264.8036 | 0 | 1264.8036 | 0 | 1264.8036 | 0 | 1264.8036 | 0 | 1264.8036 | 0 | 1264.8036 | 0 | 1264.8036 | 0 | 1264.8036 | 0 | 1264.8036 | 0
2025-06-10 | 14053.3735 | 0 | 1405.3373 | 0 | 1405.3373 | 0 | 1405.3373 | 0 | 1405.3373 | 0 | 1405.3373 | 0 | 1405.3373 | 0 | 1405.3373 | 0 | 1405.3373 | 0 | 1405.3373 | 0 | 1405.3373 | 0
2025-06-11 | 15458.7108 | 0 | 1545.8711 | 0 | 1545.8711 | 0 | 1545.8711 | 0 | 1545.8711 | 0 | 1545.8711 | 0 | 1545.8711 | 0 | 1545.8711 | 0 | 1545.8711 | 0 | 1545.8711 | 0 | 1545.8711 | 0
2025-06-12 | 16864.0482 | 0 | 1686.4048 | 0 | 1686.4048 | 0 | 1686.4048 | 0 | 1686.4048 | 0 | 1686.4048 | 0 | 1686.4048 | 0 | 1686.4048 | 0 | 1686.4048 | 0 | 1686.4048 | 0 | 1686.4048 | 0
2025-06-13 | 18269.3855 | 0 | 1826.9386 | 0 | 1826.9386 | 0 | 1826.9386 | 0 | 1826.9386 | 0 | 1826.9386 | 0 | 1826.9386 | 0 | 1826.9386 | 0 | 1826.9386 | 0 | 1826.9386 | 0 | 1826.9386 | 0
2025-06-14 | 19674.7229 | 0 | 1967.4723 | 0 | 1967.4723 | 0 | 1967.4723 | 0 | 1967.4723 | 0 | 1967.4723 | 0 | 1967.4723 | 0 | 1967.4723 | 0 | 1967.4723 | 0 | 1967.4723 | 0 | 1967.4723 | 0
2025-06-15 | 21080.0602 | 0 | 2108.006 | 0 | 2108.006 | 0 | 2108.006 | 0 | 2108.006 | 0 | 2108.006 | 0 | 2108.006 | 0 | 2108.006 | 0 | 2108.006 | 0 | 2108.006 | 0 | 2108.006 | 0
2025-06-16 | 22485.3976 | 0 | 2248.5398 | 0 | 2248.5398 | 0 | 2248.5398 | 0 | 2248.5398 | 0 | 2248.5398 | 0 | 2248.5398 | 0 | 2248.5398 | 0 | 2248.5398 | 0 | 2248.5398 | 0 | 2248.5398 | 0
2025-06-17 | 23890.7349 | 0 | 2389.0735 | 0 | 2389.0735 | 0 | 2389.0735 | 0 | 2389.0735 | 0 | 2389.0735 | 0 | 2389.0735 | 0 | 2389.0735 | 0 | 2389.0735 | 0 | 2389.0735 | 0 | 2389.0735 | 0
2025-06-18 | 25296.0723 | 0 | 2529.6072 | 0 | 2529.6072 | 0 | 2529.6072 | 0 | 2529.6072 | 0 | 2529.6072 | 0 | 2529.6072 | 0 | 2529.6072 | 0 | 2529.6072 | 0 | 2529.6072 | 0 | 2529.6072 | 0
2025-06-19 | 26701.4096 | 0 | 2670.141 | 0 | 2670.141 | 0 | 2670.141 | 0 | 2670.141 | 0 | 2670.141 | 0 | 2670.141 | 0 | 2670.141 | 0 | 2670.141 | 0 | 2670.141 | 0 | 2670.141 | 0
2025-06-20 | 28106.747 | 582.5 | 2810.6747 | 0 | 2810.6747 | 0 | 2810.6747 | 0 | 2810.6747 | 0 | 2810.6747 | 0 | 2810.6747 | 0 | 2810.6747 | 0 | 2810.6747 | 0 | 2810.6747 | 582.5 | 2810.6747 | 0
2025-06-21 | 29512.0843 | 582.5 | 2951.2084 | 0 | 2951.2084 | 0 | 2951.2084 | 0 | 2951.2084 | 0 | 2951.2084 | 0 | 2951.2084 | 0 | 2951.2084 | 0 | 2951.2084 | 0 | 2951.2084 | 582.5 | 2951.2084 | 0
2025-06-22 | 30917.4217 | 582.5 | 3091.7422 | 0 | 3091.7422 | 0 | 3091.7422 | 0 | 3091.7422 | 0 | 3091.7422 | 0 | 3091.7422 | 0 | 3091.7422 | 0 | 3091.7422 | 0 | 3091.7422 | 582.5 | 3091.7422 | 0
2025-06-23 | 32322.759 | 582.5 | 3232.2759 | 0 | 3232.2759 | 0 | 3232.2759 | 0 | 3232.2759 | 0 | 3232.2759 | 0 | 3232.2759 | 0 | 3232.2759 | 0 | 3232.2759 | 0 | 3232.2759 | 582.5 | 3232.2759 | 0
2025-06-24 | 33728.0964 | 582.5 | 3372.8096 | 0 | 3372.8096 | 0 | 3372.8096 | 0 | 3372.8096 | 0 | 3372.8096 | 0 | 3372.8096 | 0 | 3372.8096 | 0 | 3372.8096 | 0 | 3372.8096 | 582.5 | 3372.8096 | 0
2025-06-25 | 35133.4337 | 582.5 | 3513.3434 | 0 | 3513.3434 | 0 | 3513.3434 | 0 | 3513.3434 | 0 | 3513.3434 | 0 | 3513.3434 | 0 | 3513.3434 | 0 | 3513.3434 | 0 | 3513.3434 | 582.5 | 3513.3434 | 0
2025-06-26 | 36538.7711 | 582.5 | 3653.8771 | 0 | 3653.8771 | 0 | 3653.8771 | 0 | 3653.8771 | 0 | 3653.8771 | 0 | 3653.8771 | 0 | 3653.8771 | 0 | 3653.8771 | 0 | 3653.8771 | 582.5 | 3653.8771 | 0
2025-06-27 | 37944.1084 | 582.5 | 3794.4108 | 0 | 3794.4108 | 0 | 3794.4108 | 0 | 3794.4108 | 0 | 3794.4108 | 0 | 3794.4108 | 0 | 3794.4108 | 0 | 3794.4108 | 0 | 3794.4108 | 582.5 | 3794.4108 | 0
2025-06-28 | 39349.4458 | 582.5 | 3934.9446 | 0 | 3934.9446 | 0 | 3934.9446 | 0 | 3934.9446 | 0 | 3934.9446 | 0 | 3934.9446 | 0 | 3934.9446 | 0 | 3934.9446 | 0 | 3934.9446 | 582.5 | 3934.9446 | 0
2025-06-29 | 40754.7831 | 582.5 | 4075.4783 | 0 | 4075.4783 | 0 | 4075.4783 | 0 | 4075.4783 | 0 | 4075.4783 | 0 | 4075.4783 | 0 | 4075.4783 | 0 | 4075.4783 | 0 | 4075.4783 | 582.5 | 4075.4783 | 0
2025-06-30 | 42160.1205 | 582.5 | 4216.012 | 0 | 4216.012 | 0 | 4216.012 | 0 | 4216.012 | 0 | 4216.012 | 0 | 4216.012 | 0 | 4216.012 | 0 | 4216.012 | 0 | 4216.012 | 582.5 | 4216.012 | 0
2025-07-01 | 43565.4578 | 582.5 | 4356.5458 | 0 | 4356.5458 | 0 | 4356.5458 | 0 | 4356.5458 | 0 | 4356.5458 | 0 | 4356.5458 | 0 | 4356.5458 | 0 | 4356.5458 | 0 | 4356.5458 | 582.5 | 4356.5458 | 0
2025-07-02 | 44970.7952 | 1036.65 | 4497.0795 | 0 | 4497.0795 | 0 | 4497.0795 | 0 | 4497.0795 | 0 | 4497.0795 | 0 | 4497.0795 | 0 | 4497.0795 | 0 | 4497.0795 | 0 | 4497.0795 | 927.5 | 4497.0795 | 0
2025-07-03 | 46376.1325 | 1036.65 | 4637.6133 | 0 | 4637.6133 | 0 | 4637.6133 | 0 | 4637.6133 | 0 | 4637.6133 | 0 | 4637.6133 | 0 | 4637.6133 | 0 | 4637.6133 | 0 | 4637.6133 | 927.5 | 4637.6133 | 0
2025-07-04 | 47781.4699 | 1486.65 | 4778.147 | 0 | 4778.147 | 0 | 4778.147 | 0 | 4778.147 | 0 | 4778.147 | 0 | 4778.147 | 0 | 4778.147 | 0 | 4778.147 | 0 | 4778.147 | 927.5 | 4778.147 | 0
2025-07-05 | 49186.8072 | 1486.65 | 4918.6807 | 0 | 4918.6807 | 0 | 4918.6807 | 0 | 4918.6807 | 0 | 4918.6807 | 0 | 4918.6807 | 0 | 4918.6807 | 0 | 4918.6807 | 0 | 4918.6807 | 927.5 | 4918.6807 | 0
2025-07-06 | 50592.1446 | 1486.65 | 5059.2145 | 0 | 5059.2145 | 0 | 5059.2145 | 0 | 5059.2145 | 0 | 5059.2145 | 0 | 5059.2145 | 0 | 5059.2145 | 0 | 5059.2145 | 0 | 5059.2145 | 927.5 | 5059.2145 | 0
2025-07-07 | 51997.4819 | 1486.65 | 5199.7482 | 0 | 5199.7482 | 0 | 5199.7482 | 0 | 5199.7482 | 0 | 5199.7482 | 0 | 5199.7482 | 0 | 5199.7482 | 0 | 5199.7482 | 0 | 5199.7482 | 927.5 | 5199.7482 | 0
2025-07-08 | 53402.8193 | 1486.65 | 5340.2819 | 0 | 5340.2819 | 0 | 5340.2819 | 0 | 5340.2819 | 0 | 5340.2819 | 0 | 5340.2819 | 0 | 5340.2819 | 0 | 5340.2819 | 0 | 5340.2819 | 927.5 | 5340.2819 | 0
2025-07-09 | 54808.1566 | 1579.35 | 5480.8157 | 0 | 5480.8157 | 0 | 5480.8157 | 0 | 5480.8157 | 0 | 5480.8157 | 0 | 5480.8157 | 0 | 5480.8157 | 0 | 5480.8157 | 0 | 5480.8157 | 927.5 | 5480.8157 | 0
2025-07-10 | 56213.494 | 1579.35 | 5621.3494 | 0 | 5621.3494 | 0 | 5621.3494 | 0 | 5621.3494 | 0 | 5621.3494 | 0 | 5621.3494 | 0 | 5621.3494 | 0 | 5621.3494 | 0 | 5621.3494 | 927.5 | 5621.3494 | 0
2025-07-11 | 57618.8313 | 1837.65 | 5761.8831 | 0 | 5761.8831 | 0 | 5761.8831 | 0 | 5761.8831 | 0 | 5761.8831 | 0 | 5761.8831 | 0 | 5761.8831 | 258.3 | 5761.8831 | 0 | 5761.8831 | 927.5 | 5761.8831 | 0
2025-07-12 | 59024.1687 | 1837.65 | 5902.4169 | 0 | 5902.4169 | 0 | 5902.4169 | 0 | 5902.4169 | 0 | 5902.4169 | 0 | 5902.4169 | 0 | 5902.4169 | 258.3 | 5902.4169 | 0 | 5902.4169 | 927.5 | 5902.4169 | 0
2025-07-13 | 60429.506 | 2003.83 | 6042.9506 | 0 | 6042.9506 | 0 | 6042.9506 | 0 | 6042.9506 | 0 | 6042.9506 | 0 | 6042.9506 | 0 | 6042.9506 | 258.3 | 6042.9506 | 0 | 6042.9506 | 927.5 | 6042.9506 | 0
2025-07-14 | 61834.8434 | 2003.83 | 6183.4843 | 0 | 6183.4843 | 0 | 6183.4843 | 0 | 6183.4843 | 0 | 6183.4843 | 0 | 6183.4843 | 0 | 6183.4843 | 258.3 | 6183.4843 | 0 | 6183.4843 | 927.5 | 6183.4843 | 0
2025-07-15 | 63240.1807 | 2125.78 | 6324.0181 | 0 | 6324.0181 | 0 | 6324.0181 | 0 | 6324.0181 | 0 | 6324.0181 | 121.95 | 6324.0181 | 0 | 6324.0181 | 258.3 | 6324.0181 | 0 | 6324.0181 | 927.5 | 6324.0181 | 0
2025-07-16 | 64645.5181 | 8425.78 | 6464.5518 | 0 | 6464.5518 | 0 | 6464.5518 | 0 | 6464.5518 | 0 | 6464.5518 | 121.95 | 6464.5518 | 0 | 6464.5518 | 6558.3 | 6464.5518 | 0 | 6464.5518 | 927.5 | 6464.5518 | 0
2025-07-17 | 66050.8554 | 8688.27 | 6605.0855 | 0 | 6605.0855 | 0 | 6605.0855 | 0 | 6605.0855 | 0 | 6605.0855 | 121.95 | 6605.0855 | 0 | 6605.0855 | 6558.3 | 6605.0855 | 0 | 6605.0855 | 927.5 | 6605.0855 | 0
2025-07-18 | 67456.1928 | 9179.36 | 6745.6193 | 0 | 6745.6193 | 0 | 6745.6193 | 0 | 6745.6193 | 0 | 6745.6193 | 121.95 | 6745.6193 | 0 | 6745.6193 | 7008.3 | 6745.6193 | 0 | 6745.6193 | 927.5 | 6745.6193 | 0
2025-07-19 | 68861.5301 | 9179.36 | 6886.153 | 0 | 6886.153 | 0 | 6886.153 | 0 | 6886.153 | 0 | 6886.153 | 121.95 | 6886.153 | 0 | 6886.153 | 7008.3 | 6886.153 | 0 | 6886.153 | 927.5 | 6886.153 | 0
2025-07-20 | 70266.8675 | 9179.36 | 7026.6867 | 0 | 7026.6867 | 0 | 7026.6867 | 0 | 7026.6867 | 0 | 7026.6867 | 121.95 | 7026.6867 | 0 | 7026.6867 | 7008.3 | 7026.6867 | 0 | 7026.6867 | 927.5 | 7026.6867 | 0
2025-07-21 | 80563.492 | 9179.36 | 8056.3492 | 0 | 8056.3492 | 0 | 8056.3492 | 0 | 8056.3492 | 0 | 8056.3492 | 121.95 | 8056.3492 | 0 | 8056.3492 | 7008.3 | 8056.3492 | 0 | 8056.3492 | 927.5 | 8056.3492 | 0
2025-07-22 | 90860.1166 | 9179.36 | 9086.0117 | 0 | 9086.0117 | 0 | 9086.0117 | 0 | 9086.0117 | 0 | 9086.0117 | 121.95 | 9086.0117 | 0 | 9086.0117 | 7008.3 | 9086.0117 | 0 | 9086.0117 | 927.5 | 9086.0117 | 0
2025-07-23 | 101156.7412 | 9179.36 | 10115.6741 | 0 | 10115.6741 | 0 | 10115.6741 | 0 | 10115.6741 | 0 | 10115.6741 | 121.95 | 10115.6741 | 0 | 10115.6741 | 7008.3 | 10115.6741 | 0 | 10115.6741 | 927.5 | 10115.6741 | 0
2025-07-24 | 111453.3657 | 9239.36 | 11145.3366 | 0 | 11145.3366 | 0 | 11145.3366 | 0 | 11145.3366 | 0 | 11145.3366 | 121.95 | 11145.3366 | 0 | 11145.3366 | 7008.3 | 11145.3366 | 0 | 11145.3366 | 927.5 | 11145.3366 | 0
2025-07-25 | 121749.9903 | 9239.36 | 12174.999 | 0 | 12174.999 | 0 | 12174.999 | 0 | 12174.999 | 0 | 12174.999 | 121.95 | 12174.999 | 0 | 12174.999 | 7008.3 | 12174.999 | 0 | 12174.999 | 927.5 | 12174.999 | 0
2025-07-26 | 132046.6149 | 9253.98 | 13204.6615 | 0 | 13204.6615 | 0 | 13204.6615 | 0 | 13204.6615 | 0 | 13204.6615 | 121.95 | 13204.6615 | 0 | 13204.6615 | 7008.3 | 13204.6615 | 0 | 13204.6615 | 927.5 | 13204.6615 | 0
2025-07-27 | 142343.2394 | 9253.98 | 14234.3239 | 0 | 14234.3239 | 0 | 14234.3239 | 0 | 14234.3239 | 0 | 14234.3239 | 121.95 | 14234.3239 | 0 | 14234.3239 | 7008.3 | 14234.3239 | 0 | 14234.3239 | 927.5 | 14234.3239 | 0
2025-07-28 | 152639.864 | 9253.98 | 15263.9864 | 0 | 15263.9864 | 0 | 15263.9864 | 0 | 15263.9864 | 0 | 15263.9864 | 121.95 | 15263.9864 | 0 | 15263.9864 | 7008.3 | 15263.9864 | 0 | 15263.9864 | 927.5 | 15263.9864 | 0
2025-07-29 | 162936.4886 | 9253.98 | 16293.6489 | 0 | 16293.6489 | 0 | 16293.6489 | 0 | 16293.6489 | 0 | 16293.6489 | 121.95 | 16293.6489 | 0 | 16293.6489 | 7008.3 | 16293.6489 | 0 | 16293.6489 | 927.5 | 16293.6489 | 0
2025-07-30 | 173233.1131 | 14925.16 | 17323.3113 | 0 | 17323.3113 | 0 | 17323.3113 | 0 | 17323.3113 | 0 | 17323.3113 | 5793.13 | 17323.3113 | 0 | 17323.3113 | 7008.3 | 17323.3113 | 0 | 17323.3113 | 927.5 | 17323.3113 | 0
2025-07-31 | 183529.7377 | 40570.58 | 18352.9738 | 23367.75 | 18352.9738 | 0 | 18352.9738 | 0 | 18352.9738 | 0 | 18352.9738 | 5793.13 | 18352.9738 | 2277.67 | 18352.9738 | 7008.3 | 18352.9738 | 0 | 18352.9738 | 927.5 | 18352.9738 | 0
2025-08-01 | 193826.3623 | 40716.18 | 19382.6362 | 23367.75 | 19382.6362 | 0 | 19382.6362 | 0 | 19382.6362 | 0 | 19382.6362 | 5830.43 | 19382.6362 | 2277.67 | 19382.6362 | 7008.3 | 19382.6362 | 0 | 19382.6362 | 927.5 | 19382.6362 | 0
2025-08-02 | 204122.9868 | 40716.18 | 20412.2987 | 23367.75 | 20412.2987 | 0 | 20412.2987 | 0 | 20412.2987 | 0 | 20412.2987 | 5830.43 | 20412.2987 | 2277.67 | 20412.2987 | 7008.3 | 20412.2987 | 0 | 20412.2987 | 927.5 | 20412.2987 | 0
2025-08-03 | 214419.6114 | 40716.18 | 21441.9611 | 23367.75 | 21441.9611 | 0 | 21441.9611 | 0 | 21441.9611 | 0 | 21441.9611 | 5830.43 | 21441.9611 | 2277.67 | 21441.9611 | 7008.3 | 21441.9611 | 0 | 21441.9611 | 927.5 | 21441.9611 | 0
2025-08-04 | 224716.236 | 40716.18 | 22471.6236 | 23367.75 | 22471.6236 | 0 | 22471.6236 | 0 | 22471.6236 | 0 | 22471.6236 | 5830.43 | 22471.6236 | 2277.67 | 22471.6236 | 7008.3 | 22471.6236 | 0 | 22471.6236 | 927.5 | 22471.6236 | 0
2025-08-05 | 235012.8605 | 43820.41 | 23501.2861 | 23367.75 | 23501.2861 | 0 | 23501.2861 | 0 | 23501.2861 | 0 | 23501.2861 | 8934.66 | 23501.2861 | 2277.67 | 23501.2861 | 7008.3 | 23501.2861 | 0 | 23501.2861 | 927.5 | 23501.2861 | 0
2025-08-06 | 245309.4851 | 48727.85 | 24530.9485 | 23367.75 | 24530.9485 | 0 | 24530.9485 | 0 | 24530.9485 | 0 | 24530.9485 | 8934.66 | 24530.9485 | 7185.11 | 24530.9485 | 7008.3 | 24530.9485 | 0 | 24530.9485 | 927.5 | 24530.9485 | 0
2025-08-07 | 255606.1097 | 48727.85 | 25560.611 | 23367.75 | 25560.611 | 0 | 25560.611 | 0 | 25560.611 | 0 | 25560.611 | 8934.66 | 25560.611 | 7185.11 | 25560.611 | 7008.3 | 25560.611 | 0 | 25560.611 | 927.5 | 25560.611 | 0
2025-08-08 | 265902.7343 | 48727.85 | 26590.2734 | 23367.75 | 26590.2734 | 0 | 26590.2734 | 0 | 26590.2734 | 0 | 26590.2734 | 8934.66 | 26590.2734 | 7185.11 | 26590.2734 | 7008.3 | 26590.2734 | 0 | 26590.2734 | 927.5 | 26590.2734 | 0
2025-08-09 | 276199.3588 | 48727.85 | 27619.9359 | 23367.75 | 27619.9359 | 0 | 27619.9359 | 0 | 27619.9359 | 0 | 27619.9359 | 8934.66 | 27619.9359 | 7185.11 | 27619.9359 | 7008.3 | 27619.9359 | 0 | 27619.9359 | 927.5 | 27619.9359 | 0
2025-08-10 | 286495.9834 | 48727.85 | 28649.5983 | 23367.75 | 28649.5983 | 0 | 28649.5983 | 0 | 28649.5983 | 0 | 28649.5983 | 8934.66 | 28649.5983 | 7185.11 | 28649.5983 | 7008.3 | 28649.5983 | 0 | 28649.5983 | 927.5 | 28649.5983 | 0
2025-08-11 | 296792.608 | 48727.85 | 29679.2608 | 23367.75 | 29679.2608 | 0 | 29679.2608 | 0 | 29679.2608 | 0 | 29679.2608 | 8934.66 | 29679.2608 | 7185.11 | 29679.2608 | 7008.3 | 29679.2608 | 0 | 29679.2608 | 927.5 | 29679.2608 | 0
2025-08-12 | 307089.2325 | 50435.47 | 30708.9233 | 23367.75 | 30708.9233 | 0 | 30708.9233 | 0 | 30708.9233 | 0 | 30708.9233 | 8934.66 | 30708.9233 | 8892.73 | 30708.9233 | 7008.3 | 30708.9233 | 0 | 30708.9233 | 927.5 | 30708.9233 | 0
2025-08-13 | 317385.8571 | 50435.47 | 31738.5857 | 23367.75 | 31738.5857 | 0 | 31738.5857 | 0 | 31738.5857 | 0 | 31738.5857 | 8934.66 | 31738.5857 | 8892.73 | 31738.5857 | 7008.3 | 31738.5857 | 0 | 31738.5857 | 927.5 | 31738.5857 | 0
2025-08-14 | 327682.4817 | 51735.47 | 32768.2482 | 23367.75 | 32768.2482 | 0 | 32768.2482 | 0 | 32768.2482 | 0 | 32768.2482 | 8934.66 | 32768.2482 | 8892.73 | 32768.2482 | 8308.3 | 32768.2482 | 0 | 32768.2482 | 927.5 | 32768.2482 | 0
2025-08-15 | 337979.1062 | 52831.39 | 33797.9106 | 23367.75 | 33797.9106 | 0 | 33797.9106 | 0 | 33797.9106 | 0 | 33797.9106 | 9998.66 | 33797.9106 | 8892.73 | 33797.9106 | 8340.22 | 33797.9106 | 0 | 33797.9106 | 927.5 | 33797.9106 | 0
2025-08-16 | 348275.7308 | 52831.39 | 34827.5731 | 23367.75 | 34827.5731 | 0 | 34827.5731 | 0 | 34827.5731 | 0 | 34827.5731 | 9998.66 | 34827.5731 | 8892.73 | 34827.5731 | 8340.22 | 34827.5731 | 0 | 34827.5731 | 927.5 | 34827.5731 | 0
2025-08-17 | 358572.3554 | 52831.39 | 35857.2355 | 23367.75 | 35857.2355 | 0 | 35857.2355 | 0 | 35857.2355 | 0 | 35857.2355 | 9998.66 | 35857.2355 | 8892.73 | 35857.2355 | 8340.22 | 35857.2355 | 0 | 35857.2355 | 927.5 | 35857.2355 | 0
2025-08-18 | 368868.9799 | 52831.39 | 36886.898 | 23367.75 | 36886.898 | 0 | 36886.898 | 0 | 36886.898 | 0 | 36886.898 | 9998.66 | 36886.898 | 8892.73 | 36886.898 | 8340.22 | 36886.898 | 0 | 36886.898 | 927.5 | 36886.898 | 0
2025-08-19 | 379165.6045 | 52831.39 | 37916.5604 | 23367.75 | 37916.5604 | 0 | 37916.5604 | 0 | 37916.5604 | 0 | 37916.5604 | 9998.66 | 37916.5604 | 8892.73 | 37916.5604 | 8340.22 | 37916.5604 | 0 | 37916.5604 | 927.5 | 37916.5604 | 0
2025-08-20 | 389462.2291 | 56637.68 | 38946.2229 | 23367.75 | 38946.2229 | 0 | 38946.2229 | 0 | 38946.2229 | 0 | 38946.2229 | 9998.66 | 38946.2229 | 12699.02 | 38946.2229 | 8340.22 | 38946.2229 | 0 | 38946.2229 | 927.5 | 38946.2229 | 0
2025-08-21 | 399758.8536 | 56637.68 | 39975.8854 | 23367.75 | 39975.8854 | 0 | 39975.8854 | 0 | 39975.8854 | 0 | 39975.8854 | 9998.66 | 39975.8854 | 12699.02 | 39975.8854 | 8340.22 | 39975.8854 | 0 | 39975.8854 | 927.5 | 39975.8854 | 0
2025-08-22 | 410055.4782 | 56637.68 | 41005.5478 | 23367.75 | 41005.5478 | 0 | 41005.5478 | 0 | 41005.5478 | 0 | 41005.5478 | 9998.66 | 41005.5478 | 12699.02 | 41005.5478 | 8340.22 | 41005.5478 | 0 | 41005.5478 | 927.5 | 41005.5478 | 0
2025-08-23 | 418946.7654 | 56637.68 | 41894.6765 | 23367.75 | 41894.6765 | 0 | 41894.6765 | 0 | 41894.6765 | 0 | 41894.6765 | 9998.66 | 41894.6765 | 12699.02 | 41894.6765 | 8340.22 | 41894.6765 | 0 | 41894.6765 | 927.5 | 41894.6765 | 0
2025-08-24 | 427838.0526 | 56637.68 | 42783.8053 | 23367.75 | 42783.8053 | 0 | 42783.8053 | 0 | 42783.8053 | 0 | 42783.8053 | 9998.66 | 42783.8053 | 12699.02 | 42783.8053 | 8340.22 | 42783.8053 | 0 | 42783.8053 | 927.5 | 42783.8053 | 0
2025-08-25 | 436729.3398 | 116880.18 | 43672.934 | 77310.25 | 43672.934 | 0 | 43672.934 | 0 | 43672.934 | 0 | 43672.934 | 9998.66 | 43672.934 | 12699.02 | 43672.934 | 14640.22 | 43672.934 | 0 | 43672.934 | 927.5 | 43672.934 | 0
2025-08-26 | 445620.6271 | 116880.18 | 44562.0627 | 77310.25 | 44562.0627 | 0 | 44562.0627 | 0 | 44562.0627 | 0 | 44562.0627 | 9998.66 | 44562.0627 | 12699.02 | 44562.0627 | 14640.22 | 44562.0627 | 0 | 44562.0627 | 927.5 | 44562.0627 | 0
2025-08-27 | 454511.9143 | 124559.72 | 45451.1914 | 77310.25 | 45451.1914 | 0 | 45451.1914 | 0 | 45451.1914 | 0 | 45451.1914 | 15099.52 | 45451.1914 | 15277.7 | 45451.1914 | 14640.22 | 45451.1914 | 0 | 45451.1914 | 927.5 | 45451.1914 | 0
2025-08-28 | 463403.2015 | 124559.72 | 46340.3202 | 77310.25 | 46340.3202 | 0 | 46340.3202 | 0 | 46340.3202 | 0 | 46340.3202 | 15099.52 | 46340.3202 | 15277.7 | 46340.3202 | 14640.22 | 46340.3202 | 0 | 46340.3202 | 927.5 | 46340.3202 | 0
2025-08-29 | 472294.4887 | 127138.4 | 47229.4489 | 77310.25 | 47229.4489 | 0 | 47229.4489 | 0 | 47229.4489 | 0 | 47229.4489 | 15099.52 | 47229.4489 | 17856.38 | 47229.4489 | 14640.22 | 47229.4489 | 0 | 47229.4489 | 927.5 | 47229.4489 | 0
2025-08-30 | 481185.7759 | 127138.4 | 48118.5776 | 77310.25 | 48118.5776 | 0 | 48118.5776 | 0 | 48118.5776 | 0 | 48118.5776 | 15099.52 | 48118.5776 | 17856.38 | 48118.5776 | 14640.22 | 48118.5776 | 0 | 48118.5776 | 927.5 | 48118.5776 | 0
2025-08-31 | 490077.0632 | 141943.27 | 49007.7063 | 77310.25 | 49007.7063 | 0 | 49007.7063 | 0 | 49007.7063 | 0 | 49007.7063 | 15099.52 | 49007.7063 | 32661.25 | 49007.7063 | 14640.22 | 49007.7063 | 0 | 49007.7063 | 927.5 | 49007.7063 | 0
2025-09-01 | 498968.3504 | 141943.27 | 49896.835 | 77310.25 | 49896.835 | 0 | 49896.835 | 0 | 49896.835 | 0 | 49896.835 | 15099.52 | 49896.835 | 32661.25 | 49896.835 | 14640.22 | 49896.835 | 0 | 49896.835 | 927.5 | 49896.835 | 0
2025-09-02 | 499245.4108 | 144616.3 | 49924.5411 | 77310.25 | 49924.5411 | 0 | 49924.5411 | 0 | 49924.5411 | 0 | 49924.5411 | 17772.55 | 49924.5411 | 32661.25 | 49924.5411 | 14640.22 | 49924.5411 | 0 | 49924.5411 | 927.5 | 49924.5411 | 0
2025-09-03 | 499522.4711 | 398048.8 | 49952.2471 | 330517.75 | 49952.2471 | 0 | 49952.2471 | 0 | 49952.2471 | 0 | 49952.2471 | 17772.55 | 49952.2471 | 32661.25 | 49952.2471 | 14865.22 | 49952.2471 | 0 | 49952.2471 | 927.5 | 49952.2471 | 0
2025-09-04 | 499799.5315 | 398048.8 | 49979.9532 | 330517.75 | 49979.9532 | 0 | 49979.9532 | 0 | 49979.9532 | 0 | 49979.9532 | 17772.55 | 49979.9532 | 32661.25 | 49979.9532 | 14865.22 | 49979.9532 | 0 | 49979.9532 | 927.5 | 49979.9532 | 0
2025-09-05 | 500076.5919 | 400603.47 | 50007.6592 | 330517.75 | 50007.6592 | 0 | 50007.6592 | 0 | 50007.6592 | 0 | 50007.6592 | 17772.55 | 50007.6592 | 35215.92 | 50007.6592 | 14865.22 | 50007.6592 | 0 | 50007.6592 | 927.5 | 50007.6592 | 0
2025-09-06 | 500353.6523 | 400603.47 | 50035.3652 | 330517.75 | 50035.3652 | 0 | 50035.3652 | 0 | 50035.3652 | 0 | 50035.3652 | 17772.55 | 50035.3652 | 35215.92 | 50035.3652 | 14865.22 | 50035.3652 | 0 | 50035.3652 | 927.5 | 50035.3652 | 0
2025-09-07 | 500630.7126 | 400603.47 | 50063.0713 | 330517.75 | 50063.0713 | 0 | 50063.0713 | 0 | 50063.0713 | 0 | 50063.0713 | 17772.55 | 50063.0713 | 35215.92 | 50063.0713 | 14865.22 | 50063.0713 | 0 | 50063.0713 | 927.5 | 50063.0713 | 0
2025-09-08 | 500907.773 | 403316.93 | 50090.7773 | 330517.75 | 50090.7773 | 0 | 50090.7773 | 0 | 50090.7773 | 0 | 50090.7773 | 17772.55 | 50090.7773 | 37929.38 | 50090.7773 | 14865.22 | 50090.7773 | 0 | 50090.7773 | 927.5 | 50090.7773 | 0
2025-09-09 | 501184.8334 | 405632.09 | 50118.4833 | 330517.75 | 50118.4833 | 0 | 50118.4833 | 0 | 50118.4833 | 0 | 50118.4833 | 17772.55 | 50118.4833 | 40057.85 | 50118.4833 | 14865.22 | 50118.4833 | 0 | 50118.4833 | 927.5 | 50118.4833 | 0
2025-09-10 | 501461.8938 | 405632.09 | 50146.1894 | 330517.75 | 50146.1894 | 0 | 50146.1894 | 0 | 50146.1894 | 0 | 50146.1894 | 17772.55 | 50146.1894 | 40057.85 | 50146.1894 | 14865.22 | 50146.1894 | 0 | 50146.1894 | 927.5 | 50146.1894 | 0
2025-09-11 | 501738.9541 | 406752.11 | 50173.8954 | 330517.75 | 50173.8954 | 0 | 50173.8954 | 0 | 50173.8954 | 0 | 50173.8954 | 18836.55 | 50173.8954 | 40057.85 | 50173.8954 | 14897.14 | 50173.8954 | 0 | 50173.8954 | 951.6 | 50173.8954 | 0
2025-09-12 | 502016.0145 | 406752.11 | 50201.6015 | 330517.75 | 50201.6015 | 0 | 50201.6015 | 0 | 50201.6015 | 0 | 50201.6015 | 18836.55 | 50201.6015 | 40057.85 | 50201.6015 | 14897.14 | 50201.6015 | 0 | 50201.6015 | 951.6 | 50201.6015 | 0
2025-09-13 | 502293.0749 | 406752.11 | 50229.3075 | 330517.75 | 50229.3075 | 0 | 50229.3075 | 0 | 50229.3075 | 0 | 50229.3075 | 18836.55 | 50229.3075 | 40057.85 | 50229.3075 | 14897.14 | 50229.3075 | 0 | 50229.3075 | 951.6 | 50229.3075 | 0
2025-09-14 | 502570.1353 | 406752.11 | 50257.0135 | 330517.75 | 50257.0135 | 0 | 50257.0135 | 0 | 50257.0135 | 0 | 50257.0135 | 18836.55 | 50257.0135 | 40057.85 | 50257.0135 | 14897.14 | 50257.0135 | 0 | 50257.0135 | 951.6 | 50257.0135 | 0
2025-09-15 | 502847.1957 | 411893.49 | 50284.7196 | 330517.75 | 50284.7196 | 0 | 50284.7196 | 0 | 50284.7196 | 0 | 50284.7196 | 18836.55 | 50284.7196 | 45199.23 | 50284.7196 | 14897.14 | 50284.7196 | 0 | 50284.7196 | 951.6 | 50284.7196 | 0
2025-09-16 | 503124.256 | 411893.49 | 50312.4256 | 330517.75 | 50312.4256 | 0 | 50312.4256 | 0 | 50312.4256 | 0 | 50312.4256 | 18836.55 | 50312.4256 | 45199.23 | 50312.4256 | 14897.14 | 50312.4256 | 0 | 50312.4256 | 951.6 | 50312.4256 | 0
2025-09-17 | 503401.3164 | 411893.49 | 50340.1316 | 330517.75 | 50340.1316 | 0 | 50340.1316 | 0 | 50340.1316 | 0 | 50340.1316 | 18836.55 | 50340.1316 | 45199.23 | 50340.1316 | 14897.14 | 50340.1316 | 0 | 50340.1316 | 951.6 | 50340.1316 | 0
2025-09-18 | 503678.3768 | 411893.49 | 50367.8377 | 330517.75 | 50367.8377 | 0 | 50367.8377 | 0 | 50367.8377 | 0 | 50367.8377 | 18836.55 | 50367.8377 | 45199.23 | 50367.8377 | 14897.14 | 50367.8377 | 0 | 50367.8377 | 951.6 | 50367.8377 | 0
2025-09-19 | 503955.4372 | 411893.49 | 50395.5437 | 330517.75 | 50395.5437 | 0 | 50395.5437 | 0 | 50395.5437 | 0 | 50395.5437 | 18836.55 | 50395.5437 | 45199.23 | 50395.5437 | 14897.14 | 50395.5437 | 0 | 50395.5437 | 951.6 | 50395.5437 | 0
2025-09-20 | 504232.4975 | 411893.49 | 50423.2498 | 330517.75 | 50423.2498 | 0 | 50423.2498 | 0 | 50423.2498 | 0 | 50423.2498 | 18836.55 | 50423.2498 | 45199.23 | 50423.2498 | 14897.14 | 50423.2498 | 0 | 50423.2498 | 951.6 | 50423.2498 | 0
2025-09-21 | 504509.5579 | 411893.49 | 50450.9558 | 330517.75 | 50450.9558 | 0 | 50450.9558 | 0 | 50450.9558 | 0 | 50450.9558 | 18836.55 | 50450.9558 | 45199.23 | 50450.9558 | 14897.14 | 50450.9558 | 0 | 50450.9558 | 951.6 | 50450.9558 | 0
2025-09-22 | 504786.6183 | 411893.49 | 50478.6618 | 330517.75 | 50478.6618 | 0 | 50478.6618 | 0 | 50478.6618 | 0 | 50478.6618 | 18836.55 | 50478.6618 | 45199.23 | 50478.6618 | 14897.14 | 50478.6618 | 0 | 50478.6618 | 951.6 | 50478.6618 | 0
2025-09-23 | 505063.6787 | 414472.17 | 50506.3679 | 330517.75 | 50506.3679 | 0 | 50506.3679 | 0 | 50506.3679 | 0 | 50506.3679 | 18836.55 | 50506.3679 | 47777.91 | 50506.3679 | 14897.14 | 50506.3679 | 0 | 50506.3679 | 951.6 | 50506.3679 | 0
2025-09-24 | 505340.739 | 422286.98 | 50534.0739 | 330517.75 | 50534.0739 | 0 | 50534.0739 | 0 | 50534.0739 | 0 | 50534.0739 | 26610.44 | 50534.0739 | 47777.91 | 50534.0739 | 14897.14 | 50534.0739 | 0 | 50534.0739 | 951.6 | 50534.0739 | 0
2025-09-25 | 505617.7994 | 432547.64 | 50561.7799 | 330517.75 | 50561.7799 | 0 | 50561.7799 | 0 | 50561.7799 | 0 | 50561.7799 | 26610.44 | 50561.7799 | 58038.57 | 50561.7799 | 14897.14 | 50561.7799 | 0 | 50561.7799 | 951.6 | 50561.7799 | 0
2025-09-26 | 505894.8598 | 438245.3 | 50589.486 | 330517.75 | 50589.486 | 0 | 50589.486 | 0 | 50589.486 | 0 | 50589.486 | 26610.44 | 50589.486 | 63736.23 | 50589.486 | 14897.14 | 50589.486 | 0 | 50589.486 | 951.6 | 50589.486 | 0
2025-09-27 | 506171.9202 | 438245.3 | 50617.192 | 330517.75 | 50617.192 | 0 | 50617.192 | 0 | 50617.192 | 0 | 50617.192 | 26610.44 | 50617.192 | 63736.23 | 50617.192 | 14897.14 | 50617.192 | 0 | 50617.192 | 951.6 | 50617.192 | 0
2025-09-28 | 506448.9806 | 438245.3 | 50644.8981 | 330517.75 | 50644.8981 | 0 | 50644.8981 | 0 | 50644.8981 | 0 | 50644.8981 | 26610.44 | 50644.8981 | 63736.23 | 50644.8981 | 14897.14 | 50644.8981 | 0 | 50644.8981 | 951.6 | 50644.8981 | 0
2025-09-29 | 506726.0409 | 453337.55 | 50672.6041 | 330517.75 | 50672.6041 | 0 | 50672.6041 | 0 | 50672.6041 | 0 | 50672.6041 | 29288.97 | 50672.6041 | 75863.08 | 50672.6041 | 14910.82 | 50672.6041 | 0 | 50672.6041 | 951.6 | 50672.6041 | 0
2025-09-30 | 507003.1013 | 458496.83 | 50700.3101 | 330517.75 | 50700.3101 | 0 | 50700.3101 | 0 | 50700.3101 | 0 | 50700.3101 | 29288.97 | 50700.3101 | 80987.59 | 50700.3101 | 14910.82 | 50700.3101 | 0 | 50700.3101 | 951.6 | 50700.3101 | 0
2025-10-01 | 507280.1617 | 458606.74 | 50728.0162 | 330517.75 | 50728.0162 | 0 | 50728.0162 | 0 | 50728.0162 | 0 | 50728.0162 | 29288.97 | 50728.0162 | 80987.59 | 50728.0162 | 14910.82 | 50728.0162 | 0 | 50728.0162 | 951.6 | 50728.0162 | 0
2025-10-02 | 507557.2221 | 458606.74 | 50755.7222 | 330517.75 | 50755.7222 | 0 | 50755.7222 | 0 | 50755.7222 | 0 | 50755.7222 | 29288.97 | 50755.7222 | 80987.59 | 50755.7222 | 14910.82 | 50755.7222 | 0 | 50755.7222 | 951.6 | 50755.7222 | 0
2025-10-03 | 507834.2824 | 458606.74 | 50783.4282 | 330517.75 | 50783.4282 | 0 | 50783.4282 | 0 | 50783.4282 | 0 | 50783.4282 | 29288.97 | 50783.4282 | 80987.59 | 50783.4282 | 14910.82 | 50783.4282 | 0 | 50783.4282 | 951.6 | 50783.4282 | 0
2025-10-04 | 508111.3428 | 462609.63 | 50811.1343 | 330517.75 | 50811.1343 | 0 | 50811.1343 | 0 | 50811.1343 | 0 | 50811.1343 | 33291.86 | 50811.1343 | 80987.59 | 50811.1343 | 14910.82 | 50811.1343 | 0 | 50811.1343 | 951.6 | 50811.1343 | 0
2025-10-05 | 508388.4032 | 462609.63 | 50838.8403 | 330517.75 | 50838.8403 | 0 | 50838.8403 | 0 | 50838.8403 | 0 | 50838.8403 | 33291.86 | 50838.8403 | 80987.59 | 50838.8403 | 14910.82 | 50838.8403 | 0 | 50838.8403 | 951.6 | 50838.8403 | 0
2025-10-06 | 508665.4636 | 462935.23 | 50866.5464 | 330517.75 | 50866.5464 | 0 | 50866.5464 | 0 | 50866.5464 | 0 | 50866.5464 | 33550.24 | 50866.5464 | 80987.59 | 50866.5464 | 14910.82 | 50866.5464 | 0 | 50866.5464 | 951.6 | 50866.5464 | 0
2025-10-07 | 508942.5239 | 464357.82 | 50894.2524 | 330517.75 | 50894.2524 | 0 | 50894.2524 | 0 | 50894.2524 | 0 | 50894.2524 | 33550.24 | 50894.2524 | 82410.18 | 50894.2524 | 14910.82 | 50894.2524 | 0 | 50894.2524 | 951.6 | 50894.2524 | 0
2025-10-08 | 509219.5843 | 464357.82 | 50921.9584 | 330517.75 | 50921.9584 | 0 | 50921.9584 | 0 | 50921.9584 | 0 | 50921.9584 | 33550.24 | 50921.9584 | 82410.18 | 50921.9584 | 14910.82 | 50921.9584 | 0 | 50921.9584 | 951.6 | 50921.9584 | 0
2025-10-09 | 509496.6447 | 464357.82 | 50949.6645 | 330517.75 | 50949.6645 | 0 | 50949.6645 | 0 | 50949.6645 | 0 | 50949.6645 | 33550.24 | 50949.6645 | 82410.18 | 50949.6645 | 14910.82 | 50949.6645 | 0 | 50949.6645 | 951.6 | 50949.6645 | 0
2025-10-10 | 509773.7051 | 464357.82 | 50977.3705 | 330517.75 | 50977.3705 | 0 | 50977.3705 | 0 | 50977.3705 | 0 | 50977.3705 | 33550.24 | 50977.3705 | 82410.18 | 50977.3705 | 14910.82 | 50977.3705 | 0 | 50977.3705 | 951.6 | 50977.3705 | 0
2025-10-11 | 510050.7655 | 464357.82 | 51005.0765 | 330517.75 | 51005.0765 | 0 | 51005.0765 | 0 | 51005.0765 | 0 | 51005.0765 | 33550.24 | 51005.0765 | 82410.18 | 51005.0765 | 14910.82 | 51005.0765 | 0 | 51005.0765 | 951.6 | 51005.0765 | 0
2025-10-12 | 510327.8258 | 464357.82 | 51032.7826 | 330517.75 | 51032.7826 | 0 | 51032.7826 | 0 | 51032.7826 | 0 | 51032.7826 | 33550.24 | 51032.7826 | 82410.18 | 51032.7826 | 14910.82 | 51032.7826 | 0 | 51032.7826 | 951.6 | 51032.7826 | 0
2025-10-13 | 510604.8862 | 464357.82 | 51060.4886 | 330517.75 | 51060.4886 | 0 | 51060.4886 | 0 | 51060.4886 | 0 | 51060.4886 | 33550.24 | 51060.4886 | 82410.18 | 51060.4886 | 14910.82 | 51060.4886 | 0 | 51060.4886 | 951.6 | 51060.4886 | 0
2025-10-14 | 510881.9466 | 465326.45 | 51088.1947 | 330517.75 | 51088.1947 | 0 | 51088.1947 | 0 | 51088.1947 | 0 | 51088.1947 | 34518.87 | 51088.1947 | 82410.18 | 51088.1947 | 14910.82 | 51088.1947 | 0 | 51088.1947 | 951.6 | 51088.1947 | 0
2025-10-15 | 511159.007 | 465356.85 | 51115.9007 | 330517.75 | 51115.9007 | 0 | 51115.9007 | 0 | 51115.9007 | 0 | 51115.9007 | 34549.27 | 51115.9007 | 82410.18 | 51115.9007 | 14910.82 | 51115.9007 | 0 | 51115.9007 | 951.6 | 51115.9007 | 0
2025-10-16 | 511436.0673 | 465356.85 | 51143.6067 | 330517.75 | 51143.6067 | 0 | 51143.6067 | 0 | 51143.6067 | 0 | 51143.6067 | 34549.27 | 51143.6067 | 82410.18 | 51143.6067 | 14910.82 | 51143.6067 | 0 | 51143.6067 | 951.6 | 51143.6067 | 0
2025-10-17 | 511713.1277 | 465356.85 | 51171.3128 | 330517.75 | 51171.3128 | 0 | 51171.3128 | 0 | 51171.3128 | 0 | 51171.3128 | 34549.27 | 51171.3128 | 82410.18 | 51171.3128 | 14910.82 | 51171.3128 | 0 | 51171.3128 | 951.6 | 51171.3128 | 0
2025-10-18 | 511990.1881 | 465812.8 | 51199.0188 | 330517.75 | 51199.0188 | 0 | 51199.0188 | 0 | 51199.0188 | 0 | 51199.0188 | 35005.22 | 51199.0188 | 82410.18 | 51199.0188 | 14910.82 | 51199.0188 | 0 | 51199.0188 | 951.6 | 51199.0188 | 0
2025-10-19 | 512267.2485 | 466009.66 | 51226.7248 | 330517.75 | 51226.7248 | 0 | 51226.7248 | 0 | 51226.7248 | 0 | 51226.7248 | 35005.22 | 51226.7248 | 82410.18 | 51226.7248 | 14910.82 | 51226.7248 | 0 | 51226.7248 | 951.6 | 51226.7248 | 0
2025-10-20 | 512544.3088 | 472204.66 | 51254.4309 | 330517.75 | 51254.4309 | 0 | 51254.4309 | 0 | 51254.4309 | 0 | 51254.4309 | 35005.22 | 51254.4309 | 82410.18 | 51254.4309 | 21105.82 | 51254.4309 | 0 | 51254.4309 | 951.6 | 51254.4309 | 0
2025-10-21 | 512821.3692 | 472319.06 | 51282.1369 | 330517.75 | 51282.1369 | 0 | 51282.1369 | 0 | 51282.1369 | 0 | 51282.1369 | 35005.22 | 51282.1369 | 82410.18 | 51282.1369 | 21220.22 | 51282.1369 | 0 | 51282.1369 | 951.6 | 51282.1369 | 0
2025-10-22 | 513098.4296 | 479011.21 | 51309.843 | 330517.75 | 51309.843 | 0 | 51309.843 | 0 | 51309.843 | 0 | 51309.843 | 41697.37 | 51309.843 | 82410.18 | 51309.843 | 21220.22 | 51309.843 | 0 | 51309.843 | 951.6 | 51309.843 | 0
2025-10-23 | 513375.49 | 479253.83 | 51337.549 | 330517.75 | 51337.549 | 0 | 51337.549 | 0 | 51337.549 | 0 | 51337.549 | 41697.37 | 51337.549 | 82410.18 | 51337.549 | 21339.51 | 51337.549 | 0 | 51337.549 | 951.6 | 51337.549 | 0
2025-10-24 | 513652.5504 | 479253.83 | 51365.255 | 330517.75 | 51365.255 | 0 | 51365.255 | 0 | 51365.255 | 0 | 51365.255 | 41697.37 | 51365.255 | 82410.18 | 51365.255 | 21339.51 | 51365.255 | 0 | 51365.255 | 951.6 | 51365.255 | 0
2025-10-25 | 513929.6107 | 479253.83 | 51392.9611 | 330517.75 | 51392.9611 | 0 | 51392.9611 | 0 | 51392.9611 | 0 | 51392.9611 | 41697.37 | 51392.9611 | 82410.18 | 51392.9611 | 21339.51 | 51392.9611 | 0 | 51392.9611 | 951.6 | 51392.9611 | 0
2025-10-26 | 514206.6711 | 479253.83 | 51420.6671 | 330517.75 | 51420.6671 | 0 | 51420.6671 | 0 | 51420.6671 | 0 | 51420.6671 | 41697.37 | 51420.6671 | 82410.18 | 51420.6671 | 21339.51 | 51420.6671 | 0 | 51420.6671 | 951.6 | 51420.6671 | 0
2025-10-27 | 514483.7315 | 479253.83 | 51448.3731 | 330517.75 | 51448.3731 | 0 | 51448.3731 | 0 | 51448.3731 | 0 | 51448.3731 | 41697.37 | 51448.3731 | 82410.18 | 51448.3731 | 21339.51 | 51448.3731 | 0 | 51448.3731 | 951.6 | 51448.3731 | 0
2025-10-28 | 514760.7919 | 482163.07 | 51476.0792 | 330517.75 | 51476.0792 | 0 | 51476.0792 | 0 | 51476.0792 | 0 | 51476.0792 | 44606.61 | 51476.0792 | 82410.18 | 51476.0792 | 21339.51 | 51476.0792 | 0 | 51476.0792 | 951.6 | 51476.0792 | 0
2025-10-29 | 515037.8522 | 485876.56 | 51503.7852 | 330517.75 | 51503.7852 | 0 | 51503.7852 | 0 | 51503.7852 | 0 | 51503.7852 | 44606.61 | 51503.7852 | 86019.06 | 51503.7852 | 21339.51 | 51503.7852 | 0 | 51503.7852 | 951.6 | 51503.7852 | 0
2025-10-30 | 515314.9126 | 548923.21 | 51531.4913 | 330517.75 | 51531.4913 | 0 | 51531.4913 | 0 | 51531.4913 | 0 | 51531.4913 | 44606.61 | 51531.4913 | 149065.71 | 51531.4913 | 21339.51 | 51531.4913 | 0 | 51531.4913 | 951.6 | 51531.4913 | 0
2025-10-31 | 515591.973 | 548923.21 | 51559.1973 | 330517.75 | 51559.1973 | 0 | 51559.1973 | 0 | 51559.1973 | 0 | 51559.1973 | 44606.61 | 51559.1973 | 149065.71 | 51559.1973 | 21339.51 | 51559.1973 | 0 | 51559.1973 | 951.6 | 51559.1973 | 0
2025-11-01 | 515869.0334 | 548923.21 | 51586.9033 | 330517.75 | 51586.9033 | 0 | 51586.9033 | 0 | 51586.9033 | 0 | 51586.9033 | 44606.61 | 51586.9033 | 149065.71 | 51586.9033 | 21339.51 | 51586.9033 | 0 | 51586.9033 | 951.6 | 51586.9033 | 0
2025-11-02 | 516146.0937 | 548923.21 | 51614.6094 | 330517.75 | 51614.6094 | 0 | 51614.6094 | 0 | 51614.6094 | 0 | 51614.6094 | 44606.61 | 51614.6094 | 149065.71 | 51614.6094 | 21339.51 | 51614.6094 | 0 | 51614.6094 | 951.6 | 51614.6094 | 0
2025-11-03 | 516423.1541 | 548923.21 | 51642.3154 | 330517.75 | 51642.3154 | 0 | 51642.3154 | 0 | 51642.3154 | 0 | 51642.3154 | 44606.61 | 51642.3154 | 149065.71 | 51642.3154 | 21339.51 | 51642.3154 | 0 | 51642.3154 | 951.6 | 51642.3154 | 0
2025-11-04 | 516700.2145 | 548923.21 | 51670.0214 | 330517.75 | 51670.0214 | 0 | 51670.0214 | 0 | 51670.0214 | 0 | 51670.0214 | 44606.61 | 51670.0214 | 149065.71 | 51670.0214 | 21339.51 | 51670.0214 | 0 | 51670.0214 | 951.6 | 51670.0214 | 0
2025-11-05 | 516977.2749 | 548923.21 | 51697.7275 | 330517.75 | 51697.7275 | 0 | 51697.7275 | 0 | 51697.7275 | 0 | 51697.7275 | 44606.61 | 51697.7275 | 149065.71 | 51697.7275 | 21339.51 | 51697.7275 | 0 | 51697.7275 | 951.6 | 51697.7275 | 0
2025-11-06 | 517254.3352 | 548939.23 | 51725.4335 | 330517.75 | 51725.4335 | 0 | 51725.4335 | 0 | 51725.4335 | 0 | 51725.4335 | 44606.61 | 51725.4335 | 149065.71 | 51725.4335 | 21355.53 | 51725.4335 | 0 | 51725.4335 | 951.6 | 51725.4335 | 0
2025-11-07 | 517531.3956 | 548939.23 | 51753.1396 | 330517.75 | 51753.1396 | 0 | 51753.1396 | 0 | 51753.1396 | 0 | 51753.1396 | 44606.61 | 51753.1396 | 149065.71 | 51753.1396 | 21355.53 | 51753.1396 | 0 | 51753.1396 | 951.6 | 51753.1396 | 0
2025-11-08 | 517808.456 | 548939.23 | 51780.8456 | 330517.75 | 51780.8456 | 0 | 51780.8456 | 0 | 51780.8456 | 0 | 51780.8456 | 44606.61 | 51780.8456 | 149065.71 | 51780.8456 | 21355.53 | 51780.8456 | 0 | 51780.8456 | 951.6 | 51780.8456 | 0
2025-11-09 | 518085.5164 | 548939.23 | 51808.5516 | 330517.75 | 51808.5516 | 0 | 51808.5516 | 0 | 51808.5516 | 0 | 51808.5516 | 44606.61 | 51808.5516 | 149065.71 | 51808.5516 | 21355.53 | 51808.5516 | 0 | 51808.5516 | 951.6 | 51808.5516 | 0
2025-11-10 | 518362.5768 | 549269.98 | 51836.2577 | 330517.75 | 51836.2577 | 0 | 51836.2577 | 0 | 51836.2577 | 0 | 51836.2577 | 44606.61 | 51836.2577 | 149065.71 | 51836.2577 | 21686.28 | 51836.2577 | 0 | 51836.2577 | 951.6 | 51836.2577 | 0
2025-11-11 | 518639.6371 | 552234.29 | 51863.9637 | 330517.75 | 51863.9637 | 0 | 51863.9637 | 0 | 51863.9637 | 0 | 51863.9637 | 47570.92 | 51863.9637 | 149065.71 | 51863.9637 | 21686.28 | 51863.9637 | 0 | 51863.9637 | 951.6 | 51863.9637 | 0
2025-11-12 | 518916.6975 | 552234.29 | 51891.6698 | 330517.75 | 51891.6698 | 0 | 51891.6698 | 0 | 51891.6698 | 0 | 51891.6698 | 47570.92 | 51891.6698 | 149065.71 | 51891.6698 | 21686.28 | 51891.6698 | 0 | 51891.6698 | 951.6 | 51891.6698 | 0
2025-11-13 | 519193.7579 | 552234.29 | 51919.3758 | 330517.75 | 51919.3758 | 0 | 51919.3758 | 0 | 51919.3758 | 0 | 51919.3758 | 47570.92 | 51919.3758 | 149065.71 | 51919.3758 | 21686.28 | 51919.3758 | 0 | 51919.3758 | 951.6 | 51919.3758 | 0
2025-11-14 | 519470.8183 | 552234.29 | 51947.0818 | 330517.75 | 51947.0818 | 0 | 51947.0818 | 0 | 51947.0818 | 0 | 51947.0818 | 47570.92 | 51947.0818 | 149065.71 | 51947.0818 | 21686.28 | 51947.0818 | 0 | 51947.0818 | 951.6 | 51947.0818 | 0
2025-11-15 | 519747.8786 | 552234.29 | 51974.7879 | 330517.75 | 51974.7879 | 0 | 51974.7879 | 0 | 51974.7879 | 0 | 51974.7879 | 47570.92 | 51974.7879 | 149065.71 | 51974.7879 | 21686.28 | 51974.7879 | 0 | 51974.7879 | 951.6 | 51974.7879 | 0
2025-11-16 | 520024.939 | 552234.29 | 52002.4939 | 330517.75 | 52002.4939 | 0 | 52002.4939 | 0 | 52002.4939 | 0 | 52002.4939 | 47570.92 | 52002.4939 | 149065.71 | 52002.4939 | 21686.28 | 52002.4939 | 0 | 52002.4939 | 951.6 | 52002.4939 | 0
2025-11-17 | 520301.9994 | 552234.29 | 52030.1999 | 330517.75 | 52030.1999 | 0 | 52030.1999 | 0 | 52030.1999 | 0 | 52030.1999 | 47570.92 | 52030.1999 | 149065.71 | 52030.1999 | 21686.28 | 52030.1999 | 0 | 52030.1999 | 951.6 | 52030.1999 | 0
2025-11-18 | 520579.0598 | 552234.29 | 52057.906 | 330517.75 | 52057.906 | 0 | 52057.906 | 0 | 52057.906 | 0 | 52057.906 | 47570.92 | 52057.906 | 149065.71 | 52057.906 | 21686.28 | 52057.906 | 0 | 52057.906 | 951.6 | 52057.906 | 0
2025-11-19 | 520856.1201 | 557335.15 | 52085.612 | 330517.75 | 52085.612 | 0 | 52085.612 | 0 | 52085.612 | 0 | 52085.612 | 52671.78 | 52085.612 | 149065.71 | 52085.612 | 21686.28 | 52085.612 | 0 | 52085.612 | 951.6 | 52085.612 | 0
2025-11-20 | 521133.1805 | 557335.15 | 52113.3181 | 330517.75 | 52113.3181 | 0 | 52113.3181 | 0 | 52113.3181 | 0 | 52113.3181 | 52671.78 | 52113.3181 | 149065.71 | 52113.3181 | 21686.28 | 52113.3181 | 0 | 52113.3181 | 951.6 | 52113.3181 | 0
2025-11-21 | 521410.2409 | 557335.15 | 52141.0241 | 330517.75 | 52141.0241 | 0 | 52141.0241 | 0 | 52141.0241 | 0 | 52141.0241 | 52671.78 | 52141.0241 | 149065.71 | 52141.0241 | 21686.28 | 52141.0241 | 0 | 52141.0241 | 951.6 | 52141.0241 | 0
2025-11-22 | 521687.3013 | 557335.15 | 52168.7301 | 330517.75 | 52168.7301 | 0 | 52168.7301 | 0 | 52168.7301 | 0 | 52168.7301 | 52671.78 | 52168.7301 | 149065.71 | 52168.7301 | 21686.28 | 52168.7301 | 0 | 52168.7301 | 951.6 | 52168.7301 | 0
2025-11-23 | 521964.3617 | 557335.15 | 52196.4362 | 330517.75 | 52196.4362 | 0 | 52196.4362 | 0 | 52196.4362 | 0 | 52196.4362 | 52671.78 | 52196.4362 | 149065.71 | 52196.4362 | 21686.28 | 52196.4362 | 0 | 52196.4362 | 951.6 | 52196.4362 | 0
2025-11-24 | 522241.422 | 563049.59 | 52224.1422 | 330517.75 | 52224.1422 | 0 | 52224.1422 | 0 | 52224.1422 | 0 | 52224.1422 | 52671.78 | 52224.1422 | 151922.93 | 52224.1422 | 21686.28 | 52224.1422 | 0 | 52224.1422 | 951.6 | 52224.1422 | 0
2025-11-25 | 522518.4824 | 563049.59 | 52251.8482 | 330517.75 | 52251.8482 | 0 | 52251.8482 | 0 | 52251.8482 | 0 | 52251.8482 | 52671.78 | 52251.8482 | 151922.93 | 52251.8482 | 21686.28 | 52251.8482 | 0 | 52251.8482 | 951.6 | 52251.8482 | 0
2025-11-26 | 522795.5428 | 575479.59 | 52279.5543 | 330517.75 | 52279.5543 | 0 | 52279.5543 | 0 | 52279.5543 | 0 | 52279.5543 | 62801.78 | 52279.5543 | 151922.93 | 52279.5543 | 23986.28 | 52279.5543 | 0 | 52279.5543 | 951.6 | 52279.5543 | 0
2025-11-27 | 523072.6032 | 575479.59 | 52307.2603 | 330517.75 | 52307.2603 | 0 | 52307.2603 | 0 | 52307.2603 | 0 | 52307.2603 | 62801.78 | 52307.2603 | 151922.93 | 52307.2603 | 23986.28 | 52307.2603 | 0 | 52307.2603 | 951.6 | 52307.2603 | 0
2025-11-28 | 523349.6635 | 575479.59 | 52334.9664 | 330517.75 | 52334.9664 | 0 | 52334.9664 | 0 | 52334.9664 | 0 | 52334.9664 | 62801.78 | 52334.9664 | 151922.93 | 52334.9664 | 23986.28 | 52334.9664 | 0 | 52334.9664 | 951.6 | 52334.9664 | 0
2025-11-29 | 523626.7239 | 575479.59 | 52362.6724 | 330517.75 | 52362.6724 | 0 | 52362.6724 | 0 | 52362.6724 | 0 | 52362.6724 | 62801.78 | 52362.6724 | 151922.93 | 52362.6724 | 23986.28 | 52362.6724 | 0 | 52362.6724 | 951.6 | 52362.6724 | 0
2025-11-30 | 523903.7843 | 575479.59 | 52390.3784 | 330517.75 | 52390.3784 | 0 | 52390.3784 | 0 | 52390.3784 | 0 | 52390.3784 | 62801.78 | 52390.3784 | 151922.93 | 52390.3784 | 23986.28 | 52390.3784 | 0 | 52390.3784 | 951.6 | 52390.3784 | 0
2025-12-01 | 524180.8447 | 575479.59 | 52418.0845 | 330517.75 | 52418.0845 | 0 | 52418.0845 | 0 | 52418.0845 | 0 | 52418.0845 | 62801.78 | 52418.0845 | 151922.93 | 52418.0845 | 23986.28 | 52418.0845 | 0 | 52418.0845 | 951.6 | 52418.0845 | 0
2025-12-02 | 524457.905 | 575479.59 | 52445.7905 | 330517.75 | 52445.7905 | 0 | 52445.7905 | 0 | 52445.7905 | 0 | 52445.7905 | 62801.78 | 52445.7905 | 151922.93 | 52445.7905 | 23986.28 | 52445.7905 | 0 | 52445.7905 | 951.6 | 52445.7905 | 0
2025-12-03 | 524734.9654 | 575479.59 | 52473.4965 | 330517.75 | 52473.4965 | 0 | 52473.4965 | 0 | 52473.4965 | 0 | 52473.4965 | 62801.78 | 52473.4965 | 151922.93 | 52473.4965 | 23986.28 | 52473.4965 | 0 | 52473.4965 | 951.6 | 52473.4965 | 0
2025-12-04 | 525012.0258 | 575479.59 | 52501.2026 | 330517.75 | 52501.2026 | 0 | 52501.2026 | 0 | 52501.2026 | 0 | 52501.2026 | 62801.78 | 52501.2026 | 151922.93 | 52501.2026 | 23986.28 | 52501.2026 | 0 | 52501.2026 | 951.6 | 52501.2026 | 0
2025-12-05 | 525289.0862 | 575633.1 | 52528.9086 | 330517.75 | 52528.9086 | 0 | 52528.9086 | 0 | 52528.9086 | 0 | 52528.9086 | 62805.29 | 52528.9086 | 151922.93 | 52528.9086 | 24136.28 | 52528.9086 | 0 | 52528.9086 | 951.6 | 52528.9086 | 0
2025-12-06 | 525566.1466 | 575633.1 | 52556.6147 | 330517.75 | 52556.6147 | 0 | 52556.6147 | 0 | 52556.6147 | 0 | 52556.6147 | 62805.29 | 52556.6147 | 151922.93 | 52556.6147 | 24136.28 | 52556.6147 | 0 | 52556.6147 | 951.6 | 52556.6147 | 0
2025-12-07 | 525843.2069 | 575633.1 | 52584.3207 | 330517.75 | 52584.3207 | 0 | 52584.3207 | 0 | 52584.3207 | 0 | 52584.3207 | 62805.29 | 52584.3207 | 151922.93 | 52584.3207 | 24136.28 | 52584.3207 | 0 | 52584.3207 | 951.6 | 52584.3207 | 0
2025-12-08 | 526120.2673 | 577383.1 | 52612.0267 | 330517.75 | 52612.0267 | 0 | 52612.0267 | 0 | 52612.0267 | 0 | 52612.0267 | 62805.29 | 52612.0267 | 151922.93 | 52612.0267 | 25886.28 | 52612.0267 | 0 | 52612.0267 | 951.6 | 52612.0267 | 0
2025-12-09 | 526397.3277 | 582673.25 | 52639.7328 | 330517.75 | 52639.7328 | 0 | 52639.7328 | 0 | 52639.7328 | 0 | 52639.7328 | 67637.56 | 52639.7328 | 151922.93 | 52639.7328 | 26344.16 | 52639.7328 | 0 | 52639.7328 | 951.6 | 52639.7328 | 0
2025-12-10 | 526674.3881 | 582673.25 | 52667.4388 | 330517.75 | 52667.4388 | 0 | 52667.4388 | 0 | 52667.4388 | 0 | 52667.4388 | 67637.56 | 52667.4388 | 151922.93 | 52667.4388 | 26344.16 | 52667.4388 | 0 | 52667.4388 | 951.6 | 52667.4388 | 0
2025-12-11 | 526951.4484 | 582673.25 | 52695.1448 | 330517.75 | 52695.1448 | 0 | 52695.1448 | 0 | 52695.1448 | 0 | 52695.1448 | 67637.56 | 52695.1448 | 151922.93 | 52695.1448 | 26344.16 | 52695.1448 | 0 | 52695.1448 | 951.6 | 52695.1448 | 0
2025-12-12 | 527228.5088 | 583167.12 | 52722.8509 | 330517.75 | 52722.8509 | 0 | 52722.8509 | 0 | 52722.8509 | 0 | 52722.8509 | 67637.56 | 52722.8509 | 151922.93 | 52722.8509 | 26838.03 | 52722.8509 | 0 | 52722.8509 | 951.6 | 52722.8509 | 0
2025-12-13 | 527505.5692 | 583167.12 | 52750.5569 | 330517.75 | 52750.5569 | 0 | 52750.5569 | 0 | 52750.5569 | 0 | 52750.5569 | 67637.56 | 52750.5569 | 151922.93 | 52750.5569 | 26838.03 | 52750.5569 | 0 | 52750.5569 | 951.6 | 52750.5569 | 0
2025-12-14 | 527782.6296 | 583167.12 | 52778.263 | 330517.75 | 52778.263 | 0 | 52778.263 | 0 | 52778.263 | 0 | 52778.263 | 67637.56 | 52778.263 | 151922.93 | 52778.263 | 26838.03 | 52778.263 | 0 | 52778.263 | 951.6 | 52778.263 | 0
2025-12-15 | 528059.6899 | 583177.8 | 52805.969 | 330517.75 | 52805.969 | 0 | 52805.969 | 0 | 52805.969 | 0 | 52805.969 | 67637.56 | 52805.969 | 151922.93 | 52805.969 | 26848.71 | 52805.969 | 0 | 52805.969 | 951.6 | 52805.969 | 0
2025-12-16 | 528336.7503 | 583177.8 | 52833.675 | 330517.75 | 52833.675 | 0 | 52833.675 | 0 | 52833.675 | 0 | 52833.675 | 67637.56 | 52833.675 | 151922.93 | 52833.675 | 26848.71 | 52833.675 | 0 | 52833.675 | 951.6 | 52833.675 | 0
2025-12-17 | 528613.8107 | 588278.66 | 52861.3811 | 330517.75 | 52861.3811 | 0 | 52861.3811 | 0 | 52861.3811 | 0 | 52861.3811 | 72738.42 | 52861.3811 | 151922.93 | 52861.3811 | 26848.71 | 52861.3811 | 0 | 52861.3811 | 951.6 | 52861.3811 | 0
2025-12-18 | 528890.8711 | 588278.66 | 52889.0871 | 330517.75 | 52889.0871 | 0 | 52889.0871 | 0 | 52889.0871 | 0 | 52889.0871 | 72738.42 | 52889.0871 | 151922.93 | 52889.0871 | 26848.71 | 52889.0871 | 0 | 52889.0871 | 951.6 | 52889.0871 | 0
2025-12-19 | 529167.9315 | 588278.66 | 52916.7931 | 330517.75 | 52916.7931 | 0 | 52916.7931 | 0 | 52916.7931 | 0 | 52916.7931 | 72738.42 | 52916.7931 | 151922.93 | 52916.7931 | 26848.71 | 52916.7931 | 0 | 52916.7931 | 951.6 | 52916.7931 | 0
2025-12-20 | 529444.9918 | 588278.66 | 52944.4992 | 330517.75 | 52944.4992 | 0 | 52944.4992 | 0 | 52944.4992 | 0 | 52944.4992 | 72738.42 | 52944.4992 | 151922.93 | 52944.4992 | 26848.71 | 52944.4992 | 0 | 52944.4992 | 951.6 | 52944.4992 | 0
2025-12-21 | 529722.0522 | 588278.66 | 52972.2052 | 330517.75 | 52972.2052 | 0 | 52972.2052 | 0 | 52972.2052 | 0 | 52972.2052 | 72738.42 | 52972.2052 | 151922.93 | 52972.2052 | 26848.71 | 52972.2052 | 0 | 52972.2052 | 951.6 | 52972.2052 | 0
2025-12-22 | 529999.1126 | 588278.66 | 52999.9113 | 330517.75 | 52999.9113 | 0 | 52999.9113 | 0 | 52999.9113 | 0 | 52999.9113 | 72738.42 | 52999.9113 | 151922.93 | 52999.9113 | 26848.71 | 52999.9113 | 0 | 52999.9113 | 951.6 | 52999.9113 | 0
2025-12-23 | 530276.173 | 588278.66 | 53027.6173 | 330517.75 | 53027.6173 | 0 | 53027.6173 | 0 | 53027.6173 | 0 | 53027.6173 | 72738.42 | 53027.6173 | 151922.93 | 53027.6173 | 26848.71 | 53027.6173 | 0 | 53027.6173 | 951.6 | 53027.6173 | 0
2025-12-24 | 530553.2333 | 588278.66 | 53055.3233 | 330517.75 | 53055.3233 | 0 | 53055.3233 | 0 | 53055.3233 | 0 | 53055.3233 | 72738.42 | 53055.3233 | 151922.93 | 53055.3233 | 26848.71 | 53055.3233 | 0 | 53055.3233 | 951.6 | 53055.3233 | 0
2025-12-25 | 530830.2937 | 588620.42 | 53083.0294 | 330517.75 | 53083.0294 | 0 | 53083.0294 | 0 | 53083.0294 | 0 | 53083.0294 | 72738.42 | 53083.0294 | 151922.93 | 53083.0294 | 27190.47 | 53083.0294 | 0 | 53083.0294 | 951.6 | 53083.0294 | 0
2025-12-26 | 531107.3541 | 588620.42 | 53110.7354 | 330517.75 | 53110.7354 | 0 | 53110.7354 | 0 | 53110.7354 | 0 | 53110.7354 | 72738.42 | 53110.7354 | 151922.93 | 53110.7354 | 27190.47 | 53110.7354 | 0 | 53110.7354 | 951.6 | 53110.7354 | 0
2025-12-27 | 531384.4145 | 588620.42 | 53138.4414 | 330517.75 | 53138.4414 | 0 | 53138.4414 | 0 | 53138.4414 | 0 | 53138.4414 | 72738.42 | 53138.4414 | 151922.93 | 53138.4414 | 27190.47 | 53138.4414 | 0 | 53138.4414 | 951.6 | 53138.4414 | 0
2025-12-28 | 531661.4748 | 588620.42 | 53166.1475 | 330517.75 | 53166.1475 | 0 | 53166.1475 | 0 | 53166.1475 | 0 | 53166.1475 | 72738.42 | 53166.1475 | 151922.93 | 53166.1475 | 27190.47 | 53166.1475 | 0 | 53166.1475 | 951.6 | 53166.1475 | 0
2025-12-29 | 531938.5352 | 588620.42 | 53193.8535 | 330517.75 | 53193.8535 | 0 | 53193.8535 | 0 | 53193.8535 | 0 | 53193.8535 | 72738.42 | 53193.8535 | 151922.93 | 53193.8535 | 27190.47 | 53193.8535 | 0 | 53193.8535 | 951.6 | 53193.8535 | 0
2025-12-30 | 532215.5956 | 591320.42 | 53221.5596 | 330517.75 | 53221.5596 | 0 | 53221.5596 | 0 | 53221.5596 | 0 | 53221.5596 | 75438.42 | 53221.5596 | 151922.93 | 53221.5596 | 27190.47 | 53221.5596 | 0 | 53221.5596 | 951.6 | 53221.5596 | 0
2025-12-31 | 532492.656 | 591320.42 | 53249.2656 | 330517.75 | 53249.2656 | 0 | 53249.2656 | 0 | 53249.2656 | 0 | 53249.2656 | 75438.42 | 53249.2656 | 151922.93 | 53249.2656 | 27190.47 | 53249.2656 | 0 | 53249.2656 | 951.6 | 53249.2656 | 0
2026-01-01 | 532769.7164 | 591320.42 | 53276.9716 | 330517.75 | 53276.9716 | 0 | 53276.9716 | 0 | 53276.9716 | 0 | 53276.9716 | 75438.42 | 53276.9716 | 151922.93 | 53276.9716 | 27190.47 | 53276.9716 | 0 | 53276.9716 | 951.6 | 53276.9716 | 0
2026-01-02 | 533046.7767 | 591320.42 | 53304.6777 | 330517.75 | 53304.6777 | 0 | 53304.6777 | 0 | 53304.6777 | 0 | 53304.6777 | 75438.42 | 53304.6777 | 151922.93 | 53304.6777 | 27190.47 | 53304.6777 | 0 | 53304.6777 | 951.6 | 53304.6777 | 0
2026-01-03 | 533323.8371 | 591320.42 | 53332.3837 | 330517.75 | 53332.3837 | 0 | 53332.3837 | 0 | 53332.3837 | 0 | 53332.3837 | 75438.42 | 53332.3837 | 151922.93 | 53332.3837 | 27190.47 | 53332.3837 | 0 | 53332.3837 | 951.6 | 53332.3837 | 0
2026-01-04 | 533600.8975 | 591320.42 | 53360.0897 | 330517.75 | 53360.0897 | 0 | 53360.0897 | 0 | 53360.0897 | 0 | 53360.0897 | 75438.42 | 53360.0897 | 151922.93 | 53360.0897 | 27190.47 | 53360.0897 | 0 | 53360.0897 | 951.6 | 53360.0897 | 0
2026-01-05 | 533877.9579 | 591625.17 | 53387.7958 | 330517.75 | 53387.7958 | 0 | 53387.7958 | 0 | 53387.7958 | 0 | 53387.7958 | 75743.17 | 53387.7958 | 151922.93 | 53387.7958 | 27190.47 | 53387.7958 | 0 | 53387.7958 | 951.6 | 53387.7958 | 0
2026-01-06 | 534155.0182 | 596954.78 | 53415.5018 | 330517.75 | 53415.5018 | 0 | 53415.5018 | 0 | 53415.5018 | 0 | 53415.5018 | 81072.78 | 53415.5018 | 151922.93 | 53415.5018 | 27190.47 | 53415.5018 | 0 | 53415.5018 | 951.6 | 53415.5018 | 0
2026-01-07 | 534432.0786 | 596954.78 | 53443.2079 | 330517.75 | 53443.2079 | 0 | 53443.2079 | 0 | 53443.2079 | 0 | 53443.2079 | 81072.78 | 53443.2079 | 151922.93 | 53443.2079 | 27190.47 | 53443.2079 | 0 | 53443.2079 | 951.6 | 53443.2079 | 0
2026-01-08 | 534709.139 | 596954.78 | 53470.9139 | 330517.75 | 53470.9139 | 0 | 53470.9139 | 0 | 53470.9139 | 0 | 53470.9139 | 81072.78 | 53470.9139 | 151922.93 | 53470.9139 | 27190.47 | 53470.9139 | 0 | 53470.9139 | 951.6 | 53470.9139 | 0
2026-01-09 | 534986.1994 | 596954.78 | 53498.6199 | 330517.75 | 53498.6199 | 0 | 53498.6199 | 0 | 53498.6199 | 0 | 53498.6199 | 81072.78 | 53498.6199 | 151922.93 | 53498.6199 | 27190.47 | 53498.6199 | 0 | 53498.6199 | 951.6 | 53498.6199 | 0
2026-01-10 | 535263.2597 | 596954.78 | 53526.326 | 330517.75 | 53526.326 | 0 | 53526.326 | 0 | 53526.326 | 0 | 53526.326 | 81072.78 | 53526.326 | 151922.93 | 53526.326 | 27190.47 | 53526.326 | 0 | 53526.326 | 951.6 | 53526.326 | 0
2026-01-11 | 535540.3201 | 596954.78 | 53554.032 | 330517.75 | 53554.032 | 0 | 53554.032 | 0 | 53554.032 | 0 | 53554.032 | 81072.78 | 53554.032 | 151922.93 | 53554.032 | 27190.47 | 53554.032 | 0 | 53554.032 | 951.6 | 53554.032 | 0
2026-01-12 | 535817.3805 | 596954.78 | 53581.7381 | 330517.75 | 53581.7381 | 0 | 53581.7381 | 0 | 53581.7381 | 0 | 53581.7381 | 81072.78 | 53581.7381 | 151922.93 | 53581.7381 | 27190.47 | 53581.7381 | 0 | 53581.7381 | 951.6 | 53581.7381 | 0
2026-01-13 | 536094.4409 | 596954.78 | 53609.4441 | 330517.75 | 53609.4441 | 0 | 53609.4441 | 0 | 53609.4441 | 0 | 53609.4441 | 81072.78 | 53609.4441 | 151922.93 | 53609.4441 | 27190.47 | 53609.4441 | 0 | 53609.4441 | 951.6 | 53609.4441 | 0
2026-01-14 | 536371.5013 | 596954.78 | 53637.1501 | 330517.75 | 53637.1501 | 0 | 53637.1501 | 0 | 53637.1501 | 0 | 53637.1501 | 81072.78 | 53637.1501 | 151922.93 | 53637.1501 | 27190.47 | 53637.1501 | 0 | 53637.1501 | 951.6 | 53637.1501 | 0
2026-01-15 | 536648.5616 | 596954.78 | 53664.8562 | 330517.75 | 53664.8562 | 0 | 53664.8562 | 0 | 53664.8562 | 0 | 53664.8562 | 81072.78 | 53664.8562 | 151922.93 | 53664.8562 | 27190.47 | 53664.8562 | 0 | 53664.8562 | 951.6 | 53664.8562 | 0
2026-01-16 | 536925.622 | 596984.78 | 53692.5622 | 330517.75 | 53692.5622 | 0 | 53692.5622 | 0 | 53692.5622 | 0 | 53692.5622 | 81072.78 | 53692.5622 | 151922.93 | 53692.5622 | 27220.47 | 53692.5622 | 0 | 53692.5622 | 951.6 | 53692.5622 | 0
2026-01-17 | 537202.6824 | 596984.78 | 53720.2682 | 330517.75 | 53720.2682 | 0 | 53720.2682 | 0 | 53720.2682 | 0 | 53720.2682 | 81072.78 | 53720.2682 | 151922.93 | 53720.2682 | 27220.47 | 53720.2682 | 0 | 53720.2682 | 951.6 | 53720.2682 | 0
2026-01-18 | 537479.7428 | 596984.78 | 53747.9743 | 330517.75 | 53747.9743 | 0 | 53747.9743 | 0 | 53747.9743 | 0 | 53747.9743 | 81072.78 | 53747.9743 | 151922.93 | 53747.9743 | 27220.47 | 53747.9743 | 0 | 53747.9743 | 951.6 | 53747.9743 | 0
2026-01-19 | 537756.8031 | 596984.78 | 53775.6803 | 330517.75 | 53775.6803 | 0 | 53775.6803 | 0 | 53775.6803 | 0 | 53775.6803 | 81072.78 | 53775.6803 | 151922.93 | 53775.6803 | 27220.47 | 53775.6803 | 0 | 53775.6803 | 951.6 | 53775.6803 | 0
2026-01-20 | 538033.8635 | 596984.78 | 53803.3864 | 330517.75 | 53803.3864 | 0 | 53803.3864 | 0 | 53803.3864 | 0 | 53803.3864 | 81072.78 | 53803.3864 | 151922.93 | 53803.3864 | 27220.47 | 53803.3864 | 0 | 53803.3864 | 951.6 | 53803.3864 | 0
2026-01-21 | 538310.9239 | 596984.78 | 53831.0924 | 330517.75 | 53831.0924 | 0 | 53831.0924 | 0 | 53831.0924 | 0 | 53831.0924 | 81072.78 | 53831.0924 | 151922.93 | 53831.0924 | 27220.47 | 53831.0924 | 0 | 53831.0924 | 951.6 | 53831.0924 | 0
2026-01-22 | 538587.9843 | 597001.12 | 53858.7984 | 330517.75 | 53858.7984 | 0 | 53858.7984 | 0 | 53858.7984 | 0 | 53858.7984 | 81072.78 | 53858.7984 | 151922.93 | 53858.7984 | 27236.81 | 53858.7984 | 0 | 53858.7984 | 951.6 | 53858.7984 | 0
2026-01-23 | 538865.0446 | 598981.28 | 53886.5045 | 330517.75 | 53886.5045 | 0 | 53886.5045 | 0 | 53886.5045 | 0 | 53886.5045 | 81072.78 | 53886.5045 | 153903.09 | 53886.5045 | 27236.81 | 53886.5045 | 0 | 53886.5045 | 951.6 | 53886.5045 | 0
2026-01-24 | 539142.105 | 598981.28 | 53914.2105 | 330517.75 | 53914.2105 | 0 | 53914.2105 | 0 | 53914.2105 | 0 | 53914.2105 | 81072.78 | 53914.2105 | 153903.09 | 53914.2105 | 27236.81 | 53914.2105 | 0 | 53914.2105 | 951.6 | 53914.2105 | 0
2026-01-25 | 539419.1654 | 598981.28 | 53941.9165 | 330517.75 | 53941.9165 | 0 | 53941.9165 | 0 | 53941.9165 | 0 | 53941.9165 | 81072.78 | 53941.9165 | 153903.09 | 53941.9165 | 27236.81 | 53941.9165 | 0 | 53941.9165 | 951.6 | 53941.9165 | 0
2026-01-26 | 539696.2258 | 599011.28 | 53969.6226 | 330517.75 | 53969.6226 | 0 | 53969.6226 | 0 | 53969.6226 | 0 | 53969.6226 | 81072.78 | 53969.6226 | 153903.09 | 53969.6226 | 27266.81 | 53969.6226 | 0 | 53969.6226 | 951.6 | 53969.6226 | 0
2026-01-27 | 539973.2862 | 601711.28 | 53997.3286 | 330517.75 | 53997.3286 | 0 | 53997.3286 | 0 | 53997.3286 | 0 | 53997.3286 | 83772.78 | 53997.3286 | 153903.09 | 53997.3286 | 27266.81 | 53997.3286 | 0 | 53997.3286 | 951.6 | 53997.3286 | 0
2026-01-28 | 540250.3465 | 601711.28 | 54025.0347 | 330517.75 | 54025.0347 | 0 | 54025.0347 | 0 | 54025.0347 | 0 | 54025.0347 | 83772.78 | 54025.0347 | 153903.09 | 54025.0347 | 27266.81 | 54025.0347 | 0 | 54025.0347 | 951.6 | 54025.0347 | 0
2026-01-29 | 540470.1882 | 601728.54 | 54047.0188 | 330517.75 | 54047.0188 | 0 | 54047.0188 | 0 | 54047.0188 | 0 | 54047.0188 | 83772.78 | 54047.0188 | 153903.09 | 54047.0188 | 27284.07 | 54047.0188 | 0 | 54047.0188 | 951.6 | 54047.0188 | 0
2026-01-30 | 540690.0299 | 601728.54 | 54069.003 | 330517.75 | 54069.003 | 0 | 54069.003 | 0 | 54069.003 | 0 | 54069.003 | 83772.78 | 54069.003 | 153903.09 | 54069.003 | 27284.07 | 54069.003 | 0 | 54069.003 | 951.6 | 54069.003 | 0
2026-01-31 | 540909.8715 | 605160.36 | 54090.9872 | 330517.75 | 54090.9872 | 0 | 54090.9872 | 0 | 54090.9872 | 0 | 54090.9872 | 87204.6 | 54090.9872 | 153903.09 | 54090.9872 | 27284.07 | 54090.9872 | 0 | 54090.9872 | 951.6 | 54090.9872 | 0
2026-02-01 | 541129.7132 | 605160.36 | 54112.9713 | 330517.75 | 54112.9713 | 0 | 54112.9713 | 0 | 54112.9713 | 0 | 54112.9713 | 87204.6 | 54112.9713 | 153903.09 | 54112.9713 | 27284.07 | 54112.9713 | 0 | 54112.9713 | 951.6 | 54112.9713 | 0
2026-02-02 | 541349.5549 | 605171.72 | 54134.9555 | 330517.75 | 54134.9555 | 0 | 54134.9555 | 0 | 54134.9555 | 0 | 54134.9555 | 87204.6 | 54134.9555 | 153903.09 | 54134.9555 | 27295.43 | 54134.9555 | 0 | 54134.9555 | 951.6 | 54134.9555 | 0
2026-02-03 | 541569.3965 | 605848.17 | 54156.9397 | 330517.75 | 54156.9397 | 0 | 54156.9397 | 0 | 54156.9397 | 0 | 54156.9397 | 87881.05 | 54156.9397 | 153903.09 | 54156.9397 | 27295.43 | 54156.9397 | 0 | 54156.9397 | 951.6 | 54156.9397 | 0
2026-02-04 | 541789.2382 | 605858.95 | 54178.9238 | 330517.75 | 54178.9238 | 0 | 54178.9238 | 0 | 54178.9238 | 0 | 54178.9238 | 87881.05 | 54178.9238 | 153903.09 | 54178.9238 | 27306.21 | 54178.9238 | 0 | 54178.9238 | 951.6 | 54178.9238 | 0
2026-02-05 | 542009.0799 | 605873.95 | 54200.908 | 330517.75 | 54200.908 | 0 | 54200.908 | 0 | 54200.908 | 0 | 54200.908 | 87881.05 | 54200.908 | 153903.09 | 54200.908 | 27321.21 | 54200.908 | 0 | 54200.908 | 951.6 | 54200.908 | 0
2026-02-06 | 542228.9215 | 605873.95 | 54222.8922 | 330517.75 | 54222.8922 | 0 | 54222.8922 | 0 | 54222.8922 | 0 | 54222.8922 | 87881.05 | 54222.8922 | 153903.09 | 54222.8922 | 27321.21 | 54222.8922 | 0 | 54222.8922 | 951.6 | 54222.8922 | 0
2026-02-07 | 542448.7632 | 605873.95 | 54244.8763 | 330517.75 | 54244.8763 | 0 | 54244.8763 | 0 | 54244.8763 | 0 | 54244.8763 | 87881.05 | 54244.8763 | 153903.09 | 54244.8763 | 27321.21 | 54244.8763 | 0 | 54244.8763 | 951.6 | 54244.8763 | 0
2026-02-08 | 542668.6049 | 605873.95 | 54266.8605 | 330517.75 | 54266.8605 | 0 | 54266.8605 | 0 | 54266.8605 | 0 | 54266.8605 | 87881.05 | 54266.8605 | 153903.09 | 54266.8605 | 27321.21 | 54266.8605 | 0 | 54266.8605 | 951.6 | 54266.8605 | 0
2026-02-09 | 542888.4465 | 609583.95 | 54288.8447 | 330517.75 | 54288.8447 | 0 | 54288.8447 | 0 | 54288.8447 | 0 | 54288.8447 | 87881.05 | 54288.8447 | 157613.09 | 54288.8447 | 27321.21 | 54288.8447 | 0 | 54288.8447 | 951.6 | 54288.8447 | 0
2026-02-10 | 543108.2882 | 609583.95 | 54310.8288 | 330517.75 | 54310.8288 | 0 | 54310.8288 | 0 | 54310.8288 | 0 | 54310.8288 | 87881.05 | 54310.8288 | 157613.09 | 54310.8288 | 27321.21 | 54310.8288 | 0 | 54310.8288 | 951.6 | 54310.8288 | 0
2026-02-11 | 543328.1299 | 609583.95 | 54332.813 | 330517.75 | 54332.813 | 0 | 54332.813 | 0 | 54332.813 | 0 | 54332.813 | 87881.05 | 54332.813 | 157613.09 | 54332.813 | 27321.21 | 54332.813 | 0 | 54332.813 | 951.6 | 54332.813 | 0
2026-02-12 | 543547.9715 | 609583.95 | 54354.7972 | 330517.75 | 54354.7972 | 0 | 54354.7972 | 0 | 54354.7972 | 0 | 54354.7972 | 87881.05 | 54354.7972 | 157613.09 | 54354.7972 | 27321.21 | 54354.7972 | 0 | 54354.7972 | 951.6 | 54354.7972 | 0
2026-02-13 | 543767.8132 | 610216.51 | 54376.7813 | 330517.75 | 54376.7813 | 0 | 54376.7813 | 0 | 54376.7813 | 0 | 54376.7813 | 87881.05 | 54376.7813 | 157613.09 | 54376.7813 | 27953.77 | 54376.7813 | 0 | 54376.7813 | 951.6 | 54376.7813 | 0
2026-02-14 | 543987.6549 | 610216.51 | 54398.7655 | 330517.75 | 54398.7655 | 0 | 54398.7655 | 0 | 54398.7655 | 0 | 54398.7655 | 87881.05 | 54398.7655 | 157613.09 | 54398.7655 | 27953.77 | 54398.7655 | 0 | 54398.7655 | 951.6 | 54398.7655 | 0
2026-02-15 | 544207.4965 | 610216.51 | 54420.7497 | 330517.75 | 54420.7497 | 0 | 54420.7497 | 0 | 54420.7497 | 0 | 54420.7497 | 87881.05 | 54420.7497 | 157613.09 | 54420.7497 | 27953.77 | 54420.7497 | 0 | 54420.7497 | 951.6 | 54420.7497 | 0
2026-02-16 | 544427.3382 | 612006.77 | 54442.7338 | 330517.75 | 54442.7338 | 0 | 54442.7338 | 0 | 54442.7338 | 0 | 54442.7338 | 89671.31 | 54442.7338 | 157613.09 | 54442.7338 | 27953.77 | 54442.7338 | 0 | 54442.7338 | 951.6 | 54442.7338 | 0
2026-02-17 | 544647.1799 | 614980.22 | 54464.718 | 330517.75 | 54464.718 | 0 | 54464.718 | 0 | 54464.718 | 0 | 54464.718 | 92644.76 | 54464.718 | 157613.09 | 54464.718 | 27953.77 | 54464.718 | 0 | 54464.718 | 951.6 | 54464.718 | 0
2026-02-18 | 544867.0215 | 614980.22 | 54486.7022 | 330517.75 | 54486.7022 | 0 | 54486.7022 | 0 | 54486.7022 | 0 | 54486.7022 | 92644.76 | 54486.7022 | 157613.09 | 54486.7022 | 27953.77 | 54486.7022 | 0 | 54486.7022 | 951.6 | 54486.7022 | 0
2026-02-19 | 545086.8632 | 614980.22 | 54508.6863 | 330517.75 | 54508.6863 | 0 | 54508.6863 | 0 | 54508.6863 | 0 | 54508.6863 | 92644.76 | 54508.6863 | 157613.09 | 54508.6863 | 27953.77 | 54508.6863 | 0 | 54508.6863 | 951.6 | 54508.6863 | 0
2026-02-20 | 545306.7049 | 614980.22 | 54530.6705 | 330517.75 | 54530.6705 | 0 | 54530.6705 | 0 | 54530.6705 | 0 | 54530.6705 | 92644.76 | 54530.6705 | 157613.09 | 54530.6705 | 27953.77 | 54530.6705 | 0 | 54530.6705 | 951.6 | 54530.6705 | 0
2026-02-21 | 545526.5465 | 614980.22 | 54552.6547 | 330517.75 | 54552.6547 | 0 | 54552.6547 | 0 | 54552.6547 | 0 | 54552.6547 | 92644.76 | 54552.6547 | 157613.09 | 54552.6547 | 27953.77 | 54552.6547 | 0 | 54552.6547 | 951.6 | 54552.6547 | 0
2026-02-22 | 545746.3882 | 614980.22 | 54574.6388 | 330517.75 | 54574.6388 | 0 | 54574.6388 | 0 | 54574.6388 | 0 | 54574.6388 | 92644.76 | 54574.6388 | 157613.09 | 54574.6388 | 27953.77 | 54574.6388 | 0 | 54574.6388 | 951.6 | 54574.6388 | 0
2026-02-23 | 545966.2299 | 614980.22 | 54596.623 | 330517.75 | 54596.623 | 0 | 54596.623 | 0 | 54596.623 | 0 | 54596.623 | 92644.76 | 54596.623 | 157613.09 | 54596.623 | 27953.77 | 54596.623 | 0 | 54596.623 | 951.6 | 54596.623 | 0
2026-02-24 | 546186.0715 | 614980.22 | 54618.6072 | 330517.75 | 54618.6072 | 0 | 54618.6072 | 0 | 54618.6072 | 0 | 54618.6072 | 92644.76 | 54618.6072 | 157613.09 | 54618.6072 | 27953.77 | 54618.6072 | 0 | 54618.6072 | 951.6 | 54618.6072 | 0
2026-02-25 | 546405.9132 | 614980.22 | 54640.5913 | 330517.75 | 54640.5913 | 0 | 54640.5913 | 0 | 54640.5913 | 0 | 54640.5913 | 92644.76 | 54640.5913 | 157613.09 | 54640.5913 | 27953.77 | 54640.5913 | 0 | 54640.5913 | 951.6 | 54640.5913 | 0
2026-02-26 | 546625.7549 | 614980.22 | 54662.5755 | 330517.75 | 54662.5755 | 0 | 54662.5755 | 0 | 54662.5755 | 0 | 54662.5755 | 92644.76 | 54662.5755 | 157613.09 | 54662.5755 | 27953.77 | 54662.5755 | 0 | 54662.5755 | 951.6 | 54662.5755 | 0
2026-02-27 | 546845.5965 | 615050.22 | 54684.5597 | 330517.75 | 54684.5597 | 0 | 54684.5597 | 0 | 54684.5597 | 0 | 54684.5597 | 92644.76 | 54684.5597 | 157613.09 | 54684.5597 | 28023.77 | 54684.5597 | 0 | 54684.5597 | 951.6 | 54684.5597 | 0
2026-02-28 | 547065.4382 | 617750.22 | 54706.5438 | 330517.75 | 54706.5438 | 0 | 54706.5438 | 0 | 54706.5438 | 0 | 54706.5438 | 95344.76 | 54706.5438 | 157613.09 | 54706.5438 | 28023.77 | 54706.5438 | 0 | 54706.5438 | 951.6 | 54706.5438 | 0
2026-03-01 | 547285.2799 | 617750.22 | 54728.528 | 330517.75 | 54728.528 | 0 | 54728.528 | 0 | 54728.528 | 0 | 54728.528 | 95344.76 | 54728.528 | 157613.09 | 54728.528 | 28023.77 | 54728.528 | 0 | 54728.528 | 951.6 | 54728.528 | 0
2026-03-02 | 547505.1215 | 617750.22 | 54750.5122 | 330517.75 | 54750.5122 | 0 | 54750.5122 | 0 | 54750.5122 | 0 | 54750.5122 | 95344.76 | 54750.5122 | 157613.09 | 54750.5122 | 28023.77 | 54750.5122 | 0 | 54750.5122 | 951.6 | 54750.5122 | 0
2026-03-03 | 547724.9632 | 618426.67 | 54772.4963 | 330517.75 | 54772.4963 | 0 | 54772.4963 | 0 | 54772.4963 | 0 | 54772.4963 | 96021.21 | 54772.4963 | 157613.09 | 54772.4963 | 28023.77 | 54772.4963 | 0 | 54772.4963 | 951.6 | 54772.4963 | 0
2026-03-04 | 547944.8049 | 624930.19 | 54794.4805 | 330517.75 | 54794.4805 | 0 | 54794.4805 | 0 | 54794.4805 | 0 | 54794.4805 | 102524.73 | 54794.4805 | 157613.09 | 54794.4805 | 28023.77 | 54794.4805 | 0 | 54794.4805 | 951.6 | 54794.4805 | 0
2026-03-05 | 548164.6465 | 624930.19 | 54816.4647 | 330517.75 | 54816.4647 | 0 | 54816.4647 | 0 | 54816.4647 | 0 | 54816.4647 | 102524.73 | 54816.4647 | 157613.09 | 54816.4647 | 28023.77 | 54816.4647 | 0 | 54816.4647 | 951.6 | 54816.4647 | 0
2026-03-06 | 548384.4882 | 624930.19 | 54838.4488 | 330517.75 | 54838.4488 | 0 | 54838.4488 | 0 | 54838.4488 | 0 | 54838.4488 | 102524.73 | 54838.4488 | 157613.09 | 54838.4488 | 28023.77 | 54838.4488 | 0 | 54838.4488 | 951.6 | 54838.4488 | 0
2026-03-07 | 548604.3299 | 624930.19 | 54860.433 | 330517.75 | 54860.433 | 0 | 54860.433 | 0 | 54860.433 | 0 | 54860.433 | 102524.73 | 54860.433 | 157613.09 | 54860.433 | 28023.77 | 54860.433 | 0 | 54860.433 | 951.6 | 54860.433 | 0
2026-03-08 | 548824.1715 | 624930.19 | 54882.4172 | 330517.75 | 54882.4172 | 0 | 54882.4172 | 0 | 54882.4172 | 0 | 54882.4172 | 102524.73 | 54882.4172 | 157613.09 | 54882.4172 | 28023.77 | 54882.4172 | 0 | 54882.4172 | 951.6 | 54882.4172 | 0
2026-03-09 | 549044.0132 | 624930.19 | 54904.4013 | 330517.75 | 54904.4013 | 0 | 54904.4013 | 0 | 54904.4013 | 0 | 54904.4013 | 102524.73 | 54904.4013 | 157613.09 | 54904.4013 | 28023.77 | 54904.4013 | 0 | 54904.4013 | 951.6 | 54904.4013 | 0
2026-03-10 | 549263.8549 | 624930.19 | 54926.3855 | 330517.75 | 54926.3855 | 0 | 54926.3855 | 0 | 54926.3855 | 0 | 54926.3855 | 102524.73 | 54926.3855 | 157613.09 | 54926.3855 | 28023.77 | 54926.3855 | 0 | 54926.3855 | 951.6 | 54926.3855 | 0
2026-03-11 | 549483.6965 | 624930.19 | 54948.3697 | 330517.75 | 54948.3697 | 0 | 54948.3697 | 0 | 54948.3697 | 0 | 54948.3697 | 102524.73 | 54948.3697 | 157613.09 | 54948.3697 | 28023.77 | 54948.3697 | 0 | 54948.3697 | 951.6 | 54948.3697 | 0
2026-03-12 | 549703.5382 | 624930.19 | 54970.3538 | 330517.75 | 54970.3538 | 0 | 54970.3538 | 0 | 54970.3538 | 0 | 54970.3538 | 102524.73 | 54970.3538 | 157613.09 | 54970.3538 | 28023.77 | 54970.3538 | 0 | 54970.3538 | 951.6 | 54970.3538 | 0
2026-03-13 | 549923.3799 | 624930.19 | 54992.338 | 330517.75 | 54992.338 | 0 | 54992.338 | 0 | 54992.338 | 0 | 54992.338 | 102524.73 | 54992.338 | 157613.09 | 54992.338 | 28023.77 | 54992.338 | 0 | 54992.338 | 951.6 | 54992.338 | 0
2026-03-14 | 550143.2215 | 624930.19 | 55014.3222 | 330517.75 | 55014.3222 | 0 | 55014.3222 | 0 | 55014.3222 | 0 | 55014.3222 | 102524.73 | 55014.3222 | 157613.09 | 55014.3222 | 28023.77 | 55014.3222 | 0 | 55014.3222 | 951.6 | 55014.3222 | 0
2026-03-15 | 550363.0632 | 624930.19 | 55036.3063 | 330517.75 | 55036.3063 | 0 | 55036.3063 | 0 | 55036.3063 | 0 | 55036.3063 | 102524.73 | 55036.3063 | 157613.09 | 55036.3063 | 28023.77 | 55036.3063 | 0 | 55036.3063 | 951.6 | 55036.3063 | 0
2026-03-16 | 550582.9049 | 624930.19 | 55058.2905 | 330517.75 | 55058.2905 | 0 | 55058.2905 | 0 | 55058.2905 | 0 | 55058.2905 | 102524.73 | 55058.2905 | 157613.09 | 55058.2905 | 28023.77 | 55058.2905 | 0 | 55058.2905 | 951.6 | 55058.2905 | 0
2026-03-17 | 550802.7465 | 624930.19 | 55080.2747 | 330517.75 | 55080.2747 | 0 | 55080.2747 | 0 | 55080.2747 | 0 | 55080.2747 | 102524.73 | 55080.2747 | 157613.09 | 55080.2747 | 28023.77 | 55080.2747 | 0 | 55080.2747 | 951.6 | 55080.2747 | 0
2026-03-18 | 551022.5882 | 624930.19 | 55102.2588 | 330517.75 | 55102.2588 | 0 | 55102.2588 | 0 | 55102.2588 | 0 | 55102.2588 | 102524.73 | 55102.2588 | 157613.09 | 55102.2588 | 28023.77 | 55102.2588 | 0 | 55102.2588 | 951.6 | 55102.2588 | 0
2026-03-19 | 551242.4299 | 624930.19 | 55124.243 | 330517.75 | 55124.243 | 0 | 55124.243 | 0 | 55124.243 | 0 | 55124.243 | 102524.73 | 55124.243 | 157613.09 | 55124.243 | 28023.77 | 55124.243 | 0 | 55124.243 | 951.6 | 55124.243 | 0
2026-03-20 | 551462.2715 | 624930.19 | 55146.2272 | 330517.75 | 55146.2272 | 0 | 55146.2272 | 0 | 55146.2272 | 0 | 55146.2272 | 102524.73 | 55146.2272 | 157613.09 | 55146.2272 | 28023.77 | 55146.2272 | 0 | 55146.2272 | 951.6 | 55146.2272 | 0
2026-03-21 | 551682.1132 | 624930.19 | 55168.2113 | 330517.75 | 55168.2113 | 0 | 55168.2113 | 0 | 55168.2113 | 0 | 55168.2113 | 102524.73 | 55168.2113 | 157613.09 | 55168.2113 | 28023.77 | 55168.2113 | 0 | 55168.2113 | 951.6 | 55168.2113 | 0
2026-03-22 | 551901.9549 | 624930.19 | 55190.1955 | 330517.75 | 55190.1955 | 0 | 55190.1955 | 0 | 55190.1955 | 0 | 55190.1955 | 102524.73 | 55190.1955 | 157613.09 | 55190.1955 | 28023.77 | 55190.1955 | 0 | 55190.1955 | 951.6 | 55190.1955 | 0
2026-03-23 | 552121.7965 |  | 55212.1797 |  | 55212.1797 |  | 55212.1797 |  | 55212.1797 |  | 55212.1797 |  | 55212.1797 |  | 55212.1797 |  | 55212.1797 |  | 55212.1797 |  | 55212.1797
2026-03-24 | 552341.6382 |  | 55234.1638 |  | 55234.1638 |  | 55234.1638 |  | 55234.1638 |  | 55234.1638 |  | 55234.1638 |  | 55234.1638 |  | 55234.1638 |  | 55234.1638 |  | 55234.1638
2026-03-25 | 552561.4799 |  | 55256.148 |  | 55256.148 |  | 55256.148 |  | 55256.148 |  | 55256.148 |  | 55256.148 |  | 55256.148 |  | 55256.148 |  | 55256.148 |  | 55256.148
2026-03-26 | 552781.3215 |  | 55278.1322 |  | 55278.1322 |  | 55278.1322 |  | 55278.1322 |  | 55278.1322 |  | 55278.1322 |  | 55278.1322 |  | 55278.1322 |  | 55278.1322 |  | 55278.1322
2026-03-27 | 553001.1632 |  | 55300.1163 |  | 55300.1163 |  | 55300.1163 |  | 55300.1163 |  | 55300.1163 |  | 55300.1163 |  | 55300.1163 |  | 55300.1163 |  | 55300.1163 |  | 55300.1163
2026-03-28 | 553221.0049 |  | 55322.1005 |  | 55322.1005 |  | 55322.1005 |  | 55322.1005 |  | 55322.1005 |  | 55322.1005 |  | 55322.1005 |  | 55322.1005 |  | 55322.1005 |  | 55322.1005
2026-03-29 | 553440.8465 |  | 55344.0847 |  | 55344.0847 |  | 55344.0847 |  | 55344.0847 |  | 55344.0847 |  | 55344.0847 |  | 55344.0847 |  | 55344.0847 |  | 55344.0847 |  | 55344.0847
2026-03-30 | 553660.6882 |  | 55366.0688 |  | 55366.0688 |  | 55366.0688 |  | 55366.0688 |  | 55366.0688 |  | 55366.0688 |  | 55366.0688 |  | 55366.0688 |  | 55366.0688 |  | 55366.0688
2026-03-31 | 553880.5299 |  | 55388.053 |  | 55388.053 |  | 55388.053 |  | 55388.053 |  | 55388.053 |  | 55388.053 |  | 55388.053 |  | 55388.053 |  | 55388.053 |  | 55388.053
2026-04-01 | 554100.3715 |  | 55410.0372 |  | 55410.0372 |  | 55410.0372 |  | 55410.0372 |  | 55410.0372 |  | 55410.0372 |  | 55410.0372 |  | 55410.0372 |  | 55410.0372 |  | 55410.0372
2026-04-02 | 554320.2132 |  | 55432.0213 |  | 55432.0213 |  | 55432.0213 |  | 55432.0213 |  | 55432.0213 |  | 55432.0213 |  | 55432.0213 |  | 55432.0213 |  | 55432.0213 |  | 55432.0213
2026-04-03 | 554540.0549 |  | 55454.0055 |  | 55454.0055 |  | 55454.0055 |  | 55454.0055 |  | 55454.0055 |  | 55454.0055 |  | 55454.0055 |  | 55454.0055 |  | 55454.0055 |  | 55454.0055
2026-04-04 | 554759.8965 |  | 55475.9897 |  | 55475.9897 |  | 55475.9897 |  | 55475.9897 |  | 55475.9897 |  | 55475.9897 |  | 55475.9897 |  | 55475.9897 |  | 55475.9897 |  | 55475.9897
2026-04-05 | 554979.7382 |  | 55497.9738 |  | 55497.9738 |  | 55497.9738 |  | 55497.9738 |  | 55497.9738 |  | 55497.9738 |  | 55497.9738 |  | 55497.9738 |  | 55497.9738 |  | 55497.9738
2026-04-06 | 555199.5799 |  | 55519.958 |  | 55519.958 |  | 55519.958 |  | 55519.958 |  | 55519.958 |  | 55519.958 |  | 55519.958 |  | 55519.958 |  | 55519.958 |  | 55519.958
2026-04-07 | 555419.4215 |  | 55541.9422 |  | 55541.9422 |  | 55541.9422 |  | 55541.9422 |  | 55541.9422 |  | 55541.9422 |  | 55541.9422 |  | 55541.9422 |  | 55541.9422 |  | 55541.9422
2026-04-08 | 555639.2632 |  | 55563.9263 |  | 55563.9263 |  | 55563.9263 |  | 55563.9263 |  | 55563.9263 |  | 55563.9263 |  | 55563.9263 |  | 55563.9263 |  | 55563.9263 |  | 55563.9263
2026-04-09 | 555859.1049 |  | 55585.9105 |  | 55585.9105 |  | 55585.9105 |  | 55585.9105 |  | 55585.9105 |  | 55585.9105 |  | 55585.9105 |  | 55585.9105 |  | 55585.9105 |  | 55585.9105
2026-04-10 | 556078.9465 |  | 55607.8947 |  | 55607.8947 |  | 55607.8947 |  | 55607.8947 |  | 55607.8947 |  | 55607.8947 |  | 55607.8947 |  | 55607.8947 |  | 55607.8947 |  | 55607.8947
2026-04-11 | 556298.7882 |  | 55629.8788 |  | 55629.8788 |  | 55629.8788 |  | 55629.8788 |  | 55629.8788 |  | 55629.8788 |  | 55629.8788 |  | 55629.8788 |  | 55629.8788 |  | 55629.8788
2026-04-12 | 556518.6299 |  | 55651.863 |  | 55651.863 |  | 55651.863 |  | 55651.863 |  | 55651.863 |  | 55651.863 |  | 55651.863 |  | 55651.863 |  | 55651.863 |  | 55651.863
2026-04-13 | 556738.4715 |  | 55673.8472 |  | 55673.8472 |  | 55673.8472 |  | 55673.8472 |  | 55673.8472 |  | 55673.8472 |  | 55673.8472 |  | 55673.8472 |  | 55673.8472 |  | 55673.8472
2026-04-14 | 556958.3132 |  | 55695.8313 |  | 55695.8313 |  | 55695.8313 |  | 55695.8313 |  | 55695.8313 |  | 55695.8313 |  | 55695.8313 |  | 55695.8313 |  | 55695.8313 |  | 55695.8313
2026-04-15 | 557178.1549 |  | 55717.8155 |  | 55717.8155 |  | 55717.8155 |  | 55717.8155 |  | 55717.8155 |  | 55717.8155 |  | 55717.8155 |  | 55717.8155 |  | 55717.8155 |  | 55717.8155
2026-04-16 | 557397.9965 |  | 55739.7997 |  | 55739.7997 |  | 55739.7997 |  | 55739.7997 |  | 55739.7997 |  | 55739.7997 |  | 55739.7997 |  | 55739.7997 |  | 55739.7997 |  | 55739.7997
2026-04-17 | 557617.8382 |  | 55761.7838 |  | 55761.7838 |  | 55761.7838 |  | 55761.7838 |  | 55761.7838 |  | 55761.7838 |  | 55761.7838 |  | 55761.7838 |  | 55761.7838 |  | 55761.7838
2026-04-18 | 557837.6799 |  | 55783.768 |  | 55783.768 |  | 55783.768 |  | 55783.768 |  | 55783.768 |  | 55783.768 |  | 55783.768 |  | 55783.768 |  | 55783.768 |  | 55783.768
2026-04-19 | 558057.5215 |  | 55805.7522 |  | 55805.7522 |  | 55805.7522 |  | 55805.7522 |  | 55805.7522 |  | 55805.7522 |  | 55805.7522 |  | 55805.7522 |  | 55805.7522 |  | 55805.7522
2026-04-20 | 558277.3632 |  | 55827.7363 |  | 55827.7363 |  | 55827.7363 |  | 55827.7363 |  | 55827.7363 |  | 55827.7363 |  | 55827.7363 |  | 55827.7363 |  | 55827.7363 |  | 55827.7363
2026-04-21 | 558497.2049 |  | 55849.7205 |  | 55849.7205 |  | 55849.7205 |  | 55849.7205 |  | 55849.7205 |  | 55849.7205 |  | 55849.7205 |  | 55849.7205 |  | 55849.7205 |  | 55849.7205
2026-04-22 | 558717.0465 |  | 55871.7047 |  | 55871.7047 |  | 55871.7047 |  | 55871.7047 |  | 55871.7047 |  | 55871.7047 |  | 55871.7047 |  | 55871.7047 |  | 55871.7047 |  | 55871.7047
2026-04-23 | 558936.8882 |  | 55893.6888 |  | 55893.6888 |  | 55893.6888 |  | 55893.6888 |  | 55893.6888 |  | 55893.6888 |  | 55893.6888 |  | 55893.6888 |  | 55893.6888 |  | 55893.6888
2026-04-24 | 559156.7299 |  | 55915.673 |  | 55915.673 |  | 55915.673 |  | 55915.673 |  | 55915.673 |  | 55915.673 |  | 55915.673 |  | 55915.673 |  | 55915.673 |  | 55915.673
2026-04-25 | 559376.5715 |  | 55937.6572 |  | 55937.6572 |  | 55937.6572 |  | 55937.6572 |  | 55937.6572 |  | 55937.6572 |  | 55937.6572 |  | 55937.6572 |  | 55937.6572 |  | 55937.6572
2026-04-26 | 559596.4132 |  | 55959.6413 |  | 55959.6413 |  | 55959.6413 |  | 55959.6413 |  | 55959.6413 |  | 55959.6413 |  | 55959.6413 |  | 55959.6413 |  | 55959.6413 |  | 55959.6413
2026-04-27 | 559816.2549 |  | 55981.6255 |  | 55981.6255 |  | 55981.6255 |  | 55981.6255 |  | 55981.6255 |  | 55981.6255 |  | 55981.6255 |  | 55981.6255 |  | 55981.6255 |  | 55981.6255
2026-04-28 | 560036.0965 |  | 56003.6097 |  | 56003.6097 |  | 56003.6097 |  | 56003.6097 |  | 56003.6097 |  | 56003.6097 |  | 56003.6097 |  | 56003.6097 |  | 56003.6097 |  | 56003.6097
2026-04-29 | 560255.9382 |  | 56025.5938 |  | 56025.5938 |  | 56025.5938 |  | 56025.5938 |  | 56025.5938 |  | 56025.5938 |  | 56025.5938 |  | 56025.5938 |  | 56025.5938 |  | 56025.5938
2026-04-30 | 560475.7799 |  | 56047.578 |  | 56047.578 |  | 56047.578 |  | 56047.578 |  | 56047.578 |  | 56047.578 |  | 56047.578 |  | 56047.578 |  | 56047.578 |  | 56047.578
2026-05-01 | 560695.6215 |  | 56069.5622 |  | 56069.5622 |  | 56069.5622 |  | 56069.5622 |  | 56069.5622 |  | 56069.5622 |  | 56069.5622 |  | 56069.5622 |  | 56069.5622 |  | 56069.5622
2026-05-02 | 560915.4632 |  | 56091.5463 |  | 56091.5463 |  | 56091.5463 |  | 56091.5463 |  | 56091.5463 |  | 56091.5463 |  | 56091.5463 |  | 56091.5463 |  | 56091.5463 |  | 56091.5463
2026-05-03 | 561135.3049 |  | 56113.5305 |  | 56113.5305 |  | 56113.5305 |  | 56113.5305 |  | 56113.5305 |  | 56113.5305 |  | 56113.5305 |  | 56113.5305 |  | 56113.5305 |  | 56113.5305
2026-05-04 | 561355.1465 |  | 56135.5147 |  | 56135.5147 |  | 56135.5147 |  | 56135.5147 |  | 56135.5147 |  | 56135.5147 |  | 56135.5147 |  | 56135.5147 |  | 56135.5147 |  | 56135.5147
2026-05-05 | 561574.9882 |  | 56157.4988 |  | 56157.4988 |  | 56157.4988 |  | 56157.4988 |  | 56157.4988 |  | 56157.4988 |  | 56157.4988 |  | 56157.4988 |  | 56157.4988 |  | 56157.4988
2026-05-06 | 561794.8299 |  | 56179.483 |  | 56179.483 |  | 56179.483 |  | 56179.483 |  | 56179.483 |  | 56179.483 |  | 56179.483 |  | 56179.483 |  | 56179.483 |  | 56179.483
2026-05-07 | 562014.6715 |  | 56201.4672 |  | 56201.4672 |  | 56201.4672 |  | 56201.4672 |  | 56201.4672 |  | 56201.4672 |  | 56201.4672 |  | 56201.4672 |  | 56201.4672 |  | 56201.4672
2026-05-08 | 562234.5132 |  | 56223.4513 |  | 56223.4513 |  | 56223.4513 |  | 56223.4513 |  | 56223.4513 |  | 56223.4513 |  | 56223.4513 |  | 56223.4513 |  | 56223.4513 |  | 56223.4513
2026-05-09 | 562454.3549 |  | 56245.4355 |  | 56245.4355 |  | 56245.4355 |  | 56245.4355 |  | 56245.4355 |  | 56245.4355 |  | 56245.4355 |  | 56245.4355 |  | 56245.4355 |  | 56245.4355
2026-05-10 | 562674.1965 |  | 56267.4197 |  | 56267.4197 |  | 56267.4197 |  | 56267.4197 |  | 56267.4197 |  | 56267.4197 |  | 56267.4197 |  | 56267.4197 |  | 56267.4197 |  | 56267.4197
2026-05-11 | 562894.0382 |  | 56289.4038 |  | 56289.4038 |  | 56289.4038 |  | 56289.4038 |  | 56289.4038 |  | 56289.4038 |  | 56289.4038 |  | 56289.4038 |  | 56289.4038 |  | 56289.4038
2026-05-12 | 563113.8799 |  | 56311.388 |  | 56311.388 |  | 56311.388 |  | 56311.388 |  | 56311.388 |  | 56311.388 |  | 56311.388 |  | 56311.388 |  | 56311.388 |  | 56311.388
2026-05-13 | 563333.7215 |  | 56333.3722 |  | 56333.3722 |  | 56333.3722 |  | 56333.3722 |  | 56333.3722 |  | 56333.3722 |  | 56333.3722 |  | 56333.3722 |  | 56333.3722 |  | 56333.3722
2026-05-14 | 563553.5632 |  | 56355.3563 |  | 56355.3563 |  | 56355.3563 |  | 56355.3563 |  | 56355.3563 |  | 56355.3563 |  | 56355.3563 |  | 56355.3563 |  | 56355.3563 |  | 56355.3563
2026-05-15 | 563773.4049 |  | 56377.3405 |  | 56377.3405 |  | 56377.3405 |  | 56377.3405 |  | 56377.3405 |  | 56377.3405 |  | 56377.3405 |  | 56377.3405 |  | 56377.3405 |  | 56377.3405
2026-05-16 | 563993.2465 |  | 56399.3247 |  | 56399.3247 |  | 56399.3247 |  | 56399.3247 |  | 56399.3247 |  | 56399.3247 |  | 56399.3247 |  | 56399.3247 |  | 56399.3247 |  | 56399.3247
2026-05-17 | 564213.0882 |  | 56421.3088 |  | 56421.3088 |  | 56421.3088 |  | 56421.3088 |  | 56421.3088 |  | 56421.3088 |  | 56421.3088 |  | 56421.3088 |  | 56421.3088 |  | 56421.3088
2026-05-18 | 564432.9299 |  | 56443.293 |  | 56443.293 |  | 56443.293 |  | 56443.293 |  | 56443.293 |  | 56443.293 |  | 56443.293 |  | 56443.293 |  | 56443.293 |  | 56443.293
2026-05-19 | 564652.7715 |  | 56465.2772 |  | 56465.2772 |  | 56465.2772 |  | 56465.2772 |  | 56465.2772 |  | 56465.2772 |  | 56465.2772 |  | 56465.2772 |  | 56465.2772 |  | 56465.2772
2026-05-20 | 564872.6132 |  | 56487.2613 |  | 56487.2613 |  | 56487.2613 |  | 56487.2613 |  | 56487.2613 |  | 56487.2613 |  | 56487.2613 |  | 56487.2613 |  | 56487.2613 |  | 56487.2613
2026-05-21 | 565092.4549 |  | 56509.2455 |  | 56509.2455 |  | 56509.2455 |  | 56509.2455 |  | 56509.2455 |  | 56509.2455 |  | 56509.2455 |  | 56509.2455 |  | 56509.2455 |  | 56509.2455
2026-05-22 | 565312.2965 |  | 56531.2297 |  | 56531.2297 |  | 56531.2297 |  | 56531.2297 |  | 56531.2297 |  | 56531.2297 |  | 56531.2297 |  | 56531.2297 |  | 56531.2297 |  | 56531.2297
2026-05-23 | 565532.1382 |  | 56553.2138 |  | 56553.2138 |  | 56553.2138 |  | 56553.2138 |  | 56553.2138 |  | 56553.2138 |  | 56553.2138 |  | 56553.2138 |  | 56553.2138 |  | 56553.2138
2026-05-24 | 565751.9799 |  | 56575.198 |  | 56575.198 |  | 56575.198 |  | 56575.198 |  | 56575.198 |  | 56575.198 |  | 56575.198 |  | 56575.198 |  | 56575.198 |  | 56575.198
2026-05-25 | 565971.8215 |  | 56597.1822 |  | 56597.1822 |  | 56597.1822 |  | 56597.1822 |  | 56597.1822 |  | 56597.1822 |  | 56597.1822 |  | 56597.1822 |  | 56597.1822 |  | 56597.1822
2026-05-26 | 566191.6632 |  | 56619.1663 |  | 56619.1663 |  | 56619.1663 |  | 56619.1663 |  | 56619.1663 |  | 56619.1663 |  | 56619.1663 |  | 56619.1663 |  | 56619.1663 |  | 56619.1663
2026-05-27 | 566411.5049 |  | 56641.1505 |  | 56641.1505 |  | 56641.1505 |  | 56641.1505 |  | 56641.1505 |  | 56641.1505 |  | 56641.1505 |  | 56641.1505 |  | 56641.1505 |  | 56641.1505
2026-05-28 | 566631.3465 |  | 56663.1347 |  | 56663.1347 |  | 56663.1347 |  | 56663.1347 |  | 56663.1347 |  | 56663.1347 |  | 56663.1347 |  | 56663.1347 |  | 56663.1347 |  | 56663.1347
2026-05-29 | 566851.1882 |  | 56685.1188 |  | 56685.1188 |  | 56685.1188 |  | 56685.1188 |  | 56685.1188 |  | 56685.1188 |  | 56685.1188 |  | 56685.1188 |  | 56685.1188 |  | 56685.1188
2026-05-30 | 567071.0299 |  | 56707.103 |  | 56707.103 |  | 56707.103 |  | 56707.103 |  | 56707.103 |  | 56707.103 |  | 56707.103 |  | 56707.103 |  | 56707.103 |  | 56707.103
2026-05-31 | 567290.8715 |  | 56729.0872 |  | 56729.0872 |  | 56729.0872 |  | 56729.0872 |  | 56729.0872 |  | 56729.0872 |  | 56729.0872 |  | 56729.0872 |  | 56729.0872 |  | 56729.0872
2026-06-01 | 567510.7132 |  | 56751.0713 |  | 56751.0713 |  | 56751.0713 |  | 56751.0713 |  | 56751.0713 |  | 56751.0713 |  | 56751.0713 |  | 56751.0713 |  | 56751.0713 |  | 56751.0713
2026-06-02 | 567730.5549 |  | 56773.0555 |  | 56773.0555 |  | 56773.0555 |  | 56773.0555 |  | 56773.0555 |  | 56773.0555 |  | 56773.0555 |  | 56773.0555 |  | 56773.0555 |  | 56773.0555
2026-06-03 | 567950.3965 |  | 56795.0397 |  | 56795.0397 |  | 56795.0397 |  | 56795.0397 |  | 56795.0397 |  | 56795.0397 |  | 56795.0397 |  | 56795.0397 |  | 56795.0397 |  | 56795.0397
2026-06-04 | 568170.2382 |  | 56817.0238 |  | 56817.0238 |  | 56817.0238 |  | 56817.0238 |  | 56817.0238 |  | 56817.0238 |  | 56817.0238 |  | 56817.0238 |  | 56817.0238 |  | 56817.0238
2026-06-05 | 568390.0799 |  | 56839.008 |  | 56839.008 |  | 56839.008 |  | 56839.008 |  | 56839.008 |  | 56839.008 |  | 56839.008 |  | 56839.008 |  | 56839.008 |  | 56839.008
2026-06-06 | 568609.9215 |  | 56860.9922 |  | 56860.9922 |  | 56860.9922 |  | 56860.9922 |  | 56860.9922 |  | 56860.9922 |  | 56860.9922 |  | 56860.9922 |  | 56860.9922 |  | 56860.9922
2026-06-07 | 568829.7632 |  | 56882.9763 |  | 56882.9763 |  | 56882.9763 |  | 56882.9763 |  | 56882.9763 |  | 56882.9763 |  | 56882.9763 |  | 56882.9763 |  | 56882.9763 |  | 56882.9763
2026-06-08 | 569049.6049 |  | 56904.9605 |  | 56904.9605 |  | 56904.9605 |  | 56904.9605 |  | 56904.9605 |  | 56904.9605 |  | 56904.9605 |  | 56904.9605 |  | 56904.9605 |  | 56904.9605
2026-06-09 | 569269.4465 |  | 56926.9447 |  | 56926.9447 |  | 56926.9447 |  | 56926.9447 |  | 56926.9447 |  | 56926.9447 |  | 56926.9447 |  | 56926.9447 |  | 56926.9447 |  | 56926.9447
2026-06-10 | 569489.2882 |  | 56948.9288 |  | 56948.9288 |  | 56948.9288 |  | 56948.9288 |  | 56948.9288 |  | 56948.9288 |  | 56948.9288 |  | 56948.9288 |  | 56948.9288 |  | 56948.9288
2026-06-11 | 569709.1299 |  | 56970.913 |  | 56970.913 |  | 56970.913 |  | 56970.913 |  | 56970.913 |  | 56970.913 |  | 56970.913 |  | 56970.913 |  | 56970.913 |  | 56970.913
2026-06-12 | 569928.9715 |  | 56992.8972 |  | 56992.8972 |  | 56992.8972 |  | 56992.8972 |  | 56992.8972 |  | 56992.8972 |  | 56992.8972 |  | 56992.8972 |  | 56992.8972 |  | 56992.8972
2026-06-13 | 570148.8132 |  | 57014.8813 |  | 57014.8813 |  | 57014.8813 |  | 57014.8813 |  | 57014.8813 |  | 57014.8813 |  | 57014.8813 |  | 57014.8813 |  | 57014.8813 |  | 57014.8813
2026-06-14 | 570368.6549 |  | 57036.8655 |  | 57036.8655 |  | 57036.8655 |  | 57036.8655 |  | 57036.8655 |  | 57036.8655 |  | 57036.8655 |  | 57036.8655 |  | 57036.8655 |  | 57036.8655
2026-06-15 | 570588.4965 |  | 57058.8497 |  | 57058.8497 |  | 57058.8497 |  | 57058.8497 |  | 57058.8497 |  | 57058.8497 |  | 57058.8497 |  | 57058.8497 |  | 57058.8497 |  | 57058.8497
2026-06-16 | 570808.3382 |  | 57080.8338 |  | 57080.8338 |  | 57080.8338 |  | 57080.8338 |  | 57080.8338 |  | 57080.8338 |  | 57080.8338 |  | 57080.8338 |  | 57080.8338 |  | 57080.8338
2026-06-17 | 571028.1799 |  | 57102.818 |  | 57102.818 |  | 57102.818 |  | 57102.818 |  | 57102.818 |  | 57102.818 |  | 57102.818 |  | 57102.818 |  | 57102.818 |  | 57102.818
2026-06-18 | 571248.0215 |  | 57124.8022 |  | 57124.8022 |  | 57124.8022 |  | 57124.8022 |  | 57124.8022 |  | 57124.8022 |  | 57124.8022 |  | 57124.8022 |  | 57124.8022 |  | 57124.8022
2026-06-19 | 571467.8632 |  | 57146.7863 |  | 57146.7863 |  | 57146.7863 |  | 57146.7863 |  | 57146.7863 |  | 57146.7863 |  | 57146.7863 |  | 57146.7863 |  | 57146.7863 |  | 57146.7863
2026-06-20 | 571687.7049 |  | 57168.7705 |  | 57168.7705 |  | 57168.7705 |  | 57168.7705 |  | 57168.7705 |  | 57168.7705 |  | 57168.7705 |  | 57168.7705 |  | 57168.7705 |  | 57168.7705
2026-06-21 | 571907.5465 |  | 57190.7547 |  | 57190.7547 |  | 57190.7547 |  | 57190.7547 |  | 57190.7547 |  | 57190.7547 |  | 57190.7547 |  | 57190.7547 |  | 57190.7547 |  | 57190.7547
2026-06-22 | 572127.3882 |  | 57212.7388 |  | 57212.7388 |  | 57212.7388 |  | 57212.7388 |  | 57212.7388 |  | 57212.7388 |  | 57212.7388 |  | 57212.7388 |  | 57212.7388 |  | 57212.7388
2026-06-23 | 572347.2299 |  | 57234.723 |  | 57234.723 |  | 57234.723 |  | 57234.723 |  | 57234.723 |  | 57234.723 |  | 57234.723 |  | 57234.723 |  | 57234.723 |  | 57234.723
2026-06-24 | 572567.0715 |  | 57256.7072 |  | 57256.7072 |  | 57256.7072 |  | 57256.7072 |  | 57256.7072 |  | 57256.7072 |  | 57256.7072 |  | 57256.7072 |  | 57256.7072 |  | 57256.7072
2026-06-25 | 572786.9132 |  | 57278.6913 |  | 57278.6913 |  | 57278.6913 |  | 57278.6913 |  | 57278.6913 |  | 57278.6913 |  | 57278.6913 |  | 57278.6913 |  | 57278.6913 |  | 57278.6913
2026-06-26 | 573006.7549 |  | 57300.6755 |  | 57300.6755 |  | 57300.6755 |  | 57300.6755 |  | 57300.6755 |  | 57300.6755 |  | 57300.6755 |  | 57300.6755 |  | 57300.6755 |  | 57300.6755
2026-06-27 | 573226.5965 |  | 57322.6597 |  | 57322.6597 |  | 57322.6597 |  | 57322.6597 |  | 57322.6597 |  | 57322.6597 |  | 57322.6597 |  | 57322.6597 |  | 57322.6597 |  | 57322.6597
2026-06-28 | 573446.4382 |  | 57344.6438 |  | 57344.6438 |  | 57344.6438 |  | 57344.6438 |  | 57344.6438 |  | 57344.6438 |  | 57344.6438 |  | 57344.6438 |  | 57344.6438 |  | 57344.6438
2026-06-29 | 573666.2799 |  | 57366.628 |  | 57366.628 |  | 57366.628 |  | 57366.628 |  | 57366.628 |  | 57366.628 |  | 57366.628 |  | 57366.628 |  | 57366.628 |  | 57366.628
2026-06-30 | 573886.1215 |  | 57388.6122 |  | 57388.6122 |  | 57388.6122 |  | 57388.6122 |  | 57388.6122 |  | 57388.6122 |  | 57388.6122 |  | 57388.6122 |  | 57388.6122 |  | 57388.6122
2026-07-01 | 574105.9632 |  | 57410.5963 |  | 57410.5963 |  | 57410.5963 |  | 57410.5963 |  | 57410.5963 |  | 57410.5963 |  | 57410.5963 |  | 57410.5963 |  | 57410.5963 |  | 57410.5963
2026-07-02 | 574325.8049 |  | 57432.5805 |  | 57432.5805 |  | 57432.5805 |  | 57432.5805 |  | 57432.5805 |  | 57432.5805 |  | 57432.5805 |  | 57432.5805 |  | 57432.5805 |  | 57432.5805
2026-07-03 | 574545.6465 |  | 57454.5647 |  | 57454.5647 |  | 57454.5647 |  | 57454.5647 |  | 57454.5647 |  | 57454.5647 |  | 57454.5647 |  | 57454.5647 |  | 57454.5647 |  | 57454.5647
2026-07-04 | 574765.4882 |  | 57476.5488 |  | 57476.5488 |  | 57476.5488 |  | 57476.5488 |  | 57476.5488 |  | 57476.5488 |  | 57476.5488 |  | 57476.5488 |  | 57476.5488 |  | 57476.5488
2026-07-05 | 574985.3299 |  | 57498.533 |  | 57498.533 |  | 57498.533 |  | 57498.533 |  | 57498.533 |  | 57498.533 |  | 57498.533 |  | 57498.533 |  | 57498.533 |  | 57498.533
2026-07-06 | 575205.1715 |  | 57520.5172 |  | 57520.5172 |  | 57520.5172 |  | 57520.5172 |  | 57520.5172 |  | 57520.5172 |  | 57520.5172 |  | 57520.5172 |  | 57520.5172 |  | 57520.5172
2026-07-07 | 575425.0132 |  | 57542.5013 |  | 57542.5013 |  | 57542.5013 |  | 57542.5013 |  | 57542.5013 |  | 57542.5013 |  | 57542.5013 |  | 57542.5013 |  | 57542.5013 |  | 57542.5013
2026-07-08 | 575644.8549 |  | 57564.4855 |  | 57564.4855 |  | 57564.4855 |  | 57564.4855 |  | 57564.4855 |  | 57564.4855 |  | 57564.4855 |  | 57564.4855 |  | 57564.4855 |  | 57564.4855
2026-07-09 | 575864.6965 |  | 57586.4697 |  | 57586.4697 |  | 57586.4697 |  | 57586.4697 |  | 57586.4697 |  | 57586.4697 |  | 57586.4697 |  | 57586.4697 |  | 57586.4697 |  | 57586.4697
2026-07-10 | 576084.5382 |  | 57608.4538 |  | 57608.4538 |  | 57608.4538 |  | 57608.4538 |  | 57608.4538 |  | 57608.4538 |  | 57608.4538 |  | 57608.4538 |  | 57608.4538 |  | 57608.4538
2026-07-11 | 576304.3799 |  | 57630.438 |  | 57630.438 |  | 57630.438 |  | 57630.438 |  | 57630.438 |  | 57630.438 |  | 57630.438 |  | 57630.438 |  | 57630.438 |  | 57630.438
2026-07-12 | 576524.2215 |  | 57652.4222 |  | 57652.4222 |  | 57652.4222 |  | 57652.4222 |  | 57652.4222 |  | 57652.4222 |  | 57652.4222 |  | 57652.4222 |  | 57652.4222 |  | 57652.4222
2026-07-13 | 576744.0632 |  | 57674.4063 |  | 57674.4063 |  | 57674.4063 |  | 57674.4063 |  | 57674.4063 |  | 57674.4063 |  | 57674.4063 |  | 57674.4063 |  | 57674.4063 |  | 57674.4063
2026-07-14 | 576963.9049 |  | 57696.3905 |  | 57696.3905 |  | 57696.3905 |  | 57696.3905 |  | 57696.3905 |  | 57696.3905 |  | 57696.3905 |  | 57696.3905 |  | 57696.3905 |  | 57696.3905
2026-07-15 | 577183.7465 |  | 57718.3747 |  | 57718.3747 |  | 57718.3747 |  | 57718.3747 |  | 57718.3747 |  | 57718.3747 |  | 57718.3747 |  | 57718.3747 |  | 57718.3747 |  | 57718.3747
2026-07-16 | 577403.5882 |  | 57740.3588 |  | 57740.3588 |  | 57740.3588 |  | 57740.3588 |  | 57740.3588 |  | 57740.3588 |  | 57740.3588 |  | 57740.3588 |  | 57740.3588 |  | 57740.3588
2026-07-17 | 577623.4299 |  | 57762.343 |  | 57762.343 |  | 57762.343 |  | 57762.343 |  | 57762.343 |  | 57762.343 |  | 57762.343 |  | 57762.343 |  | 57762.343 |  | 57762.343
2026-07-18 | 577843.2715 |  | 57784.3272 |  | 57784.3272 |  | 57784.3272 |  | 57784.3272 |  | 57784.3272 |  | 57784.3272 |  | 57784.3272 |  | 57784.3272 |  | 57784.3272 |  | 57784.3272
2026-07-19 | 578063.1132 |  | 57806.3113 |  | 57806.3113 |  | 57806.3113 |  | 57806.3113 |  | 57806.3113 |  | 57806.3113 |  | 57806.3113 |  | 57806.3113 |  | 57806.3113 |  | 57806.3113
2026-07-20 | 578282.9549 |  | 57828.2955 |  | 57828.2955 |  | 57828.2955 |  | 57828.2955 |  | 57828.2955 |  | 57828.2955 |  | 57828.2955 |  | 57828.2955 |  | 57828.2955 |  | 57828.2955
2026-07-21 | 578502.7965 |  | 57850.2797 |  | 57850.2797 |  | 57850.2797 |  | 57850.2797 |  | 57850.2797 |  | 57850.2797 |  | 57850.2797 |  | 57850.2797 |  | 57850.2797 |  | 57850.2797
2026-07-22 | 578722.6382 |  | 57872.2638 |  | 57872.2638 |  | 57872.2638 |  | 57872.2638 |  | 57872.2638 |  | 57872.2638 |  | 57872.2638 |  | 57872.2638 |  | 57872.2638 |  | 57872.2638
2026-07-23 | 578942.4799 |  | 57894.248 |  | 57894.248 |  | 57894.248 |  | 57894.248 |  | 57894.248 |  | 57894.248 |  | 57894.248 |  | 57894.248 |  | 57894.248 |  | 57894.248
2026-07-24 | 579162.3215 |  | 57916.2322 |  | 57916.2322 |  | 57916.2322 |  | 57916.2322 |  | 57916.2322 |  | 57916.2322 |  | 57916.2322 |  | 57916.2322 |  | 57916.2322 |  | 57916.2322
2026-07-25 | 579382.1632 |  | 57938.2163 |  | 57938.2163 |  | 57938.2163 |  | 57938.2163 |  | 57938.2163 |  | 57938.2163 |  | 57938.2163 |  | 57938.2163 |  | 57938.2163 |  | 57938.2163
2026-07-26 | 579602.0049 |  | 57960.2005 |  | 57960.2005 |  | 57960.2005 |  | 57960.2005 |  | 57960.2005 |  | 57960.2005 |  | 57960.2005 |  | 57960.2005 |  | 57960.2005 |  | 57960.2005
2026-07-27 | 579821.8465 |  | 57982.1847 |  | 57982.1847 |  | 57982.1847 |  | 57982.1847 |  | 57982.1847 |  | 57982.1847 |  | 57982.1847 |  | 57982.1847 |  | 57982.1847 |  | 57982.1847
2026-07-28 | 580041.6882 |  | 58004.1688 |  | 58004.1688 |  | 58004.1688 |  | 58004.1688 |  | 58004.1688 |  | 58004.1688 |  | 58004.1688 |  | 58004.1688 |  | 58004.1688 |  | 58004.1688
2026-07-29 | 580261.5299 |  | 58026.153 |  | 58026.153 |  | 58026.153 |  | 58026.153 |  | 58026.153 |  | 58026.153 |  | 58026.153 |  | 58026.153 |  | 58026.153 |  | 58026.153
2026-07-30 | 580481.3715 |  | 58048.1372 |  | 58048.1372 |  | 58048.1372 |  | 58048.1372 |  | 58048.1372 |  | 58048.1372 |  | 58048.1372 |  | 58048.1372 |  | 58048.1372 |  | 58048.1372
2026-07-31 | 580701.2132 |  | 58070.1213 |  | 58070.1213 |  | 58070.1213 |  | 58070.1213 |  | 58070.1213 |  | 58070.1213 |  | 58070.1213 |  | 58070.1213 |  | 58070.1213 |  | 58070.1213
2026-08-01 | 580921.0549 |  | 58092.1055 |  | 58092.1055 |  | 58092.1055 |  | 58092.1055 |  | 58092.1055 |  | 58092.1055 |  | 58092.1055 |  | 58092.1055 |  | 58092.1055 |  | 58092.1055
2026-08-02 | 581140.8965 |  | 58114.0897 |  | 58114.0897 |  | 58114.0897 |  | 58114.0897 |  | 58114.0897 |  | 58114.0897 |  | 58114.0897 |  | 58114.0897 |  | 58114.0897 |  | 58114.0897
2026-08-03 | 581360.7382 |  | 58136.0738 |  | 58136.0738 |  | 58136.0738 |  | 58136.0738 |  | 58136.0738 |  | 58136.0738 |  | 58136.0738 |  | 58136.0738 |  | 58136.0738 |  | 58136.0738
2026-08-04 | 581580.5799 |  | 58158.058 |  | 58158.058 |  | 58158.058 |  | 58158.058 |  | 58158.058 |  | 58158.058 |  | 58158.058 |  | 58158.058 |  | 58158.058 |  | 58158.058
2026-08-05 | 581800.4215 |  | 58180.0422 |  | 58180.0422 |  | 58180.0422 |  | 58180.0422 |  | 58180.0422 |  | 58180.0422 |  | 58180.0422 |  | 58180.0422 |  | 58180.0422 |  | 58180.0422
2026-08-06 | 582020.2632 |  | 58202.0263 |  | 58202.0263 |  | 58202.0263 |  | 58202.0263 |  | 58202.0263 |  | 58202.0263 |  | 58202.0263 |  | 58202.0263 |  | 58202.0263 |  | 58202.0263
2026-08-07 | 582240.1049 |  | 58224.0105 |  | 58224.0105 |  | 58224.0105 |  | 58224.0105 |  | 58224.0105 |  | 58224.0105 |  | 58224.0105 |  | 58224.0105 |  | 58224.0105 |  | 58224.0105
2026-08-08 | 582459.9465 |  | 58245.9947 |  | 58245.9947 |  | 58245.9947 |  | 58245.9947 |  | 58245.9947 |  | 58245.9947 |  | 58245.9947 |  | 58245.9947 |  | 58245.9947 |  | 58245.9947
2026-08-09 | 582679.7882 |  | 58267.9788 |  | 58267.9788 |  | 58267.9788 |  | 58267.9788 |  | 58267.9788 |  | 58267.9788 |  | 58267.9788 |  | 58267.9788 |  | 58267.9788 |  | 58267.9788
2026-08-10 | 582899.6299 |  | 58289.963 |  | 58289.963 |  | 58289.963 |  | 58289.963 |  | 58289.963 |  | 58289.963 |  | 58289.963 |  | 58289.963 |  | 58289.963 |  | 58289.963
2026-08-11 | 583119.4715 |  | 58311.9472 |  | 58311.9472 |  | 58311.9472 |  | 58311.9472 |  | 58311.9472 |  | 58311.9472 |  | 58311.9472 |  | 58311.9472 |  | 58311.9472 |  | 58311.9472
2026-08-12 | 583339.3132 |  | 58333.9313 |  | 58333.9313 |  | 58333.9313 |  | 58333.9313 |  | 58333.9313 |  | 58333.9313 |  | 58333.9313 |  | 58333.9313 |  | 58333.9313 |  | 58333.9313
2026-08-13 | 583559.1549 |  | 58355.9155 |  | 58355.9155 |  | 58355.9155 |  | 58355.9155 |  | 58355.9155 |  | 58355.9155 |  | 58355.9155 |  | 58355.9155 |  | 58355.9155 |  | 58355.9155
2026-08-14 | 583778.9965 |  | 58377.8997 |  | 58377.8997 |  | 58377.8997 |  | 58377.8997 |  | 58377.8997 |  | 58377.8997 |  | 58377.8997 |  | 58377.8997 |  | 58377.8997 |  | 58377.8997
2026-08-15 | 583998.8382 |  | 58399.8838 |  | 58399.8838 |  | 58399.8838 |  | 58399.8838 |  | 58399.8838 |  | 58399.8838 |  | 58399.8838 |  | 58399.8838 |  | 58399.8838 |  | 58399.8838
2026-08-16 | 584218.6799 |  | 58421.868 |  | 58421.868 |  | 58421.868 |  | 58421.868 |  | 58421.868 |  | 58421.868 |  | 58421.868 |  | 58421.868 |  | 58421.868 |  | 58421.868
2026-08-18 | 588395.3882 |  | 58839.5388 |  | 58839.5388 |  | 58839.5388 |  | 58839.5388 |  | 58839.5388 |  | 58839.5388 |  | 58839.5388 |  | 58839.5388 |  | 58839.5388 |  | 58839.5388
2026-08-19 | 592572.0965 |  | 59257.2097 |  | 59257.2097 |  | 59257.2097 |  | 59257.2097 |  | 59257.2097 |  | 59257.2097 |  | 59257.2097 |  | 59257.2097 |  | 59257.2097 |  | 59257.2097
2026-08-20 | 596748.8049 |  | 59674.8805 |  | 59674.8805 |  | 59674.8805 |  | 59674.8805 |  | 59674.8805 |  | 59674.8805 |  | 59674.8805 |  | 59674.8805 |  | 59674.8805 |  | 59674.8805
2026-08-21 | 600925.5132 |  | 60092.5513 |  | 60092.5513 |  | 60092.5513 |  | 60092.5513 |  | 60092.5513 |  | 60092.5513 |  | 60092.5513 |  | 60092.5513 |  | 60092.5513 |  | 60092.5513
2026-08-22 | 605102.2215 |  | 60510.2222 |  | 60510.2222 |  | 60510.2222 |  | 60510.2222 |  | 60510.2222 |  | 60510.2222 |  | 60510.2222 |  | 60510.2222 |  | 60510.2222 |  | 60510.2222
2026-08-23 | 609278.9299 |  | 60927.893 |  | 60927.893 |  | 60927.893 |  | 60927.893 |  | 60927.893 |  | 60927.893 |  | 60927.893 |  | 60927.893 |  | 60927.893 |  | 60927.893
2026-08-24 | 613455.6382 |  | 61345.5638 |  | 61345.5638 |  | 61345.5638 |  | 61345.5638 |  | 61345.5638 |  | 61345.5638 |  | 61345.5638 |  | 61345.5638 |  | 61345.5638 |  | 61345.5638
2026-08-25 | 617632.3465 |  | 61763.2347 |  | 61763.2347 |  | 61763.2347 |  | 61763.2347 |  | 61763.2347 |  | 61763.2347 |  | 61763.2347 |  | 61763.2347 |  | 61763.2347 |  | 61763.2347
2026-08-26 | 621809.0549 |  | 62180.9055 |  | 62180.9055 |  | 62180.9055 |  | 62180.9055 |  | 62180.9055 |  | 62180.9055 |  | 62180.9055 |  | 62180.9055 |  | 62180.9055 |  | 62180.9055
2026-08-27 | 625985.7632 |  | 62598.5763 |  | 62598.5763 |  | 62598.5763 |  | 62598.5763 |  | 62598.5763 |  | 62598.5763 |  | 62598.5763 |  | 62598.5763 |  | 62598.5763 |  | 62598.5763
2026-08-28 | 630162.4715 |  | 63016.2472 |  | 63016.2472 |  | 63016.2472 |  | 63016.2472 |  | 63016.2472 |  | 63016.2472 |  | 63016.2472 |  | 63016.2472 |  | 63016.2472 |  | 63016.2472
2026-08-29 | 634339.1799 |  | 63433.918 |  | 63433.918 |  | 63433.918 |  | 63433.918 |  | 63433.918 |  | 63433.918 |  | 63433.918 |  | 63433.918 |  | 63433.918 |  | 63433.918
2026-08-30 | 638515.8882 |  | 63851.5888 |  | 63851.5888 |  | 63851.5888 |  | 63851.5888 |  | 63851.5888 |  | 63851.5888 |  | 63851.5888 |  | 63851.5888 |  | 63851.5888 |  | 63851.5888
2026-08-31 | 642692.5965 |  | 64269.2597 |  | 64269.2597 |  | 64269.2597 |  | 64269.2597 |  | 64269.2597 |  | 64269.2597 |  | 64269.2597 |  | 64269.2597 |  | 64269.2597 |  | 64269.2597
2026-09-01 | 646869.3049 |  | 64686.9305 |  | 64686.9305 |  | 64686.9305 |  | 64686.9305 |  | 64686.9305 |  | 64686.9305 |  | 64686.9305 |  | 64686.9305 |  | 64686.9305 |  | 64686.9305
2026-09-02 | 651046.0132 |  | 65104.6013 |  | 65104.6013 |  | 65104.6013 |  | 65104.6013 |  | 65104.6013 |  | 65104.6013 |  | 65104.6013 |  | 65104.6013 |  | 65104.6013 |  | 65104.6013
2026-09-03 | 655222.7215 |  | 65522.2722 |  | 65522.2722 |  | 65522.2722 |  | 65522.2722 |  | 65522.2722 |  | 65522.2722 |  | 65522.2722 |  | 65522.2722 |  | 65522.2722 |  | 65522.2722
2026-09-04 | 659399.4299 |  | 65939.943 |  | 65939.943 |  | 65939.943 |  | 65939.943 |  | 65939.943 |  | 65939.943 |  | 65939.943 |  | 65939.943 |  | 65939.943 |  | 65939.943
2026-09-05 | 663576.1382 |  | 66357.6138 |  | 66357.6138 |  | 66357.6138 |  | 66357.6138 |  | 66357.6138 |  | 66357.6138 |  | 66357.6138 |  | 66357.6138 |  | 66357.6138 |  | 66357.6138
2026-09-06 | 667752.8465 |  | 66775.2847 |  | 66775.2847 |  | 66775.2847 |  | 66775.2847 |  | 66775.2847 |  | 66775.2847 |  | 66775.2847 |  | 66775.2847 |  | 66775.2847 |  | 66775.2847
2026-09-07 | 671929.5549 |  | 67192.9555 |  | 67192.9555 |  | 67192.9555 |  | 67192.9555 |  | 67192.9555 |  | 67192.9555 |  | 67192.9555 |  | 67192.9555 |  | 67192.9555 |  | 67192.9555
2026-09-08 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-09 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-10 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-11 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-12 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-13 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-14 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-15 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-16 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-17 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-18 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-19 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-20 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-21 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-22 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-23 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-24 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-25 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-26 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-27 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-28 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-29 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-09-30 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-10-01 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-10-02 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-10-03 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-10-04 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-10-05 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-10-06 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-10-07 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-10-08 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-10-09 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-10-10 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-10-11 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263
2026-10-12 | 676106.2632 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263 |  | 67610.6263

## Equipment Cost
Date | Planned Equipment (Cumulative) | Actual Equipment (Cumulative) | Planned 1805 · Equipment - Forklift (Cumulative) | Actual 1805 · Equipment - Forklift (Cumulative) | Planned 1818 · Equipment - BCU (Cumulative) | Actual 1818 · Equipment - BCU (Cumulative) | Planned 1819 · Equipment - TPMB (Cumulative) | Actual 1819 · Equipment - TPMB (Cumulative) | Planned 1820 · Equipment & Tools (Cumulative) | Actual 1820 · Equipment & Tools (Cumulative) | Planned 1821 · Equipment - C3 (Cumulative) | Actual 1821 · Equipment - C3 (Cumulative) | Planned 1822 · Equipment - C2 (Cumulative) | Actual 1822 · Equipment - C2 (Cumulative) | Planned 1823 · Equipment - TCU Basic (Cumulative) | Actual 1823 · Equipment - TCU Basic (Cumulative) | Planned 1824 · Equipment - TCU PLC (Cumulative) | Actual 1824 · Equipment - TCU PLC (Cumulative) | Planned 1825 · Equipment - Blower Skids (Cumulative) | Actual 1825 · Equipment - Blower Skids (Cumulative) | Planned 1826 · Equipment - Well Heads (Cumulative) | Actual 1826 · Equipment - Well Heads (Cumulative) | Planned 1827 · Equipment - Thermal Wells (Cumulative) | Actual 1827 · Equipment - Thermal Wells (Cumulative) | Planned 1829 · Equipment - Water Treatment Sys (Cumulative) | Actual 1829 · Equipment - Water Treatment Sys (Cumulative) | Planned 1830 · Equipment - Vapor Extraction (Cumulative) | Actual 1830 · Equipment - Vapor Extraction (Cumulative) | Planned 1831 · Equipment - GTR/C3 Components (Cumulative) | Actual 1831 · Equipment - GTR/C3 Components (Cumulative) | Planned 1832 · Equip - Control/Dist panels (Cumulative) | Actual 1832 · Equip - Control/Dist panels (Cumulative) | Planned 1833 · Equipment - Office & computer (Cumulative) | Actual 1833 · Equipment - Office & computer (Cumulative) | Planned 5113 · Repairs & maint (Direct) (Cumulative) | Actual 5113 · Repairs & maint (Direct) (Cumulative)
2025-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 1441.4843 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0
2025-06-02 | 2882.9687 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0
2025-06-03 | 4324.453 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0
2025-06-04 | 5765.9373 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0
2025-06-05 | 7207.4217 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0
2025-06-06 | 8648.906 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0
2025-06-07 | 10090.3904 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0
2025-06-08 | 11531.8747 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0
2025-06-09 | 12973.359 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0
2025-06-10 | 14414.8434 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0
2025-06-11 | 15856.3277 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0
2025-06-12 | 17297.812 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0
2025-06-13 | 18739.2964 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0
2025-06-14 | 20180.7807 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0
2025-06-15 | 21622.2651 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0
2025-06-16 | 23063.7494 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0
2025-06-17 | 24505.2337 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0
2025-06-18 | 25946.7181 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0
2025-06-19 | 27388.2024 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0
2025-06-20 | 28829.6867 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0
2025-06-21 | 30271.1711 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0
2025-06-22 | 31712.6554 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0
2025-06-23 | 33154.1398 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0
2025-06-24 | 34595.6241 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0
2025-06-25 | 36037.1084 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0
2025-06-26 | 37478.5928 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0
2025-06-27 | 38920.0771 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0
2025-06-28 | 40361.5614 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0
2025-06-29 | 41803.0458 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0
2025-06-30 | 43244.5301 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0
2025-07-01 | 44686.0145 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0
2025-07-02 | 46127.4988 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0
2025-07-03 | 47568.9831 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0
2025-07-04 | 49010.4675 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0
2025-07-05 | 50451.9518 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0
2025-07-06 | 51893.4361 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0
2025-07-07 | 53334.9205 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0
2025-07-08 | 54776.4048 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0
2025-07-09 | 56217.8892 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0
2025-07-10 | 57659.3735 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0
2025-07-11 | 59100.8578 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0
2025-07-12 | 60542.3422 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0
2025-07-13 | 61983.8265 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0
2025-07-14 | 63425.3108 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0
2025-07-15 | 64866.7952 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0
2025-07-16 | 66308.2795 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0
2025-07-17 | 67749.7639 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0
2025-07-18 | 69191.2482 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0
2025-07-19 | 70632.7325 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0
2025-07-20 | 72074.2169 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0
2025-07-21 | 73515.7012 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0
2025-07-22 | 74957.1855 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0
2025-07-23 | 76398.6699 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0
2025-07-24 | 77840.1542 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0
2025-07-25 | 79281.6386 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0
2025-07-26 | 80723.1229 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0
2025-07-27 | 82164.6072 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0
2025-07-28 | 83606.0916 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0
2025-07-29 | 85047.5759 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0
2025-07-30 | 86489.0602 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0
2025-07-31 | 87930.5446 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0
2025-08-01 | 89372.0289 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0
2025-08-02 | 90813.5133 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0
2025-08-03 | 92254.9976 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0
2025-08-04 | 93696.4819 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0
2025-08-05 | 95137.9663 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0
2025-08-06 | 96579.4506 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0
2025-08-07 | 98020.9349 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0
2025-08-08 | 99462.4193 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0
2025-08-09 | 100903.9036 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0
2025-08-10 | 102345.388 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0
2025-08-11 | 103786.8723 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0
2025-08-12 | 105228.3566 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0
2025-08-13 | 106669.841 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0
2025-08-14 | 108111.3253 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0
2025-08-15 | 109552.8096 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0
2025-08-16 | 110994.294 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0
2025-08-17 | 112435.7783 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0
2025-08-18 | 113877.2627 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0
2025-08-19 | 115318.747 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0
2025-08-20 | 116760.2313 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0
2025-08-21 | 118201.7157 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0
2025-08-22 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-08-23 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-08-24 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-08-25 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-08-26 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-08-27 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-08-28 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-08-29 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-08-30 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-08-31 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-01 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-02 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-03 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-04 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-05 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-06 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-07 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-08 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-09 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-10 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-11 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-12 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-13 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-14 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-15 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-16 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-17 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-18 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-19 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-20 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-21 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-22 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-23 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-24 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-25 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-26 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-27 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-28 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-29 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-30 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-01 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-02 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-03 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-04 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-05 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-06 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-07 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-08 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-09 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-10 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-11 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-12 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-13 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-14 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-15 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-16 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-17 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-18 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-19 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-20 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-21 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-22 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-23 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-24 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-25 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-26 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-27 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-28 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-29 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-30 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-31 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-01 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-02 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-03 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-04 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-05 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-06 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-07 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-08 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-09 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-10 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-11 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-12 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-13 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-14 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-15 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-16 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-17 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-18 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-19 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-20 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-21 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-22 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-23 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-24 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-25 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-26 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-27 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-28 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-29 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-11-30 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-01 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-02 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-03 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-04 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-05 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-06 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-07 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-08 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-09 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-10 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-11 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-12 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-13 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-14 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-15 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-16 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-17 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-18 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-19 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-20 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-21 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-22 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-23 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-24 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-25 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-26 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-27 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-28 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-29 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-30 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-12-31 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-01 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-02 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-03 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-04 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-05 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-06 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-07 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-08 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-09 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-10 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-11 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-12 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-13 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-14 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-15 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-16 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-17 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-18 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-19 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-20 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-21 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-22 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-23 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-24 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-25 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-26 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-27 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-28 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-29 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-30 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-01-31 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-01 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-02 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-03 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-04 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-05 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-06 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-07 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-08 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-09 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-10 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-11 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-12 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-13 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-14 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-15 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-16 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-17 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-18 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-19 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-20 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-21 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-22 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-23 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-24 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-25 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-26 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-27 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-02-28 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-01 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-02 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-03 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-04 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-05 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-06 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-07 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-08 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-09 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-10 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-11 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-12 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-13 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-14 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-15 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-16 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-17 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-18 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-19 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-20 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-21 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-22 | 119643.2 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 386.82 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2026-03-23 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-24 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-25 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-26 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-27 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-28 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-29 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-30 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-31 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-01 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-02 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-03 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-04 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-05 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-06 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-07 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-08 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-09 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-10 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-11 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-12 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-13 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-14 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-15 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-16 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-17 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-18 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-19 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-20 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-21 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-22 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-23 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-24 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-25 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-26 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-27 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-28 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-29 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-30 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-01 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-02 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-03 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-04 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-05 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-06 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-07 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-08 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-09 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-10 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-11 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-12 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-13 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-14 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-15 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-16 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-17 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-18 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-19 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-20 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-21 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-22 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-23 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-24 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-25 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-26 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-27 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-28 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-29 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-30 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-31 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-01 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-02 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-03 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-04 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-05 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-06 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-07 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-08 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-09 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-10 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-11 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-12 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-13 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-14 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-15 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-16 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-17 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-18 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-19 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-20 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-21 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-22 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-23 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-24 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-25 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-26 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-27 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-28 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-29 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-30 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-01 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-02 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-03 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-04 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-05 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-06 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-07 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-08 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-09 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-10 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-11 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-12 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-13 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-14 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-15 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-16 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-17 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-18 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-19 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-20 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-21 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-22 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-23 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-24 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-25 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-26 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-27 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-28 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-29 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-30 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-31 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-01 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-02 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-03 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-04 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-05 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-06 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-07 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-08 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-09 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-10 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-11 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-12 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-13 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-14 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-15 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-16 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-18 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-19 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-20 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-21 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-22 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-23 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-24 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-25 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-26 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-27 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-28 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-29 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-30 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-08-31 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-01 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-02 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-03 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-04 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-05 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-06 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-07 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-08 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-09 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-10 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-11 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-12 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-13 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-14 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-15 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-16 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-17 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-18 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-19 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-20 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-21 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-22 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-23 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-24 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-25 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-26 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-27 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-28 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-29 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-09-30 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-10-01 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-10-02 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-10-03 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-10-04 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-10-05 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-10-06 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-10-07 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-10-08 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-10-09 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-10-10 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-10-11 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-10-12 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353

## Labor-by months
Month | Actual Geo Total (Monthly) | Actual On Site Personal (Monthly) | Actual Remote Personal (Monthly) | Planned GEO total personal (Monthly) | Planned on site personal (Monthly) | Planned remote personal (Monthly) | Planned Technician I (Monthly) | Actual Technician I (Monthly) | Planned Technician II (Monthly) | Actual Technician II (Monthly) | Planned Welder (Monthly) | Actual Welder (Monthly) | Planned Engineer/supervisor (Monthly) | Actual Engineer/supervisor (Monthly) | Planned Manager/senior Engineer (Monthly) | Actual Manager/senior Engineer (Monthly) | Planned Remote mid engineer (Monthly) | Actual Remote mid engineer (Monthly) | Planned Remote senior (Monthly) | Actual Remote senior (Monthly) | Assigned Task ID
April 25 | 25 | 0 | 25 | 68.75 | 0 | 68.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.5 | 0 | 15.25 | 0 | 100
May 25 | 6 | 0 | 6 | 68.75 | 0 | 68.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.5 | 0 | 15.25 | 0 | 100
June 25 | 14 | 4 | 10 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200
July 25 | 54 | 52 | 2 | 34.086 | 27.9892 | 6.0968 | 0 | 0 | 10.1613 | 0 | 3.8333 | 0 | 13.9946 | 0 | 0 | 0 | 5.0806 | 0 | 1.0161 | 0 | 300
August 25 | 78 | 74 | 4 | 66.9785 | 52.7527 | 14.2258 | 0 | 0 | 23.7097 | 0 | 2.6667 | 0 | 26.3763 | 0 | 0 | 0 | 11.8548 | 0 | 2.371 | 0 | 300
September 25 | 106.625 | 92 | 14.625 | 32.3747 | 25.8095 | 6.5653 | 5.8879 | 0 | 7.0169 | 0 | 8.8318 | 0 | 9.9608 | 0 | 2.9439 | 0 | 5.2748 | 0 | 1.2905 | 0 | 400
October 25 | 76.375 | 75 | 1.375 | 32.243 | 25.7944 | 6.4486 | 6.4486 | 0 | 6.4486 | 0 | 9.6729 | 0 | 9.6729 | 0 | 3.2243 | 0 | 5.1589 | 0 | 1.2897 | 0 | 400
November 25 | 52.625 | 52 | 0.625 | 28.0374 | 22.4299 | 5.6075 | 5.6075 | 0 | 5.6075 | 0 | 8.4112 | 0 | 8.4112 | 0 | 2.8037 | 0 | 4.486 | 0 | 1.1215 | 0 | 400
December 25 | 80.125 | 80 | 0.125 | 32.243 | 25.7944 | 6.4486 | 6.4486 | 0 | 6.4486 | 0 | 9.6729 | 0 | 9.6729 | 0 | 3.2243 | 0 | 5.1589 | 0 | 1.2897 | 0 | 400
January 26 | 64.625 | 64 | 0.625 | 33.7131 | 26.0056 | 7.7075 | 7.394 | 0 | 7.394 | 0 | 8.4112 | 0 | 10.2004 | 0 | 3.4001 | 0 | 5.986 | 0 | 1.7215 | 0 | 500
February 26 | 42.375 | 39 | 3.375 | 52.9732 | 33.3732 | 19.6 | 16.674 | 0 | 16.674 | 0 | 0 | 0 | 16.6992 | 0 | 5.5664 | 0 | 14 | 0 | 5.6 | 0 | 500
March 26 | 28.375 | 24 | 4.375 | 58.6489 | 36.9489 | 21.7 | 18.4605 | 0 | 18.4605 | 0 | 0 | 0 | 18.4884 | 0 | 6.1628 | 0 | 15.5 | 0 | 6.2 | 0 | 500
April 26 | 0 | 0 | 0 | 56.757 | 35.757 | 21 | 17.865 | 0 | 17.865 | 0 | 0 | 0 | 17.892 | 0 | 5.964 | 0 | 15 | 0 | 6 | 0 | 500
May 26 | 0 | 0 | 0 | 58.6489 | 36.9489 | 21.7 | 18.4605 | 0 | 18.4605 | 0 | 0 | 0 | 18.4884 | 0 | 6.1628 | 0 | 15.5 | 0 | 6.2 | 0 | 500
June 26 | 0 | 0 | 0 | 56.757 | 35.757 | 21 | 17.865 | 0 | 17.865 | 0 | 0 | 0 | 17.892 | 0 | 5.964 | 0 | 15 | 0 | 6 | 0 | 500
July 26 | 0 | 0 | 0 | 58.6489 | 36.9489 | 21.7 | 18.4605 | 0 | 18.4605 | 0 | 0 | 0 | 18.4884 | 0 | 6.1628 | 0 | 15.5 | 0 | 6.2 | 0 | 500
August 26 | 0 | 0 | 0 | 93.0954 | 65.3204 | 27.775 | 29.528 | 0 | 29.528 | 0 | 10 | 0 | 25.7924 | 0 | 8.1808 | 0 | 20.45 | 0 | 7.325 | 0 | 700
September 26 | 0 | 0 | 0 | 64.215 | 27.75 | 36.465 | 12 | 0 | 12 | 0 | 6 | 0 | 9.75 | 0 | 3 | 0 | 27.39 | 0 | 9.075 | 0 | 700
October 26 | 0 | 0 | 0 | 13.26 | 0 | 13.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.96 | 0 | 3.3 | 0 | 700

## Deleted Duplicates
Date | Account | Amount | Type | Num | Memo | Split | Source_File | Category
No duplicates found

## Labor-by days
Date | Actual Geo Total (Daily) | Actual On Site Personal (Daily) | Actual Remote Personal (Daily) | Planned GEO total personal (Daily) | Planned on site personal (Daily) | Planned remote personal (Daily) | Assigned Task ID | Planned Remote senior (Daily) | Actual Remote senior (Daily) | Planned Remote mid engineer (Daily) | Actual Remote mid engineer (Daily) | Planned Engineer/supervisor (Daily) | Actual Engineer/supervisor (Daily) | Planned Technician II (Daily) | Actual Technician II (Daily) | Planned Welder (Daily) | Actual Welder (Daily) | Planned Technician I (Daily) | Actual Technician I (Daily) | Planned Manager/senior Engineer (Daily) | Actual Manager/senior Engineer (Daily)
2025-04-01 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-02 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-26 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-27 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-28 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-29 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-30 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-07-01 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-02 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-03 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-04 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-05 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-06 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-07 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-08 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-09 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-10 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-11 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-12 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-13 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-14 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-15 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-16 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-17 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-18 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-19 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-20 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-21 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-22 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-23 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-24 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-25 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-26 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-27 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-28 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-29 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-30 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-31 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-08-01 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-02 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-03 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-04 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-05 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-06 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-07 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-08 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-09 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-10 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-11 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-12 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-13 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-14 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-15 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-16 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-17 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-18 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-19 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-20 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-21 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-22 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-23 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-24 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-25 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-26 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-27 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-28 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-29 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-30 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-31 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-09-01 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-02 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-03 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-04 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-05 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-06 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-07 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-08 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-09 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-10 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-11 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-12 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-13 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-14 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-15 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-16 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-17 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-18 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-19 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-20 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-21 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-22 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-23 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-24 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-25 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-26 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-27 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-28 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-29 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-09-30 | 3.5542 | 3.0667 | 0.4875 | 1.0792 | 0.86032 | 0.21884 | 400 | 0.043016 | 0 | 0.17583 | 0 | 0.33203 | 0 | 0.2339 | 0 | 0.29439 | 0 | 0.19626 | 0 | 0.098131 | 0
2025-10-01 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-02 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-03 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-04 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-05 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-06 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-07 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-08 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-09 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-10 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-11 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-12 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-13 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-14 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-15 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-16 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-17 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-18 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-19 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-20 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-21 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-22 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-23 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-24 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-25 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-26 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-27 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-28 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-29 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-30 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-10-31 | 2.4637 | 2.4194 | 0.044355 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-11-01 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-02 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-03 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-04 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-05 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-06 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-07 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-08 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-09 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-10 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-11 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-12 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-13 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-14 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-15 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-16 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-17 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-18 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-19 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-20 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-21 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-22 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-23 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-24 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-25 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-26 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-27 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-28 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-29 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-11-30 | 1.7542 | 1.7333 | 0.020833 | 0.93458 | 0.74766 | 0.18692 | 400 | 0.037383 | 0 | 0.14953 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.28037 | 0 | 0.18692 | 0 | 0.093458 | 0
2025-12-01 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-02 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-03 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-04 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-05 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-06 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-07 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-08 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-09 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-10 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-11 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-12 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-13 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-14 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-15 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-16 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-17 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-18 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-19 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-20 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-21 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-22 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-23 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-24 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-25 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-26 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-27 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-28 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-29 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-30 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2025-12-31 | 2.5847 | 2.5806 | 0.0040323 | 1.0401 | 0.83208 | 0.20802 | 400 | 0.041604 | 0 | 0.16642 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.31203 | 0 | 0.20802 | 0 | 0.10401 | 0
2026-01-01 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-02 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-03 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-04 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-05 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-06 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-07 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-08 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-09 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-10 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-11 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-12 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-13 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-14 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-15 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-16 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-17 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-18 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-19 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-20 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-21 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-22 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-23 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-24 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-25 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-26 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-27 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-28 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-29 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-30 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-01-31 | 2.0847 | 2.0645 | 0.020161 | 1.0875 | 0.83889 | 0.24863 | 500 | 0.055532 | 0 | 0.1931 | 0 | 0.32905 | 0 | 0.23852 | 0 | 0.27133 | 0 | 0.23852 | 0 | 0.10968 | 0
2026-02-01 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-02 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-03 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-04 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-05 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-06 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-07 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-08 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-09 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-10 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-11 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-12 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-13 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-14 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-15 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-16 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-17 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-18 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-19 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-20 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-21 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-22 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-23 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-24 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-25 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-26 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-27 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-28 | 1.5134 | 1.3929 | 0.12054 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-01 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-02 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-03 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-04 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-05 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-06 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-07 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-08 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-09 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-10 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-11 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-12 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-13 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-14 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-15 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-16 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-17 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-18 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-19 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-20 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-21 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-22 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-23 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-24 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-25 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-26 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-27 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-28 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-29 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-30 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-31 | 0.91532 | 0.77419 | 0.14113 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-01 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-02 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-03 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-04 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-05 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-06 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-07 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-08 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-09 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-10 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-11 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-12 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-13 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-14 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-15 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-16 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-17 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-18 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-19 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-20 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-21 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-22 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-23 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-24 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-25 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-26 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-27 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-28 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-29 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-30 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-01 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-02 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-03 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-04 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-05 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-06 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-07 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-08 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-09 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-10 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-11 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-12 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-13 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-14 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-15 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-16 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-17 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-18 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-19 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-20 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-21 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-22 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-23 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-24 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-25 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-26 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-27 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-28 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-29 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-30 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-31 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-01 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-02 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-03 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-04 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-05 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-06 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-07 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-08 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-09 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-10 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-11 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-12 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-13 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-14 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-15 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-16 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-17 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-18 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-19 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-20 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-21 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-22 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-23 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-24 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-25 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-26 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-27 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-28 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-29 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-06-30 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-01 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-02 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-03 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-04 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-05 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-06 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-07 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-08 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-09 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-10 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-11 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-12 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-13 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-14 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-15 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-16 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-17 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-18 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-19 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-20 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-21 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-22 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-23 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-24 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-25 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-26 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-27 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-28 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-29 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-30 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-07-31 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-08-01 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-02 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-03 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-04 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-05 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-06 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-07 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-08 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-09 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-10 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-11 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-12 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-13 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-14 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-15 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-16 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-17 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-18 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-19 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-20 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-21 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-22 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-23 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-24 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-25 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-26 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-27 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-28 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-29 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-30 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-08-31 | 0 | 0 | 0 | 3.0031 | 2.1071 | 0.89597 | 700 | 0.23629 | 0 | 0.65968 | 0 | 0.83201 | 0 | 0.95252 | 0 | 0.32258 | 0 | 0.95252 | 0 | 0.2639 | 0
2026-09-01 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-02 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-03 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-04 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-05 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-06 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-07 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-08 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-09 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-10 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-11 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-12 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-13 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-14 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-15 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-16 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-17 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-18 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-19 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-20 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-21 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-22 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-23 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-24 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-25 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-26 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-27 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-28 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-29 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-09-30 | 0 | 0 | 0 | 2.1405 | 0.925 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.325 | 0 | 0.4 | 0 | 0.2 | 0 | 0.4 | 0 | 0.1 | 0
2026-10-01 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-02 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-03 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-04 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-05 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-06 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-07 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-08 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-09 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-10 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-11 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-12 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-13 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-14 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-15 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-16 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-17 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-18 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-19 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-20 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-21 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-22 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-23 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-24 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-25 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-26 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-27 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-28 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-29 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-30 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-10-31 | 0 | 0 | 0 | 0.42774 | 0 | 0.42774 | 700 | 0.10645 | 0 | 0.32129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0