## Summary
Task ID | Task Name | Status | Schedule | Planned Duration | Actual Duration | Duration % | Invoice | Income Received | Income % | Planned Spend | Actual Spend | Spent Cost % | Profit % | Planned Labor Days | Actual Labor Days | Applied Labor %
100 | Design and Plans For Thermal Remediation | Completed | 04/01/25 - 05/30/25 | 48 | 44 | 92% | 105053.625 | 105053.63 | 100% | 77817.5 | 17797.25 | 23% | 490% | 137.5 | 31 | 23%
200 | Site Preparation & Mobilization Prep | Completed | 06/01/25 - 08/22/25 | 50 | 60 | 120% | 344279.25 | 284997.05 | 83% | 357756.6 | 224821.8 | 63% | 27% | 20 | 14 | 70%
300 | Drilling and Well Installation | Completed | 07/21/25 - 09/01/25 | 35 | 31 | 89% | 592513.235 | 271959.07 | 46% | 498551.8558 | 405730.57 | 81% | -33% | 91 | 132 | 145%
400 | Construction and Installation | In Progress | 09/02/25 - 10/31/25 | 30 | 34 | 113% | 279193.4456 | 0 |  | 218009.4962 | 155994.59 | 72% | -100% | 195 | 137.75 | 71%
500 | Operation and Maintenance | Future | 11/03/25 - 05/21/26 | 200 |  |  | 648306.4923 | 0 |  | 437461.4253 | 0 |  |  | 537.24 | 0
600 | Demobilization | Future | 05/22/26 - 06/12/26 | 16 |  |  | 278872.0413 | 0 |  | 189445.2548 | 0 |  |  | 114 | 0
700 | Reporting | Future | 05/22/26 - 07/16/26 | 40 |  |  | 46149.75 | 0 |  | 34185 | 0 |  |  | 66.4 | 0
| TOTAL |  | 04/01/25 - 07/16/26 | 471 | 199 | 42% | 2294367.8392 | 662009.75 | 29% | 1813227.1321 | 804344.21 | 44% | -18% | 1161.14 | 314.75 | 27%

## Invoice Sum
Date | Planned Income (Cumulative) | Actual Income (Daily) | Actual Income (Cumulative) | Planned Labor Sum (Cumulative) | Planned Travel&perdiem (Direct Cost) Sum (Cumulative) | Planned Parts&materials (Direct Cost) Sum (Cumulative) | Planned Outsource (Direct Cost) Sum (Cumulative) | Planned Equipment (Cumulative) | Planned 1805 · EQUIPMENT - FORKLIFT (Cumulative) | Planned 1818 · EQUIPMENT - BCU (Cumulative) | Planned 1819 · EQUIPMENT - TPMB (Cumulative) | Planned 1820 · EQUIPMENT & TOOLS (Cumulative) | Planned 1821 · EQUIPMENT - C3 (Cumulative) | Planned 1822 · EQUIPMENT - C2 (Cumulative) | Planned 1823 · EQUIPMENT - TCU BASIC (Cumulative) | Planned 1824 · EQUIPMENT - TCU PLC (Cumulative) | Planned 1825 · EQUIPMENT - BLOWER SKIDS (Cumulative) | Planned 1826 · EQUIPMENT - WELL HEADS (Cumulative) | Planned 1827 · EQUIPMENT - THERMAL WELLS (Cumulative) | Planned 1829 · EQUIPMENT - WATER TREATMENT SYS (Cumulative) | Planned 1830 · EQUIPMENT - VAPOR EXTRACTION (Cumulative) | Planned 1831 · EQUIPMENT - GTR/C3 COMPONENTS (Cumulative) | Planned 1832 · EQUIP - CONTROL/DIST PANELS (Cumulative) | Planned 1833 · EQUIPMENT - OFFICE & COMPUTER (Cumulative) | Planned 5004 · GTR COST OF SALES - PARTS (Cumulative) | Planned 5006 · DRILLING EXPENSE (Cumulative) | Planned 5101 · SALARY AND WAGES (DIRECT) (Cumulative) | Planned 5102 · PAYROLL TAXES (DIRECT) (Cumulative) | Planned 5105 · TRAVEL - AIRFARE (DIRECT) (Cumulative) | Planned 5106 · TRAVEL - HOTEL (DIRECT) (Cumulative) | Planned 5107 · TRAVEL - OTHER (DIRECT) (Cumulative) | Planned 5108 · MEALS & ENTERTAINMENT (DIRECT) (Cumulative) | Planned 5110 · TEMPORARY LABOR (DIRECT) (Cumulative) | Planned 5111 · PARTS & MATERIAL COSTS (DIRECT) (Cumulative) | Planned 5112 · CARBON & LAB SAMPLIES (DRIECT) (Cumulative) | Planned 5113 · REPAIRS & MAINT (DIRECT) (Cumulative) | Planned 5114 · RENT - BUILDING (DIRECT) (Cumulative) | Planned 5115 · RENT - EQUIPMENT (DIRECT) (Cumulative) | Planned 5120 · OUTSIDE SERVICES (DIRECT) (Cumulative) | Planned 5121 · FREIGHT & SHIPPING (DIRECT) (Cumulative) | Planned 5122 · MOTOR VEHICLE EXP (DIRECT) (Cumulative) | Planned 5123 · AUTO FUEL (DIRECT) (Cumulative) | Planned 5124 · LICENSE AND PERMITS (DIRECT) (Cumulative) | Planned 5128 · HEALTH & SAFETY EQUIP (DIRECT) (Cumulative) | Planned 5129 · MISC EXPENSES (DIRECT) (Cumulative) | Planned 5132 · INTERNET FEE (DIRECT) (Cumulative) | Planned 6999 · UNCATEGORIZED EXPENSES (Cumulative) | Planned 4001 · SERVICE INCOME (Cumulative) | Planned 4002 · EQUIPMENT RENTAL INCOME (Cumulative) | Planned 4003 · MOBILIZATION INCOME (Cumulative) | Planned 4004 · DEMOBILIZATION INCOME (Cumulative) | Planned 4005 · PERDIEM INCOME (Cumulative) | Planned 4006 · DRILLING INCOME (Cumulative) | Planned 4011 · - SERVICE INCOME - (Cumulative) | Planned 4012 · GTR- UNITS SOLD (Cumulative) | Planned 4100 · ACCOUNTS RECEIVABLE (Cumulative) | Planned 4110 · MARK UP ACCOUNT (Cumulative)
2025-04-01 | 1750.8937 | 0 | 0 | 1750.8937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750.8937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-02 | 3501.7875 | 0 | 0 | 3501.7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3501.7875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 5252.6812 | 0 | 0 | 5252.6812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5252.6812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 7003.575 | 0 | 0 | 7003.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7003.575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 8754.4688 | 0 | 0 | 8754.4688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8754.4688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 10505.3625 | 0 | 0 | 10505.3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10505.3625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 12256.2563 | 0 | 0 | 12256.2563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12256.2563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 14007.15 | 0 | 0 | 14007.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14007.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 15758.0438 | 0 | 0 | 15758.0438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15758.0438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 17508.9375 | 0 | 0 | 17508.9375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17508.9375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 19259.8312 | 0 | 0 | 19259.8312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19259.8312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 21010.725 | 0 | 0 | 21010.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21010.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 22761.6187 | 0 | 0 | 22761.6187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22761.6187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 24512.5125 | 0 | 0 | 24512.5125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24512.5125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 26263.4062 | 0 | 0 | 26263.4062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26263.4062 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 28014.3 | 0 | 0 | 28014.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28014.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 29765.1937 | 0 | 0 | 29765.1937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29765.1937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 31516.0875 | 0 | 0 | 31516.0875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31516.0875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 33266.9812 | 0 | 0 | 33266.9812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33266.9812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 35017.875 | 0 | 0 | 35017.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35017.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 36768.7688 | 0 | 0 | 36768.7688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36768.7688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 38519.6625 | 0 | 0 | 38519.6625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38519.6625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 40270.5563 | 0 | 0 | 40270.5563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40270.5563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 42021.45 | 0 | 0 | 42021.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42021.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 43772.3438 | 0 | 0 | 43772.3438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43772.3438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 45523.2375 | 0 | 0 | 45523.2375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45523.2375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 47274.1313 | 0 | 0 | 47274.1313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47274.1313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 49025.025 | 0 | 0 | 49025.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49025.025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 50775.9188 | 0 | 0 | 50775.9188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50775.9188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 52526.8125 | 0 | 0 | 52526.8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52526.8125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 54277.7063 | 0 | 0 | 54277.7063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54277.7063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 56028.6 | 0 | 0 | 56028.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56028.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 57779.4938 | 0 | 0 | 57779.4938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57779.4938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 59530.3875 | 0 | 0 | 59530.3875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59530.3875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 61281.2813 | 0 | 0 | 61281.2813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61281.2813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 63032.175 | 0 | 0 | 63032.175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63032.175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 64783.0688 | 0 | 0 | 64783.0688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64783.0688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 66533.9625 | 0 | 0 | 66533.9625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66533.9625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 68284.8563 | 0 | 0 | 68284.8563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68284.8563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 70035.75 | 0 | 0 | 70035.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70035.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 71786.6438 | 0 | 0 | 71786.6438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 71786.6438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 73537.5375 | 0 | 0 | 73537.5375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73537.5375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 75288.4313 | 0 | 0 | 75288.4313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75288.4313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 77039.325 | 0 | 0 | 77039.325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77039.325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 78790.2188 | 0 | 0 | 78790.2188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78790.2188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 80541.1125 | 0 | 0 | 80541.1125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80541.1125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 82292.0063 | 0 | 0 | 82292.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82292.0063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 84042.9 | 0 | 0 | 84042.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84042.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 85793.7938 | 0 | 0 | 85793.7938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85793.7938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 87544.6875 | 0 | 0 | 87544.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 87544.6875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 89295.5813 | 0 | 0 | 89295.5813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89295.5813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 91046.475 | 0 | 0 | 91046.475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 91046.475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 92797.3688 | 0 | 0 | 92797.3688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92797.3688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 94548.2625 | 0 | 0 | 94548.2625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94548.2625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 96299.1563 | 0 | 0 | 96299.1563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96299.1563 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 98050.05 | 0 | 0 | 98050.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98050.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 99800.9438 | 0 | 0 | 99800.9438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99800.9438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 101551.8375 | 0 | 0 | 101551.8375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101551.8375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 103302.7313 | 0 | 0 | 103302.7313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103302.7313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 105053.625 | 0 | 0 | 105053.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105053.625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 109201.5678 | 0 | 0 | 105217.0889 | 100.8434 | 1640.2617 | 1306.409 | 936.9648 | 0 | 96.4819 | 15.6627 | 0 | 0 | 462.2863 | 159.759 | 0 | 0 | 0 | 0 | 0 | 77.4737 | 50.1205 | 75.1807 | 0 | 0 | 0 | 105217.0889 | 0 | 9.759 | 59.2048 | 9.1084 | 22.7711 | 0 | 1640.2617 | 0 | 0 | 0 | 435.5392 | 651.5928 | 156.6265 | 0 | 0 | 0 | 0 | 0 | 62.6506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 113349.5105 | 0 | 0 | 105380.5527 | 201.6867 | 3280.5234 | 2612.8181 | 1873.9296 | 0 | 192.9639 | 31.3253 | 0 | 0 | 924.5725 | 319.5181 | 0 | 0 | 0 | 0 | 0 | 154.9475 | 100.241 | 150.3614 | 0 | 0 | 0 | 105380.5527 | 0 | 19.5181 | 118.4096 | 18.2169 | 45.5422 | 0 | 3280.5234 | 0 | 0 | 0 | 871.0783 | 1303.1855 | 313.253 | 0 | 0 | 0 | 0 | 0 | 125.3012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 117497.4533 | 0 | 0 | 105544.0166 | 302.5301 | 4920.7851 | 3919.2271 | 2810.8945 | 0 | 289.4458 | 46.988 | 0 | 0 | 1386.8588 | 479.2771 | 0 | 0 | 0 | 0 | 0 | 232.4212 | 150.3614 | 225.5422 | 0 | 0 | 0 | 105544.0166 | 0 | 29.2771 | 177.6145 | 27.3253 | 68.3133 | 0 | 4920.7851 | 0 | 0 | 0 | 1306.6175 | 1954.7783 | 469.8795 | 0 | 0 | 0 | 0 | 0 | 187.9518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 121645.3961 | 0 | 0 | 105707.4804 | 403.3735 | 6561.0467 | 5225.6361 | 3747.8593 | 0 | 385.9277 | 62.6506 | 0 | 0 | 1849.1451 | 639.0361 | 0 | 0 | 0 | 0 | 0 | 309.8949 | 200.4819 | 300.7229 | 0 | 0 | 0 | 105707.4804 | 0 | 39.0361 | 236.8193 | 36.4337 | 91.0843 | 0 | 6561.0467 | 0 | 0 | 0 | 1742.1566 | 2606.3711 | 626.506 | 0 | 0 | 0 | 0 | 0 | 250.6024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 125793.3389 | 0 | 0 | 105870.9443 | 504.2169 | 8201.3084 | 6532.0452 | 4684.8241 | 0 | 482.4096 | 78.3133 | 0 | 0 | 2311.4313 | 798.7952 | 0 | 0 | 0 | 0 | 0 | 387.3687 | 250.6024 | 375.9036 | 0 | 0 | 0 | 105870.9443 | 0 | 48.7952 | 296.0241 | 45.5422 | 113.8554 | 0 | 8201.3084 | 0 | 0 | 0 | 2177.6958 | 3257.9639 | 783.1325 | 0 | 0 | 0 | 0 | 0 | 313.253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 129941.2816 | 0 | 0 | 106034.4081 | 605.0602 | 9841.5701 | 7838.4542 | 5621.7889 | 0 | 578.8916 | 93.9759 | 0 | 0 | 2773.7176 | 958.5542 | 0 | 0 | 0 | 0 | 0 | 464.8424 | 300.7229 | 451.0843 | 0 | 0 | 0 | 106034.4081 | 0 | 58.5542 | 355.2289 | 54.6506 | 136.6265 | 0 | 9841.5701 | 0 | 0 | 0 | 2613.2349 | 3909.5566 | 939.759 | 0 | 0 | 0 | 0 | 0 | 375.9036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 134089.2244 | 0 | 0 | 106197.872 | 705.9036 | 11481.8318 | 9144.8633 | 6558.7537 | 0 | 675.3735 | 109.6386 | 0 | 0 | 3236.0039 | 1118.3133 | 0 | 0 | 0 | 0 | 0 | 542.3161 | 350.8434 | 526.2651 | 0 | 0 | 0 | 106197.872 | 0 | 68.3133 | 414.4337 | 63.759 | 159.3976 | 0 | 11481.8318 | 0 | 0 | 0 | 3048.7741 | 4561.1494 | 1096.3855 | 0 | 0 | 0 | 0 | 0 | 438.5542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 138237.1672 | 0 | 0 | 106361.3358 | 806.747 | 13122.0935 | 10451.2723 | 7495.7186 | 0 | 771.8554 | 125.3012 | 0 | 0 | 3698.2901 | 1278.0723 | 0 | 0 | 0 | 0 | 0 | 619.7899 | 400.9639 | 601.4458 | 0 | 0 | 0 | 106361.3358 | 0 | 78.0723 | 473.6386 | 72.8675 | 182.1687 | 0 | 13122.0935 | 0 | 0 | 0 | 3484.3133 | 5212.7422 | 1253.012 | 0 | 0 | 0 | 0 | 0 | 501.2048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 142385.1099 | 0 | 0 | 106524.7997 | 907.5904 | 14762.3552 | 11757.6813 | 8432.6834 | 0 | 868.3373 | 140.9639 | 0 | 0 | 4160.5764 | 1437.8313 | 0 | 0 | 0 | 0 | 0 | 697.2636 | 451.0843 | 676.6265 | 0 | 0 | 0 | 106524.7997 | 0 | 87.8313 | 532.8434 | 81.9759 | 204.9398 | 0 | 14762.3552 | 0 | 0 | 0 | 3919.8524 | 5864.3349 | 1409.6386 | 0 | 0 | 0 | 0 | 0 | 563.8554 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 146533.0527 | 0 | 0 | 106688.2636 | 1008.4337 | 16402.6169 | 13064.0904 | 9369.6482 | 0 | 964.8193 | 156.6265 | 0 | 0 | 4622.8627 | 1597.5904 | 0 | 0 | 0 | 0 | 0 | 774.7373 | 501.2048 | 751.8072 | 0 | 0 | 0 | 106688.2636 | 0 | 97.5904 | 592.0482 | 91.0843 | 227.7108 | 0 | 16402.6169 | 0 | 0 | 0 | 4355.3916 | 6515.9277 | 1566.2651 | 0 | 0 | 0 | 0 | 0 | 626.506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 150680.9955 | 0 | 0 | 106851.7274 | 1109.2771 | 18042.8786 | 14370.4994 | 10306.613 | 0 | 1061.3012 | 172.2892 | 0 | 0 | 5085.1489 | 1757.3494 | 0 | 0 | 0 | 0 | 0 | 852.2111 | 551.3253 | 826.988 | 0 | 0 | 0 | 106851.7274 | 0 | 107.3494 | 651.253 | 100.1928 | 250.4819 | 0 | 18042.8786 | 0 | 0 | 0 | 4790.9307 | 7167.5205 | 1722.8916 | 0 | 0 | 0 | 0 | 0 | 689.1566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 154828.9383 | 0 | 0 | 107015.1913 | 1210.1205 | 19683.1402 | 15676.9084 | 11243.5778 | 0 | 1157.7831 | 187.9518 | 0 | 0 | 5547.4352 | 1917.1084 | 0 | 0 | 0 | 0 | 0 | 929.6848 | 601.4458 | 902.1687 | 0 | 0 | 0 | 107015.1913 | 0 | 117.1084 | 710.4578 | 109.3012 | 273.253 | 0 | 19683.1402 | 0 | 0 | 0 | 5226.4699 | 7819.1133 | 1879.5181 | 0 | 0 | 0 | 0 | 0 | 751.8072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 158976.881 | 0 | 0 | 107178.6551 | 1310.9639 | 21323.4019 | 16983.3175 | 12180.5427 | 0 | 1254.2651 | 203.6145 | 0 | 0 | 6009.7214 | 2076.8675 | 0 | 0 | 0 | 0 | 0 | 1007.1586 | 651.5663 | 977.3494 | 0 | 0 | 0 | 107178.6551 | 0 | 126.8675 | 769.6627 | 118.4096 | 296.0241 | 0 | 21323.4019 | 0 | 0 | 0 | 5662.009 | 8470.706 | 2036.1446 | 0 | 0 | 0 | 0 | 0 | 814.4578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 163124.8238 | 0 | 0 | 107342.119 | 1411.8072 | 22963.6636 | 18289.7265 | 13117.5075 | 0 | 1350.747 | 219.2771 | 0 | 0 | 6472.0077 | 2236.6265 | 0 | 0 | 0 | 0 | 0 | 1084.6323 | 701.6867 | 1052.5301 | 0 | 0 | 0 | 107342.119 | 0 | 136.6265 | 828.8675 | 127.5181 | 318.7952 | 0 | 22963.6636 | 0 | 0 | 0 | 6097.5482 | 9122.2988 | 2192.7711 | 0 | 0 | 0 | 0 | 0 | 877.1084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 167272.7666 | 0 | 0 | 107505.5828 | 1512.6506 | 24603.9253 | 19596.1355 | 14054.4723 | 0 | 1447.2289 | 234.9398 | 0 | 0 | 6934.294 | 2396.3855 | 0 | 0 | 0 | 0 | 0 | 1162.106 | 751.8072 | 1127.7108 | 0 | 0 | 0 | 107505.5828 | 0 | 146.3855 | 888.0723 | 136.6265 | 341.5663 | 0 | 24603.9253 | 0 | 0 | 0 | 6533.0873 | 9773.8916 | 2349.3976 | 0 | 0 | 0 | 0 | 0 | 939.759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 171420.7093 | 0 | 0 | 107669.0467 | 1613.494 | 26244.187 | 20902.5446 | 14991.4371 | 0 | 1543.7108 | 250.6024 | 0 | 0 | 7396.5802 | 2556.1446 | 0 | 0 | 0 | 0 | 0 | 1239.5798 | 801.9277 | 1202.8916 | 0 | 0 | 0 | 107669.0467 | 0 | 156.1446 | 947.2771 | 145.7349 | 364.3373 | 0 | 26244.187 | 0 | 0 | 0 | 6968.6265 | 10425.4843 | 2506.0241 | 0 | 0 | 0 | 0 | 0 | 1002.4096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 175568.6521 | 0 | 0 | 107832.5105 | 1714.3373 | 27884.4487 | 22208.9536 | 15928.4019 | 0 | 1640.1928 | 266.2651 | 0 | 0 | 7858.8665 | 2715.9036 | 0 | 0 | 0 | 0 | 0 | 1317.0535 | 852.0482 | 1278.0723 | 0 | 0 | 0 | 107832.5105 | 0 | 165.9036 | 1006.4819 | 154.8434 | 387.1084 | 0 | 27884.4487 | 0 | 0 | 0 | 7404.1657 | 11077.0771 | 2662.6506 | 0 | 0 | 0 | 0 | 0 | 1065.0602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 179716.5949 | 0 | 0 | 107995.9744 | 1815.1807 | 29524.7104 | 23515.3627 | 16865.3667 | 0 | 1736.6747 | 281.9277 | 0 | 0 | 8321.1528 | 2875.6627 | 0 | 0 | 0 | 0 | 0 | 1394.5272 | 902.1687 | 1353.253 | 0 | 0 | 0 | 107995.9744 | 0 | 175.6627 | 1065.6867 | 163.9518 | 409.8795 | 0 | 29524.7104 | 0 | 0 | 0 | 7839.7048 | 11728.6699 | 2819.2771 | 0 | 0 | 0 | 0 | 0 | 1127.7108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 183864.5377 | 0 | 0 | 108159.4383 | 1916.0241 | 31164.972 | 24821.7717 | 17802.3316 | 0 | 1833.1566 | 297.5904 | 0 | 0 | 8783.439 | 3035.4217 | 0 | 0 | 0 | 0 | 0 | 1472.001 | 952.2892 | 1428.4337 | 0 | 0 | 0 | 108159.4383 | 0 | 185.4217 | 1124.8916 | 173.0602 | 432.6506 | 0 | 31164.972 | 0 | 0 | 0 | 8275.244 | 12380.2627 | 2975.9036 | 0 | 0 | 0 | 0 | 0 | 1190.3614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 188012.4804 | 0 | 0 | 108322.9021 | 2016.8675 | 32805.2337 | 26128.1807 | 18739.2964 | 0 | 1929.6386 | 313.253 | 0 | 0 | 9245.7253 | 3195.1807 | 0 | 0 | 0 | 0 | 0 | 1549.4747 | 1002.4096 | 1503.6145 | 0 | 0 | 0 | 108322.9021 | 0 | 195.1807 | 1184.0964 | 182.1687 | 455.4217 | 0 | 32805.2337 | 0 | 0 | 0 | 8710.7831 | 13031.8554 | 3132.5301 | 0 | 0 | 0 | 0 | 0 | 1253.012 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 192160.4232 | 0 | 0 | 108486.366 | 2117.7108 | 34445.4954 | 27434.5898 | 19676.2612 | 0 | 2026.1205 | 328.9157 | 0 | 0 | 9708.0116 | 3354.9398 | 0 | 0 | 0 | 0 | 0 | 1626.9484 | 1052.5301 | 1578.7952 | 0 | 0 | 0 | 108486.366 | 0 | 204.9398 | 1243.3012 | 191.2771 | 478.1928 | 0 | 34445.4954 | 0 | 0 | 0 | 9146.3223 | 13683.4482 | 3289.1566 | 0 | 0 | 0 | 0 | 0 | 1315.6627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 196308.366 | 0 | 0 | 108649.8298 | 2218.5542 | 36085.7571 | 28740.9988 | 20613.226 | 0 | 2122.6024 | 344.5783 | 0 | 0 | 10170.2978 | 3514.6988 | 0 | 0 | 0 | 0 | 0 | 1704.4222 | 1102.6506 | 1653.9759 | 0 | 0 | 0 | 108649.8298 | 0 | 214.6988 | 1302.506 | 200.3855 | 500.9639 | 0 | 36085.7571 | 0 | 0 | 0 | 9581.8614 | 14335.041 | 3445.7831 | 0 | 0 | 0 | 0 | 0 | 1378.3133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 200456.3087 | 0 | 0 | 108813.2937 | 2319.3976 | 37726.0188 | 30047.4078 | 21550.1908 | 0 | 2219.0843 | 360.241 | 0 | 0 | 10632.5841 | 3674.4578 | 0 | 0 | 0 | 0 | 0 | 1781.8959 | 1152.7711 | 1729.1566 | 0 | 0 | 0 | 108813.2937 | 0 | 224.4578 | 1361.7108 | 209.494 | 523.7349 | 0 | 37726.0188 | 0 | 0 | 0 | 10017.4006 | 14986.6337 | 3602.4096 | 0 | 0 | 0 | 0 | 0 | 1440.9639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 204604.2515 | 0 | 0 | 108976.7575 | 2420.241 | 39366.2805 | 31353.8169 | 22487.1557 | 0 | 2315.5663 | 375.9036 | 0 | 0 | 11094.8704 | 3834.2169 | 0 | 0 | 0 | 0 | 0 | 1859.3696 | 1202.8916 | 1804.3373 | 0 | 0 | 0 | 108976.7575 | 0 | 234.2169 | 1420.9157 | 218.6024 | 546.506 | 0 | 39366.2805 | 0 | 0 | 0 | 10452.9398 | 15638.2265 | 3759.0361 | 0 | 0 | 0 | 0 | 0 | 1503.6145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 208752.1943 | 0 | 0 | 109140.2214 | 2521.0843 | 41006.5422 | 32660.2259 | 23424.1205 | 0 | 2412.0482 | 391.5663 | 0 | 0 | 11557.1566 | 3993.9759 | 0 | 0 | 0 | 0 | 0 | 1936.8434 | 1253.012 | 1879.5181 | 0 | 0 | 0 | 109140.2214 | 0 | 243.9759 | 1480.1205 | 227.7108 | 569.2771 | 0 | 41006.5422 | 0 | 0 | 0 | 10888.4789 | 16289.8193 | 3915.6627 | 0 | 0 | 0 | 0 | 0 | 1566.2651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-26 | 212900.137 | 0 | 0 | 109303.6852 | 2621.9277 | 42646.8039 | 33966.6349 | 24361.0853 | 0 | 2508.5301 | 407.2289 | 0 | 0 | 12019.4429 | 4153.7349 | 0 | 0 | 0 | 0 | 0 | 2014.3171 | 1303.1325 | 1954.6988 | 0 | 0 | 0 | 109303.6852 | 0 | 253.7349 | 1539.3253 | 236.8193 | 592.0482 | 0 | 42646.8039 | 0 | 0 | 0 | 11324.0181 | 16941.412 | 4072.2892 | 0 | 0 | 0 | 0 | 0 | 1628.9157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-27 | 217048.0798 | 0 | 0 | 109467.1491 | 2722.7711 | 44287.0655 | 35273.044 | 25298.0501 | 0 | 2605.012 | 422.8916 | 0 | 0 | 12481.7292 | 4313.494 | 0 | 0 | 0 | 0 | 0 | 2091.7908 | 1353.253 | 2029.8795 | 0 | 0 | 0 | 109467.1491 | 0 | 263.494 | 1598.5301 | 245.9277 | 614.8193 | 0 | 44287.0655 | 0 | 0 | 0 | 11759.5572 | 17593.0048 | 4228.9157 | 0 | 0 | 0 | 0 | 0 | 1691.5663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-28 | 221196.0226 | 0 | 0 | 109630.613 | 2823.6145 | 45927.3272 | 36579.453 | 26235.0149 | 0 | 2701.494 | 438.5542 | 0 | 0 | 12944.0154 | 4473.253 | 0 | 0 | 0 | 0 | 0 | 2169.2646 | 1403.3735 | 2105.0602 | 0 | 0 | 0 | 109630.613 | 0 | 273.253 | 1657.7349 | 255.0361 | 637.5904 | 0 | 45927.3272 | 0 | 0 | 0 | 12195.0964 | 18244.5976 | 4385.5422 | 0 | 0 | 0 | 0 | 0 | 1754.2169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-29 | 225343.9654 | 0 | 0 | 109794.0768 | 2924.4578 | 47567.5889 | 37885.862 | 27171.9798 | 0 | 2797.9759 | 454.2169 | 0 | 0 | 13406.3017 | 4633.012 | 0 | 0 | 0 | 0 | 0 | 2246.7383 | 1453.494 | 2180.241 | 0 | 0 | 0 | 109794.0768 | 0 | 283.012 | 1716.9398 | 264.1446 | 660.3614 | 0 | 47567.5889 | 0 | 0 | 0 | 12630.6355 | 18896.1904 | 4542.1687 | 0 | 0 | 0 | 0 | 0 | 1816.8675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-30 | 229491.9081 | 0 | 0 | 109957.5407 | 3025.3012 | 49207.8506 | 39192.2711 | 28108.9446 | 0 | 2894.4578 | 469.8795 | 0 | 0 | 13868.588 | 4792.7711 | 0 | 0 | 0 | 0 | 0 | 2324.212 | 1503.6145 | 2255.4217 | 0 | 0 | 0 | 109957.5407 | 0 | 292.7711 | 1776.1446 | 273.253 | 683.1325 | 0 | 49207.8506 | 0 | 0 | 0 | 13066.1747 | 19547.7831 | 4698.7952 | 0 | 0 | 0 | 0 | 0 | 1879.5181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-01 | 233639.8509 | 0 | 0 | 110121.0045 | 3126.1446 | 50848.1123 | 40498.6801 | 29045.9094 | 0 | 2990.9398 | 485.5422 | 0 | 0 | 14330.8742 | 4952.5301 | 0 | 0 | 0 | 0 | 0 | 2401.6858 | 1553.7349 | 2330.6024 | 0 | 0 | 0 | 110121.0045 | 0 | 302.5301 | 1835.3494 | 282.3614 | 705.9036 | 0 | 50848.1123 | 0 | 0 | 0 | 13501.7139 | 20199.3759 | 4855.4217 | 0 | 0 | 0 | 0 | 0 | 1942.1687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-02 | 237787.7937 | 0 | 0 | 110284.4684 | 3226.988 | 52488.374 | 41805.0892 | 29982.8742 | 0 | 3087.4217 | 501.2048 | 0 | 0 | 14793.1605 | 5112.2892 | 0 | 0 | 0 | 0 | 0 | 2479.1595 | 1603.8554 | 2405.7831 | 0 | 0 | 0 | 110284.4684 | 0 | 312.2892 | 1894.5542 | 291.4699 | 728.6747 | 0 | 52488.374 | 0 | 0 | 0 | 13937.253 | 20850.9687 | 5012.0482 | 0 | 0 | 0 | 0 | 0 | 2004.8193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-03 | 241935.7364 | 0 | 0 | 110447.9322 | 3327.8313 | 54128.6357 | 43111.4982 | 30919.839 | 0 | 3183.9036 | 516.8675 | 0 | 0 | 15255.4467 | 5272.0482 | 0 | 0 | 0 | 0 | 0 | 2556.6333 | 1653.9759 | 2480.9639 | 0 | 0 | 0 | 110447.9322 | 0 | 322.0482 | 1953.759 | 300.5783 | 751.4458 | 0 | 54128.6357 | 0 | 0 | 0 | 14372.7922 | 21502.5614 | 5168.6747 | 0 | 0 | 0 | 0 | 0 | 2067.4699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-04 | 246083.6792 | 0 | 0 | 110611.3961 | 3428.6747 | 55768.8973 | 44417.9072 | 31856.8039 | 0 | 3280.3855 | 532.5301 | 0 | 0 | 15717.733 | 5431.8072 | 0 | 0 | 0 | 0 | 0 | 2634.107 | 1704.0964 | 2556.1446 | 0 | 0 | 0 | 110611.3961 | 0 | 331.8072 | 2012.9639 | 309.6867 | 774.2169 | 0 | 55768.8973 | 0 | 0 | 0 | 14808.3313 | 22154.1542 | 5325.3012 | 0 | 0 | 0 | 0 | 0 | 2130.1205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-05 | 250231.622 | 0 | 0 | 110774.8599 | 3529.5181 | 57409.159 | 45724.3163 | 32793.7687 | 0 | 3376.8675 | 548.1928 | 0 | 0 | 16180.0193 | 5591.5663 | 0 | 0 | 0 | 0 | 0 | 2711.5807 | 1754.2169 | 2631.3253 | 0 | 0 | 0 | 110774.8599 | 0 | 341.5663 | 2072.1687 | 318.7952 | 796.988 | 0 | 57409.159 | 0 | 0 | 0 | 15243.8705 | 22805.747 | 5481.9277 | 0 | 0 | 0 | 0 | 0 | 2192.7711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-06 | 254379.5648 | 0 | 0 | 110938.3238 | 3630.3614 | 59049.4207 | 47030.7253 | 33730.7335 | 0 | 3473.3494 | 563.8554 | 0 | 0 | 16642.3055 | 5751.3253 | 0 | 0 | 0 | 0 | 0 | 2789.0545 | 1804.3373 | 2706.506 | 0 | 0 | 0 | 110938.3238 | 0 | 351.3253 | 2131.3735 | 327.9036 | 819.759 | 0 | 59049.4207 | 0 | 0 | 0 | 15679.4096 | 23457.3398 | 5638.5542 | 0 | 0 | 0 | 0 | 0 | 2255.4217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-07 | 258527.5075 | 0 | 0 | 111101.7877 | 3731.2048 | 60689.6824 | 48337.1343 | 34667.6983 | 0 | 3569.8313 | 579.5181 | 0 | 0 | 17104.5918 | 5911.0843 | 0 | 0 | 0 | 0 | 0 | 2866.5282 | 1854.4578 | 2781.6867 | 0 | 0 | 0 | 111101.7877 | 0 | 361.0843 | 2190.5783 | 337.012 | 842.5301 | 0 | 60689.6824 | 0 | 0 | 0 | 16114.9488 | 24108.9325 | 5795.1807 | 0 | 0 | 0 | 0 | 0 | 2318.0723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-08 | 262675.4503 | 0 | 0 | 111265.2515 | 3832.0482 | 62329.9441 | 49643.5434 | 35604.6631 | 0 | 3666.3133 | 595.1807 | 0 | 0 | 17566.8781 | 6070.8434 | 0 | 0 | 0 | 0 | 0 | 2944.0019 | 1904.5783 | 2856.8675 | 0 | 0 | 0 | 111265.2515 | 0 | 370.8434 | 2249.7831 | 346.1205 | 865.3012 | 0 | 62329.9441 | 0 | 0 | 0 | 16550.488 | 24760.5253 | 5951.8072 | 0 | 0 | 0 | 0 | 0 | 2380.7229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-09 | 266823.3931 | 0 | 0 | 111428.7154 | 3932.8916 | 63970.2058 | 50949.9524 | 36541.628 | 0 | 3762.7952 | 610.8434 | 0 | 0 | 18029.1643 | 6230.6024 | 0 | 0 | 0 | 0 | 0 | 3021.4757 | 1954.6988 | 2932.0482 | 0 | 0 | 0 | 111428.7154 | 0 | 380.6024 | 2308.988 | 355.2289 | 888.0723 | 0 | 63970.2058 | 0 | 0 | 0 | 16986.0271 | 25412.1181 | 6108.4337 | 0 | 0 | 0 | 0 | 0 | 2443.3735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-10 | 270971.3358 | 0 | 0 | 111592.1792 | 4033.7349 | 65610.4675 | 52256.3614 | 37478.5928 | 0 | 3859.2771 | 626.506 | 0 | 0 | 18491.4506 | 6390.3614 | 0 | 0 | 0 | 0 | 0 | 3098.9494 | 2004.8193 | 3007.2289 | 0 | 0 | 0 | 111592.1792 | 0 | 390.3614 | 2368.1928 | 364.3373 | 910.8434 | 0 | 65610.4675 | 0 | 0 | 0 | 17421.5663 | 26063.7108 | 6265.0602 | 0 | 0 | 0 | 0 | 0 | 2506.0241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-11 | 275119.2786 | 0 | 0 | 111755.6431 | 4134.5783 | 67250.7292 | 53562.7705 | 38415.5576 | 0 | 3955.759 | 642.1687 | 0 | 0 | 18953.7369 | 6550.1205 | 0 | 0 | 0 | 0 | 0 | 3176.4231 | 2054.9398 | 3082.4096 | 0 | 0 | 0 | 111755.6431 | 0 | 400.1205 | 2427.3976 | 373.4458 | 933.6145 | 0 | 67250.7292 | 0 | 0 | 0 | 17857.1054 | 26715.3036 | 6421.6867 | 0 | 0 | 0 | 0 | 0 | 2568.6747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-12 | 279267.2214 | 0 | 0 | 111919.1069 | 4235.4217 | 68890.9908 | 54869.1795 | 39352.5224 | 0 | 4052.241 | 657.8313 | 0 | 0 | 19416.0231 | 6709.8795 | 0 | 0 | 0 | 0 | 0 | 3253.8969 | 2105.0602 | 3157.5904 | 0 | 0 | 0 | 111919.1069 | 0 | 409.8795 | 2486.6024 | 382.5542 | 956.3855 | 0 | 68890.9908 | 0 | 0 | 0 | 18292.6446 | 27366.8964 | 6578.3133 | 0 | 0 | 0 | 0 | 0 | 2631.3253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-13 | 283415.1642 | 0 | 0 | 112082.5708 | 4336.2651 | 70531.2525 | 56175.5886 | 40289.4872 | 0 | 4148.7229 | 673.494 | 0 | 0 | 19878.3094 | 6869.6386 | 0 | 0 | 0 | 0 | 0 | 3331.3706 | 2155.1807 | 3232.7711 | 0 | 0 | 0 | 112082.5708 | 0 | 419.6386 | 2545.8072 | 391.6627 | 979.1566 | 0 | 70531.2525 | 0 | 0 | 0 | 18728.1837 | 28018.4892 | 6734.9398 | 0 | 0 | 0 | 0 | 0 | 2693.9759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-14 | 287563.1069 | 0 | 0 | 112246.0346 | 4437.1084 | 72171.5142 | 57481.9976 | 41226.452 | 0 | 4245.2048 | 689.1566 | 0 | 0 | 20340.5957 | 7029.3976 | 0 | 0 | 0 | 0 | 0 | 3408.8443 | 2205.3012 | 3307.9518 | 0 | 0 | 0 | 112246.0346 | 0 | 429.3976 | 2605.012 | 400.7711 | 1001.9277 | 0 | 72171.5142 | 0 | 0 | 0 | 19163.7229 | 28670.0819 | 6891.5663 | 0 | 0 | 0 | 0 | 0 | 2756.6265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-15 | 291711.0497 | 0 | 0 | 112409.4985 | 4537.9518 | 73811.7759 | 58788.4066 | 42163.4169 | 0 | 4341.6867 | 704.8193 | 0 | 0 | 20802.8819 | 7189.1566 | 0 | 0 | 0 | 0 | 0 | 3486.3181 | 2255.4217 | 3383.1325 | 0 | 0 | 0 | 112409.4985 | 0 | 439.1566 | 2664.2169 | 409.8795 | 1024.6988 | 0 | 73811.7759 | 0 | 0 | 0 | 19599.262 | 29321.6747 | 7048.1928 | 0 | 0 | 0 | 0 | 0 | 2819.2771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-16 | 295858.9925 | 0 | 0 | 112572.9623 | 4638.7952 | 75452.0376 | 60094.8157 | 43100.3817 | 0 | 4438.1687 | 720.4819 | 0 | 0 | 21265.1682 | 7348.9157 | 0 | 0 | 0 | 0 | 0 | 3563.7918 | 2305.5422 | 3458.3133 | 0 | 0 | 0 | 112572.9623 | 0 | 448.9157 | 2723.4217 | 418.988 | 1047.4699 | 0 | 75452.0376 | 0 | 0 | 0 | 20034.8012 | 29973.2675 | 7204.8193 | 0 | 0 | 0 | 0 | 0 | 2881.9277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-17 | 300006.9352 | 0 | 0 | 112736.4262 | 4739.6386 | 77092.2993 | 61401.2247 | 44037.3465 | 0 | 4534.6506 | 736.1446 | 0 | 0 | 21727.4545 | 7508.6747 | 0 | 0 | 0 | 0 | 0 | 3641.2655 | 2355.6627 | 3533.494 | 0 | 0 | 0 | 112736.4262 | 0 | 458.6747 | 2782.6265 | 428.0964 | 1070.241 | 0 | 77092.2993 | 0 | 0 | 0 | 20470.3404 | 30624.8602 | 7361.4458 | 0 | 0 | 0 | 0 | 0 | 2944.5783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-18 | 304154.878 | 0 | 0 | 112899.8901 | 4840.4819 | 78732.561 | 62707.6337 | 44974.3113 | 0 | 4631.1325 | 751.8072 | 0 | 0 | 22189.7407 | 7668.4337 | 0 | 0 | 0 | 0 | 0 | 3718.7393 | 2405.7831 | 3608.6747 | 0 | 0 | 0 | 112899.8901 | 0 | 468.4337 | 2841.8313 | 437.2048 | 1093.012 | 0 | 78732.561 | 0 | 0 | 0 | 20905.8795 | 31276.453 | 7518.0723 | 0 | 0 | 0 | 0 | 0 | 3007.2289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-19 | 308302.8208 | 0 | 0 | 113063.3539 | 4941.3253 | 80372.8227 | 64014.0428 | 45911.2761 | 0 | 4727.6145 | 767.4699 | 0 | 0 | 22652.027 | 7828.1928 | 0 | 0 | 0 | 0 | 0 | 3796.213 | 2455.9036 | 3683.8554 | 0 | 0 | 0 | 113063.3539 | 0 | 478.1928 | 2901.0361 | 446.3133 | 1115.7831 | 0 | 80372.8227 | 0 | 0 | 0 | 21341.4187 | 31928.0458 | 7674.6988 | 0 | 0 | 0 | 0 | 0 | 3069.8795 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-20 | 312450.7636 | 0 | 0 | 113226.8178 | 5042.1687 | 82013.0843 | 65320.4518 | 46848.241 | 0 | 4824.0964 | 783.1325 | 0 | 0 | 23114.3133 | 7987.9518 | 0 | 0 | 0 | 0 | 0 | 3873.6867 | 2506.0241 | 3759.0361 | 0 | 0 | 0 | 113226.8178 | 0 | 487.9518 | 2960.241 | 455.4217 | 1138.5542 | 0 | 82013.0843 | 0 | 0 | 0 | 21776.9578 | 32579.6386 | 7831.3253 | 0 | 0 | 0 | 0 | 0 | 3132.5301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-21 | 330378.0839 | 0 | 0 | 114848.5485 | 5824.2911 | 85054.3834 | 76865.6551 | 47785.2058 | 0 | 4920.5783 | 798.7952 | 0 | 0 | 23576.5995 | 8147.7108 | 0 | 0 | 0 | 0 | 0 | 3951.1605 | 2556.1446 | 3834.2169 | 0 | 0 | 7093.6413 | 114848.5485 | 0 | 563.6411 | 3419.4225 | 526.065 | 1315.1625 | 0 | 85054.3834 | 0 | 0 | 0 | 22332.2179 | 36256.6634 | 7987.9518 | 0 | 0 | 0 | 0 | 0 | 3195.1807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-22 | 348305.4042 | 0 | 0 | 116470.2792 | 6606.4136 | 88095.6825 | 88410.8584 | 48722.1706 | 0 | 5017.0602 | 814.4578 | 0 | 0 | 24038.8858 | 8307.4699 | 0 | 0 | 0 | 0 | 0 | 4028.6342 | 2606.2651 | 3909.3976 | 0 | 0 | 14187.2826 | 116470.2792 | 0 | 639.3303 | 3878.6041 | 596.7083 | 1491.7708 | 0 | 88095.6825 | 0 | 0 | 0 | 22887.478 | 39933.6882 | 8144.5783 | 0 | 0 | 0 | 0 | 0 | 3257.8313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-23 | 366232.7245 | 0 | 0 | 118092.0099 | 7388.536 | 91136.9815 | 99956.0617 | 49659.1354 | 0 | 5113.5422 | 830.1205 | 0 | 0 | 24501.172 | 8467.2289 | 0 | 0 | 0 | 0 | 0 | 4106.108 | 2656.3855 | 3984.5783 | 0 | 0 | 21280.9238 | 118092.0099 | 0 | 715.0196 | 4337.7857 | 667.3516 | 1668.3791 | 0 | 91136.9815 | 0 | 0 | 0 | 23442.7381 | 43610.713 | 8301.2048 | 0 | 0 | 0 | 0 | 0 | 3320.4819 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-24 | 384160.0449 | 0 | 0 | 119713.7406 | 8170.6584 | 94178.2806 | 111501.265 | 50596.1002 | 0 | 5210.0241 | 845.7831 | 0 | 0 | 24963.4583 | 8626.988 | 0 | 0 | 0 | 0 | 0 | 4183.5817 | 2706.506 | 4059.759 | 0 | 0 | 28374.5651 | 119713.7406 | 0 | 790.7089 | 4796.9672 | 737.995 | 1844.9874 | 0 | 94178.2806 | 0 | 0 | 0 | 23997.9982 | 47287.7378 | 8457.8313 | 0 | 0 | 0 | 0 | 0 | 3383.1325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-25 | 402087.3652 | 0 | 0 | 121335.4714 | 8952.7809 | 97219.5796 | 123046.4683 | 51533.0651 | 0 | 5306.506 | 861.4458 | 0 | 0 | 25425.7446 | 8786.747 | 0 | 0 | 0 | 0 | 0 | 4261.0554 | 2756.6265 | 4134.9398 | 0 | 0 | 35468.2064 | 121335.4714 | 0 | 866.3982 | 5256.1488 | 808.6383 | 2021.5957 | 0 | 97219.5796 | 0 | 0 | 0 | 24553.2583 | 50964.7626 | 8614.4578 | 0 | 0 | 0 | 0 | 0 | 3445.7831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-26 | 420014.6855 | 0 | 0 | 122957.2021 | 9734.9033 | 100260.8787 | 134591.6715 | 52470.0299 | 0 | 5402.988 | 877.1084 | 0 | 0 | 25888.0308 | 8946.506 | 0 | 0 | 0 | 0 | 0 | 4338.5292 | 2806.747 | 4210.1205 | 0 | 0 | 42561.8477 | 122957.2021 | 0 | 942.0874 | 5715.3303 | 879.2816 | 2198.204 | 0 | 100260.8787 | 0 | 0 | 0 | 25108.5184 | 54641.7875 | 8771.0843 | 0 | 0 | 0 | 0 | 0 | 3508.4337 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-27 | 437942.0059 | 0 | 0 | 124578.9328 | 10517.0258 | 103302.1778 | 146136.8748 | 53406.9947 | 0 | 5499.4699 | 892.7711 | 0 | 0 | 26350.3171 | 9106.2651 | 0 | 0 | 0 | 0 | 0 | 4416.0029 | 2856.8675 | 4285.3012 | 0 | 0 | 49655.489 | 124578.9328 | 0 | 1017.7767 | 6174.5119 | 949.9249 | 2374.8123 | 0 | 103302.1778 | 0 | 0 | 0 | 25663.7784 | 58318.8123 | 8927.7108 | 0 | 0 | 0 | 0 | 0 | 3571.0843 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-28 | 455869.3262 | 0 | 0 | 126200.6635 | 11299.1482 | 106343.4768 | 157682.0781 | 54343.9595 | 0 | 5595.9518 | 908.4337 | 0 | 0 | 26812.6034 | 9266.0241 | 0 | 0 | 0 | 0 | 0 | 4493.4766 | 2906.988 | 4360.4819 | 0 | 0 | 56749.1302 | 126200.6635 | 0 | 1093.466 | 6633.6935 | 1020.5682 | 2551.4206 | 0 | 106343.4768 | 0 | 0 | 0 | 26219.0385 | 61995.8371 | 9084.3373 | 0 | 0 | 0 | 0 | 0 | 3633.7349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-29 | 473796.6465 | 0 | 0 | 127822.3942 | 12081.2707 | 109384.7759 | 169227.2814 | 55280.9243 | 0 | 5692.4337 | 924.0964 | 0 | 0 | 27274.8896 | 9425.7831 | 0 | 0 | 0 | 0 | 0 | 4570.9504 | 2957.1084 | 4435.6627 | 0 | 0 | 63842.7715 | 127822.3942 | 0 | 1169.1552 | 7092.875 | 1091.2115 | 2728.0289 | 0 | 109384.7759 | 0 | 0 | 0 | 26774.2986 | 65672.8619 | 9240.9639 | 0 | 0 | 0 | 0 | 0 | 3696.3855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-30 | 491723.9668 | 0 | 0 | 129444.1249 | 12863.3931 | 112426.0749 | 180772.4847 | 56217.8892 | 0 | 5788.9157 | 939.759 | 0 | 0 | 27737.1759 | 9585.5422 | 0 | 0 | 0 | 0 | 0 | 4648.4241 | 3007.2289 | 4510.8434 | 0 | 0 | 70936.4128 | 129444.1249 | 0 | 1244.8445 | 7552.0566 | 1161.8549 | 2904.6372 | 0 | 112426.0749 | 0 | 0 | 0 | 27329.5587 | 69349.8867 | 9397.5904 | 0 | 0 | 0 | 0 | 0 | 3759.0361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-07-31 | 509651.2872 | 484608.92 | 484608.92 | 131065.8556 | 13645.5156 | 115467.374 | 192317.688 | 57154.854 | 0 | 5885.3976 | 955.4217 | 0 | 0 | 28199.4622 | 9745.3012 | 0 | 0 | 0 | 0 | 0 | 4725.8978 | 3057.3494 | 4586.0241 | 0 | 0 | 78030.0541 | 131065.8556 | 0 | 1320.5338 | 8011.2382 | 1232.4982 | 3081.2454 | 0 | 115467.374 | 0 | 0 | 0 | 27884.8188 | 73026.9115 | 9554.2169 | 0 | 0 | 0 | 0 | 0 | 3821.6867 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-01 | 527578.6075 | 0 | 484608.92 | 132687.5864 | 14427.638 | 118508.6731 | 203862.8913 | 58091.8188 | 0 | 5981.8795 | 971.0843 | 0 | 0 | 28661.7484 | 9905.0602 | 0 | 0 | 0 | 0 | 0 | 4803.3716 | 3107.4699 | 4661.2048 | 0 | 0 | 85123.6953 | 132687.5864 | 0 | 1396.223 | 8470.4197 | 1303.1415 | 3257.8537 | 0 | 118508.6731 | 0 | 0 | 0 | 28440.0789 | 76703.9363 | 9710.8434 | 0 | 0 | 0 | 0 | 0 | 3884.3373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-02 | 545505.9278 | 0 | 484608.92 | 134309.3171 | 15209.7604 | 121549.9721 | 215408.0946 | 59028.7836 | 0 | 6078.3614 | 986.747 | 0 | 0 | 29124.0347 | 10064.8193 | 0 | 0 | 0 | 0 | 0 | 4880.8453 | 3157.5904 | 4736.3855 | 0 | 0 | 92217.3366 | 134309.3171 | 0 | 1471.9123 | 8929.6013 | 1373.7848 | 3434.462 | 0 | 121549.9721 | 0 | 0 | 0 | 28995.339 | 80380.9612 | 9867.4699 | 0 | 0 | 0 | 0 | 0 | 3946.988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-03 | 563433.2482 | 0 | 484608.92 | 135931.0478 | 15991.8829 | 124591.2712 | 226953.2979 | 59965.7484 | 0 | 6174.8434 | 1002.4096 | 0 | 0 | 29586.321 | 10224.5783 | 0 | 0 | 0 | 0 | 0 | 4958.319 | 3207.7108 | 4811.5663 | 0 | 0 | 99310.9779 | 135931.0478 | 0 | 1547.6016 | 9388.7829 | 1444.4281 | 3611.0703 | 0 | 124591.2712 | 0 | 0 | 0 | 29550.599 | 84057.986 | 10024.0964 | 0 | 0 | 0 | 0 | 0 | 4009.6386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-04 | 581360.5685 | 0 | 484608.92 | 137552.7785 | 16774.0053 | 127632.5702 | 238498.5012 | 60902.7133 | 0 | 6271.3253 | 1018.0723 | 0 | 0 | 30048.6072 | 10384.3373 | 0 | 0 | 0 | 0 | 0 | 5035.7928 | 3257.8313 | 4886.747 | 0 | 0 | 106404.6192 | 137552.7785 | 0 | 1623.2908 | 9847.9644 | 1515.0714 | 3787.6786 | 0 | 127632.5702 | 0 | 0 | 0 | 30105.8591 | 87735.0108 | 10180.7229 | 0 | 0 | 0 | 0 | 0 | 4072.2892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-05 | 599287.8888 | 0 | 484608.92 | 139174.5092 | 17556.1278 | 130673.8693 | 250043.7045 | 61839.6781 | 0 | 6367.8072 | 1033.7349 | 0 | 0 | 30510.8935 | 10544.0964 | 0 | 0 | 0 | 0 | 0 | 5113.2665 | 3307.9518 | 4961.9277 | 0 | 0 | 113498.2605 | 139174.5092 | 0 | 1698.9801 | 10307.146 | 1585.7148 | 3964.2869 | 0 | 130673.8693 | 0 | 0 | 0 | 30661.1192 | 91412.0356 | 10337.3494 | 0 | 0 | 0 | 0 | 0 | 4134.9398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-06 | 617215.2092 | 0 | 484608.92 | 140796.2399 | 18338.2502 | 133715.1684 | 261588.9077 | 62776.6429 | 0 | 6464.2892 | 1049.3976 | 0 | 0 | 30973.1798 | 10703.8554 | 0 | 0 | 0 | 0 | 0 | 5190.7402 | 3358.0723 | 5037.1084 | 0 | 0 | 120591.9017 | 140796.2399 | 0 | 1774.6694 | 10766.3275 | 1656.3581 | 4140.8952 | 0 | 133715.1684 | 0 | 0 | 0 | 31216.3793 | 95089.0604 | 10493.9759 | 0 | 0 | 0 | 0 | 0 | 4197.5904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-07 | 635142.5295 | 0 | 484608.92 | 142417.9707 | 19120.3727 | 136756.4674 | 273134.111 | 63713.6077 | 0 | 6560.7711 | 1065.0602 | 0 | 0 | 31435.466 | 10863.6145 | 0 | 0 | 0 | 0 | 0 | 5268.214 | 3408.1928 | 5112.2892 | 0 | 0 | 127685.543 | 142417.9707 | 0 | 1850.3586 | 11225.5091 | 1727.0014 | 4317.5035 | 0 | 136756.4674 | 0 | 0 | 0 | 31771.6394 | 98766.0852 | 10650.6024 | 0 | 0 | 0 | 0 | 0 | 4260.241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-08 | 653069.8498 | 0 | 484608.92 | 144039.7014 | 19902.4951 | 139797.7665 | 284679.3143 | 64650.5725 | 0 | 6657.253 | 1080.7229 | 0 | 0 | 31897.7523 | 11023.3735 | 0 | 0 | 0 | 0 | 0 | 5345.6877 | 3458.3133 | 5187.4699 | 0 | 0 | 134779.1843 | 144039.7014 | 0 | 1926.0479 | 11684.6907 | 1797.6447 | 4494.1118 | 0 | 139797.7665 | 0 | 0 | 0 | 32326.8995 | 102443.1101 | 10807.2289 | 0 | 0 | 0 | 0 | 0 | 4322.8916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-09 | 670997.1701 | 0 | 484608.92 | 145661.4321 | 20684.6175 | 142839.0655 | 296224.5176 | 65587.5373 | 0 | 6753.7349 | 1096.3855 | 0 | 0 | 32360.0386 | 11183.1325 | 0 | 0 | 0 | 0 | 0 | 5423.1614 | 3508.4337 | 5262.6506 | 0 | 0 | 141872.8256 | 145661.4321 | 0 | 2001.7372 | 12143.8722 | 1868.288 | 4670.7201 | 0 | 142839.0655 | 0 | 0 | 0 | 32882.1596 | 106120.1349 | 10963.8554 | 0 | 0 | 0 | 0 | 0 | 4385.5422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-10 | 688924.4905 | 0 | 484608.92 | 147283.1628 | 21466.74 | 145880.3646 | 307769.7209 | 66524.5022 | 0 | 6850.2169 | 1112.0482 | 0 | 0 | 32822.3248 | 11342.8916 | 0 | 0 | 0 | 0 | 0 | 5500.6352 | 3558.5542 | 5337.8313 | 0 | 0 | 148966.4669 | 147283.1628 | 0 | 2077.4264 | 12603.0538 | 1938.9314 | 4847.3284 | 0 | 145880.3646 | 0 | 0 | 0 | 33437.4197 | 109797.1597 | 11120.4819 | 0 | 0 | 0 | 0 | 0 | 4448.1928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-11 | 706851.8108 | 0 | 484608.92 | 148904.8935 | 22248.8624 | 148921.6637 | 319314.9242 | 67461.467 | 0 | 6946.6988 | 1127.7108 | 0 | 0 | 33284.6111 | 11502.6506 | 0 | 0 | 0 | 0 | 0 | 5578.1089 | 3608.6747 | 5413.012 | 0 | 0 | 156060.1081 | 148904.8935 | 0 | 2153.1157 | 13062.2354 | 2009.5747 | 5023.9367 | 0 | 148921.6637 | 0 | 0 | 0 | 33992.6797 | 113474.1845 | 11277.1084 | 0 | 0 | 0 | 0 | 0 | 4510.8434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-12 | 724779.1311 | 0 | 484608.92 | 150526.6242 | 23030.9849 | 151962.9627 | 330860.1275 | 68398.4318 | 0 | 7043.1807 | 1143.3735 | 0 | 0 | 33746.8973 | 11662.4096 | 0 | 0 | 0 | 0 | 0 | 5655.5827 | 3658.7952 | 5488.1928 | 0 | 0 | 163153.7494 | 150526.6242 | 0 | 2228.805 | 13521.4169 | 2080.218 | 5200.545 | 0 | 151962.9627 | 0 | 0 | 0 | 34547.9398 | 117151.2093 | 11433.7349 | 0 | 0 | 0 | 0 | 0 | 4573.494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-13 | 742706.4515 | 0 | 484608.92 | 152148.355 | 23813.1073 | 155004.2618 | 342405.3308 | 69335.3966 | 0 | 7139.6627 | 1159.0361 | 0 | 0 | 34209.1836 | 11822.1687 | 0 | 0 | 0 | 0 | 0 | 5733.0564 | 3708.9157 | 5563.3735 | 0 | 0 | 170247.3907 | 152148.355 | 0 | 2304.4943 | 13980.5985 | 2150.8613 | 5377.1533 | 0 | 155004.2618 | 0 | 0 | 0 | 35103.1999 | 120828.2341 | 11590.3614 | 0 | 0 | 0 | 0 | 0 | 4636.1446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-14 | 760633.7718 | 0 | 484608.92 | 153770.0857 | 24595.2298 | 158045.5608 | 353950.5341 | 70272.3614 | 0 | 7236.1446 | 1174.6988 | 0 | 0 | 34671.4699 | 11981.9277 | 0 | 0 | 0 | 0 | 0 | 5810.5301 | 3759.0361 | 5638.5542 | 0 | 0 | 177341.032 | 153770.0857 | 0 | 2380.1835 | 14439.7801 | 2221.5046 | 5553.7616 | 0 | 158045.5608 | 0 | 0 | 0 | 35658.46 | 124505.259 | 11746.988 | 0 | 0 | 0 | 0 | 0 | 4698.7952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-15 | 778561.0921 | 0 | 484608.92 | 155391.8164 | 25377.3522 | 161086.8599 | 365495.7374 | 71209.3263 | 0 | 7332.6265 | 1190.3614 | 0 | 0 | 35133.7561 | 12141.6867 | 0 | 0 | 0 | 0 | 0 | 5888.0039 | 3809.1566 | 5713.7349 | 0 | 0 | 184434.6733 | 155391.8164 | 0 | 2455.8728 | 14898.9616 | 2292.1479 | 5730.3699 | 0 | 161086.8599 | 0 | 0 | 0 | 36213.7201 | 128182.2838 | 11903.6145 | 0 | 0 | 0 | 0 | 0 | 4761.4458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-16 | 796488.4124 | 0 | 484608.92 | 157013.5471 | 26159.4746 | 164128.159 | 377040.9406 | 72146.2911 | 0 | 7429.1084 | 1206.0241 | 0 | 0 | 35596.0424 | 12301.4458 | 0 | 0 | 0 | 0 | 0 | 5965.4776 | 3859.2771 | 5788.9157 | 0 | 0 | 191528.3145 | 157013.5471 | 0 | 2531.5621 | 15358.1432 | 2362.7913 | 5906.9781 | 0 | 164128.159 | 0 | 0 | 0 | 36768.9802 | 131859.3086 | 12060.241 | 0 | 0 | 0 | 0 | 0 | 4824.0964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-17 | 814415.7328 | 0 | 484608.92 | 158635.2778 | 26941.5971 | 167169.458 | 388586.1439 | 73083.2559 | 0 | 7525.5904 | 1221.6867 | 0 | 0 | 36058.3287 | 12461.2048 | 0 | 0 | 0 | 0 | 0 | 6042.9513 | 3909.3976 | 5864.0964 | 0 | 0 | 198621.9558 | 158635.2778 | 0 | 2607.2513 | 15817.3247 | 2433.4346 | 6083.5864 | 0 | 167169.458 | 0 | 0 | 0 | 37324.2403 | 135536.3334 | 12216.8675 | 0 | 0 | 0 | 0 | 0 | 4886.747 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-18 | 832343.0531 | 0 | 484608.92 | 160257.0085 | 27723.7195 | 170210.7571 | 400131.3472 | 74020.2207 | 0 | 7622.0723 | 1237.3494 | 0 | 0 | 36520.6149 | 12620.9639 | 0 | 0 | 0 | 0 | 0 | 6120.4251 | 3959.5181 | 5939.2771 | 0 | 0 | 205715.5971 | 160257.0085 | 0 | 2682.9406 | 16276.5063 | 2504.0779 | 6260.1947 | 0 | 170210.7571 | 0 | 0 | 0 | 37879.5004 | 139213.3582 | 12373.494 | 0 | 0 | 0 | 0 | 0 | 4949.3976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-19 | 850270.3734 | 0 | 484608.92 | 161878.7392 | 28505.842 | 173252.0562 | 411676.5505 | 74957.1855 | 0 | 7718.5542 | 1253.012 | 0 | 0 | 36982.9012 | 12780.7229 | 0 | 0 | 0 | 0 | 0 | 6197.8988 | 4009.6386 | 6014.4578 | 0 | 0 | 212809.2384 | 161878.7392 | 0 | 2758.6299 | 16735.6879 | 2574.7212 | 6436.803 | 0 | 173252.0562 | 0 | 0 | 0 | 38434.7604 | 142890.383 | 12530.1205 | 0 | 0 | 0 | 0 | 0 | 5012.0482 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-20 | 868197.6938 | 0 | 484608.92 | 163500.47 | 29287.9644 | 176293.3552 | 423221.7538 | 75894.1504 | 0 | 7815.0361 | 1268.6747 | 0 | 0 | 37445.1875 | 12940.4819 | 0 | 0 | 0 | 0 | 0 | 6275.3725 | 4059.759 | 6089.6386 | 0 | 0 | 219902.8797 | 163500.47 | 0 | 2834.3191 | 17194.8694 | 2645.3645 | 6613.4113 | 0 | 176293.3552 | 0 | 0 | 0 | 38990.0205 | 146567.4079 | 12686.747 | 0 | 0 | 0 | 0 | 0 | 5074.6988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-21 | 886125.0141 | 0 | 484608.92 | 165122.2007 | 30070.0869 | 179334.6543 | 434766.9571 | 76831.1152 | 0 | 7911.5181 | 1284.3373 | 0 | 0 | 37907.4737 | 13100.241 | 0 | 0 | 0 | 0 | 0 | 6352.8463 | 4109.8795 | 6164.8193 | 0 | 0 | 226996.5209 | 165122.2007 | 0 | 2910.0084 | 17654.051 | 2716.0078 | 6790.0196 | 0 | 179334.6543 | 0 | 0 | 0 | 39545.2806 | 150244.4327 | 12843.3735 | 0 | 0 | 0 | 0 | 0 | 5137.3494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-22 | 904052.3344 | 0 | 484608.92 | 166743.9314 | 30852.2093 | 182375.9533 | 446312.1604 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 234090.1622 | 166743.9314 | 0 | 2985.6977 | 18113.2326 | 2786.6512 | 6966.6279 | 0 | 182375.9533 | 0 | 0 | 0 | 40100.5407 | 153921.4575 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-23 | 917831.712 | 0 | 484608.92 | 168202.1983 | 31533.4884 | 183776.9907 | 456550.9546 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 241183.8035 | 168202.1983 | 0 | 3051.6279 | 18513.2093 | 2848.186 | 7120.4651 | 0 | 183776.9907 | 0 | 0 | 0 | 40220.2616 | 156946.8895 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-24 | 931611.0895 | 0 | 484608.92 | 169660.4651 | 32214.7674 | 185178.0281 | 466789.7489 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 248277.4448 | 169660.4651 | 0 | 3117.5581 | 18913.186 | 2909.7209 | 7274.3023 | 0 | 185178.0281 | 0 | 0 | 0 | 40339.9826 | 159972.3216 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-25 | 945390.4671 | 0 | 484608.92 | 171118.732 | 32896.0465 | 186579.0655 | 477028.5432 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 255371.086 | 171118.732 | 0 | 3183.4884 | 19313.1628 | 2971.2558 | 7428.1395 | 0 | 186579.0655 | 0 | 0 | 0 | 40459.7035 | 162997.7536 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-26 | 959169.8447 | 0 | 484608.92 | 172576.9988 | 33577.3256 | 187980.1028 | 487267.3374 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 262464.7273 | 172576.9988 | 0 | 3249.4186 | 19713.1395 | 3032.7907 | 7581.9767 | 0 | 187980.1028 | 0 | 0 | 0 | 40579.4244 | 166023.1857 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-27 | 972949.2222 | 0 | 484608.92 | 174035.2657 | 34258.6047 | 189381.1402 | 497506.1317 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 269558.3686 | 174035.2657 | 0 | 3315.3488 | 20113.1163 | 3094.3256 | 7735.814 | 0 | 189381.1402 | 0 | 0 | 0 | 40699.1453 | 169048.6177 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-28 | 986728.5998 | 0 | 484608.92 | 175493.5326 | 34939.8837 | 190782.1776 | 507744.9259 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 276652.0099 | 175493.5326 | 0 | 3381.2791 | 20513.093 | 3155.8605 | 7889.6512 | 0 | 190782.1776 | 0 | 0 | 0 | 40818.8663 | 172074.0498 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-29 | 1000507.9773 | 0 | 484608.92 | 176951.7994 | 35621.1628 | 192183.2149 | 517983.7202 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 283745.6512 | 176951.7994 | 0 | 3447.2093 | 20913.0698 | 3217.3953 | 8043.4884 | 0 | 192183.2149 | 0 | 0 | 0 | 40938.5872 | 175099.4818 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-30 | 1014287.3549 | 0 | 484608.92 | 178410.0663 | 36302.4419 | 193584.2523 | 528222.5144 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 290839.2924 | 178410.0663 | 0 | 3513.1395 | 21313.0465 | 3278.9302 | 8197.3256 | 0 | 193584.2523 | 0 | 0 | 0 | 41058.3081 | 178124.9138 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-08-31 | 1028066.7324 | 177400.83 | 662009.75 | 179868.3331 | 36983.7209 | 194985.2897 | 538461.3087 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 297932.9337 | 179868.3331 | 0 | 3579.0698 | 21713.0233 | 3340.4651 | 8351.1628 | 0 | 194985.2897 | 0 | 0 | 0 | 41178.0291 | 181150.3459 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-01 | 1041846.11 | 0 | 662009.75 | 181326.6 | 37665 | 196386.3271 | 548700.1029 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 181326.6 | 0 | 3645 | 22113 | 3402 | 8505 | 0 | 196386.3271 | 0 | 0 | 0 | 41297.75 | 184175.7779 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-02 | 1046499.3341 | 0 | 662009.75 | 183457.575 | 38815.875 | 196966.4629 | 549491.3412 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 183457.575 | 0 | 3756.375 | 22788.675 | 3505.95 | 8764.875 | 0 | 196966.4629 | 0 | 0 | 0 | 41297.75 | 184967.0162 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-03 | 1051152.5582 | 0 | 662009.75 | 185588.55 | 39966.75 | 197546.5987 | 550282.5795 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 185588.55 | 0 | 3867.75 | 23464.35 | 3609.9 | 9024.75 | 0 | 197546.5987 | 0 | 0 | 0 | 41297.75 | 185758.2545 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-04 | 1055805.7823 | 0 | 662009.75 | 187719.525 | 41117.625 | 198126.7346 | 551073.8177 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 187719.525 | 0 | 3979.125 | 24140.025 | 3713.85 | 9284.625 | 0 | 198126.7346 | 0 | 0 | 0 | 41297.75 | 186549.4927 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-05 | 1060459.0064 | 0 | 662009.75 | 189850.5 | 42268.5 | 198706.8704 | 551865.056 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 189850.5 | 0 | 4090.5 | 24815.7 | 3817.8 | 9544.5 | 0 | 198706.8704 | 0 | 0 | 0 | 41297.75 | 187340.731 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-06 | 1065112.2305 | 0 | 662009.75 | 191981.475 | 43419.375 | 199287.0062 | 552656.2942 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 191981.475 | 0 | 4201.875 | 25491.375 | 3921.75 | 9804.375 | 0 | 199287.0062 | 0 | 0 | 0 | 41297.75 | 188131.9692 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-07 | 1069765.4546 | 0 | 662009.75 | 194112.45 | 44570.25 | 199867.1421 | 553447.5325 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 194112.45 | 0 | 4313.25 | 26167.05 | 4025.7 | 10064.25 | 0 | 199867.1421 | 0 | 0 | 0 | 41297.75 | 188923.2075 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-08 | 1074418.6787 | 0 | 662009.75 | 196243.425 | 45721.125 | 200447.2779 | 554238.7707 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 196243.425 | 0 | 4424.625 | 26842.725 | 4129.65 | 10324.125 | 0 | 200447.2779 | 0 | 0 | 0 | 41297.75 | 189714.4457 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-09 | 1079071.9027 | 0 | 662009.75 | 198374.4 | 46872 | 201027.4137 | 555030.009 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 198374.4 | 0 | 4536 | 27518.4 | 4233.6 | 10584 | 0 | 201027.4137 | 0 | 0 | 0 | 41297.75 | 190505.684 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-10 | 1083725.1268 | 0 | 662009.75 | 200505.375 | 48022.875 | 201607.5496 | 555821.2473 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 200505.375 | 0 | 4647.375 | 28194.075 | 4337.55 | 10843.875 | 0 | 201607.5496 | 0 | 0 | 0 | 41297.75 | 191296.9223 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-11 | 1088378.3509 | 0 | 662009.75 | 202636.35 | 49173.75 | 202187.6854 | 556612.4855 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 202636.35 | 0 | 4758.75 | 28869.75 | 4441.5 | 11103.75 | 0 | 202187.6854 | 0 | 0 | 0 | 41297.75 | 192088.1605 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-12 | 1093031.575 | 0 | 662009.75 | 204767.325 | 50324.625 | 202767.8212 | 557403.7238 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 204767.325 | 0 | 4870.125 | 29545.425 | 4545.45 | 11363.625 | 0 | 202767.8212 | 0 | 0 | 0 | 41297.75 | 192879.3988 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-13 | 1097684.7991 | 0 | 662009.75 | 206898.3 | 51475.5 | 203347.9571 | 558194.962 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 206898.3 | 0 | 4981.5 | 30221.1 | 4649.4 | 11623.5 | 0 | 203347.9571 | 0 | 0 | 0 | 41297.75 | 193670.637 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-14 | 1102338.0232 | 0 | 662009.75 | 209029.275 | 52626.375 | 203928.0929 | 558986.2003 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 209029.275 | 0 | 5092.875 | 30896.775 | 4753.35 | 11883.375 | 0 | 203928.0929 | 0 | 0 | 0 | 41297.75 | 194461.8753 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-15 | 1106991.2473 | 0 | 662009.75 | 211160.25 | 53777.25 | 204508.2287 | 559777.4386 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 211160.25 | 0 | 5204.25 | 31572.45 | 4857.3 | 12143.25 | 0 | 204508.2287 | 0 | 0 | 0 | 41297.75 | 195253.1136 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-16 | 1111644.4714 | 0 | 662009.75 | 213291.225 | 54928.125 | 205088.3646 | 560568.6768 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 213291.225 | 0 | 5315.625 | 32248.125 | 4961.25 | 12403.125 | 0 | 205088.3646 | 0 | 0 | 0 | 41297.75 | 196044.3518 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-17 | 1116297.6955 | 0 | 662009.75 | 215422.2 | 56079 | 205668.5004 | 561359.9151 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 215422.2 | 0 | 5427 | 32923.8 | 5065.2 | 12663 | 0 | 205668.5004 | 0 | 0 | 0 | 41297.75 | 196835.5901 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-18 | 1120950.9196 | 0 | 662009.75 | 217553.175 | 57229.875 | 206248.6362 | 562151.1533 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 217553.175 | 0 | 5538.375 | 33599.475 | 5169.15 | 12922.875 | 0 | 206248.6362 | 0 | 0 | 0 | 41297.75 | 197626.8283 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-19 | 1125604.1437 | 0 | 662009.75 | 219684.15 | 58380.75 | 206828.7721 | 562942.3916 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 219684.15 | 0 | 5649.75 | 34275.15 | 5273.1 | 13182.75 | 0 | 206828.7721 | 0 | 0 | 0 | 41297.75 | 198418.0666 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-20 | 1130257.3678 | 0 | 662009.75 | 221815.125 | 59531.625 | 207408.9079 | 563733.6299 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 221815.125 | 0 | 5761.125 | 34950.825 | 5377.05 | 13442.625 | 0 | 207408.9079 | 0 | 0 | 0 | 41297.75 | 199209.3049 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-21 | 1134910.5919 | 0 | 662009.75 | 223946.1 | 60682.5 | 207989.0437 | 564524.8681 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 223946.1 | 0 | 5872.5 | 35626.5 | 5481 | 13702.5 | 0 | 207989.0437 | 0 | 0 | 0 | 41297.75 | 200000.5431 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-22 | 1139563.816 | 0 | 662009.75 | 226077.075 | 61833.375 | 208569.1796 | 565316.1064 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 226077.075 | 0 | 5983.875 | 36302.175 | 5584.95 | 13962.375 | 0 | 208569.1796 | 0 | 0 | 0 | 41297.75 | 200791.7814 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-23 | 1144217.04 | 0 | 662009.75 | 228208.05 | 62984.25 | 209149.3154 | 566107.3446 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 228208.05 | 0 | 6095.25 | 36977.85 | 5688.9 | 14222.25 | 0 | 209149.3154 | 0 | 0 | 0 | 41297.75 | 201583.0196 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-24 | 1148870.2641 | 0 | 662009.75 | 230339.025 | 64135.125 | 209729.4512 | 566898.5829 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 230339.025 | 0 | 6206.625 | 37653.525 | 5792.85 | 14482.125 | 0 | 209729.4512 | 0 | 0 | 0 | 41297.75 | 202374.2579 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-25 | 1153523.4882 | 0 | 662009.75 | 232470 | 65286 | 210309.5871 | 567689.8212 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 232470 | 0 | 6318 | 38329.2 | 5896.8 | 14742 | 0 | 210309.5871 | 0 | 0 | 0 | 41297.75 | 203165.4962 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-26 | 1158176.7123 | 0 | 662009.75 | 234600.975 | 66436.875 | 210889.7229 | 568481.0594 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 234600.975 | 0 | 6429.375 | 39004.875 | 6000.75 | 15001.875 | 0 | 210889.7229 | 0 | 0 | 0 | 41297.75 | 203956.7344 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-27 | 1162829.9364 | 0 | 662009.75 | 236731.95 | 67587.75 | 211469.8587 | 569272.2977 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 236731.95 | 0 | 6540.75 | 39680.55 | 6104.7 | 15261.75 | 0 | 211469.8587 | 0 | 0 | 0 | 41297.75 | 204747.9727 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-28 | 1167483.1605 | 0 | 662009.75 | 238862.925 | 68738.625 | 212049.9946 | 570063.5359 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 238862.925 | 0 | 6652.125 | 40356.225 | 6208.65 | 15521.625 | 0 | 212049.9946 | 0 | 0 | 0 | 41297.75 | 205539.2109 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-29 | 1172136.3846 | 0 | 662009.75 | 240993.9 | 69889.5 | 212630.1304 | 570854.7742 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 240993.9 | 0 | 6763.5 | 41031.9 | 6312.6 | 15781.5 | 0 | 212630.1304 | 0 | 0 | 0 | 41297.75 | 206330.4492 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-09-30 | 1176789.6087 | 0 | 662009.75 | 243124.875 | 71040.375 | 213210.2662 | 571646.0125 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 243124.875 | 0 | 6874.875 | 41707.575 | 6416.55 | 16041.375 | 0 | 213210.2662 | 0 | 0 | 0 | 41297.75 | 207121.6875 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-01 | 1181442.8328 | 0 | 662009.75 | 245255.85 | 72191.25 | 213790.4021 | 572437.2507 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 245255.85 | 0 | 6986.25 | 42383.25 | 6520.5 | 16301.25 | 0 | 213790.4021 | 0 | 0 | 0 | 41297.75 | 207912.9257 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-02 | 1186096.0569 | 0 | 662009.75 | 247386.825 | 73342.125 | 214370.5379 | 573228.489 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 247386.825 | 0 | 7097.625 | 43058.925 | 6624.45 | 16561.125 | 0 | 214370.5379 | 0 | 0 | 0 | 41297.75 | 208704.164 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-03 | 1190749.281 | 0 | 662009.75 | 249517.8 | 74493 | 214950.6737 | 574019.7272 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 249517.8 | 0 | 7209 | 43734.6 | 6728.4 | 16821 | 0 | 214950.6737 | 0 | 0 | 0 | 41297.75 | 209495.4022 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-04 | 1195402.5051 | 0 | 662009.75 | 251648.775 | 75643.875 | 215530.8096 | 574810.9655 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 251648.775 | 0 | 7320.375 | 44410.275 | 6832.35 | 17080.875 | 0 | 215530.8096 | 0 | 0 | 0 | 41297.75 | 210286.6405 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-05 | 1200055.7292 | 0 | 662009.75 | 253779.75 | 76794.75 | 216110.9454 | 575602.2038 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 253779.75 | 0 | 7431.75 | 45085.95 | 6936.3 | 17340.75 | 0 | 216110.9454 | 0 | 0 | 0 | 41297.75 | 211077.8788 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-06 | 1204708.9533 | 0 | 662009.75 | 255910.725 | 77945.625 | 216691.0812 | 576393.442 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 255910.725 | 0 | 7543.125 | 45761.625 | 7040.25 | 17600.625 | 0 | 216691.0812 | 0 | 0 | 0 | 41297.75 | 211869.117 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-07 | 1209362.1773 | 0 | 662009.75 | 258041.7 | 79096.5 | 217271.2171 | 577184.6803 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 258041.7 | 0 | 7654.5 | 46437.3 | 7144.2 | 17860.5 | 0 | 217271.2171 | 0 | 0 | 0 | 41297.75 | 212660.3553 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-08 | 1214015.4014 | 0 | 662009.75 | 260172.675 | 80247.375 | 217851.3529 | 577975.9185 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 260172.675 | 0 | 7765.875 | 47112.975 | 7248.15 | 18120.375 | 0 | 217851.3529 | 0 | 0 | 0 | 41297.75 | 213451.5935 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-09 | 1218668.6255 | 0 | 662009.75 | 262303.65 | 81398.25 | 218431.4887 | 578767.1568 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 262303.65 | 0 | 7877.25 | 47788.65 | 7352.1 | 18380.25 | 0 | 218431.4887 | 0 | 0 | 0 | 41297.75 | 214242.8318 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-10 | 1223321.8496 | 0 | 662009.75 | 264434.625 | 82549.125 | 219011.6246 | 579558.3951 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 264434.625 | 0 | 7988.625 | 48464.325 | 7456.05 | 18640.125 | 0 | 219011.6246 | 0 | 0 | 0 | 41297.75 | 215034.0701 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-11 | 1227975.0737 | 0 | 662009.75 | 266565.6 | 83700 | 219591.7604 | 580349.6333 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 266565.6 | 0 | 8100 | 49140 | 7560 | 18900 | 0 | 219591.7604 | 0 | 0 | 0 | 41297.75 | 215825.3083 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-12 | 1232628.2978 | 0 | 662009.75 | 268696.575 | 84850.875 | 220171.8962 | 581140.8716 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 268696.575 | 0 | 8211.375 | 49815.675 | 7663.95 | 19159.875 | 0 | 220171.8962 | 0 | 0 | 0 | 41297.75 | 216616.5466 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-13 | 1237281.5219 | 0 | 662009.75 | 270827.55 | 86001.75 | 220752.0321 | 581932.1098 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 270827.55 | 0 | 8322.75 | 50491.35 | 7767.9 | 19419.75 | 0 | 220752.0321 | 0 | 0 | 0 | 41297.75 | 217407.7848 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-14 | 1241934.746 | 0 | 662009.75 | 272958.525 | 87152.625 | 221332.1679 | 582723.3481 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 272958.525 | 0 | 8434.125 | 51167.025 | 7871.85 | 19679.625 | 0 | 221332.1679 | 0 | 0 | 0 | 41297.75 | 218199.0231 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-15 | 1246587.9701 | 0 | 662009.75 | 275089.5 | 88303.5 | 221912.3037 | 583514.5864 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 275089.5 | 0 | 8545.5 | 51842.7 | 7975.8 | 19939.5 | 0 | 221912.3037 | 0 | 0 | 0 | 41297.75 | 218990.2614 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-16 | 1251241.1942 | 0 | 662009.75 | 277220.475 | 89454.375 | 222492.4396 | 584305.8246 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 277220.475 | 0 | 8656.875 | 52518.375 | 8079.75 | 20199.375 | 0 | 222492.4396 | 0 | 0 | 0 | 41297.75 | 219781.4996 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-17 | 1255894.4183 | 0 | 662009.75 | 279351.45 | 90605.25 | 223072.5754 | 585097.0629 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 279351.45 | 0 | 8768.25 | 53194.05 | 8183.7 | 20459.25 | 0 | 223072.5754 | 0 | 0 | 0 | 41297.75 | 220572.7379 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-18 | 1260547.6424 | 0 | 662009.75 | 281482.425 | 91756.125 | 223652.7112 | 585888.3011 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 281482.425 | 0 | 8879.625 | 53869.725 | 8287.65 | 20719.125 | 0 | 223652.7112 | 0 | 0 | 0 | 41297.75 | 221363.9761 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-19 | 1265200.8665 | 0 | 662009.75 | 283613.4 | 92907 | 224232.8471 | 586679.5394 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 283613.4 | 0 | 8991 | 54545.4 | 8391.6 | 20979 | 0 | 224232.8471 | 0 | 0 | 0 | 41297.75 | 222155.2144 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-20 | 1269854.0906 |  |  | 285744.375 | 94057.875 | 224812.9829 | 587470.7777 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 285744.375 | 0 | 9102.375 | 55221.075 | 8495.55 | 21238.875 | 0 | 224812.9829 | 0 | 0 | 0 | 41297.75 | 222946.4527 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-21 | 1274507.3147 |  |  | 287875.35 | 95208.75 | 225393.1187 | 588262.0159 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 287875.35 | 0 | 9213.75 | 55896.75 | 8599.5 | 21498.75 | 0 | 225393.1187 | 0 | 0 | 0 | 41297.75 | 223737.6909 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-22 | 1279160.5387 |  |  | 290006.325 | 96359.625 | 225973.2546 | 589053.2542 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 290006.325 | 0 | 9325.125 | 56572.425 | 8703.45 | 21758.625 | 0 | 225973.2546 | 0 | 0 | 0 | 41297.75 | 224528.9292 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-23 | 1283813.7628 |  |  | 292137.3 | 97510.5 | 226553.3904 | 589844.4924 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 292137.3 | 0 | 9436.5 | 57248.1 | 8807.4 | 22018.5 | 0 | 226553.3904 | 0 | 0 | 0 | 41297.75 | 225320.1674 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-24 | 1288466.9869 |  |  | 294268.275 | 98661.375 | 227133.5262 | 590635.7307 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 294268.275 | 0 | 9547.875 | 57923.775 | 8911.35 | 22278.375 | 0 | 227133.5262 | 0 | 0 | 0 | 41297.75 | 226111.4057 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-25 | 1293120.211 |  |  | 296399.25 | 99812.25 | 227713.6621 | 591426.969 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 296399.25 | 0 | 9659.25 | 58599.45 | 9015.3 | 22538.25 | 0 | 227713.6621 | 0 | 0 | 0 | 41297.75 | 226902.644 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-26 | 1297773.4351 |  |  | 298530.225 | 100963.125 | 228293.7979 | 592218.2072 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 298530.225 | 0 | 9770.625 | 59275.125 | 9119.25 | 22798.125 | 0 | 228293.7979 | 0 | 0 | 0 | 41297.75 | 227693.8822 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-27 | 1302426.6592 |  |  | 300661.2 | 102114 | 228873.9337 | 593009.4455 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 300661.2 | 0 | 9882 | 59950.8 | 9223.2 | 23058 | 0 | 228873.9337 | 0 | 0 | 0 | 41297.75 | 228485.1205 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-28 | 1307079.8833 |  |  | 302792.175 | 103264.875 | 229454.0696 | 593800.6837 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 302792.175 | 0 | 9993.375 | 60626.475 | 9327.15 | 23317.875 | 0 | 229454.0696 | 0 | 0 | 0 | 41297.75 | 229276.3587 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-29 | 1311733.1074 |  |  | 304923.15 | 104415.75 | 230034.2054 | 594591.922 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 304923.15 | 0 | 10104.75 | 61302.15 | 9431.1 | 23577.75 | 0 | 230034.2054 | 0 | 0 | 0 | 41297.75 | 230067.597 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-30 | 1316386.3315 |  |  | 307054.125 | 105566.625 | 230614.3412 | 595383.1602 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 307054.125 | 0 | 10216.125 | 61977.825 | 9535.05 | 23837.625 | 0 | 230614.3412 | 0 | 0 | 0 | 41297.75 | 230858.8352 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-10-31 | 1321039.5556 |  |  | 309185.1 | 106717.5 | 231194.4771 | 596174.3985 | 77768.08 | 0 | 8008 | 1300 | 0 | 0 | 38369.76 | 13260 | 0 | 0 | 0 | 0 | 0 | 6430.32 | 4160 | 6240 | 0 | 0 | 305026.575 | 309185.1 | 0 | 10327.5 | 62653.5 | 9639 | 24097.5 | 0 | 231194.4771 | 0 | 0 | 0 | 41297.75 | 231650.0735 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-03 | 1324281.088 |  |  | 310943.4557 | 107548.7247 | 231194.4771 | 596437.5102 | 78156.9204 | 0 | 8048.04 | 1306.5 | 0 | 0 | 38561.6088 | 13326.3 | 0 | 0 | 0 | 0 | 0 | 6462.4716 | 4180.8 | 6271.2 | 0 | 0 | 305026.575 | 310943.4557 | 0 | 10407.9411 | 63141.5093 | 9714.0784 | 24285.1959 | 0 | 231194.4771 | 89.2125 | 0 | 0 | 41297.75 | 231823.9727 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-04 | 1327522.6205 |  |  | 312701.8114 | 108379.9494 | 231194.4771 | 596700.6218 | 78545.7608 | 0 | 8088.08 | 1313 | 0 | 0 | 38753.4576 | 13392.6 | 0 | 0 | 0 | 0 | 0 | 6494.6232 | 4201.6 | 6302.4 | 0 | 0 | 305026.575 | 312701.8114 | 0 | 10488.3822 | 63629.5187 | 9789.1567 | 24472.8918 | 0 | 231194.4771 | 178.425 | 0 | 0 | 41297.75 | 231997.8718 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-05 | 1330764.153 |  |  | 314460.1671 | 109211.1741 | 231194.4771 | 596963.7335 | 78934.6012 | 0 | 8128.12 | 1319.5 | 0 | 0 | 38945.3064 | 13458.9 | 0 | 0 | 0 | 0 | 0 | 6526.7748 | 4222.4 | 6333.6 | 0 | 0 | 305026.575 | 314460.1671 | 0 | 10568.8233 | 64117.528 | 9864.2351 | 24660.5877 | 0 | 231194.4771 | 267.6375 | 0 | 0 | 41297.75 | 232171.771 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-06 | 1334005.6854 |  |  | 316218.5228 | 110042.3988 | 231194.4771 | 597226.8452 | 79323.4416 | 0 | 8168.16 | 1326 | 0 | 0 | 39137.1552 | 13525.2 | 0 | 0 | 0 | 0 | 0 | 6558.9264 | 4243.2 | 6364.8 | 0 | 0 | 305026.575 | 316218.5228 | 0 | 10649.2644 | 64605.5374 | 9939.3134 | 24848.2836 | 0 | 231194.4771 | 356.85 | 0 | 0 | 41297.75 | 232345.6702 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-07 | 1337247.2179 |  |  | 317976.8785 | 110873.6235 | 231194.4771 | 597489.9568 | 79712.282 | 0 | 8208.2 | 1332.5 | 0 | 0 | 39329.004 | 13591.5 | 0 | 0 | 0 | 0 | 0 | 6591.078 | 4264 | 6396 | 0 | 0 | 305026.575 | 317976.8785 | 0 | 10729.7055 | 65093.5467 | 10014.3918 | 25035.9795 | 0 | 231194.4771 | 446.0625 | 0 | 0 | 41297.75 | 232519.5693 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-08 | 1340488.7504 |  |  | 319735.2342 | 111704.8482 | 231194.4771 | 597753.0685 | 80101.1224 | 0 | 8248.24 | 1339 | 0 | 0 | 39520.8528 | 13657.8 | 0 | 0 | 0 | 0 | 0 | 6623.2296 | 4284.8 | 6427.2 | 0 | 0 | 305026.575 | 319735.2342 | 0 | 10810.1466 | 65581.556 | 10089.4702 | 25223.6754 | 0 | 231194.4771 | 535.275 | 0 | 0 | 41297.75 | 232693.4685 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-09 | 1343730.2828 |  |  | 321493.5899 | 112536.0729 | 231194.4771 | 598016.1802 | 80489.9628 | 0 | 8288.28 | 1345.5 | 0 | 0 | 39712.7016 | 13724.1 | 0 | 0 | 0 | 0 | 0 | 6655.3812 | 4305.6 | 6458.4 | 0 | 0 | 305026.575 | 321493.5899 | 0 | 10890.5877 | 66069.5654 | 10164.5485 | 25411.3713 | 0 | 231194.4771 | 624.4875 | 0 | 0 | 41297.75 | 232867.3677 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-10 | 1346971.8153 |  |  | 323251.9456 | 113367.2976 | 231194.4771 | 598279.2918 | 80878.8032 | 0 | 8328.32 | 1352 | 0 | 0 | 39904.5504 | 13790.4 | 0 | 0 | 0 | 0 | 0 | 6687.5328 | 4326.4 | 6489.6 | 0 | 0 | 305026.575 | 323251.9456 | 0 | 10971.0288 | 66557.5747 | 10239.6269 | 25599.0672 | 0 | 231194.4771 | 713.7 | 0 | 0 | 41297.75 | 233041.2668 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-11 | 1350213.3477 |  |  | 325010.3013 | 114198.5223 | 231194.4771 | 598542.4035 | 81267.6436 | 0 | 8368.36 | 1358.5 | 0 | 0 | 40096.3992 | 13856.7 | 0 | 0 | 0 | 0 | 0 | 6719.6844 | 4347.2 | 6520.8 | 0 | 0 | 305026.575 | 325010.3013 | 0 | 11051.4699 | 67045.5841 | 10314.7052 | 25786.7631 | 0 | 231194.4771 | 802.9125 | 0 | 0 | 41297.75 | 233215.166 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-12 | 1353454.8802 |  |  | 326768.6569 | 115029.747 | 231194.4771 | 598805.5152 | 81656.484 | 0 | 8408.4 | 1365 | 0 | 0 | 40288.248 | 13923 | 0 | 0 | 0 | 0 | 0 | 6751.836 | 4368 | 6552 | 0 | 0 | 305026.575 | 326768.6569 | 0 | 11131.911 | 67533.5934 | 10389.7836 | 25974.459 | 0 | 231194.4771 | 892.125 | 0 | 0 | 41297.75 | 233389.0652 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-13 | 1356696.4127 |  |  | 328527.0126 | 115860.9717 | 231194.4771 | 599068.6268 | 82045.3244 | 0 | 8448.44 | 1371.5 | 0 | 0 | 40480.0968 | 13989.3 | 0 | 0 | 0 | 0 | 0 | 6783.9876 | 4388.8 | 6583.2 | 0 | 0 | 305026.575 | 328527.0126 | 0 | 11212.3521 | 68021.6027 | 10464.862 | 26162.1549 | 0 | 231194.4771 | 981.3375 | 0 | 0 | 41297.75 | 233562.9643 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-14 | 1359937.9451 |  |  | 330285.3683 | 116692.1964 | 231194.4771 | 599331.7385 | 82434.1648 | 0 | 8488.48 | 1378 | 0 | 0 | 40671.9456 | 14055.6 | 0 | 0 | 0 | 0 | 0 | 6816.1392 | 4409.6 | 6614.4 | 0 | 0 | 305026.575 | 330285.3683 | 0 | 11292.7932 | 68509.6121 | 10539.9403 | 26349.8508 | 0 | 231194.4771 | 1070.55 | 0 | 0 | 41297.75 | 233736.8635 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-15 | 1363179.4776 |  |  | 332043.724 | 117523.4211 | 231194.4771 | 599594.8502 | 82823.0052 | 0 | 8528.52 | 1384.5 | 0 | 0 | 40863.7944 | 14121.9 | 0 | 0 | 0 | 0 | 0 | 6848.2908 | 4430.4 | 6645.6 | 0 | 0 | 305026.575 | 332043.724 | 0 | 11373.2343 | 68997.6214 | 10615.0187 | 26537.5467 | 0 | 231194.4771 | 1159.7625 | 0 | 0 | 41297.75 | 233910.7627 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-16 | 1366421.01 |  |  | 333802.0797 | 118354.6458 | 231194.4771 | 599857.9618 | 83211.8456 | 0 | 8568.56 | 1391 | 0 | 0 | 41055.6432 | 14188.2 | 0 | 0 | 0 | 0 | 0 | 6880.4424 | 4451.2 | 6676.8 | 0 | 0 | 305026.575 | 333802.0797 | 0 | 11453.6754 | 69485.6308 | 10690.097 | 26725.2426 | 0 | 231194.4771 | 1248.975 | 0 | 0 | 41297.75 | 234084.6618 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-17 | 1369662.5425 |  |  | 335560.4354 | 119185.8705 | 231194.4771 | 600121.0735 | 83600.686 | 0 | 8608.6 | 1397.5 | 0 | 0 | 41247.492 | 14254.5 | 0 | 0 | 0 | 0 | 0 | 6912.594 | 4472 | 6708 | 0 | 0 | 305026.575 | 335560.4354 | 0 | 11534.1165 | 69973.6401 | 10765.1754 | 26912.9385 | 0 | 231194.4771 | 1338.1875 | 0 | 0 | 41297.75 | 234258.561 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-18 | 1372904.075 |  |  | 337318.7911 | 120017.0952 | 231194.4771 | 600384.1852 | 83989.5264 | 0 | 8648.64 | 1404 | 0 | 0 | 41439.3408 | 14320.8 | 0 | 0 | 0 | 0 | 0 | 6944.7456 | 4492.8 | 6739.2 | 0 | 0 | 305026.575 | 337318.7911 | 0 | 11614.5576 | 70461.6494 | 10840.2538 | 27100.6344 | 0 | 231194.4771 | 1427.4 | 0 | 0 | 41297.75 | 234432.4602 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-19 | 1376145.6074 |  |  | 339077.1468 | 120848.3199 | 231194.4771 | 600647.2968 | 84378.3668 | 0 | 8688.68 | 1410.5 | 0 | 0 | 41631.1896 | 14387.1 | 0 | 0 | 0 | 0 | 0 | 6976.8972 | 4513.6 | 6770.4 | 0 | 0 | 305026.575 | 339077.1468 | 0 | 11694.9987 | 70949.6588 | 10915.3321 | 27288.3303 | 0 | 231194.4771 | 1516.6125 | 0 | 0 | 41297.75 | 234606.3593 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-20 | 1379387.1399 |  |  | 340835.5025 | 121679.5446 | 231194.4771 | 600910.4085 | 84767.2072 | 0 | 8728.72 | 1417 | 0 | 0 | 41823.0384 | 14453.4 | 0 | 0 | 0 | 0 | 0 | 7009.0488 | 4534.4 | 6801.6 | 0 | 0 | 305026.575 | 340835.5025 | 0 | 11775.4398 | 71437.6681 | 10990.4105 | 27476.0262 | 0 | 231194.4771 | 1605.825 | 0 | 0 | 41297.75 | 234780.2585 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-21 | 1382628.6724 |  |  | 342593.8582 | 122510.7693 | 231194.4771 | 601173.5202 | 85156.0476 | 0 | 8768.76 | 1423.5 | 0 | 0 | 42014.8872 | 14519.7 | 0 | 0 | 0 | 0 | 0 | 7041.2004 | 4555.2 | 6832.8 | 0 | 0 | 305026.575 | 342593.8582 | 0 | 11855.8809 | 71925.6775 | 11065.4888 | 27663.7221 | 0 | 231194.4771 | 1695.0375 | 0 | 0 | 41297.75 | 234954.1577 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-22 | 1385870.2048 |  |  | 344352.2139 | 123341.994 | 231194.4771 | 601436.6318 | 85544.888 | 0 | 8808.8 | 1430 | 0 | 0 | 42206.736 | 14586 | 0 | 0 | 0 | 0 | 0 | 7073.352 | 4576 | 6864 | 0 | 0 | 305026.575 | 344352.2139 | 0 | 11936.322 | 72413.6868 | 11140.5672 | 27851.418 | 0 | 231194.4771 | 1784.25 | 0 | 0 | 41297.75 | 235128.0568 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-23 | 1389111.7373 |  |  | 346110.5696 | 124173.2187 | 231194.4771 | 601699.7435 | 85933.7284 | 0 | 8848.84 | 1436.5 | 0 | 0 | 42398.5848 | 14652.3 | 0 | 0 | 0 | 0 | 0 | 7105.5036 | 4596.8 | 6895.2 | 0 | 0 | 305026.575 | 346110.5696 | 0 | 12016.7631 | 72901.6961 | 11215.6456 | 28039.1139 | 0 | 231194.4771 | 1873.4625 | 0 | 0 | 41297.75 | 235301.956 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-24 | 1392353.2697 |  |  | 347868.9253 | 125004.4434 | 231194.4771 | 601962.8552 | 86322.5688 | 0 | 8888.88 | 1443 | 0 | 0 | 42590.4336 | 14718.6 | 0 | 0 | 0 | 0 | 0 | 7137.6552 | 4617.6 | 6926.4 | 0 | 0 | 305026.575 | 347868.9253 | 0 | 12097.2042 | 73389.7055 | 11290.7239 | 28226.8098 | 0 | 231194.4771 | 1962.675 | 0 | 0 | 41297.75 | 235475.8552 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-25 | 1395594.8022 |  |  | 349627.281 | 125835.6681 | 231194.4771 | 602225.9668 | 86711.4092 | 0 | 8928.92 | 1449.5 | 0 | 0 | 42782.2824 | 14784.9 | 0 | 0 | 0 | 0 | 0 | 7169.8068 | 4638.4 | 6957.6 | 0 | 0 | 305026.575 | 349627.281 | 0 | 12177.6453 | 73877.7148 | 11365.8023 | 28414.5057 | 0 | 231194.4771 | 2051.8875 | 0 | 0 | 41297.75 | 235649.7543 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-26 | 1398836.3347 |  |  | 351385.6367 | 126666.8928 | 231194.4771 | 602489.0785 | 87100.2496 | 0 | 8968.96 | 1456 | 0 | 0 | 42974.1312 | 14851.2 | 0 | 0 | 0 | 0 | 0 | 7201.9584 | 4659.2 | 6988.8 | 0 | 0 | 305026.575 | 351385.6367 | 0 | 12258.0864 | 74365.7242 | 11440.8806 | 28602.2016 | 0 | 231194.4771 | 2141.1 | 0 | 0 | 41297.75 | 235823.6535 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-27 | 1402077.8671 |  |  | 353143.9924 | 127498.1175 | 231194.4771 | 602752.1902 | 87489.09 | 0 | 9009 | 1462.5 | 0 | 0 | 43165.98 | 14917.5 | 0 | 0 | 0 | 0 | 0 | 7234.11 | 4680 | 7020 | 0 | 0 | 305026.575 | 353143.9924 | 0 | 12338.5275 | 74853.7335 | 11515.959 | 28789.8975 | 0 | 231194.4771 | 2230.3125 | 0 | 0 | 41297.75 | 235997.5527 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-28 | 1405319.3996 |  |  | 354902.3481 | 128329.3422 | 231194.4771 | 603015.3018 | 87877.9304 | 0 | 9049.04 | 1469 | 0 | 0 | 43357.8288 | 14983.8 | 0 | 0 | 0 | 0 | 0 | 7266.2616 | 4700.8 | 7051.2 | 0 | 0 | 305026.575 | 354902.3481 | 0 | 12418.9686 | 75341.7428 | 11591.0374 | 28977.5934 | 0 | 231194.4771 | 2319.525 | 0 | 0 | 41297.75 | 236171.4518 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-29 | 1408560.932 |  |  | 356660.7038 | 129160.5669 | 231194.4771 | 603278.4135 | 88266.7708 | 0 | 9089.08 | 1475.5 | 0 | 0 | 43549.6776 | 15050.1 | 0 | 0 | 0 | 0 | 0 | 7298.4132 | 4721.6 | 7082.4 | 0 | 0 | 305026.575 | 356660.7038 | 0 | 12499.4097 | 75829.7522 | 11666.1157 | 29165.2893 | 0 | 231194.4771 | 2408.7375 | 0 | 0 | 41297.75 | 236345.351 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-11-30 | 1411802.4645 |  |  | 358419.0595 | 129991.7916 | 231194.4771 | 603541.5252 | 88655.6112 | 0 | 9129.12 | 1482 | 0 | 0 | 43741.5264 | 15116.4 | 0 | 0 | 0 | 0 | 0 | 7330.5648 | 4742.4 | 7113.6 | 0 | 0 | 305026.575 | 358419.0595 | 0 | 12579.8508 | 76317.7615 | 11741.1941 | 29352.9852 | 0 | 231194.4771 | 2497.95 | 0 | 0 | 41297.75 | 236519.2502 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-01 | 1415043.997 |  |  | 360177.4152 | 130823.0163 | 231194.4771 | 603804.6368 | 89044.4516 | 0 | 9169.16 | 1488.5 | 0 | 0 | 43933.3752 | 15182.7 | 0 | 0 | 0 | 0 | 0 | 7362.7164 | 4763.2 | 7144.8 | 0 | 0 | 305026.575 | 360177.4152 | 0 | 12660.2919 | 76805.7709 | 11816.2724 | 29540.6811 | 0 | 231194.4771 | 2587.1625 | 0 | 0 | 41297.75 | 236693.1493 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-02 | 1418285.5294 |  |  | 361935.7708 | 131654.241 | 231194.4771 | 604067.7485 | 89433.292 | 0 | 9209.2 | 1495 | 0 | 0 | 44125.224 | 15249 | 0 | 0 | 0 | 0 | 0 | 7394.868 | 4784 | 7176 | 0 | 0 | 305026.575 | 361935.7708 | 0 | 12740.733 | 77293.7802 | 11891.3508 | 29728.377 | 0 | 231194.4771 | 2676.375 | 0 | 0 | 41297.75 | 236867.0485 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-03 | 1421527.0619 |  |  | 363694.1265 | 132485.4657 | 231194.4771 | 604330.8602 | 89822.1324 | 0 | 9249.24 | 1501.5 | 0 | 0 | 44317.0728 | 15315.3 | 0 | 0 | 0 | 0 | 0 | 7427.0196 | 4804.8 | 7207.2 | 0 | 0 | 305026.575 | 363694.1265 | 0 | 12821.1741 | 77781.7895 | 11966.4292 | 29916.0729 | 0 | 231194.4771 | 2765.5875 | 0 | 0 | 41297.75 | 237040.9477 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-04 | 1424768.5944 |  |  | 365452.4822 | 133316.6904 | 231194.4771 | 604593.9718 | 90210.9728 | 0 | 9289.28 | 1508 | 0 | 0 | 44508.9216 | 15381.6 | 0 | 0 | 0 | 0 | 0 | 7459.1712 | 4825.6 | 7238.4 | 0 | 0 | 305026.575 | 365452.4822 | 0 | 12901.6152 | 78269.7989 | 12041.5075 | 30103.7688 | 0 | 231194.4771 | 2854.8 | 0 | 0 | 41297.75 | 237214.8468 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-05 | 1428010.1268 |  |  | 367210.8379 | 134147.9151 | 231194.4771 | 604857.0835 | 90599.8132 | 0 | 9329.32 | 1514.5 | 0 | 0 | 44700.7704 | 15447.9 | 0 | 0 | 0 | 0 | 0 | 7491.3228 | 4846.4 | 7269.6 | 0 | 0 | 305026.575 | 367210.8379 | 0 | 12982.0563 | 78757.8082 | 12116.5859 | 30291.4647 | 0 | 231194.4771 | 2944.0125 | 0 | 0 | 41297.75 | 237388.746 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-06 | 1431251.6593 |  |  | 368969.1936 | 134979.1398 | 231194.4771 | 605120.1952 | 90988.6536 | 0 | 9369.36 | 1521 | 0 | 0 | 44892.6192 | 15514.2 | 0 | 0 | 0 | 0 | 0 | 7523.4744 | 4867.2 | 7300.8 | 0 | 0 | 305026.575 | 368969.1936 | 0 | 13062.4974 | 79245.8176 | 12191.6642 | 30479.1606 | 0 | 231194.4771 | 3033.225 | 0 | 0 | 41297.75 | 237562.6452 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-07 | 1434493.1917 |  |  | 370727.5493 | 135810.3645 | 231194.4771 | 605383.3068 | 91377.494 | 0 | 9409.4 | 1527.5 | 0 | 0 | 45084.468 | 15580.5 | 0 | 0 | 0 | 0 | 0 | 7555.626 | 4888 | 7332 | 0 | 0 | 305026.575 | 370727.5493 | 0 | 13142.9385 | 79733.8269 | 12266.7426 | 30666.8565 | 0 | 231194.4771 | 3122.4375 | 0 | 0 | 41297.75 | 237736.5443 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-08 | 1437734.7242 |  |  | 372485.905 | 136641.5892 | 231194.4771 | 605646.4185 | 91766.3344 | 0 | 9449.44 | 1534 | 0 | 0 | 45276.3168 | 15646.8 | 0 | 0 | 0 | 0 | 0 | 7587.7776 | 4908.8 | 7363.2 | 0 | 0 | 305026.575 | 372485.905 | 0 | 13223.3796 | 80221.8362 | 12341.821 | 30854.5524 | 0 | 231194.4771 | 3211.65 | 0 | 0 | 41297.75 | 237910.4435 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-09 | 1440976.2567 |  |  | 374244.2607 | 137472.8139 | 231194.4771 | 605909.5302 | 92155.1748 | 0 | 9489.48 | 1540.5 | 0 | 0 | 45468.1656 | 15713.1 | 0 | 0 | 0 | 0 | 0 | 7619.9292 | 4929.6 | 7394.4 | 0 | 0 | 305026.575 | 374244.2607 | 0 | 13303.8207 | 80709.8456 | 12416.8993 | 31042.2483 | 0 | 231194.4771 | 3300.8625 | 0 | 0 | 41297.75 | 238084.3427 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-10 | 1444217.7891 |  |  | 376002.6164 | 138304.0386 | 231194.4771 | 606172.6418 | 92544.0152 | 0 | 9529.52 | 1547 | 0 | 0 | 45660.0144 | 15779.4 | 0 | 0 | 0 | 0 | 0 | 7652.0808 | 4950.4 | 7425.6 | 0 | 0 | 305026.575 | 376002.6164 | 0 | 13384.2618 | 81197.8549 | 12491.9777 | 31229.9442 | 0 | 231194.4771 | 3390.075 | 0 | 0 | 41297.75 | 238258.2418 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-11 | 1447459.3216 |  |  | 377760.9721 | 139135.2633 | 231194.4771 | 606435.7535 | 92932.8556 | 0 | 9569.56 | 1553.5 | 0 | 0 | 45851.8632 | 15845.7 | 0 | 0 | 0 | 0 | 0 | 7684.2324 | 4971.2 | 7456.8 | 0 | 0 | 305026.575 | 377760.9721 | 0 | 13464.7029 | 81685.8643 | 12567.056 | 31417.6401 | 0 | 231194.4771 | 3479.2875 | 0 | 0 | 41297.75 | 238432.141 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-12 | 1450700.854 |  |  | 379519.3278 | 139966.488 | 231194.4771 | 606698.8652 | 93321.696 | 0 | 9609.6 | 1560 | 0 | 0 | 46043.712 | 15912 | 0 | 0 | 0 | 0 | 0 | 7716.384 | 4992 | 7488 | 0 | 0 | 305026.575 | 379519.3278 | 0 | 13545.144 | 82173.8736 | 12642.1344 | 31605.336 | 0 | 231194.4771 | 3568.5 | 0 | 0 | 41297.75 | 238606.0402 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-13 | 1453942.3865 |  |  | 381277.6835 | 140797.7127 | 231194.4771 | 606961.9768 | 93710.5364 | 0 | 9649.64 | 1566.5 | 0 | 0 | 46235.5608 | 15978.3 | 0 | 0 | 0 | 0 | 0 | 7748.5356 | 5012.8 | 7519.2 | 0 | 0 | 305026.575 | 381277.6835 | 0 | 13625.5851 | 82661.8829 | 12717.2128 | 31793.0319 | 0 | 231194.4771 | 3657.7125 | 0 | 0 | 41297.75 | 238779.9393 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-14 | 1457183.919 |  |  | 383036.0392 | 141628.9374 | 231194.4771 | 607225.0885 | 94099.3768 | 0 | 9689.68 | 1573 | 0 | 0 | 46427.4096 | 16044.6 | 0 | 0 | 0 | 0 | 0 | 7780.6872 | 5033.6 | 7550.4 | 0 | 0 | 305026.575 | 383036.0392 | 0 | 13706.0262 | 83149.8923 | 12792.2911 | 31980.7278 | 0 | 231194.4771 | 3746.925 | 0 | 0 | 41297.75 | 238953.8385 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-15 | 1460425.4514 |  |  | 384794.3949 | 142460.1621 | 231194.4771 | 607488.2002 | 94488.2172 | 0 | 9729.72 | 1579.5 | 0 | 0 | 46619.2584 | 16110.9 | 0 | 0 | 0 | 0 | 0 | 7812.8388 | 5054.4 | 7581.6 | 0 | 0 | 305026.575 | 384794.3949 | 0 | 13786.4673 | 83637.9016 | 12867.3695 | 32168.4237 | 0 | 231194.4771 | 3836.1375 | 0 | 0 | 41297.75 | 239127.7377 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-16 | 1463666.9839 |  |  | 386552.7506 | 143291.3868 | 231194.4771 | 607751.3118 | 94877.0576 | 0 | 9769.76 | 1586 | 0 | 0 | 46811.1072 | 16177.2 | 0 | 0 | 0 | 0 | 0 | 7844.9904 | 5075.2 | 7612.8 | 0 | 0 | 305026.575 | 386552.7506 | 0 | 13866.9084 | 84125.911 | 12942.4478 | 32356.1196 | 0 | 231194.4771 | 3925.35 | 0 | 0 | 41297.75 | 239301.6368 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-17 | 1466908.5164 |  |  | 388311.1063 | 144122.6115 | 231194.4771 | 608014.4235 | 95265.898 | 0 | 9809.8 | 1592.5 | 0 | 0 | 47002.956 | 16243.5 | 0 | 0 | 0 | 0 | 0 | 7877.142 | 5096 | 7644 | 0 | 0 | 305026.575 | 388311.1063 | 0 | 13947.3495 | 84613.9203 | 13017.5262 | 32543.8155 | 0 | 231194.4771 | 4014.5625 | 0 | 0 | 41297.75 | 239475.536 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-18 | 1470150.0488 |  |  | 390069.462 | 144953.8362 | 231194.4771 | 608277.5352 | 95654.7384 | 0 | 9849.84 | 1599 | 0 | 0 | 47194.8048 | 16309.8 | 0 | 0 | 0 | 0 | 0 | 7909.2936 | 5116.8 | 7675.2 | 0 | 0 | 305026.575 | 390069.462 | 0 | 14027.7906 | 85101.9296 | 13092.6046 | 32731.5114 | 0 | 231194.4771 | 4103.775 | 0 | 0 | 41297.75 | 239649.4352 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-19 | 1473391.5813 |  |  | 391827.8177 | 145785.0609 | 231194.4771 | 608540.6468 | 96043.5788 | 0 | 9889.88 | 1605.5 | 0 | 0 | 47386.6536 | 16376.1 | 0 | 0 | 0 | 0 | 0 | 7941.4452 | 5137.6 | 7706.4 | 0 | 0 | 305026.575 | 391827.8177 | 0 | 14108.2317 | 85589.939 | 13167.6829 | 32919.2073 | 0 | 231194.4771 | 4192.9875 | 0 | 0 | 41297.75 | 239823.3343 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-20 | 1476633.1137 |  |  | 393586.1734 | 146616.2856 | 231194.4771 | 608803.7585 | 96432.4192 | 0 | 9929.92 | 1612 | 0 | 0 | 47578.5024 | 16442.4 | 0 | 0 | 0 | 0 | 0 | 7973.5968 | 5158.4 | 7737.6 | 0 | 0 | 305026.575 | 393586.1734 | 0 | 14188.6728 | 86077.9483 | 13242.7613 | 33106.9032 | 0 | 231194.4771 | 4282.2 | 0 | 0 | 41297.75 | 239997.2335 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-21 | 1479874.6462 |  |  | 395344.5291 | 147447.5103 | 231194.4771 | 609066.8702 | 96821.2596 | 0 | 9969.96 | 1618.5 | 0 | 0 | 47770.3512 | 16508.7 | 0 | 0 | 0 | 0 | 0 | 8005.7484 | 5179.2 | 7768.8 | 0 | 0 | 305026.575 | 395344.5291 | 0 | 14269.1139 | 86565.9577 | 13317.8396 | 33294.5991 | 0 | 231194.4771 | 4371.4125 | 0 | 0 | 41297.75 | 240171.1327 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-22 | 1483116.1787 |  |  | 397102.8847 | 148278.735 | 231194.4771 | 609329.9818 | 97210.1 | 0 | 10010 | 1625 | 0 | 0 | 47962.2 | 16575 | 0 | 0 | 0 | 0 | 0 | 8037.9 | 5200 | 7800 | 0 | 0 | 305026.575 | 397102.8847 | 0 | 14349.555 | 87053.967 | 13392.918 | 33482.295 | 0 | 231194.4771 | 4460.625 | 0 | 0 | 41297.75 | 240345.0318 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-23 | 1486357.7111 |  |  | 398861.2404 | 149109.9597 | 231194.4771 | 609593.0935 | 97598.9404 | 0 | 10050.04 | 1631.5 | 0 | 0 | 48154.0488 | 16641.3 | 0 | 0 | 0 | 0 | 0 | 8070.0516 | 5220.8 | 7831.2 | 0 | 0 | 305026.575 | 398861.2404 | 0 | 14429.9961 | 87541.9763 | 13467.9964 | 33669.9909 | 0 | 231194.4771 | 4549.8375 | 0 | 0 | 41297.75 | 240518.931 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-24 | 1489599.2436 |  |  | 400619.5961 | 149941.1844 | 231194.4771 | 609856.2052 | 97987.7808 | 0 | 10090.08 | 1638 | 0 | 0 | 48345.8976 | 16707.6 | 0 | 0 | 0 | 0 | 0 | 8102.2032 | 5241.6 | 7862.4 | 0 | 0 | 305026.575 | 400619.5961 | 0 | 14510.4372 | 88029.9857 | 13543.0747 | 33857.6868 | 0 | 231194.4771 | 4639.05 | 0 | 0 | 41297.75 | 240692.8302 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-25 | 1492840.776 |  |  | 402377.9518 | 150772.4091 | 231194.4771 | 610119.3168 | 98376.6212 | 0 | 10130.12 | 1644.5 | 0 | 0 | 48537.7464 | 16773.9 | 0 | 0 | 0 | 0 | 0 | 8134.3548 | 5262.4 | 7893.6 | 0 | 0 | 305026.575 | 402377.9518 | 0 | 14590.8783 | 88517.995 | 13618.1531 | 34045.3827 | 0 | 231194.4771 | 4728.2625 | 0 | 0 | 41297.75 | 240866.7293 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-26 | 1496082.3085 |  |  | 404136.3075 | 151603.6338 | 231194.4771 | 610382.4285 | 98765.4616 | 0 | 10170.16 | 1651 | 0 | 0 | 48729.5952 | 16840.2 | 0 | 0 | 0 | 0 | 0 | 8166.5064 | 5283.2 | 7924.8 | 0 | 0 | 305026.575 | 404136.3075 | 0 | 14671.3194 | 89006.0044 | 13693.2314 | 34233.0786 | 0 | 231194.4771 | 4817.475 | 0 | 0 | 41297.75 | 241040.6285 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-27 | 1499323.841 |  |  | 405894.6632 | 152434.8585 | 231194.4771 | 610645.5402 | 99154.302 | 0 | 10210.2 | 1657.5 | 0 | 0 | 48921.444 | 16906.5 | 0 | 0 | 0 | 0 | 0 | 8198.658 | 5304 | 7956 | 0 | 0 | 305026.575 | 405894.6632 | 0 | 14751.7605 | 89494.0137 | 13768.3098 | 34420.7745 | 0 | 231194.4771 | 4906.6875 | 0 | 0 | 41297.75 | 241214.5277 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-28 | 1502565.3734 |  |  | 407653.0189 | 153266.0832 | 231194.4771 | 610908.6518 | 99543.1424 | 0 | 10250.24 | 1664 | 0 | 0 | 49113.2928 | 16972.8 | 0 | 0 | 0 | 0 | 0 | 8230.8096 | 5324.8 | 7987.2 | 0 | 0 | 305026.575 | 407653.0189 | 0 | 14832.2016 | 89982.023 | 13843.3882 | 34608.4704 | 0 | 231194.4771 | 4995.9 | 0 | 0 | 41297.75 | 241388.4268 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-29 | 1505806.9059 |  |  | 409411.3746 | 154097.3079 | 231194.4771 | 611171.7635 | 99931.9828 | 0 | 10290.28 | 1670.5 | 0 | 0 | 49305.1416 | 17039.1 | 0 | 0 | 0 | 0 | 0 | 8262.9612 | 5345.6 | 8018.4 | 0 | 0 | 305026.575 | 409411.3746 | 0 | 14912.6427 | 90470.0324 | 13918.4665 | 34796.1663 | 0 | 231194.4771 | 5085.1125 | 0 | 0 | 41297.75 | 241562.326 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-30 | 1509048.4384 |  |  | 411169.7303 | 154928.5326 | 231194.4771 | 611434.8752 | 100320.8232 | 0 | 10330.32 | 1677 | 0 | 0 | 49496.9904 | 17105.4 | 0 | 0 | 0 | 0 | 0 | 8295.1128 | 5366.4 | 8049.6 | 0 | 0 | 305026.575 | 411169.7303 | 0 | 14993.0838 | 90958.0417 | 13993.5449 | 34983.8622 | 0 | 231194.4771 | 5174.325 | 0 | 0 | 41297.75 | 241736.2252 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-12-31 | 1512289.9708 |  |  | 412928.086 | 155759.7573 | 231194.4771 | 611697.9868 | 100709.6636 | 0 | 10370.36 | 1683.5 | 0 | 0 | 49688.8392 | 17171.7 | 0 | 0 | 0 | 0 | 0 | 8327.2644 | 5387.2 | 8080.8 | 0 | 0 | 305026.575 | 412928.086 | 0 | 15073.5249 | 91446.0511 | 14068.6232 | 35171.5581 | 0 | 231194.4771 | 5263.5375 | 0 | 0 | 41297.75 | 241910.1243 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-01 | 1515531.5033 |  |  | 414686.4417 | 156590.982 | 231194.4771 | 611961.0985 | 101098.504 | 0 | 10410.4 | 1690 | 0 | 0 | 49880.688 | 17238 | 0 | 0 | 0 | 0 | 0 | 8359.416 | 5408 | 8112 | 0 | 0 | 305026.575 | 414686.4417 | 0 | 15153.966 | 91934.0604 | 14143.7016 | 35359.254 | 0 | 231194.4771 | 5352.75 | 0 | 0 | 41297.75 | 242084.0235 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-02 | 1518773.0357 |  |  | 416444.7974 | 157422.2067 | 231194.4771 | 612224.2102 | 101487.3444 | 0 | 10450.44 | 1696.5 | 0 | 0 | 50072.5368 | 17304.3 | 0 | 0 | 0 | 0 | 0 | 8391.5676 | 5428.8 | 8143.2 | 0 | 0 | 305026.575 | 416444.7974 | 0 | 15234.4071 | 92422.0697 | 14218.78 | 35546.9499 | 0 | 231194.4771 | 5441.9625 | 0 | 0 | 41297.75 | 242257.9227 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-03 | 1522014.5682 |  |  | 418203.1531 | 158253.4314 | 231194.4771 | 612487.3218 | 101876.1848 | 0 | 10490.48 | 1703 | 0 | 0 | 50264.3856 | 17370.6 | 0 | 0 | 0 | 0 | 0 | 8423.7192 | 5449.6 | 8174.4 | 0 | 0 | 305026.575 | 418203.1531 | 0 | 15314.8482 | 92910.0791 | 14293.8583 | 35734.6458 | 0 | 231194.4771 | 5531.175 | 0 | 0 | 41297.75 | 242431.8218 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-04 | 1525256.1007 |  |  | 419961.5088 | 159084.6561 | 231194.4771 | 612750.4335 | 102265.0252 | 0 | 10530.52 | 1709.5 | 0 | 0 | 50456.2344 | 17436.9 | 0 | 0 | 0 | 0 | 0 | 8455.8708 | 5470.4 | 8205.6 | 0 | 0 | 305026.575 | 419961.5088 | 0 | 15395.2893 | 93398.0884 | 14368.9367 | 35922.3417 | 0 | 231194.4771 | 5620.3875 | 0 | 0 | 41297.75 | 242605.721 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-05 | 1528497.6331 |  |  | 421719.8645 | 159915.8808 | 231194.4771 | 613013.5452 | 102653.8656 | 0 | 10570.56 | 1716 | 0 | 0 | 50648.0832 | 17503.2 | 0 | 0 | 0 | 0 | 0 | 8488.0224 | 5491.2 | 8236.8 | 0 | 0 | 305026.575 | 421719.8645 | 0 | 15475.7304 | 93886.0978 | 14444.015 | 36110.0376 | 0 | 231194.4771 | 5709.6 | 0 | 0 | 41297.75 | 242779.6202 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-06 | 1531739.1656 |  |  | 423478.2202 | 160747.1055 | 231194.4771 | 613276.6568 | 103042.706 | 0 | 10610.6 | 1722.5 | 0 | 0 | 50839.932 | 17569.5 | 0 | 0 | 0 | 0 | 0 | 8520.174 | 5512 | 8268 | 0 | 0 | 305026.575 | 423478.2202 | 0 | 15556.1715 | 94374.1071 | 14519.0934 | 36297.7335 | 0 | 231194.4771 | 5798.8125 | 0 | 0 | 41297.75 | 242953.5193 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-07 | 1534980.6981 |  |  | 425236.5759 | 161578.3302 | 231194.4771 | 613539.7685 | 103431.5464 | 0 | 10650.64 | 1729 | 0 | 0 | 51031.7808 | 17635.8 | 0 | 0 | 0 | 0 | 0 | 8552.3256 | 5532.8 | 8299.2 | 0 | 0 | 305026.575 | 425236.5759 | 0 | 15636.6126 | 94862.1164 | 14594.1718 | 36485.4294 | 0 | 231194.4771 | 5888.025 | 0 | 0 | 41297.75 | 243127.4185 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-08 | 1538222.2305 |  |  | 426994.9316 | 162409.5549 | 231194.4771 | 613802.8802 | 103820.3868 | 0 | 10690.68 | 1735.5 | 0 | 0 | 51223.6296 | 17702.1 | 0 | 0 | 0 | 0 | 0 | 8584.4772 | 5553.6 | 8330.4 | 0 | 0 | 305026.575 | 426994.9316 | 0 | 15717.0537 | 95350.1258 | 14669.2501 | 36673.1253 | 0 | 231194.4771 | 5977.2375 | 0 | 0 | 41297.75 | 243301.3177 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-09 | 1541463.763 |  |  | 428753.2873 | 163240.7796 | 231194.4771 | 614065.9918 | 104209.2272 | 0 | 10730.72 | 1742 | 0 | 0 | 51415.4784 | 17768.4 | 0 | 0 | 0 | 0 | 0 | 8616.6288 | 5574.4 | 8361.6 | 0 | 0 | 305026.575 | 428753.2873 | 0 | 15797.4948 | 95838.1351 | 14744.3285 | 36860.8212 | 0 | 231194.4771 | 6066.45 | 0 | 0 | 41297.75 | 243475.2168 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-10 | 1544705.2954 |  |  | 430511.643 | 164072.0043 | 231194.4771 | 614329.1035 | 104598.0676 | 0 | 10770.76 | 1748.5 | 0 | 0 | 51607.3272 | 17834.7 | 0 | 0 | 0 | 0 | 0 | 8648.7804 | 5595.2 | 8392.8 | 0 | 0 | 305026.575 | 430511.643 | 0 | 15877.9359 | 96326.1445 | 14819.4068 | 37048.5171 | 0 | 231194.4771 | 6155.6625 | 0 | 0 | 41297.75 | 243649.116 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-11 | 1547946.8279 |  |  | 432269.9986 | 164903.229 | 231194.4771 | 614592.2152 | 104986.908 | 0 | 10810.8 | 1755 | 0 | 0 | 51799.176 | 17901 | 0 | 0 | 0 | 0 | 0 | 8680.932 | 5616 | 8424 | 0 | 0 | 305026.575 | 432269.9986 | 0 | 15958.377 | 96814.1538 | 14894.4852 | 37236.213 | 0 | 231194.4771 | 6244.875 | 0 | 0 | 41297.75 | 243823.0152 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-12 | 1551188.3604 |  |  | 434028.3543 | 165734.4537 | 231194.4771 | 614855.3268 | 105375.7484 | 0 | 10850.84 | 1761.5 | 0 | 0 | 51991.0248 | 17967.3 | 0 | 0 | 0 | 0 | 0 | 8713.0836 | 5636.8 | 8455.2 | 0 | 0 | 305026.575 | 434028.3543 | 0 | 16038.8181 | 97302.1631 | 14969.5636 | 37423.9089 | 0 | 231194.4771 | 6334.0875 | 0 | 0 | 41297.75 | 243996.9143 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-13 | 1554429.8928 |  |  | 435786.71 | 166565.6784 | 231194.4771 | 615118.4385 | 105764.5888 | 0 | 10890.88 | 1768 | 0 | 0 | 52182.8736 | 18033.6 | 0 | 0 | 0 | 0 | 0 | 8745.2352 | 5657.6 | 8486.4 | 0 | 0 | 305026.575 | 435786.71 | 0 | 16119.2592 | 97790.1725 | 15044.6419 | 37611.6048 | 0 | 231194.4771 | 6423.3 | 0 | 0 | 41297.75 | 244170.8135 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-14 | 1557671.4253 |  |  | 437545.0657 | 167396.9031 | 231194.4771 | 615381.5502 | 106153.4292 | 0 | 10930.92 | 1774.5 | 0 | 0 | 52374.7224 | 18099.9 | 0 | 0 | 0 | 0 | 0 | 8777.3868 | 5678.4 | 8517.6 | 0 | 0 | 305026.575 | 437545.0657 | 0 | 16199.7003 | 98278.1818 | 15119.7203 | 37799.3007 | 0 | 231194.4771 | 6512.5125 | 0 | 0 | 41297.75 | 244344.7127 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-15 | 1560912.9577 |  |  | 439303.4214 | 168228.1278 | 231194.4771 | 615644.6618 | 106542.2696 | 0 | 10970.96 | 1781 | 0 | 0 | 52566.5712 | 18166.2 | 0 | 0 | 0 | 0 | 0 | 8809.5384 | 5699.2 | 8548.8 | 0 | 0 | 305026.575 | 439303.4214 | 0 | 16280.1414 | 98766.1912 | 15194.7986 | 37986.9966 | 0 | 231194.4771 | 6601.725 | 0 | 0 | 41297.75 | 244518.6118 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-16 | 1564154.4902 |  |  | 441061.7771 | 169059.3525 | 231194.4771 | 615907.7735 | 106931.11 | 0 | 11011 | 1787.5 | 0 | 0 | 52758.42 | 18232.5 | 0 | 0 | 0 | 0 | 0 | 8841.69 | 5720 | 8580 | 0 | 0 | 305026.575 | 441061.7771 | 0 | 16360.5825 | 99254.2005 | 15269.877 | 38174.6925 | 0 | 231194.4771 | 6690.9375 | 0 | 0 | 41297.75 | 244692.511 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-17 | 1567396.0227 |  |  | 442820.1328 | 169890.5772 | 231194.4771 | 616170.8852 | 107319.9504 | 0 | 11051.04 | 1794 | 0 | 0 | 52950.2688 | 18298.8 | 0 | 0 | 0 | 0 | 0 | 8873.8416 | 5740.8 | 8611.2 | 0 | 0 | 305026.575 | 442820.1328 | 0 | 16441.0236 | 99742.2098 | 15344.9554 | 38362.3884 | 0 | 231194.4771 | 6780.15 | 0 | 0 | 41297.75 | 244866.4102 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-18 | 1570637.5551 |  |  | 444578.4885 | 170721.8019 | 231194.4771 | 616433.9968 | 107708.7908 | 0 | 11091.08 | 1800.5 | 0 | 0 | 53142.1176 | 18365.1 | 0 | 0 | 0 | 0 | 0 | 8905.9932 | 5761.6 | 8642.4 | 0 | 0 | 305026.575 | 444578.4885 | 0 | 16521.4647 | 100230.2192 | 15420.0337 | 38550.0843 | 0 | 231194.4771 | 6869.3625 | 0 | 0 | 41297.75 | 245040.3093 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-19 | 1573879.0876 |  |  | 446336.8442 | 171553.0266 | 231194.4771 | 616697.1085 | 108097.6312 | 0 | 11131.12 | 1807 | 0 | 0 | 53333.9664 | 18431.4 | 0 | 0 | 0 | 0 | 0 | 8938.1448 | 5782.4 | 8673.6 | 0 | 0 | 305026.575 | 446336.8442 | 0 | 16601.9058 | 100718.2285 | 15495.1121 | 38737.7802 | 0 | 231194.4771 | 6958.575 | 0 | 0 | 41297.75 | 245214.2085 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-20 | 1577120.6201 |  |  | 448095.1999 | 172384.2513 | 231194.4771 | 616960.2202 | 108486.4716 | 0 | 11171.16 | 1813.5 | 0 | 0 | 53525.8152 | 18497.7 | 0 | 0 | 0 | 0 | 0 | 8970.2964 | 5803.2 | 8704.8 | 0 | 0 | 305026.575 | 448095.1999 | 0 | 16682.3469 | 101206.2379 | 15570.1904 | 38925.4761 | 0 | 231194.4771 | 7047.7875 | 0 | 0 | 41297.75 | 245388.1077 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-21 | 1580362.1525 |  |  | 449853.5556 | 173215.476 | 231194.4771 | 617223.3318 | 108875.312 | 0 | 11211.2 | 1820 | 0 | 0 | 53717.664 | 18564 | 0 | 0 | 0 | 0 | 0 | 9002.448 | 5824 | 8736 | 0 | 0 | 305026.575 | 449853.5556 | 0 | 16762.788 | 101694.2472 | 15645.2688 | 39113.172 | 0 | 231194.4771 | 7137 | 0 | 0 | 41297.75 | 245562.0068 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-22 | 1583603.685 |  |  | 451611.9113 | 174046.7007 | 231194.4771 | 617486.4435 | 109264.1524 | 0 | 11251.24 | 1826.5 | 0 | 0 | 53909.5128 | 18630.3 | 0 | 0 | 0 | 0 | 0 | 9034.5996 | 5844.8 | 8767.2 | 0 | 0 | 305026.575 | 451611.9113 | 0 | 16843.2291 | 102182.2565 | 15720.3472 | 39300.8679 | 0 | 231194.4771 | 7226.2125 | 0 | 0 | 41297.75 | 245735.906 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-23 | 1586845.2174 |  |  | 453370.267 | 174877.9254 | 231194.4771 | 617749.5552 | 109652.9928 | 0 | 11291.28 | 1833 | 0 | 0 | 54101.3616 | 18696.6 | 0 | 0 | 0 | 0 | 0 | 9066.7512 | 5865.6 | 8798.4 | 0 | 0 | 305026.575 | 453370.267 | 0 | 16923.6702 | 102670.2659 | 15795.4255 | 39488.5638 | 0 | 231194.4771 | 7315.425 | 0 | 0 | 41297.75 | 245909.8052 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-24 | 1590086.7499 |  |  | 455128.6227 | 175709.1501 | 231194.4771 | 618012.6668 | 110041.8332 | 0 | 11331.32 | 1839.5 | 0 | 0 | 54293.2104 | 18762.9 | 0 | 0 | 0 | 0 | 0 | 9098.9028 | 5886.4 | 8829.6 | 0 | 0 | 305026.575 | 455128.6227 | 0 | 17004.1113 | 103158.2752 | 15870.5039 | 39676.2597 | 0 | 231194.4771 | 7404.6375 | 0 | 0 | 41297.75 | 246083.7043 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-25 | 1593328.2824 |  |  | 456886.9784 | 176540.3748 | 231194.4771 | 618275.7785 | 110430.6736 | 0 | 11371.36 | 1846 | 0 | 0 | 54485.0592 | 18829.2 | 0 | 0 | 0 | 0 | 0 | 9131.0544 | 5907.2 | 8860.8 | 0 | 0 | 305026.575 | 456886.9784 | 0 | 17084.5524 | 103646.2846 | 15945.5822 | 39863.9556 | 0 | 231194.4771 | 7493.85 | 0 | 0 | 41297.75 | 246257.6035 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-26 | 1596569.8148 |  |  | 458645.3341 | 177371.5995 | 231194.4771 | 618538.8902 | 110819.514 | 0 | 11411.4 | 1852.5 | 0 | 0 | 54676.908 | 18895.5 | 0 | 0 | 0 | 0 | 0 | 9163.206 | 5928 | 8892 | 0 | 0 | 305026.575 | 458645.3341 | 0 | 17164.9935 | 104134.2939 | 16020.6606 | 40051.6515 | 0 | 231194.4771 | 7583.0625 | 0 | 0 | 41297.75 | 246431.5027 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-27 | 1599811.3473 |  |  | 460403.6898 | 178202.8242 | 231194.4771 | 618802.0018 | 111208.3544 | 0 | 11451.44 | 1859 | 0 | 0 | 54868.7568 | 18961.8 | 0 | 0 | 0 | 0 | 0 | 9195.3576 | 5948.8 | 8923.2 | 0 | 0 | 305026.575 | 460403.6898 | 0 | 17245.4346 | 104622.3032 | 16095.739 | 40239.3474 | 0 | 231194.4771 | 7672.275 | 0 | 0 | 41297.75 | 246605.4018 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-28 | 1603052.8797 |  |  | 462162.0455 | 179034.0489 | 231194.4771 | 619065.1135 | 111597.1948 | 0 | 11491.48 | 1865.5 | 0 | 0 | 55060.6056 | 19028.1 | 0 | 0 | 0 | 0 | 0 | 9227.5092 | 5969.6 | 8954.4 | 0 | 0 | 305026.575 | 462162.0455 | 0 | 17325.8757 | 105110.3126 | 16170.8173 | 40427.0433 | 0 | 231194.4771 | 7761.4875 | 0 | 0 | 41297.75 | 246779.301 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-29 | 1606294.4122 |  |  | 463920.4012 | 179865.2736 | 231194.4771 | 619328.2252 | 111986.0352 | 0 | 11531.52 | 1872 | 0 | 0 | 55252.4544 | 19094.4 | 0 | 0 | 0 | 0 | 0 | 9259.6608 | 5990.4 | 8985.6 | 0 | 0 | 305026.575 | 463920.4012 | 0 | 17406.3168 | 105598.3219 | 16245.8957 | 40614.7392 | 0 | 231194.4771 | 7850.7 | 0 | 0 | 41297.75 | 246953.2002 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-30 | 1609535.9447 |  |  | 465678.7569 | 180696.4983 | 231194.4771 | 619591.3368 | 112374.8756 | 0 | 11571.56 | 1878.5 | 0 | 0 | 55444.3032 | 19160.7 | 0 | 0 | 0 | 0 | 0 | 9291.8124 | 6011.2 | 9016.8 | 0 | 0 | 305026.575 | 465678.7569 | 0 | 17486.7579 | 106086.3313 | 16320.974 | 40802.4351 | 0 | 231194.4771 | 7939.9125 | 0 | 0 | 41297.75 | 247127.0993 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-01-31 | 1612777.4771 |  |  | 467437.1125 | 181527.723 | 231194.4771 | 619854.4485 | 112763.716 | 0 | 11611.6 | 1885 | 0 | 0 | 55636.152 | 19227 | 0 | 0 | 0 | 0 | 0 | 9323.964 | 6032 | 9048 | 0 | 0 | 305026.575 | 467437.1125 | 0 | 17567.199 | 106574.3406 | 16396.0524 | 40990.131 | 0 | 231194.4771 | 8029.125 | 0 | 0 | 41297.75 | 247300.9985 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-01 | 1616019.0096 |  |  | 469195.4682 | 182358.9477 | 231194.4771 | 620117.5602 | 113152.5564 | 0 | 11651.64 | 1891.5 | 0 | 0 | 55828.0008 | 19293.3 | 0 | 0 | 0 | 0 | 0 | 9356.1156 | 6052.8 | 9079.2 | 0 | 0 | 305026.575 | 469195.4682 | 0 | 17647.6401 | 107062.3499 | 16471.1308 | 41177.8269 | 0 | 231194.4771 | 8118.3375 | 0 | 0 | 41297.75 | 247474.8977 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-02 | 1619260.5421 |  |  | 470953.8239 | 183190.1724 | 231194.4771 | 620380.6718 | 113541.3968 | 0 | 11691.68 | 1898 | 0 | 0 | 56019.8496 | 19359.6 | 0 | 0 | 0 | 0 | 0 | 9388.2672 | 6073.6 | 9110.4 | 0 | 0 | 305026.575 | 470953.8239 | 0 | 17728.0812 | 107550.3593 | 16546.2091 | 41365.5228 | 0 | 231194.4771 | 8207.55 | 0 | 0 | 41297.75 | 247648.7968 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-03 | 1622502.0745 |  |  | 472712.1796 | 184021.3971 | 231194.4771 | 620643.7835 | 113930.2372 | 0 | 11731.72 | 1904.5 | 0 | 0 | 56211.6984 | 19425.9 | 0 | 0 | 0 | 0 | 0 | 9420.4188 | 6094.4 | 9141.6 | 0 | 0 | 305026.575 | 472712.1796 | 0 | 17808.5223 | 108038.3686 | 16621.2875 | 41553.2187 | 0 | 231194.4771 | 8296.7625 | 0 | 0 | 41297.75 | 247822.696 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-04 | 1625743.607 |  |  | 474470.5353 | 184852.6218 | 231194.4771 | 620906.8952 | 114319.0776 | 0 | 11771.76 | 1911 | 0 | 0 | 56403.5472 | 19492.2 | 0 | 0 | 0 | 0 | 0 | 9452.5704 | 6115.2 | 9172.8 | 0 | 0 | 305026.575 | 474470.5353 | 0 | 17888.9634 | 108526.378 | 16696.3658 | 41740.9146 | 0 | 231194.4771 | 8385.975 | 0 | 0 | 41297.75 | 247996.5952 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-05 | 1628985.1394 |  |  | 476228.891 | 185683.8465 | 231194.4771 | 621170.0068 | 114707.918 | 0 | 11811.8 | 1917.5 | 0 | 0 | 56595.396 | 19558.5 | 0 | 0 | 0 | 0 | 0 | 9484.722 | 6136 | 9204 | 0 | 0 | 305026.575 | 476228.891 | 0 | 17969.4045 | 109014.3873 | 16771.4442 | 41928.6105 | 0 | 231194.4771 | 8475.1875 | 0 | 0 | 41297.75 | 248170.4943 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-06 | 1632226.6719 |  |  | 477987.2467 | 186515.0712 | 231194.4771 | 621433.1185 | 115096.7584 | 0 | 11851.84 | 1924 | 0 | 0 | 56787.2448 | 19624.8 | 0 | 0 | 0 | 0 | 0 | 9516.8736 | 6156.8 | 9235.2 | 0 | 0 | 305026.575 | 477987.2467 | 0 | 18049.8456 | 109502.3966 | 16846.5226 | 42116.3064 | 0 | 231194.4771 | 8564.4 | 0 | 0 | 41297.75 | 248344.3935 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-07 | 1635468.2044 |  |  | 479745.6024 | 187346.2959 | 231194.4771 | 621696.2302 | 115485.5988 | 0 | 11891.88 | 1930.5 | 0 | 0 | 56979.0936 | 19691.1 | 0 | 0 | 0 | 0 | 0 | 9549.0252 | 6177.6 | 9266.4 | 0 | 0 | 305026.575 | 479745.6024 | 0 | 18130.2867 | 109990.406 | 16921.6009 | 42304.0023 | 0 | 231194.4771 | 8653.6125 | 0 | 0 | 41297.75 | 248518.2927 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-08 | 1638709.7368 |  |  | 481503.9581 | 188177.5206 | 231194.4771 | 621959.3418 | 115874.4392 | 0 | 11931.92 | 1937 | 0 | 0 | 57170.9424 | 19757.4 | 0 | 0 | 0 | 0 | 0 | 9581.1768 | 6198.4 | 9297.6 | 0 | 0 | 305026.575 | 481503.9581 | 0 | 18210.7278 | 110478.4153 | 16996.6793 | 42491.6982 | 0 | 231194.4771 | 8742.825 | 0 | 0 | 41297.75 | 248692.1918 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-09 | 1641951.2693 |  |  | 483262.3138 | 189008.7453 | 231194.4771 | 622222.4535 | 116263.2796 | 0 | 11971.96 | 1943.5 | 0 | 0 | 57362.7912 | 19823.7 | 0 | 0 | 0 | 0 | 0 | 9613.3284 | 6219.2 | 9328.8 | 0 | 0 | 305026.575 | 483262.3138 | 0 | 18291.1689 | 110966.4247 | 17071.7576 | 42679.3941 | 0 | 231194.4771 | 8832.0375 | 0 | 0 | 41297.75 | 248866.091 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-10 | 1645192.8017 |  |  | 485020.6695 | 189839.97 | 231194.4771 | 622485.5652 | 116652.12 | 0 | 12012 | 1950 | 0 | 0 | 57554.64 | 19890 | 0 | 0 | 0 | 0 | 0 | 9645.48 | 6240 | 9360 | 0 | 0 | 305026.575 | 485020.6695 | 0 | 18371.61 | 111454.434 | 17146.836 | 42867.09 | 0 | 231194.4771 | 8921.25 | 0 | 0 | 41297.75 | 249039.9902 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-11 | 1648434.3342 |  |  | 486779.0252 | 190671.1947 | 231194.4771 | 622748.6768 | 117040.9604 | 0 | 12052.04 | 1956.5 | 0 | 0 | 57746.4888 | 19956.3 | 0 | 0 | 0 | 0 | 0 | 9677.6316 | 6260.8 | 9391.2 | 0 | 0 | 305026.575 | 486779.0252 | 0 | 18452.0511 | 111942.4433 | 17221.9144 | 43054.7859 | 0 | 231194.4771 | 9010.4625 | 0 | 0 | 41297.75 | 249213.8893 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-12 | 1651675.8667 |  |  | 488537.3809 | 191502.4194 | 231194.4771 | 623011.7885 | 117429.8008 | 0 | 12092.08 | 1963 | 0 | 0 | 57938.3376 | 20022.6 | 0 | 0 | 0 | 0 | 0 | 9709.7832 | 6281.6 | 9422.4 | 0 | 0 | 305026.575 | 488537.3809 | 0 | 18532.4922 | 112430.4527 | 17296.9927 | 43242.4818 | 0 | 231194.4771 | 9099.675 | 0 | 0 | 41297.75 | 249387.7885 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-13 | 1654917.3991 |  |  | 490295.7366 | 192333.6441 | 231194.4771 | 623274.9002 | 117818.6412 | 0 | 12132.12 | 1969.5 | 0 | 0 | 58130.1864 | 20088.9 | 0 | 0 | 0 | 0 | 0 | 9741.9348 | 6302.4 | 9453.6 | 0 | 0 | 305026.575 | 490295.7366 | 0 | 18612.9333 | 112918.462 | 17372.0711 | 43430.1777 | 0 | 231194.4771 | 9188.8875 | 0 | 0 | 41297.75 | 249561.6877 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-14 | 1658158.9316 |  |  | 492054.0923 | 193164.8688 | 231194.4771 | 623538.0118 | 118207.4816 | 0 | 12172.16 | 1976 | 0 | 0 | 58322.0352 | 20155.2 | 0 | 0 | 0 | 0 | 0 | 9774.0864 | 6323.2 | 9484.8 | 0 | 0 | 305026.575 | 492054.0923 | 0 | 18693.3744 | 113406.4714 | 17447.1494 | 43617.8736 | 0 | 231194.4771 | 9278.1 | 0 | 0 | 41297.75 | 249735.5868 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-15 | 1661400.4641 |  |  | 493812.448 | 193996.0935 | 231194.4771 | 623801.1235 | 118596.322 | 0 | 12212.2 | 1982.5 | 0 | 0 | 58513.884 | 20221.5 | 0 | 0 | 0 | 0 | 0 | 9806.238 | 6344 | 9516 | 0 | 0 | 305026.575 | 493812.448 | 0 | 18773.8155 | 113894.4807 | 17522.2278 | 43805.5695 | 0 | 231194.4771 | 9367.3125 | 0 | 0 | 41297.75 | 249909.486 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-16 | 1664641.9965 |  |  | 495570.8037 | 194827.3182 | 231194.4771 | 624064.2352 | 118985.1624 | 0 | 12252.24 | 1989 | 0 | 0 | 58705.7328 | 20287.8 | 0 | 0 | 0 | 0 | 0 | 9838.3896 | 6364.8 | 9547.2 | 0 | 0 | 305026.575 | 495570.8037 | 0 | 18854.2566 | 114382.49 | 17597.3062 | 43993.2654 | 0 | 231194.4771 | 9456.525 | 0 | 0 | 41297.75 | 250083.3852 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-17 | 1667883.529 |  |  | 497329.1594 | 195658.5429 | 231194.4771 | 624327.3468 | 119374.0028 | 0 | 12292.28 | 1995.5 | 0 | 0 | 58897.5816 | 20354.1 | 0 | 0 | 0 | 0 | 0 | 9870.5412 | 6385.6 | 9578.4 | 0 | 0 | 305026.575 | 497329.1594 | 0 | 18934.6977 | 114870.4994 | 17672.3845 | 44180.9613 | 0 | 231194.4771 | 9545.7375 | 0 | 0 | 41297.75 | 250257.2843 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-18 | 1671125.0614 |  |  | 499087.5151 | 196489.7676 | 231194.4771 | 624590.4585 | 119762.8432 | 0 | 12332.32 | 2002 | 0 | 0 | 59089.4304 | 20420.4 | 0 | 0 | 0 | 0 | 0 | 9902.6928 | 6406.4 | 9609.6 | 0 | 0 | 305026.575 | 499087.5151 | 0 | 19015.1388 | 115358.5087 | 17747.4629 | 44368.6572 | 0 | 231194.4771 | 9634.95 | 0 | 0 | 41297.75 | 250431.1835 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-19 | 1674366.5939 |  |  | 500845.8708 | 197320.9923 | 231194.4771 | 624853.5702 | 120151.6836 | 0 | 12372.36 | 2008.5 | 0 | 0 | 59281.2792 | 20486.7 | 0 | 0 | 0 | 0 | 0 | 9934.8444 | 6427.2 | 9640.8 | 0 | 0 | 305026.575 | 500845.8708 | 0 | 19095.5799 | 115846.5181 | 17822.5412 | 44556.3531 | 0 | 231194.4771 | 9724.1625 | 0 | 0 | 41297.75 | 250605.0827 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-20 | 1677608.1264 |  |  | 502604.2264 | 198152.217 | 231194.4771 | 625116.6818 | 120540.524 | 0 | 12412.4 | 2015 | 0 | 0 | 59473.128 | 20553 | 0 | 0 | 0 | 0 | 0 | 9966.996 | 6448 | 9672 | 0 | 0 | 305026.575 | 502604.2264 | 0 | 19176.021 | 116334.5274 | 17897.6196 | 44744.049 | 0 | 231194.4771 | 9813.375 | 0 | 0 | 41297.75 | 250778.9818 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-21 | 1680849.6588 |  |  | 504362.5821 | 198983.4417 | 231194.4771 | 625379.7935 | 120929.3644 | 0 | 12452.44 | 2021.5 | 0 | 0 | 59664.9768 | 20619.3 | 0 | 0 | 0 | 0 | 0 | 9999.1476 | 6468.8 | 9703.2 | 0 | 0 | 305026.575 | 504362.5821 | 0 | 19256.4621 | 116822.5367 | 17972.698 | 44931.7449 | 0 | 231194.4771 | 9902.5875 | 0 | 0 | 41297.75 | 250952.881 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-22 | 1684091.1913 |  |  | 506120.9378 | 199814.6664 | 231194.4771 | 625642.9052 | 121318.2048 | 0 | 12492.48 | 2028 | 0 | 0 | 59856.8256 | 20685.6 | 0 | 0 | 0 | 0 | 0 | 10031.2992 | 6489.6 | 9734.4 | 0 | 0 | 305026.575 | 506120.9378 | 0 | 19336.9032 | 117310.5461 | 18047.7763 | 45119.4408 | 0 | 231194.4771 | 9991.8 | 0 | 0 | 41297.75 | 251126.7802 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-23 | 1687332.7237 |  |  | 507879.2935 | 200645.8911 | 231194.4771 | 625906.0168 | 121707.0452 | 0 | 12532.52 | 2034.5 | 0 | 0 | 60048.6744 | 20751.9 | 0 | 0 | 0 | 0 | 0 | 10063.4508 | 6510.4 | 9765.6 | 0 | 0 | 305026.575 | 507879.2935 | 0 | 19417.3443 | 117798.5554 | 18122.8547 | 45307.1367 | 0 | 231194.4771 | 10081.0125 | 0 | 0 | 41297.75 | 251300.6793 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-24 | 1690574.2562 |  |  | 509637.6492 | 201477.1158 | 231194.4771 | 626169.1285 | 122095.8856 | 0 | 12572.56 | 2041 | 0 | 0 | 60240.5232 | 20818.2 | 0 | 0 | 0 | 0 | 0 | 10095.6024 | 6531.2 | 9796.8 | 0 | 0 | 305026.575 | 509637.6492 | 0 | 19497.7854 | 118286.5648 | 18197.933 | 45494.8326 | 0 | 231194.4771 | 10170.225 | 0 | 0 | 41297.75 | 251474.5785 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-25 | 1693815.7887 |  |  | 511396.0049 | 202308.3405 | 231194.4771 | 626432.2402 | 122484.726 | 0 | 12612.6 | 2047.5 | 0 | 0 | 60432.372 | 20884.5 | 0 | 0 | 0 | 0 | 0 | 10127.754 | 6552 | 9828 | 0 | 0 | 305026.575 | 511396.0049 | 0 | 19578.2265 | 118774.5741 | 18273.0114 | 45682.5285 | 0 | 231194.4771 | 10259.4375 | 0 | 0 | 41297.75 | 251648.4777 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-26 | 1697057.3211 |  |  | 513154.3606 | 203139.5652 | 231194.4771 | 626695.3518 | 122873.5664 | 0 | 12652.64 | 2054 | 0 | 0 | 60624.2208 | 20950.8 | 0 | 0 | 0 | 0 | 0 | 10159.9056 | 6572.8 | 9859.2 | 0 | 0 | 305026.575 | 513154.3606 | 0 | 19658.6676 | 119262.5834 | 18348.0898 | 45870.2244 | 0 | 231194.4771 | 10348.65 | 0 | 0 | 41297.75 | 251822.3768 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-27 | 1700298.8536 |  |  | 514912.7163 | 203970.7899 | 231194.4771 | 626958.4635 | 123262.4068 | 0 | 12692.68 | 2060.5 | 0 | 0 | 60816.0696 | 21017.1 | 0 | 0 | 0 | 0 | 0 | 10192.0572 | 6593.6 | 9890.4 | 0 | 0 | 305026.575 | 514912.7163 | 0 | 19739.1087 | 119750.5928 | 18423.1681 | 46057.9203 | 0 | 231194.4771 | 10437.8625 | 0 | 0 | 41297.75 | 251996.276 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-02-28 | 1703540.3861 |  |  | 516671.072 | 204802.0146 | 231194.4771 | 627221.5752 | 123651.2472 | 0 | 12732.72 | 2067 | 0 | 0 | 61007.9184 | 21083.4 | 0 | 0 | 0 | 0 | 0 | 10224.2088 | 6614.4 | 9921.6 | 0 | 0 | 305026.575 | 516671.072 | 0 | 19819.5498 | 120238.6021 | 18498.2465 | 46245.6162 | 0 | 231194.4771 | 10527.075 | 0 | 0 | 41297.75 | 252170.1752 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-01 | 1706781.9185 |  |  | 518429.4277 | 205633.2393 | 231194.4771 | 627484.6868 | 124040.0876 | 0 | 12772.76 | 2073.5 | 0 | 0 | 61199.7672 | 21149.7 | 0 | 0 | 0 | 0 | 0 | 10256.3604 | 6635.2 | 9952.8 | 0 | 0 | 305026.575 | 518429.4277 | 0 | 19899.9909 | 120726.6115 | 18573.3248 | 46433.3121 | 0 | 231194.4771 | 10616.2875 | 0 | 0 | 41297.75 | 252344.0743 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-02 | 1710023.451 |  |  | 520187.7834 | 206464.464 | 231194.4771 | 627747.7985 | 124428.928 | 0 | 12812.8 | 2080 | 0 | 0 | 61391.616 | 21216 | 0 | 0 | 0 | 0 | 0 | 10288.512 | 6656 | 9984 | 0 | 0 | 305026.575 | 520187.7834 | 0 | 19980.432 | 121214.6208 | 18648.4032 | 46621.008 | 0 | 231194.4771 | 10705.5 | 0 | 0 | 41297.75 | 252517.9735 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-03 | 1713264.9834 |  |  | 521946.1391 | 207295.6887 | 231194.4771 | 628010.9102 | 124817.7684 | 0 | 12852.84 | 2086.5 | 0 | 0 | 61583.4648 | 21282.3 | 0 | 0 | 0 | 0 | 0 | 10320.6636 | 6676.8 | 10015.2 | 0 | 0 | 305026.575 | 521946.1391 | 0 | 20060.8731 | 121702.6301 | 18723.4816 | 46808.7039 | 0 | 231194.4771 | 10794.7125 | 0 | 0 | 41297.75 | 252691.8727 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-04 | 1716506.5159 |  |  | 523704.4948 | 208126.9134 | 231194.4771 | 628274.0218 | 125206.6088 | 0 | 12892.88 | 2093 | 0 | 0 | 61775.3136 | 21348.6 | 0 | 0 | 0 | 0 | 0 | 10352.8152 | 6697.6 | 10046.4 | 0 | 0 | 305026.575 | 523704.4948 | 0 | 20141.3142 | 122190.6395 | 18798.5599 | 46996.3998 | 0 | 231194.4771 | 10883.925 | 0 | 0 | 41297.75 | 252865.7718 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-05 | 1719748.0484 |  |  | 525462.8505 | 208958.1381 | 231194.4771 | 628537.1335 | 125595.4492 | 0 | 12932.92 | 2099.5 | 0 | 0 | 61967.1624 | 21414.9 | 0 | 0 | 0 | 0 | 0 | 10384.9668 | 6718.4 | 10077.6 | 0 | 0 | 305026.575 | 525462.8505 | 0 | 20221.7553 | 122678.6488 | 18873.6383 | 47184.0957 | 0 | 231194.4771 | 10973.1375 | 0 | 0 | 41297.75 | 253039.671 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-06 | 1722989.5808 |  |  | 527221.2062 | 209789.3628 | 231194.4771 | 628800.2452 | 125984.2896 | 0 | 12972.96 | 2106 | 0 | 0 | 62159.0112 | 21481.2 | 0 | 0 | 0 | 0 | 0 | 10417.1184 | 6739.2 | 10108.8 | 0 | 0 | 305026.575 | 527221.2062 | 0 | 20302.1964 | 123166.6582 | 18948.7166 | 47371.7916 | 0 | 231194.4771 | 11062.35 | 0 | 0 | 41297.75 | 253213.5702 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-07 | 1726231.1133 |  |  | 528979.5619 | 210620.5875 | 231194.4771 | 629063.3568 | 126373.13 | 0 | 13013 | 2112.5 | 0 | 0 | 62350.86 | 21547.5 | 0 | 0 | 0 | 0 | 0 | 10449.27 | 6760 | 10140 | 0 | 0 | 305026.575 | 528979.5619 | 0 | 20382.6375 | 123654.6675 | 19023.795 | 47559.4875 | 0 | 231194.4771 | 11151.5625 | 0 | 0 | 41297.75 | 253387.4693 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-08 | 1729472.6458 |  |  | 530737.9176 | 211451.8122 | 231194.4771 | 629326.4685 | 126761.9704 | 0 | 13053.04 | 2119 | 0 | 0 | 62542.7088 | 21613.8 | 0 | 0 | 0 | 0 | 0 | 10481.4216 | 6780.8 | 10171.2 | 0 | 0 | 305026.575 | 530737.9176 | 0 | 20463.0786 | 124142.6768 | 19098.8734 | 47747.1834 | 0 | 231194.4771 | 11240.775 | 0 | 0 | 41297.75 | 253561.3685 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-09 | 1732714.1782 |  |  | 532496.2733 | 212283.0369 | 231194.4771 | 629589.5802 | 127150.8108 | 0 | 13093.08 | 2125.5 | 0 | 0 | 62734.5576 | 21680.1 | 0 | 0 | 0 | 0 | 0 | 10513.5732 | 6801.6 | 10202.4 | 0 | 0 | 305026.575 | 532496.2733 | 0 | 20543.5197 | 124630.6862 | 19173.9517 | 47934.8793 | 0 | 231194.4771 | 11329.9875 | 0 | 0 | 41297.75 | 253735.2677 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-10 | 1735955.7107 |  |  | 534254.629 | 213114.2616 | 231194.4771 | 629852.6918 | 127539.6512 | 0 | 13133.12 | 2132 | 0 | 0 | 62926.4064 | 21746.4 | 0 | 0 | 0 | 0 | 0 | 10545.7248 | 6822.4 | 10233.6 | 0 | 0 | 305026.575 | 534254.629 | 0 | 20623.9608 | 125118.6955 | 19249.0301 | 48122.5752 | 0 | 231194.4771 | 11419.2 | 0 | 0 | 41297.75 | 253909.1668 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-11 | 1739197.2431 |  |  | 536012.9847 | 213945.4863 | 231194.4771 | 630115.8035 | 127928.4916 | 0 | 13173.16 | 2138.5 | 0 | 0 | 63118.2552 | 21812.7 | 0 | 0 | 0 | 0 | 0 | 10577.8764 | 6843.2 | 10264.8 | 0 | 0 | 305026.575 | 536012.9847 | 0 | 20704.4019 | 125606.7049 | 19324.1084 | 48310.2711 | 0 | 231194.4771 | 11508.4125 | 0 | 0 | 41297.75 | 254083.066 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-12 | 1742438.7756 |  |  | 537771.3403 | 214776.711 | 231194.4771 | 630378.9152 | 128317.332 | 0 | 13213.2 | 2145 | 0 | 0 | 63310.104 | 21879 | 0 | 0 | 0 | 0 | 0 | 10610.028 | 6864 | 10296 | 0 | 0 | 305026.575 | 537771.3403 | 0 | 20784.843 | 126094.7142 | 19399.1868 | 48497.967 | 0 | 231194.4771 | 11597.625 | 0 | 0 | 41297.75 | 254256.9652 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-13 | 1745680.3081 |  |  | 539529.696 | 215607.9357 | 231194.4771 | 630642.0268 | 128706.1724 | 0 | 13253.24 | 2151.5 | 0 | 0 | 63501.9528 | 21945.3 | 0 | 0 | 0 | 0 | 0 | 10642.1796 | 6884.8 | 10327.2 | 0 | 0 | 305026.575 | 539529.696 | 0 | 20865.2841 | 126582.7235 | 19474.2652 | 48685.6629 | 0 | 231194.4771 | 11686.8375 | 0 | 0 | 41297.75 | 254430.8643 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-14 | 1748921.8405 |  |  | 541288.0517 | 216439.1604 | 231194.4771 | 630905.1385 | 129095.0128 | 0 | 13293.28 | 2158 | 0 | 0 | 63693.8016 | 22011.6 | 0 | 0 | 0 | 0 | 0 | 10674.3312 | 6905.6 | 10358.4 | 0 | 0 | 305026.575 | 541288.0517 | 0 | 20945.7252 | 127070.7329 | 19549.3435 | 48873.3588 | 0 | 231194.4771 | 11776.05 | 0 | 0 | 41297.75 | 254604.7635 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-15 | 1752163.373 |  |  | 543046.4074 | 217270.3851 | 231194.4771 | 631168.2502 | 129483.8532 | 0 | 13333.32 | 2164.5 | 0 | 0 | 63885.6504 | 22077.9 | 0 | 0 | 0 | 0 | 0 | 10706.4828 | 6926.4 | 10389.6 | 0 | 0 | 305026.575 | 543046.4074 | 0 | 21026.1663 | 127558.7422 | 19624.4219 | 49061.0547 | 0 | 231194.4771 | 11865.2625 | 0 | 0 | 41297.75 | 254778.6627 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-16 | 1755404.9054 |  |  | 544804.7631 | 218101.6098 | 231194.4771 | 631431.3618 | 129872.6936 | 0 | 13373.36 | 2171 | 0 | 0 | 64077.4992 | 22144.2 | 0 | 0 | 0 | 0 | 0 | 10738.6344 | 6947.2 | 10420.8 | 0 | 0 | 305026.575 | 544804.7631 | 0 | 21106.6074 | 128046.7516 | 19699.5002 | 49248.7506 | 0 | 231194.4771 | 11954.475 | 0 | 0 | 41297.75 | 254952.5618 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-17 | 1758646.4379 |  |  | 546563.1188 | 218932.8345 | 231194.4771 | 631694.4735 | 130261.534 | 0 | 13413.4 | 2177.5 | 0 | 0 | 64269.348 | 22210.5 | 0 | 0 | 0 | 0 | 0 | 10770.786 | 6968 | 10452 | 0 | 0 | 305026.575 | 546563.1188 | 0 | 21187.0485 | 128534.7609 | 19774.5786 | 49436.4465 | 0 | 231194.4771 | 12043.6875 | 0 | 0 | 41297.75 | 255126.461 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-18 | 1761887.9704 |  |  | 548321.4745 | 219764.0592 | 231194.4771 | 631957.5852 | 130650.3744 | 0 | 13453.44 | 2184 | 0 | 0 | 64461.1968 | 22276.8 | 0 | 0 | 0 | 0 | 0 | 10802.9376 | 6988.8 | 10483.2 | 0 | 0 | 305026.575 | 548321.4745 | 0 | 21267.4896 | 129022.7702 | 19849.657 | 49624.1424 | 0 | 231194.4771 | 12132.9 | 0 | 0 | 41297.75 | 255300.3602 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-19 | 1765129.5028 |  |  | 550079.8302 | 220595.2839 | 231194.4771 | 632220.6968 | 131039.2148 | 0 | 13493.48 | 2190.5 | 0 | 0 | 64653.0456 | 22343.1 | 0 | 0 | 0 | 0 | 0 | 10835.0892 | 7009.6 | 10514.4 | 0 | 0 | 305026.575 | 550079.8302 | 0 | 21347.9307 | 129510.7796 | 19924.7353 | 49811.8383 | 0 | 231194.4771 | 12222.1125 | 0 | 0 | 41297.75 | 255474.2593 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-20 | 1768371.0353 |  |  | 551838.1859 | 221426.5086 | 231194.4771 | 632483.8085 | 131428.0552 | 0 | 13533.52 | 2197 | 0 | 0 | 64844.8944 | 22409.4 | 0 | 0 | 0 | 0 | 0 | 10867.2408 | 7030.4 | 10545.6 | 0 | 0 | 305026.575 | 551838.1859 | 0 | 21428.3718 | 129998.7889 | 19999.8137 | 49999.5342 | 0 | 231194.4771 | 12311.325 | 0 | 0 | 41297.75 | 255648.1585 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-21 | 1771612.5678 |  |  | 553596.5416 | 222257.7333 | 231194.4771 | 632746.9202 | 131816.8956 | 0 | 13573.56 | 2203.5 | 0 | 0 | 65036.7432 | 22475.7 | 0 | 0 | 0 | 0 | 0 | 10899.3924 | 7051.2 | 10576.8 | 0 | 0 | 305026.575 | 553596.5416 | 0 | 21508.8129 | 130486.7983 | 20074.892 | 50187.2301 | 0 | 231194.4771 | 12400.5375 | 0 | 0 | 41297.75 | 255822.0577 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-22 | 1774854.1002 |  |  | 555354.8973 | 223088.958 | 231194.4771 | 633010.0318 | 132205.736 | 0 | 13613.6 | 2210 | 0 | 0 | 65228.592 | 22542 | 0 | 0 | 0 | 0 | 0 | 10931.544 | 7072 | 10608 | 0 | 0 | 305026.575 | 555354.8973 | 0 | 21589.254 | 130974.8076 | 20149.9704 | 50374.926 | 0 | 231194.4771 | 12489.75 | 0 | 0 | 41297.75 | 255995.9568 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-23 | 1778095.6327 |  |  | 557113.253 | 223920.1827 | 231194.4771 | 633273.1435 | 132594.5764 | 0 | 13653.64 | 2216.5 | 0 | 0 | 65420.4408 | 22608.3 | 0 | 0 | 0 | 0 | 0 | 10963.6956 | 7092.8 | 10639.2 | 0 | 0 | 305026.575 | 557113.253 | 0 | 21669.6951 | 131462.8169 | 20225.0488 | 50562.6219 | 0 | 231194.4771 | 12578.9625 | 0 | 0 | 41297.75 | 256169.856 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-24 | 1781337.1651 |  |  | 558871.6087 | 224751.4074 | 231194.4771 | 633536.2552 | 132983.4168 | 0 | 13693.68 | 2223 | 0 | 0 | 65612.2896 | 22674.6 | 0 | 0 | 0 | 0 | 0 | 10995.8472 | 7113.6 | 10670.4 | 0 | 0 | 305026.575 | 558871.6087 | 0 | 21750.1362 | 131950.8263 | 20300.1271 | 50750.3178 | 0 | 231194.4771 | 12668.175 | 0 | 0 | 41297.75 | 256343.7552 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-25 | 1784578.6976 |  |  | 560629.9644 | 225582.6321 | 231194.4771 | 633799.3668 | 133372.2572 | 0 | 13733.72 | 2229.5 | 0 | 0 | 65804.1384 | 22740.9 | 0 | 0 | 0 | 0 | 0 | 11027.9988 | 7134.4 | 10701.6 | 0 | 0 | 305026.575 | 560629.9644 | 0 | 21830.5773 | 132438.8356 | 20375.2055 | 50938.0137 | 0 | 231194.4771 | 12757.3875 | 0 | 0 | 41297.75 | 256517.6543 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-26 | 1787820.2301 |  |  | 562388.3201 | 226413.8568 | 231194.4771 | 634062.4785 | 133761.0976 | 0 | 13773.76 | 2236 | 0 | 0 | 65995.9872 | 22807.2 | 0 | 0 | 0 | 0 | 0 | 11060.1504 | 7155.2 | 10732.8 | 0 | 0 | 305026.575 | 562388.3201 | 0 | 21911.0184 | 132926.845 | 20450.2838 | 51125.7096 | 0 | 231194.4771 | 12846.6 | 0 | 0 | 41297.75 | 256691.5535 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-27 | 1791061.7625 |  |  | 564146.6758 | 227245.0815 | 231194.4771 | 634325.5902 | 134149.938 | 0 | 13813.8 | 2242.5 | 0 | 0 | 66187.836 | 22873.5 | 0 | 0 | 0 | 0 | 0 | 11092.302 | 7176 | 10764 | 0 | 0 | 305026.575 | 564146.6758 | 0 | 21991.4595 | 133414.8543 | 20525.3622 | 51313.4055 | 0 | 231194.4771 | 12935.8125 | 0 | 0 | 41297.75 | 256865.4527 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-28 | 1794303.295 |  |  | 565905.0315 | 228076.3062 | 231194.4771 | 634588.7018 | 134538.7784 | 0 | 13853.84 | 2249 | 0 | 0 | 66379.6848 | 22939.8 | 0 | 0 | 0 | 0 | 0 | 11124.4536 | 7196.8 | 10795.2 | 0 | 0 | 305026.575 | 565905.0315 | 0 | 22071.9006 | 133902.8636 | 20600.4406 | 51501.1014 | 0 | 231194.4771 | 13025.025 | 0 | 0 | 41297.75 | 257039.3518 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-29 | 1797544.8274 |  |  | 567663.3872 | 228907.5309 | 231194.4771 | 634851.8135 | 134927.6188 | 0 | 13893.88 | 2255.5 | 0 | 0 | 66571.5336 | 23006.1 | 0 | 0 | 0 | 0 | 0 | 11156.6052 | 7217.6 | 10826.4 | 0 | 0 | 305026.575 | 567663.3872 | 0 | 22152.3417 | 134390.873 | 20675.5189 | 51688.7973 | 0 | 231194.4771 | 13114.2375 | 0 | 0 | 41297.75 | 257213.251 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-30 | 1800786.3599 |  |  | 569421.7429 | 229738.7556 | 231194.4771 | 635114.9252 | 135316.4592 | 0 | 13933.92 | 2262 | 0 | 0 | 66763.3824 | 23072.4 | 0 | 0 | 0 | 0 | 0 | 11188.7568 | 7238.4 | 10857.6 | 0 | 0 | 305026.575 | 569421.7429 | 0 | 22232.7828 | 134878.8823 | 20750.5973 | 51876.4932 | 0 | 231194.4771 | 13203.45 | 0 | 0 | 41297.75 | 257387.1502 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-03-31 | 1804027.8924 |  |  | 571180.0986 | 230569.9803 | 231194.4771 | 635378.0368 | 135705.2996 | 0 | 13973.96 | 2268.5 | 0 | 0 | 66955.2312 | 23138.7 | 0 | 0 | 0 | 0 | 0 | 11220.9084 | 7259.2 | 10888.8 | 0 | 0 | 305026.575 | 571180.0986 | 0 | 22313.2239 | 135366.8917 | 20825.6756 | 52064.1891 | 0 | 231194.4771 | 13292.6625 | 0 | 0 | 41297.75 | 257561.0493 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-01 | 1807269.4248 |  |  | 572938.4542 | 231401.205 | 231194.4771 | 635641.1485 | 136094.14 | 0 | 14014 | 2275 | 0 | 0 | 67147.08 | 23205 | 0 | 0 | 0 | 0 | 0 | 11253.06 | 7280 | 10920 | 0 | 0 | 305026.575 | 572938.4542 | 0 | 22393.665 | 135854.901 | 20900.754 | 52251.885 | 0 | 231194.4771 | 13381.875 | 0 | 0 | 41297.75 | 257734.9485 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-02 | 1810510.9573 |  |  | 574696.8099 | 232232.4297 | 231194.4771 | 635904.2602 | 136482.9804 | 0 | 14054.04 | 2281.5 | 0 | 0 | 67338.9288 | 23271.3 | 0 | 0 | 0 | 0 | 0 | 11285.2116 | 7300.8 | 10951.2 | 0 | 0 | 305026.575 | 574696.8099 | 0 | 22474.1061 | 136342.9103 | 20975.8324 | 52439.5809 | 0 | 231194.4771 | 13471.0875 | 0 | 0 | 41297.75 | 257908.8477 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-03 | 1813752.4898 |  |  | 576455.1656 | 233063.6544 | 231194.4771 | 636167.3718 | 136871.8208 | 0 | 14094.08 | 2288 | 0 | 0 | 67530.7776 | 23337.6 | 0 | 0 | 0 | 0 | 0 | 11317.3632 | 7321.6 | 10982.4 | 0 | 0 | 305026.575 | 576455.1656 | 0 | 22554.5472 | 136830.9197 | 21050.9107 | 52627.2768 | 0 | 231194.4771 | 13560.3 | 0 | 0 | 41297.75 | 258082.7468 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-04 | 1816994.0222 |  |  | 578213.5213 | 233894.8791 | 231194.4771 | 636430.4835 | 137260.6612 | 0 | 14134.12 | 2294.5 | 0 | 0 | 67722.6264 | 23403.9 | 0 | 0 | 0 | 0 | 0 | 11349.5148 | 7342.4 | 11013.6 | 0 | 0 | 305026.575 | 578213.5213 | 0 | 22634.9883 | 137318.929 | 21125.9891 | 52814.9727 | 0 | 231194.4771 | 13649.5125 | 0 | 0 | 41297.75 | 258256.646 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-05 | 1820235.5547 |  |  | 579971.877 | 234726.1038 | 231194.4771 | 636693.5952 | 137649.5016 | 0 | 14174.16 | 2301 | 0 | 0 | 67914.4752 | 23470.2 | 0 | 0 | 0 | 0 | 0 | 11381.6664 | 7363.2 | 11044.8 | 0 | 0 | 305026.575 | 579971.877 | 0 | 22715.4294 | 137806.9384 | 21201.0674 | 53002.6686 | 0 | 231194.4771 | 13738.725 | 0 | 0 | 41297.75 | 258430.5452 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-06 | 1823477.0871 |  |  | 581730.2327 | 235557.3285 | 231194.4771 | 636956.7068 | 138038.342 | 0 | 14214.2 | 2307.5 | 0 | 0 | 68106.324 | 23536.5 | 0 | 0 | 0 | 0 | 0 | 11413.818 | 7384 | 11076 | 0 | 0 | 305026.575 | 581730.2327 | 0 | 22795.8705 | 138294.9477 | 21276.1458 | 53190.3645 | 0 | 231194.4771 | 13827.9375 | 0 | 0 | 41297.75 | 258604.4443 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-07 | 1826718.6196 |  |  | 583488.5884 | 236388.5532 | 231194.4771 | 637219.8185 | 138427.1824 | 0 | 14254.24 | 2314 | 0 | 0 | 68298.1728 | 23602.8 | 0 | 0 | 0 | 0 | 0 | 11445.9696 | 7404.8 | 11107.2 | 0 | 0 | 305026.575 | 583488.5884 | 0 | 22876.3116 | 138782.957 | 21351.2242 | 53378.0604 | 0 | 231194.4771 | 13917.15 | 0 | 0 | 41297.75 | 258778.3435 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-08 | 1829960.1521 |  |  | 585246.9441 | 237219.7779 | 231194.4771 | 637482.9302 | 138816.0228 | 0 | 14294.28 | 2320.5 | 0 | 0 | 68490.0216 | 23669.1 | 0 | 0 | 0 | 0 | 0 | 11478.1212 | 7425.6 | 11138.4 | 0 | 0 | 305026.575 | 585246.9441 | 0 | 22956.7527 | 139270.9664 | 21426.3025 | 53565.7563 | 0 | 231194.4771 | 14006.3625 | 0 | 0 | 41297.75 | 258952.2427 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-09 | 1833201.6845 |  |  | 587005.2998 | 238051.0026 | 231194.4771 | 637746.0418 | 139204.8632 | 0 | 14334.32 | 2327 | 0 | 0 | 68681.8704 | 23735.4 | 0 | 0 | 0 | 0 | 0 | 11510.2728 | 7446.4 | 11169.6 | 0 | 0 | 305026.575 | 587005.2998 | 0 | 23037.1938 | 139758.9757 | 21501.3809 | 53753.4522 | 0 | 231194.4771 | 14095.575 | 0 | 0 | 41297.75 | 259126.1418 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-10 | 1836443.217 |  |  | 588763.6555 | 238882.2273 | 231194.4771 | 638009.1535 | 139593.7036 | 0 | 14374.36 | 2333.5 | 0 | 0 | 68873.7192 | 23801.7 | 0 | 0 | 0 | 0 | 0 | 11542.4244 | 7467.2 | 11200.8 | 0 | 0 | 305026.575 | 588763.6555 | 0 | 23117.6349 | 140246.9851 | 21576.4592 | 53941.1481 | 0 | 231194.4771 | 14184.7875 | 0 | 0 | 41297.75 | 259300.041 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-11 | 1839684.7494 |  |  | 590522.0112 | 239713.452 | 231194.4771 | 638272.2652 | 139982.544 | 0 | 14414.4 | 2340 | 0 | 0 | 69065.568 | 23868 | 0 | 0 | 0 | 0 | 0 | 11574.576 | 7488 | 11232 | 0 | 0 | 305026.575 | 590522.0112 | 0 | 23198.076 | 140734.9944 | 21651.5376 | 54128.844 | 0 | 231194.4771 | 14274 | 0 | 0 | 41297.75 | 259473.9402 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-12 | 1842926.2819 |  |  | 592280.3669 | 240544.6767 | 231194.4771 | 638535.3768 | 140371.3844 | 0 | 14454.44 | 2346.5 | 0 | 0 | 69257.4168 | 23934.3 | 0 | 0 | 0 | 0 | 0 | 11606.7276 | 7508.8 | 11263.2 | 0 | 0 | 305026.575 | 592280.3669 | 0 | 23278.5171 | 141223.0037 | 21726.616 | 54316.5399 | 0 | 231194.4771 | 14363.2125 | 0 | 0 | 41297.75 | 259647.8393 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-13 | 1846167.8144 |  |  | 594038.7226 | 241375.9014 | 231194.4771 | 638798.4885 | 140760.2248 | 0 | 14494.48 | 2353 | 0 | 0 | 69449.2656 | 24000.6 | 0 | 0 | 0 | 0 | 0 | 11638.8792 | 7529.6 | 11294.4 | 0 | 0 | 305026.575 | 594038.7226 | 0 | 23358.9582 | 141711.0131 | 21801.6943 | 54504.2358 | 0 | 231194.4771 | 14452.425 | 0 | 0 | 41297.75 | 259821.7385 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-14 | 1849409.3468 |  |  | 595797.0783 | 242207.1261 | 231194.4771 | 639061.6002 | 141149.0652 | 0 | 14534.52 | 2359.5 | 0 | 0 | 69641.1144 | 24066.9 | 0 | 0 | 0 | 0 | 0 | 11671.0308 | 7550.4 | 11325.6 | 0 | 0 | 305026.575 | 595797.0783 | 0 | 23439.3993 | 142199.0224 | 21876.7727 | 54691.9317 | 0 | 231194.4771 | 14541.6375 | 0 | 0 | 41297.75 | 259995.6377 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-15 | 1852650.8793 |  |  | 597555.434 | 243038.3508 | 231194.4771 | 639324.7118 | 141537.9056 | 0 | 14574.56 | 2366 | 0 | 0 | 69832.9632 | 24133.2 | 0 | 0 | 0 | 0 | 0 | 11703.1824 | 7571.2 | 11356.8 | 0 | 0 | 305026.575 | 597555.434 | 0 | 23519.8404 | 142687.0318 | 21951.851 | 54879.6276 | 0 | 231194.4771 | 14630.85 | 0 | 0 | 41297.75 | 260169.5368 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-16 | 1855892.4118 |  |  | 599313.7897 | 243869.5755 | 231194.4771 | 639587.8235 | 141926.746 | 0 | 14614.6 | 2372.5 | 0 | 0 | 70024.812 | 24199.5 | 0 | 0 | 0 | 0 | 0 | 11735.334 | 7592 | 11388 | 0 | 0 | 305026.575 | 599313.7897 | 0 | 23600.2815 | 143175.0411 | 22026.9294 | 55067.3235 | 0 | 231194.4771 | 14720.0625 | 0 | 0 | 41297.75 | 260343.436 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-17 | 1859133.9442 |  |  | 601072.1454 | 244700.8002 | 231194.4771 | 639850.9352 | 142315.5864 | 0 | 14654.64 | 2379 | 0 | 0 | 70216.6608 | 24265.8 | 0 | 0 | 0 | 0 | 0 | 11767.4856 | 7612.8 | 11419.2 | 0 | 0 | 305026.575 | 601072.1454 | 0 | 23680.7226 | 143663.0504 | 22102.0078 | 55255.0194 | 0 | 231194.4771 | 14809.275 | 0 | 0 | 41297.75 | 260517.3352 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-18 | 1862375.4767 |  |  | 602830.5011 | 245532.0249 | 231194.4771 | 640114.0468 | 142704.4268 | 0 | 14694.68 | 2385.5 | 0 | 0 | 70408.5096 | 24332.1 | 0 | 0 | 0 | 0 | 0 | 11799.6372 | 7633.6 | 11450.4 | 0 | 0 | 305026.575 | 602830.5011 | 0 | 23761.1637 | 144151.0598 | 22177.0861 | 55442.7153 | 0 | 231194.4771 | 14898.4875 | 0 | 0 | 41297.75 | 260691.2343 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-19 | 1865617.0091 |  |  | 604588.8568 | 246363.2496 | 231194.4771 | 640377.1585 | 143093.2672 | 0 | 14734.72 | 2392 | 0 | 0 | 70600.3584 | 24398.4 | 0 | 0 | 0 | 0 | 0 | 11831.7888 | 7654.4 | 11481.6 | 0 | 0 | 305026.575 | 604588.8568 | 0 | 23841.6048 | 144639.0691 | 22252.1645 | 55630.4112 | 0 | 231194.4771 | 14987.7 | 0 | 0 | 41297.75 | 260865.1335 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-20 | 1868858.5416 |  |  | 606347.2125 | 247194.4743 | 231194.4771 | 640640.2702 | 143482.1076 | 0 | 14774.76 | 2398.5 | 0 | 0 | 70792.2072 | 24464.7 | 0 | 0 | 0 | 0 | 0 | 11863.9404 | 7675.2 | 11512.8 | 0 | 0 | 305026.575 | 606347.2125 | 0 | 23922.0459 | 145127.0785 | 22327.2428 | 55818.1071 | 0 | 231194.4771 | 15076.9125 | 0 | 0 | 41297.75 | 261039.0327 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-21 | 1872100.0741 |  |  | 608105.5681 | 248025.699 | 231194.4771 | 640903.3818 | 143870.948 | 0 | 14814.8 | 2405 | 0 | 0 | 70984.056 | 24531 | 0 | 0 | 0 | 0 | 0 | 11896.092 | 7696 | 11544 | 0 | 0 | 305026.575 | 608105.5681 | 0 | 24002.487 | 145615.0878 | 22402.3212 | 56005.803 | 0 | 231194.4771 | 15166.125 | 0 | 0 | 41297.75 | 261212.9318 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-22 | 1875341.6065 |  |  | 609863.9238 | 248856.9237 | 231194.4771 | 641166.4935 | 144259.7884 | 0 | 14854.84 | 2411.5 | 0 | 0 | 71175.9048 | 24597.3 | 0 | 0 | 0 | 0 | 0 | 11928.2436 | 7716.8 | 11575.2 | 0 | 0 | 305026.575 | 609863.9238 | 0 | 24082.9281 | 146103.0971 | 22477.3996 | 56193.4989 | 0 | 231194.4771 | 15255.3375 | 0 | 0 | 41297.75 | 261386.831 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-23 | 1878583.139 |  |  | 611622.2795 | 249688.1484 | 231194.4771 | 641429.6052 | 144648.6288 | 0 | 14894.88 | 2418 | 0 | 0 | 71367.7536 | 24663.6 | 0 | 0 | 0 | 0 | 0 | 11960.3952 | 7737.6 | 11606.4 | 0 | 0 | 305026.575 | 611622.2795 | 0 | 24163.3692 | 146591.1065 | 22552.4779 | 56381.1948 | 0 | 231194.4771 | 15344.55 | 0 | 0 | 41297.75 | 261560.7302 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-24 | 1881824.6714 |  |  | 613380.6352 | 250519.3731 | 231194.4771 | 641692.7168 | 145037.4692 | 0 | 14934.92 | 2424.5 | 0 | 0 | 71559.6024 | 24729.9 | 0 | 0 | 0 | 0 | 0 | 11992.5468 | 7758.4 | 11637.6 | 0 | 0 | 305026.575 | 613380.6352 | 0 | 24243.8103 | 147079.1158 | 22627.5563 | 56568.8907 | 0 | 231194.4771 | 15433.7625 | 0 | 0 | 41297.75 | 261734.6293 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-25 | 1885066.2039 |  |  | 615138.9909 | 251350.5978 | 231194.4771 | 641955.8285 | 145426.3096 | 0 | 14974.96 | 2431 | 0 | 0 | 71751.4512 | 24796.2 | 0 | 0 | 0 | 0 | 0 | 12024.6984 | 7779.2 | 11668.8 | 0 | 0 | 305026.575 | 615138.9909 | 0 | 24324.2514 | 147567.1252 | 22702.6346 | 56756.5866 | 0 | 231194.4771 | 15522.975 | 0 | 0 | 41297.75 | 261908.5285 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-26 | 1888307.7364 |  |  | 616897.3466 | 252181.8225 | 231194.4771 | 642218.9402 | 145815.15 | 0 | 15015 | 2437.5 | 0 | 0 | 71943.3 | 24862.5 | 0 | 0 | 0 | 0 | 0 | 12056.85 | 7800 | 11700 | 0 | 0 | 305026.575 | 616897.3466 | 0 | 24404.6925 | 148055.1345 | 22777.713 | 56944.2825 | 0 | 231194.4771 | 15612.1875 | 0 | 0 | 41297.75 | 262082.4277 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-27 | 1891549.2688 |  |  | 618655.7023 | 253013.0472 | 231194.4771 | 642482.0518 | 146203.9904 | 0 | 15055.04 | 2444 | 0 | 0 | 72135.1488 | 24928.8 | 0 | 0 | 0 | 0 | 0 | 12089.0016 | 7820.8 | 11731.2 | 0 | 0 | 305026.575 | 618655.7023 | 0 | 24485.1336 | 148543.1438 | 22852.7914 | 57131.9784 | 0 | 231194.4771 | 15701.4 | 0 | 0 | 41297.75 | 262256.3268 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-28 | 1894790.8013 |  |  | 620414.058 | 253844.2719 | 231194.4771 | 642745.1635 | 146592.8308 | 0 | 15095.08 | 2450.5 | 0 | 0 | 72326.9976 | 24995.1 | 0 | 0 | 0 | 0 | 0 | 12121.1532 | 7841.6 | 11762.4 | 0 | 0 | 305026.575 | 620414.058 | 0 | 24565.5747 | 149031.1532 | 22927.8697 | 57319.6743 | 0 | 231194.4771 | 15790.6125 | 0 | 0 | 41297.75 | 262430.226 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-29 | 1898032.3338 |  |  | 622172.4137 | 254675.4966 | 231194.4771 | 643008.2752 | 146981.6712 | 0 | 15135.12 | 2457 | 0 | 0 | 72518.8464 | 25061.4 | 0 | 0 | 0 | 0 | 0 | 12153.3048 | 7862.4 | 11793.6 | 0 | 0 | 305026.575 | 622172.4137 | 0 | 24646.0158 | 149519.1625 | 23002.9481 | 57507.3702 | 0 | 231194.4771 | 15879.825 | 0 | 0 | 41297.75 | 262604.1252 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-04-30 | 1901273.8662 |  |  | 623930.7694 | 255506.7213 | 231194.4771 | 643271.3868 | 147370.5116 | 0 | 15175.16 | 2463.5 | 0 | 0 | 72710.6952 | 25127.7 | 0 | 0 | 0 | 0 | 0 | 12185.4564 | 7883.2 | 11824.8 | 0 | 0 | 305026.575 | 623930.7694 | 0 | 24726.4569 | 150007.1719 | 23078.0264 | 57695.0661 | 0 | 231194.4771 | 15969.0375 | 0 | 0 | 41297.75 | 262778.0243 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-01 | 1904515.3987 |  |  | 625689.1251 | 256337.946 | 231194.4771 | 643534.4985 | 147759.352 | 0 | 15215.2 | 2470 | 0 | 0 | 72902.544 | 25194 | 0 | 0 | 0 | 0 | 0 | 12217.608 | 7904 | 11856 | 0 | 0 | 305026.575 | 625689.1251 | 0 | 24806.898 | 150495.1812 | 23153.1048 | 57882.762 | 0 | 231194.4771 | 16058.25 | 0 | 0 | 41297.75 | 262951.9235 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-02 | 1907756.9311 |  |  | 627447.4808 | 257169.1707 | 231194.4771 | 643797.6102 | 148148.1924 | 0 | 15255.24 | 2476.5 | 0 | 0 | 73094.3928 | 25260.3 | 0 | 0 | 0 | 0 | 0 | 12249.7596 | 7924.8 | 11887.2 | 0 | 0 | 305026.575 | 627447.4808 | 0 | 24887.3391 | 150983.1905 | 23228.1832 | 58070.4579 | 0 | 231194.4771 | 16147.4625 | 0 | 0 | 41297.75 | 263125.8227 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-03 | 1910998.4636 |  |  | 629205.8365 | 258000.3954 | 231194.4771 | 644060.7218 | 148537.0328 | 0 | 15295.28 | 2483 | 0 | 0 | 73286.2416 | 25326.6 | 0 | 0 | 0 | 0 | 0 | 12281.9112 | 7945.6 | 11918.4 | 0 | 0 | 305026.575 | 629205.8365 | 0 | 24967.7802 | 151471.1999 | 23303.2615 | 58258.1538 | 0 | 231194.4771 | 16236.675 | 0 | 0 | 41297.75 | 263299.7218 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-04 | 1914239.9961 |  |  | 630964.1922 | 258831.6201 | 231194.4771 | 644323.8335 | 148925.8732 | 0 | 15335.32 | 2489.5 | 0 | 0 | 73478.0904 | 25392.9 | 0 | 0 | 0 | 0 | 0 | 12314.0628 | 7966.4 | 11949.6 | 0 | 0 | 305026.575 | 630964.1922 | 0 | 25048.2213 | 151959.2092 | 23378.3399 | 58445.8497 | 0 | 231194.4771 | 16325.8875 | 0 | 0 | 41297.75 | 263473.621 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-05 | 1917481.5285 |  |  | 632722.5479 | 259662.8448 | 231194.4771 | 644586.9452 | 149314.7136 | 0 | 15375.36 | 2496 | 0 | 0 | 73669.9392 | 25459.2 | 0 | 0 | 0 | 0 | 0 | 12346.2144 | 7987.2 | 11980.8 | 0 | 0 | 305026.575 | 632722.5479 | 0 | 25128.6624 | 152447.2186 | 23453.4182 | 58633.5456 | 0 | 231194.4771 | 16415.1 | 0 | 0 | 41297.75 | 263647.5202 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-06 | 1920723.061 |  |  | 634480.9036 | 260494.0695 | 231194.4771 | 644850.0568 | 149703.554 | 0 | 15415.4 | 2502.5 | 0 | 0 | 73861.788 | 25525.5 | 0 | 0 | 0 | 0 | 0 | 12378.366 | 8008 | 12012 | 0 | 0 | 305026.575 | 634480.9036 | 0 | 25209.1035 | 152935.2279 | 23528.4966 | 58821.2415 | 0 | 231194.4771 | 16504.3125 | 0 | 0 | 41297.75 | 263821.4193 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-07 | 1923964.5935 |  |  | 636239.2593 | 261325.2942 | 231194.4771 | 645113.1685 | 150092.3944 | 0 | 15455.44 | 2509 | 0 | 0 | 74053.6368 | 25591.8 | 0 | 0 | 0 | 0 | 0 | 12410.5176 | 8028.8 | 12043.2 | 0 | 0 | 305026.575 | 636239.2593 | 0 | 25289.5446 | 153423.2372 | 23603.575 | 59008.9374 | 0 | 231194.4771 | 16593.525 | 0 | 0 | 41297.75 | 263995.3185 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-08 | 1927206.1259 |  |  | 637997.615 | 262156.5189 | 231194.4771 | 645376.2802 | 150481.2348 | 0 | 15495.48 | 2515.5 | 0 | 0 | 74245.4856 | 25658.1 | 0 | 0 | 0 | 0 | 0 | 12442.6692 | 8049.6 | 12074.4 | 0 | 0 | 305026.575 | 637997.615 | 0 | 25369.9857 | 153911.2466 | 23678.6533 | 59196.6333 | 0 | 231194.4771 | 16682.7375 | 0 | 0 | 41297.75 | 264169.2177 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-09 | 1930447.6584 |  |  | 639755.9707 | 262987.7436 | 231194.4771 | 645639.3918 | 150870.0752 | 0 | 15535.52 | 2522 | 0 | 0 | 74437.3344 | 25724.4 | 0 | 0 | 0 | 0 | 0 | 12474.8208 | 8070.4 | 12105.6 | 0 | 0 | 305026.575 | 639755.9707 | 0 | 25450.4268 | 154399.2559 | 23753.7317 | 59384.3292 | 0 | 231194.4771 | 16771.95 | 0 | 0 | 41297.75 | 264343.1168 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-10 | 1933689.1908 |  |  | 641514.3264 | 263818.9683 | 231194.4771 | 645902.5035 | 151258.9156 | 0 | 15575.56 | 2528.5 | 0 | 0 | 74629.1832 | 25790.7 | 0 | 0 | 0 | 0 | 0 | 12506.9724 | 8091.2 | 12136.8 | 0 | 0 | 305026.575 | 641514.3264 | 0 | 25530.8679 | 154887.2653 | 23828.81 | 59572.0251 | 0 | 231194.4771 | 16861.1625 | 0 | 0 | 41297.75 | 264517.016 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-11 | 1936930.7233 |  |  | 643272.682 | 264650.193 | 231194.4771 | 646165.6152 | 151647.756 | 0 | 15615.6 | 2535 | 0 | 0 | 74821.032 | 25857 | 0 | 0 | 0 | 0 | 0 | 12539.124 | 8112 | 12168 | 0 | 0 | 305026.575 | 643272.682 | 0 | 25611.309 | 155375.2746 | 23903.8884 | 59759.721 | 0 | 231194.4771 | 16950.375 | 0 | 0 | 41297.75 | 264690.9152 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-12 | 1940172.2558 |  |  | 645031.0377 | 265481.4177 | 231194.4771 | 646428.7268 | 152036.5964 | 0 | 15655.64 | 2541.5 | 0 | 0 | 75012.8808 | 25923.3 | 0 | 0 | 0 | 0 | 0 | 12571.2756 | 8132.8 | 12199.2 | 0 | 0 | 305026.575 | 645031.0377 | 0 | 25691.7501 | 155863.2839 | 23978.9668 | 59947.4169 | 0 | 231194.4771 | 17039.5875 | 0 | 0 | 41297.75 | 264864.8143 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-13 | 1943413.7882 |  |  | 646789.3934 | 266312.6424 | 231194.4771 | 646691.8385 | 152425.4368 | 0 | 15695.68 | 2548 | 0 | 0 | 75204.7296 | 25989.6 | 0 | 0 | 0 | 0 | 0 | 12603.4272 | 8153.6 | 12230.4 | 0 | 0 | 305026.575 | 646789.3934 | 0 | 25772.1912 | 156351.2933 | 24054.0451 | 60135.1128 | 0 | 231194.4771 | 17128.8 | 0 | 0 | 41297.75 | 265038.7135 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-14 | 1946655.3207 |  |  | 648547.7491 | 267143.8671 | 231194.4771 | 646954.9502 | 152814.2772 | 0 | 15735.72 | 2554.5 | 0 | 0 | 75396.5784 | 26055.9 | 0 | 0 | 0 | 0 | 0 | 12635.5788 | 8174.4 | 12261.6 | 0 | 0 | 305026.575 | 648547.7491 | 0 | 25852.6323 | 156839.3026 | 24129.1235 | 60322.8087 | 0 | 231194.4771 | 17218.0125 | 0 | 0 | 41297.75 | 265212.6127 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-15 | 1949896.8531 |  |  | 650306.1048 | 267975.0918 | 231194.4771 | 647218.0618 | 153203.1176 | 0 | 15775.76 | 2561 | 0 | 0 | 75588.4272 | 26122.2 | 0 | 0 | 0 | 0 | 0 | 12667.7304 | 8195.2 | 12292.8 | 0 | 0 | 305026.575 | 650306.1048 | 0 | 25933.0734 | 157327.312 | 24204.2018 | 60510.5046 | 0 | 231194.4771 | 17307.225 | 0 | 0 | 41297.75 | 265386.5118 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-16 | 1953138.3856 |  |  | 652064.4605 | 268806.3165 | 231194.4771 | 647481.1735 | 153591.958 | 0 | 15815.8 | 2567.5 | 0 | 0 | 75780.276 | 26188.5 | 0 | 0 | 0 | 0 | 0 | 12699.882 | 8216 | 12324 | 0 | 0 | 305026.575 | 652064.4605 | 0 | 26013.5145 | 157815.3213 | 24279.2802 | 60698.2005 | 0 | 231194.4771 | 17396.4375 | 0 | 0 | 41297.75 | 265560.411 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-17 | 1956379.9181 |  |  | 653822.8162 | 269637.5412 | 231194.4771 | 647744.2852 | 153980.7984 | 0 | 15855.84 | 2574 | 0 | 0 | 75972.1248 | 26254.8 | 0 | 0 | 0 | 0 | 0 | 12732.0336 | 8236.8 | 12355.2 | 0 | 0 | 305026.575 | 653822.8162 | 0 | 26093.9556 | 158303.3306 | 24354.3586 | 60885.8964 | 0 | 231194.4771 | 17485.65 | 0 | 0 | 41297.75 | 265734.3102 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-18 | 1959621.4505 |  |  | 655581.1719 | 270468.7659 | 231194.4771 | 648007.3968 | 154369.6388 | 0 | 15895.88 | 2580.5 | 0 | 0 | 76163.9736 | 26321.1 | 0 | 0 | 0 | 0 | 0 | 12764.1852 | 8257.6 | 12386.4 | 0 | 0 | 305026.575 | 655581.1719 | 0 | 26174.3967 | 158791.34 | 24429.4369 | 61073.5923 | 0 | 231194.4771 | 17574.8625 | 0 | 0 | 41297.75 | 265908.2093 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-19 | 1962862.983 |  |  | 657339.5276 | 271299.9906 | 231194.4771 | 648270.5085 | 154758.4792 | 0 | 15935.92 | 2587 | 0 | 0 | 76355.8224 | 26387.4 | 0 | 0 | 0 | 0 | 0 | 12796.3368 | 8278.4 | 12417.6 | 0 | 0 | 305026.575 | 657339.5276 | 0 | 26254.8378 | 159279.3493 | 24504.5153 | 61261.2882 | 0 | 231194.4771 | 17664.075 | 0 | 0 | 41297.75 | 266082.1085 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-20 | 1966104.5155 |  |  | 659097.8833 | 272131.2153 | 231194.4771 | 648533.6202 | 155147.3196 | 0 | 15975.96 | 2593.5 | 0 | 0 | 76547.6712 | 26453.7 | 0 | 0 | 0 | 0 | 0 | 12828.4884 | 8299.2 | 12448.8 | 0 | 0 | 305026.575 | 659097.8833 | 0 | 26335.2789 | 159767.3587 | 24579.5936 | 61448.9841 | 0 | 231194.4771 | 17753.2875 | 0 | 0 | 41297.75 | 266256.0077 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-21 | 1969346.0479 |  |  | 660856.239 | 272962.44 | 231194.4771 | 648796.7318 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 660856.239 | 0 | 26415.72 | 160255.368 | 24654.672 | 61636.68 | 0 | 231194.4771 | 17842.5 | 0 | 0 | 41297.75 | 266429.9068 | 13000 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-22 | 1982846.1525 |  |  | 665023.8253 | 275131.0309 | 231484.2631 | 655670.8731 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 665023.8253 | 0 | 26625.5836 | 161528.5407 | 24850.5447 | 62126.3618 | 3057.2208 | 231484.2631 | 17842.5 | 0 | 0 | 43118.1932 | 267953.6568 | 13472.7273 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-23 | 1996346.257 |  |  | 669191.4116 | 277299.6218 | 231774.0492 | 662545.0144 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 669191.4116 | 0 | 26835.4473 | 162801.7135 | 25046.4175 | 62616.0436 | 6114.4417 | 231774.0492 | 17842.5 | 0 | 0 | 44938.6364 | 269477.4068 | 13945.4545 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-24 | 2009846.3616 |  |  | 673358.9979 | 279468.2127 | 232063.8352 | 669419.1557 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 673358.9979 | 0 | 27045.3109 | 164074.8862 | 25242.2902 | 63105.7255 | 9171.6625 | 232063.8352 | 17842.5 | 0 | 0 | 46759.0795 | 271001.1568 | 14418.1818 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-25 | 2023346.4661 |  |  | 677526.5843 | 281636.8036 | 232353.6212 | 676293.297 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 677526.5843 | 0 | 27255.1745 | 165348.0589 | 25438.1629 | 63595.4073 | 12228.8833 | 232353.6212 | 17842.5 | 0 | 0 | 48579.5227 | 272524.9068 | 14890.9091 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-26 | 2036846.5707 |  |  | 681694.1706 | 283805.3945 | 232643.4073 | 683167.4383 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 681694.1706 | 0 | 27465.0382 | 166621.2316 | 25634.0356 | 64085.0891 | 15286.1042 | 232643.4073 | 17842.5 | 0 | 0 | 50399.9659 | 274048.6568 | 15363.6364 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-27 | 2050346.6752 |  |  | 685861.7569 | 285973.9855 | 232933.1933 | 690041.5796 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 685861.7569 | 0 | 27674.9018 | 167894.4044 | 25829.9084 | 64574.7709 | 18343.325 | 232933.1933 | 17842.5 | 0 | 0 | 52220.4091 | 275572.4068 | 15836.3636 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-28 | 2063846.7798 |  |  | 690029.3432 | 288142.5764 | 233222.9794 | 696915.7209 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 690029.3432 | 0 | 27884.7655 | 169167.5771 | 26025.7811 | 65064.4527 | 21400.5458 | 233222.9794 | 17842.5 | 0 | 0 | 54040.8523 | 277096.1568 | 16309.0909 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-29 | 2077346.8844 |  |  | 694196.9295 | 290311.1673 | 233512.7654 | 703789.8621 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 694196.9295 | 0 | 28094.6291 | 170440.7498 | 26221.6538 | 65554.1345 | 24457.7667 | 233512.7654 | 17842.5 | 0 | 0 | 55861.2955 | 278619.9068 | 16781.8182 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-30 | 2090846.9889 |  |  | 698364.5158 | 292479.7582 | 233802.5515 | 710664.0034 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 698364.5158 | 0 | 28304.4927 | 171713.9225 | 26417.5265 | 66043.8164 | 27514.9875 | 233802.5515 | 17842.5 | 0 | 0 | 57681.7386 | 280143.6568 | 17254.5455 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-05-31 | 2104347.0935 |  |  | 702532.1021 | 294648.3491 | 234092.3375 | 717538.1447 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 702532.1021 | 0 | 28514.3564 | 172987.0953 | 26613.3993 | 66533.4982 | 30572.2083 | 234092.3375 | 17842.5 | 0 | 0 | 59502.1818 | 281667.4068 | 17727.2727 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-01 | 2117847.198 |  |  | 706699.6885 | 296816.94 | 234382.1235 | 724412.286 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 706699.6885 | 0 | 28724.22 | 174260.268 | 26809.272 | 67023.18 | 33629.4292 | 234382.1235 | 17842.5 | 0 | 0 | 61322.625 | 283191.1568 | 18200 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-02 | 2131347.3026 |  |  | 710867.2748 | 298985.5309 | 234671.9096 | 731286.4273 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 710867.2748 | 0 | 28934.0836 | 175533.4407 | 27005.1447 | 67512.8618 | 36686.65 | 234671.9096 | 17842.5 | 0 | 0 | 63143.0682 | 284714.9068 | 18672.7273 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-03 | 2144847.4071 |  |  | 715034.8611 | 301154.1218 | 234961.6956 | 738160.5686 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 715034.8611 | 0 | 29143.9473 | 176806.6135 | 27201.0175 | 68002.5436 | 39743.8708 | 234961.6956 | 17842.5 | 0 | 0 | 64963.5114 | 286238.6568 | 19145.4545 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-04 | 2158347.5117 |  |  | 719202.4474 | 303322.7127 | 235251.4817 | 745034.7099 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 719202.4474 | 0 | 29353.8109 | 178079.7862 | 27396.8902 | 68492.2255 | 42801.0917 | 235251.4817 | 17842.5 | 0 | 0 | 66783.9545 | 287762.4068 | 19618.1818 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-05 | 2171847.6162 |  |  | 723370.0337 | 305491.3036 | 235541.2677 | 751908.8512 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 723370.0337 | 0 | 29563.6745 | 179352.9589 | 27592.7629 | 68981.9073 | 45858.3125 | 235541.2677 | 17842.5 | 0 | 0 | 68604.3977 | 289286.1568 | 20090.9091 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-06 | 2185347.7208 |  |  | 727537.62 | 307659.8945 | 235831.0538 | 758782.9924 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 727537.62 | 0 | 29773.5382 | 180626.1316 | 27788.6356 | 69471.5891 | 48915.5333 | 235831.0538 | 17842.5 | 0 | 0 | 70424.8409 | 290809.9068 | 20563.6364 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-07 | 2198847.8253 |  |  | 731705.2064 | 309828.4855 | 236120.8398 | 765657.1337 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 731705.2064 | 0 | 29983.4018 | 181899.3044 | 27984.5084 | 69961.2709 | 51972.7542 | 236120.8398 | 17842.5 | 0 | 0 | 72245.2841 | 292333.6568 | 21036.3636 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-08 | 2212347.9299 |  |  | 735872.7927 | 311997.0764 | 236410.6258 | 772531.275 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 735872.7927 | 0 | 30193.2655 | 183172.4771 | 28180.3811 | 70450.9527 | 55029.975 | 236410.6258 | 17842.5 | 0 | 0 | 74065.7273 | 293857.4068 | 21509.0909 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-09 | 2225848.0345 |  |  | 740040.379 | 314165.6673 | 236700.4119 | 779405.4163 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 740040.379 | 0 | 30403.1291 | 184445.6498 | 28376.2538 | 70940.6345 | 58087.1958 | 236700.4119 | 17842.5 | 0 | 0 | 75886.1705 | 295381.1568 | 21981.8182 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-10 | 2239348.139 |  |  | 744207.9653 | 316334.2582 | 236990.1979 | 786279.5576 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 744207.9653 | 0 | 30612.9927 | 185718.8225 | 28572.1265 | 71430.3164 | 61144.4167 | 236990.1979 | 17842.5 | 0 | 0 | 77706.6136 | 296904.9068 | 22454.5455 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-11 | 2252848.2436 |  |  | 748375.5516 | 318502.8491 | 237279.984 | 793153.6989 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 748375.5516 | 0 | 30822.8564 | 186991.9953 | 28767.9993 | 71919.9982 | 64201.6375 | 237279.984 | 17842.5 | 0 | 0 | 79527.0568 | 298428.6568 | 22927.2727 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-12 | 2266348.3481 |  |  | 752543.1379 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 752543.1379 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-13 | 2267172.4508 |  |  | 753367.2406 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 753367.2406 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-14 | 2267996.5535 |  |  | 754191.3433 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 754191.3433 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-15 | 2268820.6562 |  |  | 755015.446 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 755015.446 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-16 | 2269644.7588 |  |  | 755839.5486 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 755839.5486 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-17 | 2270468.8615 |  |  | 756663.6513 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 756663.6513 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-18 | 2271292.9642 |  |  | 757487.754 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 757487.754 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-19 | 2272117.0669 |  |  | 758311.8567 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 758311.8567 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-20 | 2272941.1696 |  |  | 759135.9594 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 759135.9594 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-21 | 2273765.2722 |  |  | 759960.062 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 759960.062 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-22 | 2274589.3749 |  |  | 760784.1647 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 760784.1647 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-23 | 2275413.4776 |  |  | 761608.2674 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 761608.2674 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-24 | 2276237.5803 |  |  | 762432.3701 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 762432.3701 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-25 | 2277061.6829 |  |  | 763256.4728 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 763256.4728 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-26 | 2277885.7856 |  |  | 764080.5754 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 764080.5754 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-27 | 2278709.8883 |  |  | 764904.6781 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 764904.6781 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-28 | 2279533.991 |  |  | 765728.7808 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 765728.7808 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-29 | 2280358.0937 |  |  | 766552.8835 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 766552.8835 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-06-30 | 2281182.1963 |  |  | 767376.9861 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 767376.9861 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-01 | 2282006.299 |  |  | 768201.0888 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 768201.0888 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-02 | 2282830.4017 |  |  | 769025.1915 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 769025.1915 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-03 | 2283654.5044 |  |  | 769849.2942 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 769849.2942 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-04 | 2284478.6071 |  |  | 770673.3969 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 770673.3969 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-05 | 2285302.7097 |  |  | 771497.4995 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 771497.4995 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-06 | 2286126.8124 |  |  | 772321.6022 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 772321.6022 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-07 | 2286950.9151 |  |  | 773145.7049 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 773145.7049 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-08 | 2287775.0178 |  |  | 773969.8076 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 773969.8076 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-09 | 2288599.1204 |  |  | 774793.9103 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 774793.9103 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-10 | 2289423.2231 |  |  | 775618.0129 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 775618.0129 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-11 | 2290247.3258 |  |  | 776442.1156 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 776442.1156 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-12 | 2291071.4285 |  |  | 777266.2183 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 777266.2183 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-13 | 2291895.5312 |  |  | 778090.321 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 778090.321 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-14 | 2292719.6338 |  |  | 778914.4236 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 778914.4236 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-15 | 2293543.7365 |  |  | 779738.5263 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 779738.5263 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-16 | 2294367.8392 |  |  | 780562.629 | 320671.44 | 237569.77 | 800027.8402 | 155536.16 | 0 | 16016 | 2600 | 0 | 0 | 76739.52 | 26520 | 0 | 0 | 0 | 0 | 0 | 12860.64 | 8320 | 12480 | 0 | 0 | 305026.575 | 780562.629 | 0 | 31032.72 | 188265.168 | 28963.872 | 72409.68 | 67258.8583 | 237569.77 | 17842.5 | 0 | 0 | 81347.5 | 299952.4068 | 23400 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Cost Sum
Date | Planned Total Cost (Cumulative) | Actual Total Cost (Cumulative) | Planned Labor (Cumulative) | Actual Labor (Cumulative) | Planned Travel&perdiem (Cumulative) | Actual Travel&perdiem (Cumulative) | Planned Parts&materials (Cumulative) | Actual Parts&materials (Cumulative) | Planned Outsource (Cumulative) | Actual Outsource (Cumulative) | Planned Equipment (Cumulative) | Actual Equipment (Cumulative) | Planned Total Cost (Daily) | Actual Total Cost (Daily) | Planned Labor (Daily) | Actual Labor (Daily) | Planned Travel&perdiem (Daily) | Actual Travel&perdiem (Daily) | Planned Parts&materials (Daily) | Actual Parts&materials (Daily) | Planned Outsource (Daily) | Actual Outsource (Daily) | Planned Equipment (Daily) | Actual Equipment (Daily)
2025-04-01 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-02 | 2593.9167 | 0 | 2593.9167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 3890.875 | 0 | 3890.875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 5187.8333 | 0 | 5187.8333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 6484.7917 | 0 | 6484.7917 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 7781.75 | 0 | 7781.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 9078.7083 | 2614.5 | 9078.7083 | 2614.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 2614.5 | 1296.9583 | 2614.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 10375.6667 | 5229 | 10375.6667 | 5229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 2614.5 | 1296.9583 | 2614.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 11672.625 | 7843.5 | 11672.625 | 7843.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 2614.5 | 1296.9583 | 2614.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 12969.5833 | 10458 | 12969.5833 | 10458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 2614.5 | 1296.9583 | 2614.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 14266.5417 | 13072.5 | 14266.5417 | 13072.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 2614.5 | 1296.9583 | 2614.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 15563.5 | 13072.5 | 15563.5 | 13072.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 16860.4583 | 13072.5 | 16860.4583 | 13072.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 18157.4167 | 13340.5 | 18157.4167 | 13340.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 268 | 1296.9583 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 19454.375 | 13608.5 | 19454.375 | 13608.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1296.9583 | 268 | 1296.9583 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 20751.3333 | 13910.22 | 20751.3333 | 13876.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 301.72 | 1296.9583 | 268 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0
2025-04-17 | 22048.2917 | 14178.22 | 22048.2917 | 14144.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 268 | 1296.9583 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 23345.25 | 14446.22 | 23345.25 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 268 | 1296.9583 | 268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 24642.2083 | 14446.22 | 24642.2083 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 25939.1667 | 14446.22 | 25939.1667 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 27236.125 | 14446.22 | 27236.125 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 28533.0833 | 14446.22 | 28533.0833 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 29830.0417 | 14446.22 | 29830.0417 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 31127 | 14446.22 | 31127 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 32423.9583 | 14446.22 | 32423.9583 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 33720.9167 | 14446.22 | 33720.9167 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 35017.875 | 14446.22 | 35017.875 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 36314.8333 | 14446.22 | 36314.8333 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 37611.7917 | 14446.22 | 37611.7917 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 38908.75 | 14446.22 | 38908.75 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 40205.7083 | 14446.22 | 40205.7083 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 41502.6667 | 14446.22 | 41502.6667 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 42799.625 | 14446.22 | 42799.625 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 44096.5833 | 14446.22 | 44096.5833 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 45393.5417 | 14446.22 | 45393.5417 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 46690.5 | 14446.22 | 46690.5 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 47987.4583 | 14446.22 | 47987.4583 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 49284.4167 | 14446.22 | 49284.4167 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 50581.375 | 14446.22 | 50581.375 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 51878.3333 | 14446.22 | 51878.3333 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 53175.2917 | 14446.22 | 53175.2917 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 54472.25 | 14446.22 | 54472.25 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 55769.2083 | 14446.22 | 55769.2083 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 57066.1667 | 14446.22 | 57066.1667 | 14412.5 | 0 | 0 | 0 | 33.72 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 58363.125 | 20539.74 | 58363.125 | 14412.5 | 0 | 0 | 0 | 6127.24 | 0 | 0 | 0 | 0 | 1296.9583 | 6093.52 | 1296.9583 | 0 | 0 | 0 | 0 | 6093.52 | 0 | 0 | 0 | 0
2025-05-16 | 59660.0833 | 20539.74 | 59660.0833 | 14412.5 | 0 | 0 | 0 | 6127.24 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 60957.0417 | 20539.74 | 60957.0417 | 14412.5 | 0 | 0 | 0 | 6127.24 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 62254 | 20539.74 | 62254 | 14412.5 | 0 | 0 | 0 | 6127.24 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 63550.9583 | 21216.69 | 63550.9583 | 15089.45 | 0 | 0 | 0 | 6127.24 | 0 | 0 | 0 | 0 | 1296.9583 | 676.95 | 1296.9583 | 676.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 64847.9167 | 22943.36 | 64847.9167 | 15766.4 | 0 | 0 | 0 | 7176.96 | 0 | 0 | 0 | 0 | 1296.9583 | 1726.67 | 1296.9583 | 676.95 | 0 | 0 | 0 | 1049.72 | 0 | 0 | 0 | 0
2025-05-21 | 66144.875 | 23620.31 | 66144.875 | 16443.35 | 0 | 0 | 0 | 7176.96 | 0 | 0 | 0 | 0 | 1296.9583 | 676.95 | 1296.9583 | 676.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 67441.8333 | 24297.26 | 67441.8333 | 17120.3 | 0 | 0 | 0 | 7176.96 | 0 | 0 | 0 | 0 | 1296.9583 | 676.95 | 1296.9583 | 676.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 68738.7917 | 24974.21 | 68738.7917 | 17797.25 | 0 | 0 | 0 | 7176.96 | 0 | 0 | 0 | 0 | 1296.9583 | 676.95 | 1296.9583 | 676.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 70035.75 | 24974.21 | 70035.75 | 17797.25 | 0 | 0 | 0 | 7176.96 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 71332.7083 | 24974.21 | 71332.7083 | 17797.25 | 0 | 0 | 0 | 7176.96 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 72629.6667 | 24974.21 | 72629.6667 | 17797.25 | 0 | 0 | 0 | 7176.96 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 73926.625 | 24974.21 | 73926.625 | 17797.25 | 0 | 0 | 0 | 7176.96 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 75223.5833 | 24974.21 | 75223.5833 | 17797.25 | 0 | 0 | 0 | 7176.96 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 76520.5417 | 24974.21 | 76520.5417 | 17797.25 | 0 | 0 | 0 | 7176.96 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 77817.5 | 24974.21 | 77817.5 | 17797.25 | 0 | 0 | 0 | 7176.96 | 0 | 0 | 0 | 0 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 82127.8205 | 24974.21 | 77938.5843 | 17797.25 | 80.6747 | 0 | 1261.7398 | 7176.96 | 1405.3373 | 0 | 1441.4843 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-02 | 86438.141 | 24974.21 | 78059.6687 | 17797.25 | 161.3494 | 0 | 2523.4795 | 7176.96 | 2810.6747 | 0 | 2882.9687 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-03 | 90748.4614 | 24974.21 | 78180.753 | 17797.25 | 242.0241 | 0 | 3785.2193 | 7176.96 | 4216.012 | 0 | 4324.453 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-04 | 95058.7819 | 24994.13 | 78301.8373 | 17797.25 | 322.6988 | 0 | 5046.959 | 7196.88 | 5621.3494 | 0 | 5765.9373 | 0 | 4310.3205 | 19.92 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 19.92 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-05 | 99369.1024 | 51480.81 | 78422.9217 | 17797.25 | 403.3735 | 0 | 6308.6988 | 33683.56 | 7026.6867 | 0 | 7207.4217 | 0 | 4310.3205 | 26486.68 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 26486.68 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-06 | 103679.4229 | 51480.81 | 78544.006 | 17797.25 | 484.0482 | 0 | 7570.4386 | 33683.56 | 8432.0241 | 0 | 8648.906 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-07 | 107989.7434 | 51480.81 | 78665.0904 | 17797.25 | 564.7229 | 0 | 8832.1783 | 33683.56 | 9837.3614 | 0 | 10090.3904 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-08 | 112300.0639 | 51480.81 | 78786.1747 | 17797.25 | 645.3976 | 0 | 10093.9181 | 33683.56 | 11242.6988 | 0 | 11531.8747 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-09 | 116610.3843 | 51916.56 | 78907.259 | 18233 | 726.0723 | 0 | 11355.6578 | 33683.56 | 12648.0361 | 0 | 12973.359 | 0 | 4310.3205 | 435.75 | 121.0843 | 435.75 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-10 | 120920.7048 | 52352.31 | 79028.3434 | 18668.75 | 806.747 | 0 | 12617.3976 | 33683.56 | 14053.3735 | 0 | 14414.8434 | 0 | 4310.3205 | 435.75 | 121.0843 | 435.75 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-11 | 125231.0253 | 52788.06 | 79149.4277 | 19104.5 | 887.4217 | 0 | 13879.1373 | 33683.56 | 15458.7108 | 0 | 15856.3277 | 0 | 4310.3205 | 435.75 | 121.0843 | 435.75 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-12 | 129541.3458 | 53223.81 | 79270.512 | 19540.25 | 968.0964 | 0 | 15140.8771 | 33683.56 | 16864.0482 | 0 | 17297.812 | 0 | 4310.3205 | 435.75 | 121.0843 | 435.75 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-13 | 133851.6663 | 53659.56 | 79391.5964 | 19976 | 1048.7711 | 0 | 16402.6169 | 33683.56 | 18269.3855 | 0 | 18739.2964 | 0 | 4310.3205 | 435.75 | 121.0843 | 435.75 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-14 | 138161.9867 | 53659.56 | 79512.6807 | 19976 | 1129.4458 | 0 | 17664.3566 | 33683.56 | 19674.7229 | 0 | 20180.7807 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-15 | 142472.3072 | 53659.56 | 79633.7651 | 19976 | 1210.1205 | 0 | 18926.0964 | 33683.56 | 21080.0602 | 0 | 21622.2651 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-16 | 146782.6277 | 53927.56 | 79754.8494 | 20244 | 1290.7952 | 0 | 20187.8361 | 33683.56 | 22485.3976 | 0 | 23063.7494 | 0 | 4310.3205 | 268 | 121.0843 | 268 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-17 | 151092.9482 | 54195.56 | 79875.9337 | 20512 | 1371.4699 | 0 | 21449.5759 | 33683.56 | 23890.7349 | 0 | 24505.2337 | 0 | 4310.3205 | 268 | 121.0843 | 268 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-18 | 155403.2687 | 54463.56 | 79997.0181 | 20780 | 1452.1446 | 0 | 22711.3157 | 33683.56 | 25296.0723 | 0 | 25946.7181 | 0 | 4310.3205 | 268 | 121.0843 | 268 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-19 | 159713.5892 | 54731.56 | 80118.1024 | 21048 | 1532.8193 | 0 | 23973.0554 | 33683.56 | 26701.4096 | 0 | 27388.2024 | 0 | 4310.3205 | 268 | 121.0843 | 268 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-20 | 164023.9096 | 55582.06 | 80239.1867 | 21316 | 1613.494 | 0 | 25234.7952 | 33683.56 | 28106.747 | 582.5 | 28829.6867 | 0 | 4310.3205 | 850.5 | 121.0843 | 268 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 582.5 | 1441.4843 | 0
2025-06-21 | 168334.2301 | 55582.06 | 80360.2711 | 21316 | 1694.1687 | 0 | 26496.5349 | 33683.56 | 29512.0843 | 582.5 | 30271.1711 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-22 | 172644.5506 | 55582.06 | 80481.3554 | 21316 | 1774.8434 | 0 | 27758.2747 | 33683.56 | 30917.4217 | 582.5 | 31712.6554 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-23 | 176954.8711 | 55582.06 | 80602.4398 | 21316 | 1855.5181 | 0 | 29020.0145 | 33683.56 | 32322.759 | 582.5 | 33154.1398 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-24 | 181265.1916 | 56508.92 | 80723.5241 | 21316 | 1936.1928 | 679.86 | 30281.7542 | 33930.56 | 33728.0964 | 582.5 | 34595.6241 | 0 | 4310.3205 | 926.86 | 121.0843 | 0 | 80.6747 | 679.86 | 1261.7398 | 247 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-25 | 185575.512 | 56897.32 | 80844.6084 | 21316 | 2016.8675 | 679.86 | 31543.494 | 34318.96 | 35133.4337 | 582.5 | 36037.1084 | 0 | 4310.3205 | 388.4 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 388.4 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-26 | 189885.8325 | 56897.32 | 80965.6928 | 21316 | 2097.5422 | 679.86 | 32805.2337 | 34318.96 | 36538.7711 | 582.5 | 37478.5928 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-27 | 194196.153 | 56897.32 | 81086.7771 | 21316 | 2178.2169 | 679.86 | 34066.9735 | 34318.96 | 37944.1084 | 582.5 | 38920.0771 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-28 | 198506.4735 | 57009.59 | 81207.8614 | 21316 | 2258.8916 | 792.13 | 35328.7133 | 34318.96 | 39349.4458 | 582.5 | 40361.5614 | 0 | 4310.3205 | 112.27 | 121.0843 | 0 | 80.6747 | 112.27 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-29 | 202816.794 | 57158.34 | 81328.9458 | 21316 | 2339.5663 | 940.88 | 36590.453 | 34318.96 | 40754.7831 | 582.5 | 41803.0458 | 0 | 4310.3205 | 148.75 | 121.0843 | 0 | 80.6747 | 148.75 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-06-30 | 207127.1145 | 58142.27 | 81450.0301 | 22180.55 | 2420.241 | 1060.26 | 37852.1928 | 34318.96 | 42160.1205 | 582.5 | 43244.5301 | 0 | 4310.3205 | 983.93 | 121.0843 | 864.55 | 80.6747 | 119.38 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-01 | 211437.4349 | 97717.64 | 81571.1145 | 23045.1 | 2500.9157 | 1060.26 | 39113.9325 | 73029.78 | 43565.4578 | 582.5 | 44686.0145 | 0 | 4310.3205 | 39575.37 | 121.0843 | 864.55 | 80.6747 | 0 | 1261.7398 | 38710.82 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-02 | 215747.7554 | 98346.34 | 81692.1988 | 23909.65 | 2581.5904 | 1060.26 | 40375.6723 | 73029.78 | 44970.7952 | 346.65 | 46127.4988 | 0 | 4310.3205 | 628.7 | 121.0843 | 864.55 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | -235.85 | 1441.4843 | 0
2025-07-03 | 220058.0759 | 99293.47 | 81813.2831 | 24774.2 | 2662.2651 | 1060.26 | 41637.412 | 73112.36 | 46376.1325 | 346.65 | 47568.9831 | 0 | 4310.3205 | 947.13 | 121.0843 | 864.55 | 80.6747 | 0 | 1261.7398 | 82.58 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-04 | 224368.3964 | 100894.64 | 81934.3675 | 25638.75 | 2742.9398 | 1060.26 | 42899.1518 | 73398.98 | 47781.4699 | 796.65 | 49010.4675 | 0 | 4310.3205 | 1601.17 | 121.0843 | 864.55 | 80.6747 | 0 | 1261.7398 | 286.62 | 1405.3373 | 450 | 1441.4843 | 0
2025-07-05 | 228678.7169 | 100944.89 | 82055.4518 | 25638.75 | 2823.6145 | 1060.26 | 44160.8916 | 73449.23 | 49186.8072 | 796.65 | 50451.9518 | 0 | 4310.3205 | 50.25 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 50.25 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-06 | 232989.0373 | 100944.89 | 82176.5361 | 25638.75 | 2904.2892 | 1060.26 | 45422.6313 | 73449.23 | 50592.1446 | 796.65 | 51893.4361 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-07 | 237299.3578 | 101846.99 | 82297.6205 | 26359.75 | 2984.9639 | 1241.36 | 46684.3711 | 73449.23 | 51997.4819 | 796.65 | 53334.9205 | 0 | 4310.3205 | 902.1 | 121.0843 | 721 | 80.6747 | 181.1 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-08 | 241609.6783 | 103729.32 | 82418.7048 | 27080.75 | 3065.6386 | 1741.36 | 47946.1108 | 74110.56 | 53402.8193 | 796.65 | 54776.4048 | 0 | 4310.3205 | 1882.33 | 121.0843 | 721 | 80.6747 | 500 | 1261.7398 | 661.33 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-09 | 245919.9988 | 104543.02 | 82539.7892 | 27801.75 | 3146.3133 | 1741.36 | 49207.8506 | 74110.56 | 54808.1566 | 889.35 | 56217.8892 | 0 | 4310.3205 | 813.7 | 121.0843 | 721 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 92.7 | 1441.4843 | 0
2025-07-10 | 250230.3193 | 105321.91 | 82660.8735 | 28522.75 | 3226.988 | 1799.25 | 50469.5904 | 74110.56 | 56213.494 | 889.35 | 57659.3735 | 0 | 4310.3205 | 778.89 | 121.0843 | 721 | 80.6747 | 57.89 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-11 | 254540.6398 | 107932.14 | 82781.9578 | 29243.75 | 3307.6627 | 2100.37 | 51731.3301 | 75440.37 | 57618.8313 | 1147.65 | 59100.8578 | 0 | 4310.3205 | 2610.23 | 121.0843 | 721 | 80.6747 | 301.12 | 1261.7398 | 1329.81 | 1405.3373 | 258.3 | 1441.4843 | 0
2025-07-12 | 258850.9602 | 108366.26 | 82903.0422 | 29243.75 | 3388.3373 | 2534.49 | 52993.0699 | 75440.37 | 59024.1687 | 1147.65 | 60542.3422 | 0 | 4310.3205 | 434.12 | 121.0843 | 0 | 80.6747 | 434.12 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-13 | 263161.2807 | 113514.07 | 83024.1265 | 29243.75 | 3469.012 | 7516.12 | 54254.8096 | 75440.37 | 60429.506 | 1313.83 | 61983.8265 | 0 | 4310.3205 | 5147.81 | 121.0843 | 0 | 80.6747 | 4981.63 | 1261.7398 | 0 | 1405.3373 | 166.18 | 1441.4843 | 0
2025-07-14 | 267471.6012 | 121091.3 | 83145.2108 | 30919.15 | 3549.6867 | 8164.67 | 55516.5494 | 80693.65 | 61834.8434 | 1313.83 | 63425.3108 | 0 | 4310.3205 | 7577.23 | 121.0843 | 1675.4 | 80.6747 | 648.55 | 1261.7398 | 5253.28 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-15 | 271781.9217 | 122575.56 | 83266.2952 | 32594.55 | 3630.3614 | 6429.32 | 56778.2892 | 82115.91 | 63240.1807 | 1435.78 | 64866.7952 | 0 | 4310.3205 | 1484.26 | 121.0843 | 1675.4 | 80.6747 | -1735.35 | 1261.7398 | 1422.26 | 1405.3373 | 121.95 | 1441.4843 | 0
2025-07-16 | 276092.2422 | 131718.51 | 83387.3795 | 34269.95 | 3711.0361 | 6779.32 | 58040.0289 | 82933.46 | 64645.5181 | 7735.78 | 66308.2795 | 0 | 4310.3205 | 9142.95 | 121.0843 | 1675.4 | 80.6747 | 350 | 1261.7398 | 817.55 | 1405.3373 | 6300 | 1441.4843 | 0
2025-07-17 | 280402.5627 | 134232.71 | 83508.4639 | 35945.35 | 3791.7108 | 7054.51 | 59301.7687 | 83234.58 | 66050.8554 | 7998.27 | 67749.7639 | 0 | 4310.3205 | 2514.2 | 121.0843 | 1675.4 | 80.6747 | 275.19 | 1261.7398 | 301.12 | 1405.3373 | 262.49 | 1441.4843 | 0
2025-07-18 | 284712.8831 | 144540.3 | 83629.5482 | 37620.75 | 3872.3855 | 9214.51 | 60563.5084 | 89166.31 | 67456.1928 | 8538.73 | 69191.2482 | 0 | 4310.3205 | 10307.59 | 121.0843 | 1675.4 | 80.6747 | 2160 | 1261.7398 | 5931.73 | 1405.3373 | 540.46 | 1441.4843 | 0
2025-07-19 | 289023.2036 | 145375.29 | 83750.6325 | 37620.75 | 3953.0602 | 9257.81 | 61825.2482 | 89958 | 68861.5301 | 8538.73 | 70632.7325 | 0 | 4310.3205 | 834.99 | 121.0843 | 0 | 80.6747 | 43.3 | 1261.7398 | 791.69 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-20 | 293333.5241 | 145375.29 | 83871.7169 | 37620.75 | 4033.7349 | 9257.81 | 63086.988 | 89958 | 70266.8675 | 8538.73 | 72074.2169 | 0 | 4310.3205 | 0 | 121.0843 | 0 | 80.6747 | 0 | 1261.7398 | 0 | 1405.3373 | 0 | 1441.4843 | 0
2025-07-21 | 309238.0738 | 148394.69 | 85072.9989 | 39350.15 | 4659.4329 | 10547.81 | 65426.4488 | 89958 | 80563.492 | 8538.73 | 73515.7012 | 0 | 15904.5497 | 3019.4 | 1201.282 | 1729.4 | 625.698 | 1290 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-07-22 | 325142.6235 | 165392.7 | 86274.2809 | 41079.55 | 5285.1308 | 10413.49 | 67765.9096 | 105360.93 | 90860.1166 | 8538.73 | 74957.1855 | 0 | 15904.5497 | 16998.01 | 1201.282 | 1729.4 | 625.698 | -134.32 | 2339.4608 | 15402.93 | 10296.6246 | 0 | 1441.4843 | 0
2025-07-23 | 341047.1732 | 169815.02 | 87475.5629 | 42808.95 | 5910.8288 | 10233.49 | 70105.3704 | 108233.85 | 101156.7412 | 8538.73 | 76398.6699 | 0 | 15904.5497 | 4422.32 | 1201.282 | 1729.4 | 625.698 | -180 | 2339.4608 | 2872.92 | 10296.6246 | 0 | 1441.4843 | 0
2025-07-24 | 356951.7228 | 171918.8 | 88676.8449 | 44538.35 | 6536.5268 | 10353.38 | 72444.8312 | 108428.34 | 111453.3657 | 8598.73 | 77840.1542 | 0 | 15904.5497 | 2103.78 | 1201.282 | 1729.4 | 625.698 | 119.89 | 2339.4608 | 194.49 | 10296.6246 | 60 | 1441.4843 | 0
2025-07-25 | 372856.2725 | 175162.97 | 89878.1269 | 46267.75 | 7162.2247 | 11503.38 | 74784.292 | 108793.11 | 121749.9903 | 8598.73 | 79281.6386 | 0 | 15904.5497 | 3244.17 | 1201.282 | 1729.4 | 625.698 | 1150 | 2339.4608 | 364.77 | 10296.6246 | 0 | 1441.4843 | 0
2025-07-26 | 388760.8222 | 175193.72 | 91079.4089 | 46267.75 | 7787.9227 | 11503.38 | 77123.7528 | 108809.24 | 132046.6149 | 8613.35 | 80723.1229 | 0 | 15904.5497 | 30.75 | 1201.282 | 0 | 625.698 | 0 | 2339.4608 | 16.13 | 10296.6246 | 14.62 | 1441.4843 | 0
2025-07-27 | 404665.3719 | 175286.16 | 92280.6909 | 46267.75 | 8413.6206 | 11595.82 | 79463.2137 | 108809.24 | 142343.2394 | 8613.35 | 82164.6072 | 0 | 15904.5497 | 92.44 | 1201.282 | 0 | 625.698 | 92.44 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-07-28 | 420569.9216 | 177283.96 | 93481.973 | 48265.55 | 9039.3186 | 11595.82 | 81802.6745 | 108809.24 | 152639.864 | 8613.35 | 83606.0916 | 0 | 15904.5497 | 1997.8 | 1201.282 | 1997.8 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-07-29 | 436474.4713 | 179341.76 | 94683.255 | 50263.35 | 9665.0165 | 11655.82 | 84142.1353 | 108809.24 | 162936.4886 | 8613.35 | 85047.5759 | 0 | 15904.5497 | 2057.8 | 1201.282 | 1997.8 | 625.698 | 60 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-07-30 | 452379.021 | 188431.8 | 95884.537 | 52261.15 | 10290.7145 | 11655.82 | 86481.5961 | 110230.3 | 173233.1131 | 14284.53 | 86489.0602 | 0 | 15904.5497 | 9090.04 | 1201.282 | 1997.8 | 625.698 | 0 | 2339.4608 | 1421.06 | 10296.6246 | 5671.18 | 1441.4843 | 0
2025-07-31 | 468283.5707 | 216791.58 | 97085.819 | 54258.95 | 10916.4124 | 12076.98 | 88821.0569 | 110525.7 | 183529.7377 | 39929.95 | 87930.5446 | 0 | 15904.5497 | 28359.78 | 1201.282 | 1997.8 | 625.698 | 421.16 | 2339.4608 | 295.4 | 10296.6246 | 25645.42 | 1441.4843 | 0
2025-08-01 | 484188.1203 | 220336.48 | 98287.101 | 56256.75 | 11542.1104 | 13439.85 | 91160.5177 | 110709.93 | 193826.3623 | 39929.95 | 89372.0289 | 0 | 15904.5497 | 3544.9 | 1201.282 | 1997.8 | 625.698 | 1362.87 | 2339.4608 | 184.23 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-02 | 500092.67 | 221413.08 | 99488.383 | 56256.75 | 12167.8083 | 14516.45 | 93499.9786 | 110709.93 | 204122.9868 | 39929.95 | 90813.5133 | 0 | 15904.5497 | 1076.6 | 1201.282 | 0 | 625.698 | 1076.6 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-03 | 515997.2197 | 223444.63 | 100689.665 | 56256.75 | 12793.5063 | 16548 | 95839.4394 | 110709.93 | 214419.6114 | 39929.95 | 92254.9976 | 0 | 15904.5497 | 2031.55 | 1201.282 | 0 | 625.698 | 2031.55 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-04 | 531901.7694 | 225443.98 | 101890.947 | 58173.75 | 13419.2043 | 16548 | 98178.9002 | 110792.28 | 224716.236 | 39929.95 | 93696.4819 | 0 | 15904.5497 | 1999.35 | 1201.282 | 1917 | 625.698 | 0 | 2339.4608 | 82.35 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-05 | 547806.3191 | 230465.21 | 103092.2291 | 60090.75 | 14044.9022 | 16548 | 100518.361 | 110792.28 | 235012.8605 | 43034.18 | 95137.9663 | 0 | 15904.5497 | 5021.23 | 1201.282 | 1917 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 3104.23 | 1441.4843 | 0
2025-08-06 | 563710.8688 | 237289.65 | 104293.5111 | 62007.75 | 14670.6002 | 16548 | 102857.8218 | 110792.28 | 245309.4851 | 47941.62 | 96579.4506 | 0 | 15904.5497 | 6824.44 | 1201.282 | 1917 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 4907.44 | 1441.4843 | 0
2025-08-07 | 579615.4185 | 239206.65 | 105494.7931 | 63924.75 | 15296.2981 | 16548 | 105197.2826 | 110792.28 | 255606.1097 | 47941.62 | 98020.9349 | 0 | 15904.5497 | 1917 | 1201.282 | 1917 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-08 | 595519.9681 | 242873.65 | 106696.0751 | 65841.75 | 15921.9961 | 18298 | 107536.7435 | 110792.28 | 265902.7343 | 47941.62 | 99462.4193 | 0 | 15904.5497 | 3667 | 1201.282 | 1917 | 625.698 | 1750 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-09 | 611424.5178 | 242873.65 | 107897.3571 | 65841.75 | 16547.694 | 18298 | 109876.2043 | 110792.28 | 276199.3588 | 47941.62 | 100903.9036 | 0 | 15904.5497 | 0 | 1201.282 | 0 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-10 | 627329.0675 | 243797.13 | 109098.6391 | 65841.75 | 17173.392 | 19221.48 | 112215.6651 | 110792.28 | 286495.9834 | 47941.62 | 102345.388 | 0 | 15904.5497 | 923.48 | 1201.282 | 0 | 625.698 | 923.48 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-11 | 643233.6172 | 247231.03 | 110299.9211 | 68429.75 | 17799.0899 | 20067.38 | 114555.1259 | 110792.28 | 296792.608 | 47941.62 | 103786.8723 | 0 | 15904.5497 | 3433.9 | 1201.282 | 2588 | 625.698 | 845.9 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-12 | 659138.1669 | 251526.65 | 111501.2031 | 71017.75 | 18424.7879 | 20067.38 | 116894.5867 | 110792.28 | 307089.2325 | 49649.24 | 105228.3566 | 0 | 15904.5497 | 4295.62 | 1201.282 | 2588 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 1707.62 | 1441.4843 | 0
2025-08-13 | 675042.7166 | 254114.65 | 112702.4851 | 73605.75 | 19050.4859 | 20067.38 | 119234.0475 | 110792.28 | 317385.8571 | 49649.24 | 106669.841 | 0 | 15904.5497 | 2588 | 1201.282 | 2588 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-14 | 690947.2663 | 258114.6 | 113903.7672 | 76193.75 | 19676.1838 | 20067.38 | 121573.5083 | 110904.23 | 327682.4817 | 50949.24 | 108111.3253 | 0 | 15904.5497 | 3999.95 | 1201.282 | 2588 | 625.698 | 0 | 2339.4608 | 111.95 | 10296.6246 | 1300 | 1441.4843 | 0
2025-08-15 | 706851.816 | 263631.51 | 115105.0492 | 78781.75 | 20301.8818 | 21817.38 | 123912.9692 | 110987.22 | 337979.1062 | 52045.16 | 109552.8096 | 0 | 15904.5497 | 5516.91 | 1201.282 | 2588 | 625.698 | 1750 | 2339.4608 | 82.99 | 10296.6246 | 1095.92 | 1441.4843 | 0
2025-08-16 | 722756.3656 | 263631.51 | 116306.3312 | 78781.75 | 20927.5797 | 21817.38 | 126252.43 | 110987.22 | 348275.7308 | 52045.16 | 110994.294 | 0 | 15904.5497 | 0 | 1201.282 | 0 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-17 | 738660.9153 | 263631.51 | 117507.6132 | 78781.75 | 21553.2777 | 21817.38 | 128591.8908 | 110987.22 | 358572.3554 | 52045.16 | 112435.7783 | 0 | 15904.5497 | 0 | 1201.282 | 0 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-18 | 754565.465 | 266219.51 | 118708.8952 | 81369.75 | 22178.9756 | 21817.38 | 130931.3516 | 110987.22 | 368868.9799 | 52045.16 | 113877.2627 | 0 | 15904.5497 | 2588 | 1201.282 | 2588 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-19 | 770470.0147 | 271366.57 | 119910.1772 | 83957.75 | 22804.6736 | 21817.38 | 133270.8124 | 113546.28 | 379165.6045 | 52045.16 | 115318.747 | 0 | 15904.5497 | 5147.06 | 1201.282 | 2588 | 625.698 | 0 | 2339.4608 | 2559.06 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-20 | 786374.5644 | 277760.86 | 121111.4592 | 86545.75 | 23430.3715 | 21817.38 | 135610.2732 | 113546.28 | 389462.2291 | 55851.45 | 116760.2313 | 0 | 15904.5497 | 6394.29 | 1201.282 | 2588 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 3806.29 | 1441.4843 | 0
2025-08-21 | 802279.1141 | 280348.86 | 122312.7412 | 89133.75 | 24056.0695 | 21817.38 | 137949.7341 | 113546.28 | 399758.8536 | 55851.45 | 118201.7157 | 0 | 15904.5497 | 2588 | 1201.282 | 2588 | 625.698 | 0 | 2339.4608 | 0 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-22 | 818183.6638 | 296720.05 | 123514.0233 | 91721.75 | 24681.7674 | 22667.38 | 140289.1949 | 126479.47 | 410055.4782 | 55851.45 | 119643.2 | 0 | 15904.5497 | 16371.19 | 1201.282 | 2588 | 625.698 | 850 | 2339.4608 | 12933.19 | 10296.6246 | 0 | 1441.4843 | 0
2025-08-23 | 829777.893 | 296720.05 | 124594.2209 | 91721.75 | 25226.7907 | 22667.38 | 141366.9159 | 126479.47 | 418946.7654 | 55851.45 | 119643.2 | 0 | 11594.2292 | 0 | 1080.1977 | 0 | 545.0233 | 0 | 1077.7211 | 0 | 8891.2872 | 0 | 0 | 0
2025-08-24 | 841372.1222 | 296720.05 | 125674.4186 | 91721.75 | 25771.814 | 22667.38 | 142444.637 | 126479.47 | 427838.0526 | 55851.45 | 119643.2 | 0 | 11594.2292 | 0 | 1080.1977 | 0 | 545.0233 | 0 | 1077.7211 | 0 | 8891.2872 | 0 | 0 | 0
2025-08-25 | 852966.3514 | 356943.39 | 126754.6163 | 93867.35 | 26316.8372 | 22667.38 | 143522.358 | 127464.71 | 436729.3398 | 112943.95 | 119643.2 | 0 | 11594.2292 | 60223.34 | 1080.1977 | 2145.6 | 545.0233 | 0 | 1077.7211 | 985.24 | 8891.2872 | 57092.5 | 0 | 0
2025-08-26 | 864560.5806 | 358902.13 | 127834.814 | 96012.95 | 26861.8605 | 22667.38 | 144600.0791 | 127277.85 | 445620.6271 | 112943.95 | 119643.2 | 0 | 11594.2292 | 1958.74 | 1080.1977 | 2145.6 | 545.0233 | 0 | 1077.7211 | -186.86 | 8891.2872 | 0 | 0 | 0
2025-08-27 | 876154.8098 | 369442.4 | 128915.0116 | 98158.55 | 27406.8837 | 22667.38 | 145677.8002 | 127992.98 | 454511.9143 | 120623.49 | 119643.2 | 0 | 11594.2292 | 10540.27 | 1080.1977 | 2145.6 | 545.0233 | 0 | 1077.7211 | 715.13 | 8891.2872 | 7679.54 | 0 | 0
2025-08-28 | 887749.039 | 371588 | 129995.2093 | 100304.15 | 27951.907 | 22667.38 | 146755.5212 | 127992.98 | 463403.2015 | 120623.49 | 119643.2 | 0 | 11594.2292 | 2145.6 | 1080.1977 | 2145.6 | 545.0233 | 0 | 1077.7211 | 0 | 8891.2872 | 0 | 0 | 0
2025-08-29 | 899343.2682 | 376955.83 | 131075.407 | 102449.75 | 28496.9302 | 23017.38 | 147833.2423 | 128286.53 | 472294.4887 | 123202.17 | 119643.2 | 0 | 11594.2292 | 5367.83 | 1080.1977 | 2145.6 | 545.0233 | 350 | 1077.7211 | 293.55 | 8891.2872 | 2578.68 | 0 | 0
2025-08-30 | 910937.4974 | 376955.83 | 132155.6047 | 102449.75 | 29041.9535 | 23017.38 | 148910.9633 | 128286.53 | 481185.7759 | 123202.17 | 119643.2 | 0 | 11594.2292 | 0 | 1080.1977 | 0 | 545.0233 | 0 | 1077.7211 | 0 | 8891.2872 | 0 | 0 | 0
2025-08-31 | 922531.7266 | 393988.92 | 133235.8023 | 102449.75 | 29586.9767 | 23017.38 | 149988.6844 | 128286.53 | 490077.0632 | 140235.26 | 119643.2 | 0 | 11594.2292 | 17033.09 | 1080.1977 | 0 | 545.0233 | 0 | 1077.7211 | 0 | 8891.2872 | 17033.09 | 0 | 0
2025-09-01 | 934125.9558 | 395142.12 | 134316 | 103602.95 | 30132 | 23017.38 | 151066.4054 | 128286.53 | 498968.3504 | 140235.26 | 119643.2 | 0 | 11594.2292 | 1153.2 | 1080.1977 | 1153.2 | 545.0233 | 0 | 1077.7211 | 0 | 8891.2872 | 0 | 0 | 0
2025-09-02 | 937759.4474 | 399248.52 | 135894.5 | 104756.15 | 31052.7 | 23017.38 | 151512.6638 | 128566.7 | 499656.3836 | 142908.29 | 119643.2 | 0 | 3633.4916 | 4106.4 | 1578.5 | 1153.2 | 920.7 | 0 | 446.2583 | 280.17 | 688.0333 | 2673.03 | 0 | 0
2025-09-03 | 941392.939 | 657697.03 | 137473 | 105909.35 | 31973.4 | 23017.38 | 151958.9221 | 132429.51 | 500344.4169 | 396340.79 | 119643.2 | 0 | 3633.4916 | 258448.51 | 1578.5 | 1153.2 | 920.7 | 0 | 446.2583 | 3862.81 | 688.0333 | 253432.5 | 0 | 0
2025-09-04 | 945026.4306 | 658850.23 | 139051.5 | 107062.55 | 32894.1 | 23017.38 | 152405.1804 | 132429.51 | 501032.4502 | 396340.79 | 119643.2 | 0 | 3633.4916 | 1153.2 | 1578.5 | 1153.2 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-09-05 | 948659.9222 | 662908.1 | 140630 | 108215.75 | 33814.8 | 23367.38 | 152851.4388 | 132429.51 | 501720.4835 | 398895.46 | 119643.2 | 0 | 3633.4916 | 4057.87 | 1578.5 | 1153.2 | 920.7 | 350 | 446.2583 | 0 | 688.0333 | 2554.67 | 0 | 0
2025-09-06 | 952293.4138 | 662908.1 | 142208.5 | 108215.75 | 34735.5 | 23367.38 | 153297.6971 | 132429.51 | 502408.5167 | 398895.46 | 119643.2 | 0 | 3633.4916 | 0 | 1578.5 | 0 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-09-07 | 955926.9054 | 662908.1 | 143787 | 108215.75 | 35656.2 | 23367.38 | 153743.9554 | 132429.51 | 503096.55 | 398895.46 | 119643.2 | 0 | 3633.4916 | 0 | 1578.5 | 0 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-09-08 | 959560.397 | 667793.96 | 145365.5 | 110388.15 | 36576.9 | 23367.38 | 154190.2138 | 132429.51 | 503784.5833 | 401608.92 | 119643.2 | 0 | 3633.4916 | 4885.86 | 1578.5 | 2172.4 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 2713.46 | 0 | 0
2025-09-09 | 963193.8886 | 672094.83 | 146944 | 112560.55 | 37497.6 | 23367.38 | 154636.4721 | 132429.51 | 504472.6165 | 403737.39 | 119643.2 | 0 | 3633.4916 | 4300.87 | 1578.5 | 2172.4 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 2128.47 | 0 | 0
2025-09-10 | 966827.3802 | 674320.83 | 148522.5 | 114732.95 | 38418.3 | 23367.38 | 155082.7304 | 132483.11 | 505160.6498 | 403737.39 | 119643.2 | 0 | 3633.4916 | 2226 | 1578.5 | 2172.4 | 920.7 | 0 | 446.2583 | 53.6 | 688.0333 | 0 | 0 | 0
2025-09-11 | 970460.8718 | 677672.14 | 150101 | 116905.35 | 39339 | 23367.38 | 155528.9888 | 132566.1 | 505848.6831 | 404833.31 | 119643.2 | 0 | 3633.4916 | 3351.31 | 1578.5 | 2172.4 | 920.7 | 0 | 446.2583 | 82.99 | 688.0333 | 1095.92 | 0 | 0
2025-09-12 | 974094.3634 | 679844.54 | 151679.5 | 119077.75 | 40259.7 | 23367.38 | 155975.2471 | 132566.1 | 506536.7163 | 404833.31 | 119643.2 | 0 | 3633.4916 | 2172.4 | 1578.5 | 2172.4 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-09-13 | 977727.855 | 679844.54 | 153258 | 119077.75 | 41180.4 | 23367.38 | 156421.5054 | 132566.1 | 507224.7496 | 404833.31 | 119643.2 | 0 | 3633.4916 | 0 | 1578.5 | 0 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-09-14 | 981361.3466 | 679844.54 | 154836.5 | 119077.75 | 42101.1 | 23367.38 | 156867.7638 | 132566.1 | 507912.7829 | 404833.31 | 119643.2 | 0 | 3633.4916 | 0 | 1578.5 | 0 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-09-15 | 984994.8383 | 690486.745 | 156415 | 122835.025 | 43021.8 | 24817.38 | 157314.0221 | 132859.65 | 508600.8161 | 409974.69 | 119643.2 | 0 | 3633.4916 | 10642.205 | 1578.5 | 3757.275 | 920.7 | 1450 | 446.2583 | 293.55 | 688.0333 | 5141.38 | 0 | 0
2025-09-16 | 988628.3299 | 694244.02 | 157993.5 | 126592.3 | 43942.5 | 24817.38 | 157760.2804 | 132859.65 | 509288.8494 | 409974.69 | 119643.2 | 0 | 3633.4916 | 3757.275 | 1578.5 | 3757.275 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-09-17 | 992261.8215 | 698001.295 | 159572 | 130349.575 | 44863.2 | 24817.38 | 158206.5388 | 132859.65 | 509976.8827 | 409974.69 | 119643.2 | 0 | 3633.4916 | 3757.275 | 1578.5 | 3757.275 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-09-18 | 995895.3131 | 701758.57 | 161150.5 | 134106.85 | 45783.9 | 24817.38 | 158652.7971 | 132859.65 | 510664.916 | 409974.69 | 119643.2 | 0 | 3633.4916 | 3757.275 | 1578.5 | 3757.275 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-09-19 | 999528.8047 | 705515.845 | 162729 | 137864.125 | 46704.6 | 24817.38 | 159099.0554 | 132859.65 | 511352.9492 | 409974.69 | 119643.2 | 0 | 3633.4916 | 3757.275 | 1578.5 | 3757.275 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-09-20 | 1003162.2963 | 705515.845 | 164307.5 | 137864.125 | 47625.3 | 24817.38 | 159545.3138 | 132859.65 | 512040.9825 | 409974.69 | 119643.2 | 0 | 3633.4916 | 0 | 1578.5 | 0 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-09-21 | 1006795.7879 | 705515.845 | 165886 | 137864.125 | 48546 | 24817.38 | 159991.5721 | 132859.65 | 512729.0158 | 409974.69 | 119643.2 | 0 | 3633.4916 | 0 | 1578.5 | 0 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-09-22 | 1010429.2795 | 710497.495 | 167464.5 | 140095.775 | 49466.7 | 27567.38 | 160437.8304 | 132859.65 | 513417.049 | 409974.69 | 119643.2 | 0 | 3633.4916 | 4981.65 | 1578.5 | 2231.65 | 920.7 | 2750 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-09-23 | 1014062.7711 | 715601.375 | 169043 | 142327.425 | 50387.4 | 27567.38 | 160884.0888 | 133153.2 | 514105.0823 | 412553.37 | 119643.2 | 0 | 3633.4916 | 5103.88 | 1578.5 | 2231.65 | 920.7 | 0 | 446.2583 | 293.55 | 688.0333 | 2578.68 | 0 | 0
2025-09-24 | 1017696.2627 | 725606.915 | 170621.5 | 144559.075 | 51308.1 | 27567.38 | 161330.3471 | 133153.2 | 514793.1156 | 420327.26 | 119643.2 | 0 | 3633.4916 | 10005.54 | 1578.5 | 2231.65 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 7773.89 | 0 | 0
2025-09-25 | 1021329.7543 | 738099.225 | 172200 | 146790.725 | 52228.8 | 27567.38 | 161776.6054 | 133153.2 | 515481.1488 | 430587.92 | 119643.2 | 0 | 3633.4916 | 12492.31 | 1578.5 | 2231.65 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 10260.66 | 0 | 0
2025-09-26 | 1024963.2459 | 746028.535 | 173778.5 | 149022.375 | 53149.5 | 27567.38 | 162222.8638 | 133153.2 | 516169.1821 | 436285.58 | 119643.2 | 0 | 3633.4916 | 7929.31 | 1578.5 | 2231.65 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 5697.66 | 0 | 0
2025-09-27 | 1028596.7375 | 746028.535 | 175357 | 149022.375 | 54070.2 | 27567.38 | 162669.1221 | 133153.2 | 516857.2154 | 436285.58 | 119643.2 | 0 | 3633.4916 | 0 | 1578.5 | 0 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-09-28 | 1032230.2291 | 746028.535 | 176935.5 | 149022.375 | 54990.9 | 27567.38 | 163115.3804 | 133153.2 | 517545.2486 | 436285.58 | 119643.2 | 0 | 3633.4916 | 0 | 1578.5 | 0 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-09-29 | 1035863.7207 | 765107.57 | 178514 | 151532.35 | 55911.6 | 29317.38 | 163561.6388 | 133153.2 | 518233.2819 | 451104.64 | 119643.2 | 0 | 3633.4916 | 19079.035 | 1578.5 | 2509.975 | 920.7 | 1750 | 446.2583 | 0 | 688.0333 | 14819.06 | 0 | 0
2025-09-30 | 1039497.2123 | 772742.055 | 180092.5 | 154042.325 | 56832.3 | 29317.38 | 164007.8971 | 133153.2 | 518921.3152 | 456229.15 | 119643.2 | 0 | 3633.4916 | 7634.485 | 1578.5 | 2509.975 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 5124.51 | 0 | 0
2025-10-01 | 1043130.7039 | 775252.03 | 181671 | 156552.3 | 57753 | 29317.38 | 164454.1554 | 133153.2 | 519609.3485 | 456229.15 | 119643.2 | 0 | 3633.4916 | 2509.975 | 1578.5 | 2509.975 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-10-02 | 1046764.1955 | 777762.005 | 183249.5 | 159062.275 | 58673.7 | 29317.38 | 164900.4138 | 133153.2 | 520297.3817 | 456229.15 | 119643.2 | 0 | 3633.4916 | 2509.975 | 1578.5 | 2509.975 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-10-03 | 1050397.6871 | 782321.98 | 184828 | 161572.25 | 59594.4 | 31367.38 | 165346.6721 | 133153.2 | 520985.415 | 456229.15 | 119643.2 | 0 | 3633.4916 | 4559.975 | 1578.5 | 2509.975 | 920.7 | 2050 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-10-04 | 1054031.1787 | 786324.87 | 186406.5 | 161572.25 | 60515.1 | 31367.38 | 165792.9304 | 133153.2 | 521673.4483 | 460232.04 | 119643.2 | 0 | 3633.4916 | 4002.89 | 1578.5 | 0 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 4002.89 | 0 | 0
2025-10-05 | 1057664.6703 | 786324.87 | 187985 | 161572.25 | 61435.8 | 31367.38 | 166239.1888 | 133153.2 | 522361.4815 | 460232.04 | 119643.2 | 0 | 3633.4916 | 0 | 1578.5 | 0 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-10-06 | 1061298.1619 | 787347.045 | 189563.5 | 162594.425 | 62356.5 | 31367.38 | 166685.4471 | 133153.2 | 523049.5148 | 460232.04 | 119643.2 | 0 | 3633.4916 | 1022.175 | 1578.5 | 1022.175 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-10-07 | 1064931.6535 | 789791.81 | 191142 | 163616.6 | 63277.2 | 31367.38 | 167131.7054 | 133153.2 | 523737.5481 | 461654.63 | 119643.2 | 0 | 3633.4916 | 2444.765 | 1578.5 | 1022.175 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 1422.59 | 0 | 0
2025-10-08 | 1068565.1451 | 790813.985 | 192720.5 | 164638.775 | 64197.9 | 31367.38 | 167577.9638 | 133153.2 | 524425.5813 | 461654.63 | 119643.2 | 0 | 3633.4916 | 1022.175 | 1578.5 | 1022.175 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-10-09 | 1072198.6367 | 791836.16 | 194299 | 165660.95 | 65118.6 | 31367.38 | 168024.2221 | 133153.2 | 525113.6146 | 461654.63 | 119643.2 | 0 | 3633.4916 | 1022.175 | 1578.5 | 1022.175 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-10-10 | 1075832.1283 | 792858.335 | 195877.5 | 166683.125 | 66039.3 | 31367.38 | 168470.4804 | 133153.2 | 525801.6479 | 461654.63 | 119643.2 | 0 | 3633.4916 | 1022.175 | 1578.5 | 1022.175 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-10-11 | 1079465.6199 | 792858.335 | 197456 | 166683.125 | 66960 | 31367.38 | 168916.7388 | 133153.2 | 526489.6811 | 461654.63 | 119643.2 | 0 | 3633.4916 | 0 | 1578.5 | 0 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-10-12 | 1083099.1115 | 792858.335 | 199034.5 | 166683.125 | 67880.7 | 31367.38 | 169362.9971 | 133153.2 | 527177.7144 | 461654.63 | 119643.2 | 0 | 3633.4916 | 0 | 1578.5 | 0 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-10-13 | 1086732.6031 | 794885.51 | 200613 | 168710.3 | 68801.4 | 31367.38 | 169809.2554 | 133153.2 | 527865.7477 | 461654.63 | 119643.2 | 0 | 3633.4916 | 2027.175 | 1578.5 | 2027.175 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-10-14 | 1090366.0947 | 797262.685 | 202191.5 | 170737.475 | 69722.1 | 31717.38 | 170255.5138 | 133153.2 | 528553.781 | 461654.63 | 119643.2 | 0 | 3633.4916 | 2377.175 | 1578.5 | 2027.175 | 920.7 | 350 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-10-15 | 1093999.5863 | 799289.86 | 203770 | 172764.65 | 70642.8 | 31717.38 | 170701.7721 | 133153.2 | 529241.8142 | 461654.63 | 119643.2 | 0 | 3633.4916 | 2027.175 | 1578.5 | 2027.175 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-10-16 | 1097633.0779 | 801317.035 | 205348.5 | 174791.825 | 71563.5 | 31717.38 | 171148.0304 | 133153.2 | 529929.8475 | 461654.63 | 119643.2 | 0 | 3633.4916 | 2027.175 | 1578.5 | 2027.175 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-10-17 | 1101266.5695 | 804344.21 | 206927 | 176819 | 72484.2 | 32717.38 | 171594.2888 | 133153.2 | 530617.8808 | 461654.63 | 119643.2 | 0 | 3633.4916 | 3027.175 | 1578.5 | 2027.175 | 920.7 | 1000 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-10-18 | 1104900.0611 | 804344.21 | 208505.5 | 176819 | 73404.9 | 32717.38 | 172040.5471 | 133153.2 | 531305.914 | 461654.63 | 119643.2 | 0 | 3633.4916 | 0 | 1578.5 | 0 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-10-19 | 1108533.5527 | 804344.21 | 210084 | 176819 | 74325.6 | 32717.38 | 172486.8054 | 133153.2 | 531993.9473 | 461654.63 | 119643.2 | 0 | 3633.4916 | 0 | 1578.5 | 0 | 920.7 | 0 | 446.2583 | 0 | 688.0333 | 0 | 0 | 0
2025-10-20 | 1112167.0443 |  | 211662.5 |  | 75246.3 |  | 172933.0638 |  | 532681.9806 |  | 119643.2 |  | 3633.4916 |  | 1578.5 |  | 920.7 |  | 446.2583 |  | 688.0333 |  | 0
2025-10-21 | 1115800.5359 |  | 213241 |  | 76167 |  | 173379.3221 |  | 533370.0138 |  | 119643.2 |  | 3633.4916 |  | 1578.5 |  | 920.7 |  | 446.2583 |  | 688.0333 |  | 0
2025-10-22 | 1119434.0275 |  | 214819.5 |  | 77087.7 |  | 173825.5804 |  | 534058.0471 |  | 119643.2 |  | 3633.4916 |  | 1578.5 |  | 920.7 |  | 446.2583 |  | 688.0333 |  | 0
2025-10-23 | 1123067.5191 |  | 216398 |  | 78008.4 |  | 174271.8388 |  | 534746.0804 |  | 119643.2 |  | 3633.4916 |  | 1578.5 |  | 920.7 |  | 446.2583 |  | 688.0333 |  | 0
2025-10-24 | 1126701.0108 |  | 217976.5 |  | 78929.1 |  | 174718.0971 |  | 535434.1136 |  | 119643.2 |  | 3633.4916 |  | 1578.5 |  | 920.7 |  | 446.2583 |  | 688.0333 |  | 0
2025-10-25 | 1130334.5024 |  | 219555 |  | 79849.8 |  | 175164.3554 |  | 536122.1469 |  | 119643.2 |  | 3633.4916 |  | 1578.5 |  | 920.7 |  | 446.2583 |  | 688.0333 |  | 0
2025-10-26 | 1133967.994 |  | 221133.5 |  | 80770.5 |  | 175610.6138 |  | 536810.1802 |  | 119643.2 |  | 3633.4916 |  | 1578.5 |  | 920.7 |  | 446.2583 |  | 688.0333 |  | 0
2025-10-27 | 1137601.4856 |  | 222712 |  | 81691.2 |  | 176056.8721 |  | 537498.2135 |  | 119643.2 |  | 3633.4916 |  | 1578.5 |  | 920.7 |  | 446.2583 |  | 688.0333 |  | 0
2025-10-28 | 1141234.9772 |  | 224290.5 |  | 82611.9 |  | 176503.1304 |  | 538186.2467 |  | 119643.2 |  | 3633.4916 |  | 1578.5 |  | 920.7 |  | 446.2583 |  | 688.0333 |  | 0
2025-10-29 | 1144868.4688 |  | 225869 |  | 83532.6 |  | 176949.3888 |  | 538874.28 |  | 119643.2 |  | 3633.4916 |  | 1578.5 |  | 920.7 |  | 446.2583 |  | 688.0333 |  | 0
2025-10-30 | 1148501.9604 |  | 227447.5 |  | 84453.3 |  | 177395.6471 |  | 539562.3133 |  | 119643.2 |  | 3633.4916 |  | 1578.5 |  | 920.7 |  | 446.2583 |  | 688.0333 |  | 0
2025-10-31 | 1152135.452 |  | 229026 |  | 85374 |  | 177841.9054 |  | 540250.3465 |  | 119643.2 |  | 3633.4916 |  | 1578.5 |  | 920.7 |  | 446.2583 |  | 688.0333 |  | 0
2025-11-03 | 1154322.7591 |  | 230328.4857 |  | 86038.9798 |  | 177841.9054 |  | 540470.1882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-04 | 1156510.0662 |  | 231630.9714 |  | 86703.9595 |  | 177841.9054 |  | 540690.0299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-05 | 1158697.3733 |  | 232933.4571 |  | 87368.9393 |  | 177841.9054 |  | 540909.8715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-06 | 1160884.6805 |  | 234235.9428 |  | 88033.919 |  | 177841.9054 |  | 541129.7132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-07 | 1163071.9876 |  | 235538.4285 |  | 88698.8988 |  | 177841.9054 |  | 541349.5549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-08 | 1165259.2947 |  | 236840.9142 |  | 89363.8786 |  | 177841.9054 |  | 541569.3965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-09 | 1167446.6019 |  | 238143.3999 |  | 90028.8583 |  | 177841.9054 |  | 541789.2382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-10 | 1169633.909 |  | 239445.8856 |  | 90693.8381 |  | 177841.9054 |  | 542009.0799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-11 | 1171821.2161 |  | 240748.3713 |  | 91358.8178 |  | 177841.9054 |  | 542228.9215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-12 | 1174008.5232 |  | 242050.857 |  | 92023.7976 |  | 177841.9054 |  | 542448.7632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-13 | 1176195.8304 |  | 243353.3427 |  | 92688.7774 |  | 177841.9054 |  | 542668.6049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-14 | 1178383.1375 |  | 244655.8284 |  | 93353.7571 |  | 177841.9054 |  | 542888.4465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-15 | 1180570.4446 |  | 245958.3141 |  | 94018.7369 |  | 177841.9054 |  | 543108.2882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-16 | 1182757.7517 |  | 247260.7998 |  | 94683.7166 |  | 177841.9054 |  | 543328.1299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-17 | 1184945.0589 |  | 248563.2855 |  | 95348.6964 |  | 177841.9054 |  | 543547.9715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-18 | 1187132.366 |  | 249865.7712 |  | 96013.6762 |  | 177841.9054 |  | 543767.8132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-19 | 1189319.6731 |  | 251168.2569 |  | 96678.6559 |  | 177841.9054 |  | 543987.6549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-20 | 1191506.9802 |  | 252470.7426 |  | 97343.6357 |  | 177841.9054 |  | 544207.4965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-21 | 1193694.2874 |  | 253773.2283 |  | 98008.6154 |  | 177841.9054 |  | 544427.3382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-22 | 1195881.5945 |  | 255075.714 |  | 98673.5952 |  | 177841.9054 |  | 544647.1799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-23 | 1198068.9016 |  | 256378.1997 |  | 99338.575 |  | 177841.9054 |  | 544867.0215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-24 | 1200256.2088 |  | 257680.6854 |  | 100003.5547 |  | 177841.9054 |  | 545086.8632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-25 | 1202443.5159 |  | 258983.1711 |  | 100668.5345 |  | 177841.9054 |  | 545306.7049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-26 | 1204630.823 |  | 260285.6568 |  | 101333.5142 |  | 177841.9054 |  | 545526.5465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-27 | 1206818.1301 |  | 261588.1425 |  | 101998.494 |  | 177841.9054 |  | 545746.3882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-28 | 1209005.4373 |  | 262890.6282 |  | 102663.4738 |  | 177841.9054 |  | 545966.2299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-29 | 1211192.7444 |  | 264193.1139 |  | 103328.4535 |  | 177841.9054 |  | 546186.0715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-11-30 | 1213380.0515 |  | 265495.5996 |  | 103993.4333 |  | 177841.9054 |  | 546405.9132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-01 | 1215567.3586 |  | 266798.0853 |  | 104658.413 |  | 177841.9054 |  | 546625.7549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-02 | 1217754.6658 |  | 268100.571 |  | 105323.3928 |  | 177841.9054 |  | 546845.5965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-03 | 1219941.9729 |  | 269403.0567 |  | 105988.3726 |  | 177841.9054 |  | 547065.4382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-04 | 1222129.28 |  | 270705.5424 |  | 106653.3523 |  | 177841.9054 |  | 547285.2799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-05 | 1224316.5871 |  | 272008.0281 |  | 107318.3321 |  | 177841.9054 |  | 547505.1215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-06 | 1226503.8943 |  | 273310.5138 |  | 107983.3118 |  | 177841.9054 |  | 547724.9632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-07 | 1228691.2014 |  | 274612.9995 |  | 108648.2916 |  | 177841.9054 |  | 547944.8049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-08 | 1230878.5085 |  | 275915.4852 |  | 109313.2714 |  | 177841.9054 |  | 548164.6465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-09 | 1233065.8157 |  | 277217.9709 |  | 109978.2511 |  | 177841.9054 |  | 548384.4882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-10 | 1235253.1228 |  | 278520.4566 |  | 110643.2309 |  | 177841.9054 |  | 548604.3299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-11 | 1237440.4299 |  | 279822.9423 |  | 111308.2106 |  | 177841.9054 |  | 548824.1715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-12 | 1239627.737 |  | 281125.428 |  | 111973.1904 |  | 177841.9054 |  | 549044.0132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-13 | 1241815.0442 |  | 282427.9137 |  | 112638.1702 |  | 177841.9054 |  | 549263.8549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-14 | 1244002.3513 |  | 283730.3994 |  | 113303.1499 |  | 177841.9054 |  | 549483.6965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-15 | 1246189.6584 |  | 285032.8851 |  | 113968.1297 |  | 177841.9054 |  | 549703.5382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-16 | 1248376.9655 |  | 286335.3708 |  | 114633.1094 |  | 177841.9054 |  | 549923.3799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-17 | 1250564.2727 |  | 287637.8565 |  | 115298.0892 |  | 177841.9054 |  | 550143.2215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-18 | 1252751.5798 |  | 288940.3422 |  | 115963.069 |  | 177841.9054 |  | 550363.0632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-19 | 1254938.8869 |  | 290242.8279 |  | 116628.0487 |  | 177841.9054 |  | 550582.9049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-20 | 1257126.194 |  | 291545.3136 |  | 117293.0285 |  | 177841.9054 |  | 550802.7465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-21 | 1259313.5012 |  | 292847.7993 |  | 117958.0082 |  | 177841.9054 |  | 551022.5882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-22 | 1261500.8083 |  | 294150.285 |  | 118622.988 |  | 177841.9054 |  | 551242.4299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-23 | 1263688.1154 |  | 295452.7707 |  | 119287.9678 |  | 177841.9054 |  | 551462.2715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-24 | 1265875.4226 |  | 296755.2564 |  | 119952.9475 |  | 177841.9054 |  | 551682.1132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-25 | 1268062.7297 |  | 298057.7421 |  | 120617.9273 |  | 177841.9054 |  | 551901.9549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-26 | 1270250.0368 |  | 299360.2278 |  | 121282.907 |  | 177841.9054 |  | 552121.7965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-27 | 1272437.3439 |  | 300662.7135 |  | 121947.8868 |  | 177841.9054 |  | 552341.6382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-28 | 1274624.6511 |  | 301965.1992 |  | 122612.8666 |  | 177841.9054 |  | 552561.4799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-29 | 1276811.9582 |  | 303267.6849 |  | 123277.8463 |  | 177841.9054 |  | 552781.3215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-30 | 1278999.2653 |  | 304570.1706 |  | 123942.8261 |  | 177841.9054 |  | 553001.1632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2025-12-31 | 1281186.5724 |  | 305872.6563 |  | 124607.8058 |  | 177841.9054 |  | 553221.0049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-01 | 1283373.8796 |  | 307175.142 |  | 125272.7856 |  | 177841.9054 |  | 553440.8465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-02 | 1285561.1867 |  | 308477.6277 |  | 125937.7654 |  | 177841.9054 |  | 553660.6882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-03 | 1287748.4938 |  | 309780.1134 |  | 126602.7451 |  | 177841.9054 |  | 553880.5299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-04 | 1289935.8009 |  | 311082.5991 |  | 127267.7249 |  | 177841.9054 |  | 554100.3715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-05 | 1292123.1081 |  | 312385.0848 |  | 127932.7046 |  | 177841.9054 |  | 554320.2132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-06 | 1294310.4152 |  | 313687.5705 |  | 128597.6844 |  | 177841.9054 |  | 554540.0549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-07 | 1296497.7223 |  | 314990.0562 |  | 129262.6642 |  | 177841.9054 |  | 554759.8965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-08 | 1298685.0295 |  | 316292.5419 |  | 129927.6439 |  | 177841.9054 |  | 554979.7382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-09 | 1300872.3366 |  | 317595.0276 |  | 130592.6237 |  | 177841.9054 |  | 555199.5799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-10 | 1303059.6437 |  | 318897.5133 |  | 131257.6034 |  | 177841.9054 |  | 555419.4215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-11 | 1305246.9508 |  | 320199.999 |  | 131922.5832 |  | 177841.9054 |  | 555639.2632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-12 | 1307434.258 |  | 321502.4847 |  | 132587.563 |  | 177841.9054 |  | 555859.1049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-13 | 1309621.5651 |  | 322804.9704 |  | 133252.5427 |  | 177841.9054 |  | 556078.9465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-14 | 1311808.8722 |  | 324107.4561 |  | 133917.5225 |  | 177841.9054 |  | 556298.7882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-15 | 1313996.1793 |  | 325409.9418 |  | 134582.5022 |  | 177841.9054 |  | 556518.6299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-16 | 1316183.4865 |  | 326712.4275 |  | 135247.482 |  | 177841.9054 |  | 556738.4715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-17 | 1318370.7936 |  | 328014.9132 |  | 135912.4618 |  | 177841.9054 |  | 556958.3132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-18 | 1320558.1007 |  | 329317.3989 |  | 136577.4415 |  | 177841.9054 |  | 557178.1549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-19 | 1322745.4078 |  | 330619.8846 |  | 137242.4213 |  | 177841.9054 |  | 557397.9965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-20 | 1324932.715 |  | 331922.3703 |  | 137907.401 |  | 177841.9054 |  | 557617.8382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-21 | 1327120.0221 |  | 333224.856 |  | 138572.3808 |  | 177841.9054 |  | 557837.6799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-22 | 1329307.3292 |  | 334527.3417 |  | 139237.3606 |  | 177841.9054 |  | 558057.5215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-23 | 1331494.6364 |  | 335829.8274 |  | 139902.3403 |  | 177841.9054 |  | 558277.3632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-24 | 1333681.9435 |  | 337132.3131 |  | 140567.3201 |  | 177841.9054 |  | 558497.2049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-25 | 1335869.2506 |  | 338434.7988 |  | 141232.2998 |  | 177841.9054 |  | 558717.0465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-26 | 1338056.5577 |  | 339737.2845 |  | 141897.2796 |  | 177841.9054 |  | 558936.8882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-27 | 1340243.8649 |  | 341039.7702 |  | 142562.2594 |  | 177841.9054 |  | 559156.7299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-28 | 1342431.172 |  | 342342.2559 |  | 143227.2391 |  | 177841.9054 |  | 559376.5715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-29 | 1344618.4791 |  | 343644.7416 |  | 143892.2189 |  | 177841.9054 |  | 559596.4132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-30 | 1346805.7862 |  | 344947.2273 |  | 144557.1986 |  | 177841.9054 |  | 559816.2549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-01-31 | 1348993.0934 |  | 346249.713 |  | 145222.1784 |  | 177841.9054 |  | 560036.0965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-01 | 1351180.4005 |  | 347552.1987 |  | 145887.1582 |  | 177841.9054 |  | 560255.9382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-02 | 1353367.7076 |  | 348854.6844 |  | 146552.1379 |  | 177841.9054 |  | 560475.7799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-03 | 1355555.0147 |  | 350157.1701 |  | 147217.1177 |  | 177841.9054 |  | 560695.6215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-04 | 1357742.3219 |  | 351459.6558 |  | 147882.0974 |  | 177841.9054 |  | 560915.4632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-05 | 1359929.629 |  | 352762.1415 |  | 148547.0772 |  | 177841.9054 |  | 561135.3049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-06 | 1362116.9361 |  | 354064.6272 |  | 149212.057 |  | 177841.9054 |  | 561355.1465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-07 | 1364304.2433 |  | 355367.1129 |  | 149877.0367 |  | 177841.9054 |  | 561574.9882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-08 | 1366491.5504 |  | 356669.5986 |  | 150542.0165 |  | 177841.9054 |  | 561794.8299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-09 | 1368678.8575 |  | 357972.0843 |  | 151206.9962 |  | 177841.9054 |  | 562014.6715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-10 | 1370866.1646 |  | 359274.57 |  | 151871.976 |  | 177841.9054 |  | 562234.5132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-11 | 1373053.4718 |  | 360577.0557 |  | 152536.9558 |  | 177841.9054 |  | 562454.3549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-12 | 1375240.7789 |  | 361879.5414 |  | 153201.9355 |  | 177841.9054 |  | 562674.1965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-13 | 1377428.086 |  | 363182.0271 |  | 153866.9153 |  | 177841.9054 |  | 562894.0382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-14 | 1379615.3931 |  | 364484.5128 |  | 154531.895 |  | 177841.9054 |  | 563113.8799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-15 | 1381802.7003 |  | 365786.9985 |  | 155196.8748 |  | 177841.9054 |  | 563333.7215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-16 | 1383990.0074 |  | 367089.4842 |  | 155861.8546 |  | 177841.9054 |  | 563553.5632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-17 | 1386177.3145 |  | 368391.9699 |  | 156526.8343 |  | 177841.9054 |  | 563773.4049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-18 | 1388364.6216 |  | 369694.4556 |  | 157191.8141 |  | 177841.9054 |  | 563993.2465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-19 | 1390551.9288 |  | 370996.9413 |  | 157856.7938 |  | 177841.9054 |  | 564213.0882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-20 | 1392739.2359 |  | 372299.427 |  | 158521.7736 |  | 177841.9054 |  | 564432.9299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-21 | 1394926.543 |  | 373601.9127 |  | 159186.7534 |  | 177841.9054 |  | 564652.7715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-22 | 1397113.8502 |  | 374904.3984 |  | 159851.7331 |  | 177841.9054 |  | 564872.6132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-23 | 1399301.1573 |  | 376206.8841 |  | 160516.7129 |  | 177841.9054 |  | 565092.4549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-24 | 1401488.4644 |  | 377509.3698 |  | 161181.6926 |  | 177841.9054 |  | 565312.2965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-25 | 1403675.7715 |  | 378811.8555 |  | 161846.6724 |  | 177841.9054 |  | 565532.1382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-26 | 1405863.0787 |  | 380114.3412 |  | 162511.6522 |  | 177841.9054 |  | 565751.9799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-27 | 1408050.3858 |  | 381416.8269 |  | 163176.6319 |  | 177841.9054 |  | 565971.8215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-02-28 | 1410237.6929 |  | 382719.3126 |  | 163841.6117 |  | 177841.9054 |  | 566191.6632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-01 | 1412425 |  | 384021.7983 |  | 164506.5914 |  | 177841.9054 |  | 566411.5049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-02 | 1414612.3072 |  | 385324.284 |  | 165171.5712 |  | 177841.9054 |  | 566631.3465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-03 | 1416799.6143 |  | 386626.7697 |  | 165836.551 |  | 177841.9054 |  | 566851.1882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-04 | 1418986.9214 |  | 387929.2554 |  | 166501.5307 |  | 177841.9054 |  | 567071.0299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-05 | 1421174.2285 |  | 389231.7411 |  | 167166.5105 |  | 177841.9054 |  | 567290.8715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-06 | 1423361.5357 |  | 390534.2268 |  | 167831.4902 |  | 177841.9054 |  | 567510.7132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-07 | 1425548.8428 |  | 391836.7125 |  | 168496.47 |  | 177841.9054 |  | 567730.5549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-08 | 1427736.1499 |  | 393139.1982 |  | 169161.4498 |  | 177841.9054 |  | 567950.3965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-09 | 1429923.4571 |  | 394441.6839 |  | 169826.4295 |  | 177841.9054 |  | 568170.2382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-10 | 1432110.7642 |  | 395744.1696 |  | 170491.4093 |  | 177841.9054 |  | 568390.0799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-11 | 1434298.0713 |  | 397046.6553 |  | 171156.389 |  | 177841.9054 |  | 568609.9215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-12 | 1436485.3784 |  | 398349.141 |  | 171821.3688 |  | 177841.9054 |  | 568829.7632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-13 | 1438672.6856 |  | 399651.6267 |  | 172486.3486 |  | 177841.9054 |  | 569049.6049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-14 | 1440859.9927 |  | 400954.1124 |  | 173151.3283 |  | 177841.9054 |  | 569269.4465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-15 | 1443047.2998 |  | 402256.5981 |  | 173816.3081 |  | 177841.9054 |  | 569489.2882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-16 | 1445234.6069 |  | 403559.0838 |  | 174481.2878 |  | 177841.9054 |  | 569709.1299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-17 | 1447421.9141 |  | 404861.5695 |  | 175146.2676 |  | 177841.9054 |  | 569928.9715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-18 | 1449609.2212 |  | 406164.0552 |  | 175811.2474 |  | 177841.9054 |  | 570148.8132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-19 | 1451796.5283 |  | 407466.5409 |  | 176476.2271 |  | 177841.9054 |  | 570368.6549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-20 | 1453983.8354 |  | 408769.0266 |  | 177141.2069 |  | 177841.9054 |  | 570588.4965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-21 | 1456171.1426 |  | 410071.5123 |  | 177806.1866 |  | 177841.9054 |  | 570808.3382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-22 | 1458358.4497 |  | 411373.998 |  | 178471.1664 |  | 177841.9054 |  | 571028.1799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-23 | 1460545.7568 |  | 412676.4837 |  | 179136.1462 |  | 177841.9054 |  | 571248.0215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-24 | 1462733.064 |  | 413978.9694 |  | 179801.1259 |  | 177841.9054 |  | 571467.8632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-25 | 1464920.3711 |  | 415281.4551 |  | 180466.1057 |  | 177841.9054 |  | 571687.7049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-26 | 1467107.6782 |  | 416583.9408 |  | 181131.0854 |  | 177841.9054 |  | 571907.5465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-27 | 1469294.9853 |  | 417886.4265 |  | 181796.0652 |  | 177841.9054 |  | 572127.3882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-28 | 1471482.2925 |  | 419188.9122 |  | 182461.045 |  | 177841.9054 |  | 572347.2299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-29 | 1473669.5996 |  | 420491.3979 |  | 183126.0247 |  | 177841.9054 |  | 572567.0715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-30 | 1475856.9067 |  | 421793.8836 |  | 183791.0045 |  | 177841.9054 |  | 572786.9132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-03-31 | 1478044.2138 |  | 423096.3693 |  | 184455.9842 |  | 177841.9054 |  | 573006.7549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-01 | 1480231.521 |  | 424398.855 |  | 185120.964 |  | 177841.9054 |  | 573226.5965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-02 | 1482418.8281 |  | 425701.3407 |  | 185785.9438 |  | 177841.9054 |  | 573446.4382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-03 | 1484606.1352 |  | 427003.8264 |  | 186450.9235 |  | 177841.9054 |  | 573666.2799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-04 | 1486793.4423 |  | 428306.3121 |  | 187115.9033 |  | 177841.9054 |  | 573886.1215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-05 | 1488980.7495 |  | 429608.7978 |  | 187780.883 |  | 177841.9054 |  | 574105.9632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-06 | 1491168.0566 |  | 430911.2835 |  | 188445.8628 |  | 177841.9054 |  | 574325.8049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-07 | 1493355.3637 |  | 432213.7692 |  | 189110.8426 |  | 177841.9054 |  | 574545.6465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-08 | 1495542.6709 |  | 433516.2549 |  | 189775.8223 |  | 177841.9054 |  | 574765.4882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-09 | 1497729.978 |  | 434818.7406 |  | 190440.8021 |  | 177841.9054 |  | 574985.3299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-10 | 1499917.2851 |  | 436121.2263 |  | 191105.7818 |  | 177841.9054 |  | 575205.1715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-11 | 1502104.5922 |  | 437423.712 |  | 191770.7616 |  | 177841.9054 |  | 575425.0132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-12 | 1504291.8994 |  | 438726.1977 |  | 192435.7414 |  | 177841.9054 |  | 575644.8549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-13 | 1506479.2065 |  | 440028.6834 |  | 193100.7211 |  | 177841.9054 |  | 575864.6965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-14 | 1508666.5136 |  | 441331.1691 |  | 193765.7009 |  | 177841.9054 |  | 576084.5382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-15 | 1510853.8207 |  | 442633.6548 |  | 194430.6806 |  | 177841.9054 |  | 576304.3799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-16 | 1513041.1279 |  | 443936.1405 |  | 195095.6604 |  | 177841.9054 |  | 576524.2215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-17 | 1515228.435 |  | 445238.6262 |  | 195760.6402 |  | 177841.9054 |  | 576744.0632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-18 | 1517415.7421 |  | 446541.1119 |  | 196425.6199 |  | 177841.9054 |  | 576963.9049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-19 | 1519603.0492 |  | 447843.5976 |  | 197090.5997 |  | 177841.9054 |  | 577183.7465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-20 | 1521790.3564 |  | 449146.0833 |  | 197755.5794 |  | 177841.9054 |  | 577403.5882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-21 | 1523977.6635 |  | 450448.569 |  | 198420.5592 |  | 177841.9054 |  | 577623.4299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-22 | 1526164.9706 |  | 451751.0547 |  | 199085.539 |  | 177841.9054 |  | 577843.2715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-23 | 1528352.2778 |  | 453053.5404 |  | 199750.5187 |  | 177841.9054 |  | 578063.1132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-24 | 1530539.5849 |  | 454356.0261 |  | 200415.4985 |  | 177841.9054 |  | 578282.9549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-25 | 1532726.892 |  | 455658.5118 |  | 201080.4782 |  | 177841.9054 |  | 578502.7965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-26 | 1534914.1991 |  | 456960.9975 |  | 201745.458 |  | 177841.9054 |  | 578722.6382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-27 | 1537101.5063 |  | 458263.4832 |  | 202410.4378 |  | 177841.9054 |  | 578942.4799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-28 | 1539288.8134 |  | 459565.9689 |  | 203075.4175 |  | 177841.9054 |  | 579162.3215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-29 | 1541476.1205 |  | 460868.4546 |  | 203740.3973 |  | 177841.9054 |  | 579382.1632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-04-30 | 1543663.4276 |  | 462170.9403 |  | 204405.377 |  | 177841.9054 |  | 579602.0049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-01 | 1545850.7348 |  | 463473.426 |  | 205070.3568 |  | 177841.9054 |  | 579821.8465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-02 | 1548038.0419 |  | 464775.9117 |  | 205735.3366 |  | 177841.9054 |  | 580041.6882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-03 | 1550225.349 |  | 466078.3974 |  | 206400.3163 |  | 177841.9054 |  | 580261.5299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-04 | 1552412.6561 |  | 467380.8831 |  | 207065.2961 |  | 177841.9054 |  | 580481.3715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-05 | 1554599.9633 |  | 468683.3688 |  | 207730.2758 |  | 177841.9054 |  | 580701.2132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-06 | 1556787.2704 |  | 469985.8545 |  | 208395.2556 |  | 177841.9054 |  | 580921.0549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-07 | 1558974.5775 |  | 471288.3402 |  | 209060.2354 |  | 177841.9054 |  | 581140.8965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-08 | 1561161.8847 |  | 472590.8259 |  | 209725.2151 |  | 177841.9054 |  | 581360.7382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-09 | 1563349.1918 |  | 473893.3116 |  | 210390.1949 |  | 177841.9054 |  | 581580.5799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-10 | 1565536.4989 |  | 475195.7973 |  | 211055.1746 |  | 177841.9054 |  | 581800.4215 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-11 | 1567723.806 |  | 476498.283 |  | 211720.1544 |  | 177841.9054 |  | 582020.2632 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-12 | 1569911.1132 |  | 477800.7687 |  | 212385.1342 |  | 177841.9054 |  | 582240.1049 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-13 | 1572098.4203 |  | 479103.2544 |  | 213050.1139 |  | 177841.9054 |  | 582459.9465 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-14 | 1574285.7274 |  | 480405.7401 |  | 213715.0937 |  | 177841.9054 |  | 582679.7882 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-15 | 1576473.0345 |  | 481708.2258 |  | 214380.0734 |  | 177841.9054 |  | 582899.6299 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-16 | 1578660.3417 |  | 483010.7115 |  | 215045.0532 |  | 177841.9054 |  | 583119.4715 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-17 | 1580847.6488 |  | 484313.1972 |  | 215710.033 |  | 177841.9054 |  | 583339.3132 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-18 | 1583034.9559 |  | 485615.6829 |  | 216375.0127 |  | 177841.9054 |  | 583559.1549 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-19 | 1585222.263 |  | 486918.1686 |  | 217039.9925 |  | 177841.9054 |  | 583778.9965 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-20 | 1587409.5702 |  | 488220.6543 |  | 217704.9722 |  | 177841.9054 |  | 583998.8382 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-21 | 1589596.8773 |  | 489523.14 |  | 218369.952 |  | 177841.9054 |  | 584218.6799 |  | 119643.2 |  | 2187.3071 |  | 1302.4857 |  | 664.9798 |  | 0 |  | 219.8417 |  | 0
2026-05-22 | 1598818.4717 |  | 492610.241 |  | 220104.8247 |  | 178064.8178 |  | 588395.3882 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-05-23 | 1608040.0661 |  | 495697.3419 |  | 221839.6975 |  | 178287.7301 |  | 592572.0965 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-05-24 | 1617261.6604 |  | 498784.4429 |  | 223574.5702 |  | 178510.6425 |  | 596748.8049 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-05-25 | 1626483.2548 |  | 501871.5439 |  | 225309.4429 |  | 178733.5548 |  | 600925.5132 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-05-26 | 1635704.8492 |  | 504958.6449 |  | 227044.3156 |  | 178956.4671 |  | 605102.2215 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-05-27 | 1644926.4436 |  | 508045.7458 |  | 228779.1884 |  | 179179.3795 |  | 609278.9299 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-05-28 | 1654148.0379 |  | 511132.8468 |  | 230514.0611 |  | 179402.2918 |  | 613455.6382 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-05-29 | 1663369.6323 |  | 514219.9478 |  | 232248.9338 |  | 179625.2042 |  | 617632.3465 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-05-30 | 1672591.2267 |  | 517307.0488 |  | 233983.8065 |  | 179848.1165 |  | 621809.0549 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-05-31 | 1681812.8211 |  | 520394.1497 |  | 235718.6793 |  | 180071.0288 |  | 625985.7632 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-06-01 | 1691034.4154 |  | 523481.2507 |  | 237453.552 |  | 180293.9412 |  | 630162.4715 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-06-02 | 1700256.0098 |  | 526568.3517 |  | 239188.4247 |  | 180516.8535 |  | 634339.1799 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-06-03 | 1709477.6042 |  | 529655.4527 |  | 240923.2975 |  | 180739.7659 |  | 638515.8882 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-06-04 | 1718699.1986 |  | 532742.5536 |  | 242658.1702 |  | 180962.6782 |  | 642692.5965 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-06-05 | 1727920.7929 |  | 535829.6546 |  | 244393.0429 |  | 181185.5906 |  | 646869.3049 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-06-06 | 1737142.3873 |  | 538916.7556 |  | 246127.9156 |  | 181408.5029 |  | 651046.0132 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-06-07 | 1746363.9817 |  | 542003.8566 |  | 247862.7884 |  | 181631.4152 |  | 655222.7215 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-06-08 | 1755585.5761 |  | 545090.9575 |  | 249597.6611 |  | 181854.3276 |  | 659399.4299 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-06-09 | 1764807.1704 |  | 548178.0585 |  | 251332.5338 |  | 182077.2399 |  | 663576.1382 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-06-10 | 1774028.7648 |  | 551265.1595 |  | 253067.4065 |  | 182300.1523 |  | 667752.8465 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-06-11 | 1783250.3592 |  | 554352.2605 |  | 254802.2793 |  | 182523.0646 |  | 671929.5549 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-06-12 | 1792471.9536 |  | 557439.3614 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 9221.5944 |  | 3087.101 |  | 1734.8727 |  | 222.9123 |  | 4176.7083 |  | 0
2026-06-13 | 1793082.4 |  | 558049.8079 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-06-14 | 1793692.8464 |  | 558660.2543 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-06-15 | 1794303.2928 |  | 559270.7007 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-06-16 | 1794913.7393 |  | 559881.1471 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-06-17 | 1795524.1857 |  | 560491.5936 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-06-18 | 1796134.6321 |  | 561102.04 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-06-19 | 1796745.0786 |  | 561712.4864 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-06-20 | 1797355.525 |  | 562322.9329 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-06-21 | 1797965.9714 |  | 562933.3793 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-06-22 | 1798576.4178 |  | 563543.8257 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-06-23 | 1799186.8643 |  | 564154.2721 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-06-24 | 1799797.3107 |  | 564764.7186 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-06-25 | 1800407.7571 |  | 565375.165 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-06-26 | 1801018.2036 |  | 565985.6114 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-06-27 | 1801628.65 |  | 566596.0579 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-06-28 | 1802239.0964 |  | 567206.5043 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-06-29 | 1802849.5428 |  | 567816.9507 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-06-30 | 1803459.9893 |  | 568427.3971 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-07-01 | 1804070.4357 |  | 569037.8436 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-07-02 | 1804680.8821 |  | 569648.29 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-07-03 | 1805291.3286 |  | 570258.7364 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-07-04 | 1805901.775 |  | 570869.1829 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-07-05 | 1806512.2214 |  | 571479.6293 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-07-06 | 1807122.6678 |  | 572090.0757 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-07-07 | 1807733.1143 |  | 572700.5221 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-07-08 | 1808343.5607 |  | 573310.9686 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-07-09 | 1808954.0071 |  | 573921.415 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-07-10 | 1809564.4536 |  | 574531.8614 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-07-11 | 1810174.9 |  | 575142.3079 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-07-12 | 1810785.3464 |  | 575752.7543 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-07-13 | 1811395.7928 |  | 576363.2007 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-07-14 | 1812006.2393 |  | 576973.6471 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-07-15 | 1812616.6857 |  | 577584.0936 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0
2026-07-16 | 1813227.1321 |  | 578194.54 |  | 256537.152 |  | 182745.9769 |  | 676106.2632 |  | 119643.2 |  | 610.4464 |  | 610.4464 |  | 0 |  | 0 |  | 0 |  | 0

## Labor Cost
Date | Planned Labor (Cumulative) | Actual Labor (Cumulative) | Planned 5101 · Salary and wages (Direct) (Cumulative) | Actual 5101 · Salary and wages (Direct) (Cumulative) | Planned 5102 · Payroll taxes (Direct) (Cumulative) | Actual 5102 · Payroll taxes (Direct) (Cumulative)
2025-04-01 | 1296.9583 | 0 | 1296.9583 | 0 | 0 | 0
2025-04-02 | 2593.9167 | 0 | 2593.9167 | 0 | 0 | 0
2025-04-03 | 3890.875 | 0 | 3890.875 | 0 | 0 | 0
2025-04-04 | 5187.8333 | 0 | 5187.8333 | 0 | 0 | 0
2025-04-05 | 6484.7917 | 0 | 6484.7917 | 0 | 0 | 0
2025-04-06 | 7781.75 | 0 | 7781.75 | 0 | 0 | 0
2025-04-07 | 9078.7083 | 2614.5 | 9078.7083 | 2614.5 | 0 | 2614.5
2025-04-08 | 10375.6667 | 5229 | 10375.6667 | 5229 | 0 | 5229
2025-04-09 | 11672.625 | 7843.5 | 11672.625 | 7843.5 | 0 | 7843.5
2025-04-10 | 12969.5833 | 10458 | 12969.5833 | 10458 | 0 | 10458
2025-04-11 | 14266.5417 | 13072.5 | 14266.5417 | 13072.5 | 0 | 13072.5
2025-04-12 | 15563.5 | 13072.5 | 15563.5 | 13072.5 | 0 | 13072.5
2025-04-13 | 16860.4583 | 13072.5 | 16860.4583 | 13072.5 | 0 | 13072.5
2025-04-14 | 18157.4167 | 13340.5 | 18157.4167 | 13340.5 | 0 | 13340.5
2025-04-15 | 19454.375 | 13608.5 | 19454.375 | 13608.5 | 0 | 13608.5
2025-04-16 | 20751.3333 | 13876.5 | 20751.3333 | 13876.5 | 0 | 13876.5
2025-04-17 | 22048.2917 | 14144.5 | 22048.2917 | 14144.5 | 0 | 14144.5
2025-04-18 | 23345.25 | 14412.5 | 23345.25 | 14412.5 | 0 | 14412.5
2025-04-19 | 24642.2083 | 14412.5 | 24642.2083 | 14412.5 | 0 | 14412.5
2025-04-20 | 25939.1667 | 14412.5 | 25939.1667 | 14412.5 | 0 | 14412.5
2025-04-21 | 27236.125 | 14412.5 | 27236.125 | 14412.5 | 0 | 14412.5
2025-04-22 | 28533.0833 | 14412.5 | 28533.0833 | 14412.5 | 0 | 14412.5
2025-04-23 | 29830.0417 | 14412.5 | 29830.0417 | 14412.5 | 0 | 14412.5
2025-04-24 | 31127 | 14412.5 | 31127 | 14412.5 | 0 | 14412.5
2025-04-25 | 32423.9583 | 14412.5 | 32423.9583 | 14412.5 | 0 | 14412.5
2025-04-26 | 33720.9167 | 14412.5 | 33720.9167 | 14412.5 | 0 | 14412.5
2025-04-27 | 35017.875 | 14412.5 | 35017.875 | 14412.5 | 0 | 14412.5
2025-04-28 | 36314.8333 | 14412.5 | 36314.8333 | 14412.5 | 0 | 14412.5
2025-04-29 | 37611.7917 | 14412.5 | 37611.7917 | 14412.5 | 0 | 14412.5
2025-04-30 | 38908.75 | 14412.5 | 38908.75 | 14412.5 | 0 | 14412.5
2025-05-01 | 40205.7083 | 14412.5 | 40205.7083 | 14412.5 | 0 | 14412.5
2025-05-02 | 41502.6667 | 14412.5 | 41502.6667 | 14412.5 | 0 | 14412.5
2025-05-03 | 42799.625 | 14412.5 | 42799.625 | 14412.5 | 0 | 14412.5
2025-05-04 | 44096.5833 | 14412.5 | 44096.5833 | 14412.5 | 0 | 14412.5
2025-05-05 | 45393.5417 | 14412.5 | 45393.5417 | 14412.5 | 0 | 14412.5
2025-05-06 | 46690.5 | 14412.5 | 46690.5 | 14412.5 | 0 | 14412.5
2025-05-07 | 47987.4583 | 14412.5 | 47987.4583 | 14412.5 | 0 | 14412.5
2025-05-08 | 49284.4167 | 14412.5 | 49284.4167 | 14412.5 | 0 | 14412.5
2025-05-09 | 50581.375 | 14412.5 | 50581.375 | 14412.5 | 0 | 14412.5
2025-05-10 | 51878.3333 | 14412.5 | 51878.3333 | 14412.5 | 0 | 14412.5
2025-05-11 | 53175.2917 | 14412.5 | 53175.2917 | 14412.5 | 0 | 14412.5
2025-05-12 | 54472.25 | 14412.5 | 54472.25 | 14412.5 | 0 | 14412.5
2025-05-13 | 55769.2083 | 14412.5 | 55769.2083 | 14412.5 | 0 | 14412.5
2025-05-14 | 57066.1667 | 14412.5 | 57066.1667 | 14412.5 | 0 | 14412.5
2025-05-15 | 58363.125 | 14412.5 | 58363.125 | 14412.5 | 0 | 14412.5
2025-05-16 | 59660.0833 | 14412.5 | 59660.0833 | 14412.5 | 0 | 14412.5
2025-05-17 | 60957.0417 | 14412.5 | 60957.0417 | 14412.5 | 0 | 14412.5
2025-05-18 | 62254 | 14412.5 | 62254 | 14412.5 | 0 | 14412.5
2025-05-19 | 63550.9583 | 15089.45 | 63550.9583 | 15089.45 | 0 | 15089.45
2025-05-20 | 64847.9167 | 15766.4 | 64847.9167 | 15766.4 | 0 | 15766.4
2025-05-21 | 66144.875 | 16443.35 | 66144.875 | 16443.35 | 0 | 16443.35
2025-05-22 | 67441.8333 | 17120.3 | 67441.8333 | 17120.3 | 0 | 17120.3
2025-05-23 | 68738.7917 | 17797.25 | 68738.7917 | 17797.25 | 0 | 17797.25
2025-05-24 | 70035.75 | 17797.25 | 70035.75 | 17797.25 | 0 | 17797.25
2025-05-25 | 71332.7083 | 17797.25 | 71332.7083 | 17797.25 | 0 | 17797.25
2025-05-26 | 72629.6667 | 17797.25 | 72629.6667 | 17797.25 | 0 | 17797.25
2025-05-27 | 73926.625 | 17797.25 | 73926.625 | 17797.25 | 0 | 17797.25
2025-05-28 | 75223.5833 | 17797.25 | 75223.5833 | 17797.25 | 0 | 17797.25
2025-05-29 | 76520.5417 | 17797.25 | 76520.5417 | 17797.25 | 0 | 17797.25
2025-05-30 | 77817.5 | 17797.25 | 77817.5 | 17797.25 | 0 | 17797.25
2025-06-01 | 77938.5843 | 17797.25 | 77938.5843 | 17797.25 | 0 | 17797.25
2025-06-02 | 78059.6687 | 17797.25 | 78059.6687 | 17797.25 | 0 | 17797.25
2025-06-03 | 78180.753 | 17797.25 | 78180.753 | 17797.25 | 0 | 17797.25
2025-06-04 | 78301.8373 | 17797.25 | 78301.8373 | 17797.25 | 0 | 17797.25
2025-06-05 | 78422.9217 | 17797.25 | 78422.9217 | 17797.25 | 0 | 17797.25
2025-06-06 | 78544.006 | 17797.25 | 78544.006 | 17797.25 | 0 | 17797.25
2025-06-07 | 78665.0904 | 17797.25 | 78665.0904 | 17797.25 | 0 | 17797.25
2025-06-08 | 78786.1747 | 17797.25 | 78786.1747 | 17797.25 | 0 | 17797.25
2025-06-09 | 78907.259 | 18233 | 78907.259 | 18233 | 0 | 18233
2025-06-10 | 79028.3434 | 18668.75 | 79028.3434 | 18668.75 | 0 | 18668.75
2025-06-11 | 79149.4277 | 19104.5 | 79149.4277 | 19104.5 | 0 | 19104.5
2025-06-12 | 79270.512 | 19540.25 | 79270.512 | 19540.25 | 0 | 19540.25
2025-06-13 | 79391.5964 | 19976 | 79391.5964 | 19976 | 0 | 19976
2025-06-14 | 79512.6807 | 19976 | 79512.6807 | 19976 | 0 | 19976
2025-06-15 | 79633.7651 | 19976 | 79633.7651 | 19976 | 0 | 19976
2025-06-16 | 79754.8494 | 20244 | 79754.8494 | 20244 | 0 | 20244
2025-06-17 | 79875.9337 | 20512 | 79875.9337 | 20512 | 0 | 20512
2025-06-18 | 79997.0181 | 20780 | 79997.0181 | 20780 | 0 | 20780
2025-06-19 | 80118.1024 | 21048 | 80118.1024 | 21048 | 0 | 21048
2025-06-20 | 80239.1867 | 21316 | 80239.1867 | 21316 | 0 | 21316
2025-06-21 | 80360.2711 | 21316 | 80360.2711 | 21316 | 0 | 21316
2025-06-22 | 80481.3554 | 21316 | 80481.3554 | 21316 | 0 | 21316
2025-06-23 | 80602.4398 | 21316 | 80602.4398 | 21316 | 0 | 21316
2025-06-24 | 80723.5241 | 21316 | 80723.5241 | 21316 | 0 | 21316
2025-06-25 | 80844.6084 | 21316 | 80844.6084 | 21316 | 0 | 21316
2025-06-26 | 80965.6928 | 21316 | 80965.6928 | 21316 | 0 | 21316
2025-06-27 | 81086.7771 | 21316 | 81086.7771 | 21316 | 0 | 21316
2025-06-28 | 81207.8614 | 21316 | 81207.8614 | 21316 | 0 | 21316
2025-06-29 | 81328.9458 | 21316 | 81328.9458 | 21316 | 0 | 21316
2025-06-30 | 81450.0301 | 22180.55 | 81450.0301 | 22180.55 | 0 | 22180.55
2025-07-01 | 81571.1145 | 23045.1 | 81571.1145 | 23045.1 | 0 | 23045.1
2025-07-02 | 81692.1988 | 23909.65 | 81692.1988 | 23909.65 | 0 | 23909.65
2025-07-03 | 81813.2831 | 24774.2 | 81813.2831 | 24774.2 | 0 | 24774.2
2025-07-04 | 81934.3675 | 25638.75 | 81934.3675 | 25638.75 | 0 | 25638.75
2025-07-05 | 82055.4518 | 25638.75 | 82055.4518 | 25638.75 | 0 | 25638.75
2025-07-06 | 82176.5361 | 25638.75 | 82176.5361 | 25638.75 | 0 | 25638.75
2025-07-07 | 82297.6205 | 26359.75 | 82297.6205 | 26359.75 | 0 | 26359.75
2025-07-08 | 82418.7048 | 27080.75 | 82418.7048 | 27080.75 | 0 | 27080.75
2025-07-09 | 82539.7892 | 27801.75 | 82539.7892 | 27801.75 | 0 | 27801.75
2025-07-10 | 82660.8735 | 28522.75 | 82660.8735 | 28522.75 | 0 | 28522.75
2025-07-11 | 82781.9578 | 29243.75 | 82781.9578 | 29243.75 | 0 | 29243.75
2025-07-12 | 82903.0422 | 29243.75 | 82903.0422 | 29243.75 | 0 | 29243.75
2025-07-13 | 83024.1265 | 29243.75 | 83024.1265 | 29243.75 | 0 | 29243.75
2025-07-14 | 83145.2108 | 30919.15 | 83145.2108 | 30919.15 | 0 | 30919.15
2025-07-15 | 83266.2952 | 32594.55 | 83266.2952 | 32594.55 | 0 | 32594.55
2025-07-16 | 83387.3795 | 34269.95 | 83387.3795 | 34269.95 | 0 | 34269.95
2025-07-17 | 83508.4639 | 35945.35 | 83508.4639 | 35945.35 | 0 | 35945.35
2025-07-18 | 83629.5482 | 37620.75 | 83629.5482 | 37620.75 | 0 | 37620.75
2025-07-19 | 83750.6325 | 37620.75 | 83750.6325 | 37620.75 | 0 | 37620.75
2025-07-20 | 83871.7169 | 37620.75 | 83871.7169 | 37620.75 | 0 | 37620.75
2025-07-21 | 85072.9989 | 39350.15 | 85072.9989 | 39350.15 | 0 | 39350.15
2025-07-22 | 86274.2809 | 41079.55 | 86274.2809 | 41079.55 | 0 | 41079.55
2025-07-23 | 87475.5629 | 42808.95 | 87475.5629 | 42808.95 | 0 | 42808.95
2025-07-24 | 88676.8449 | 44538.35 | 88676.8449 | 44538.35 | 0 | 44538.35
2025-07-25 | 89878.1269 | 46267.75 | 89878.1269 | 46267.75 | 0 | 46267.75
2025-07-26 | 91079.4089 | 46267.75 | 91079.4089 | 46267.75 | 0 | 46267.75
2025-07-27 | 92280.6909 | 46267.75 | 92280.6909 | 46267.75 | 0 | 46267.75
2025-07-28 | 93481.973 | 48265.55 | 93481.973 | 48265.55 | 0 | 48265.55
2025-07-29 | 94683.255 | 50263.35 | 94683.255 | 50263.35 | 0 | 50263.35
2025-07-30 | 95884.537 | 52261.15 | 95884.537 | 52261.15 | 0 | 52261.15
2025-07-31 | 97085.819 | 54258.95 | 97085.819 | 54258.95 | 0 | 54258.95
2025-08-01 | 98287.101 | 56256.75 | 98287.101 | 56256.75 | 0 | 56256.75
2025-08-02 | 99488.383 | 56256.75 | 99488.383 | 56256.75 | 0 | 56256.75
2025-08-03 | 100689.665 | 56256.75 | 100689.665 | 56256.75 | 0 | 56256.75
2025-08-04 | 101890.947 | 58173.75 | 101890.947 | 58173.75 | 0 | 58173.75
2025-08-05 | 103092.2291 | 60090.75 | 103092.2291 | 60090.75 | 0 | 60090.75
2025-08-06 | 104293.5111 | 62007.75 | 104293.5111 | 62007.75 | 0 | 62007.75
2025-08-07 | 105494.7931 | 63924.75 | 105494.7931 | 63924.75 | 0 | 63924.75
2025-08-08 | 106696.0751 | 65841.75 | 106696.0751 | 65841.75 | 0 | 65841.75
2025-08-09 | 107897.3571 | 65841.75 | 107897.3571 | 65841.75 | 0 | 65841.75
2025-08-10 | 109098.6391 | 65841.75 | 109098.6391 | 65841.75 | 0 | 65841.75
2025-08-11 | 110299.9211 | 68429.75 | 110299.9211 | 68429.75 | 0 | 68429.75
2025-08-12 | 111501.2031 | 71017.75 | 111501.2031 | 71017.75 | 0 | 71017.75
2025-08-13 | 112702.4851 | 73605.75 | 112702.4851 | 73605.75 | 0 | 73605.75
2025-08-14 | 113903.7672 | 76193.75 | 113903.7672 | 76193.75 | 0 | 76193.75
2025-08-15 | 115105.0492 | 78781.75 | 115105.0492 | 78781.75 | 0 | 78781.75
2025-08-16 | 116306.3312 | 78781.75 | 116306.3312 | 78781.75 | 0 | 78781.75
2025-08-17 | 117507.6132 | 78781.75 | 117507.6132 | 78781.75 | 0 | 78781.75
2025-08-18 | 118708.8952 | 81369.75 | 118708.8952 | 81369.75 | 0 | 81369.75
2025-08-19 | 119910.1772 | 83957.75 | 119910.1772 | 83957.75 | 0 | 83957.75
2025-08-20 | 121111.4592 | 86545.75 | 121111.4592 | 86545.75 | 0 | 86545.75
2025-08-21 | 122312.7412 | 89133.75 | 122312.7412 | 89133.75 | 0 | 89133.75
2025-08-22 | 123514.0233 | 91721.75 | 123514.0233 | 91721.75 | 0 | 91721.75
2025-08-23 | 124594.2209 | 91721.75 | 124594.2209 | 91721.75 | 0 | 91721.75
2025-08-24 | 125674.4186 | 91721.75 | 125674.4186 | 91721.75 | 0 | 91721.75
2025-08-25 | 126754.6163 | 93867.35 | 126754.6163 | 93867.35 | 0 | 93867.35
2025-08-26 | 127834.814 | 96012.95 | 127834.814 | 96012.95 | 0 | 96012.95
2025-08-27 | 128915.0116 | 98158.55 | 128915.0116 | 98158.55 | 0 | 98158.55
2025-08-28 | 129995.2093 | 100304.15 | 129995.2093 | 100304.15 | 0 | 100304.15
2025-08-29 | 131075.407 | 102449.75 | 131075.407 | 102449.75 | 0 | 102449.75
2025-08-30 | 132155.6047 | 102449.75 | 132155.6047 | 102449.75 | 0 | 102449.75
2025-08-31 | 133235.8023 | 102449.75 | 133235.8023 | 102449.75 | 0 | 102449.75
2025-09-01 | 134316 | 103602.95 | 134316 | 103602.95 | 0 | 103602.95
2025-09-02 | 135894.5 | 104756.15 | 135894.5 | 104756.15 | 0 | 104756.15
2025-09-03 | 137473 | 105909.35 | 137473 | 105909.35 | 0 | 105909.35
2025-09-04 | 139051.5 | 107062.55 | 139051.5 | 107062.55 | 0 | 107062.55
2025-09-05 | 140630 | 108215.75 | 140630 | 108215.75 | 0 | 108215.75
2025-09-06 | 142208.5 | 108215.75 | 142208.5 | 108215.75 | 0 | 108215.75
2025-09-07 | 143787 | 108215.75 | 143787 | 108215.75 | 0 | 108215.75
2025-09-08 | 145365.5 | 110388.15 | 145365.5 | 110388.15 | 0 | 110388.15
2025-09-09 | 146944 | 112560.55 | 146944 | 112560.55 | 0 | 112560.55
2025-09-10 | 148522.5 | 114732.95 | 148522.5 | 114732.95 | 0 | 114732.95
2025-09-11 | 150101 | 116905.35 | 150101 | 116905.35 | 0 | 116905.35
2025-09-12 | 151679.5 | 119077.75 | 151679.5 | 119077.75 | 0 | 119077.75
2025-09-13 | 153258 | 119077.75 | 153258 | 119077.75 | 0 | 119077.75
2025-09-14 | 154836.5 | 119077.75 | 154836.5 | 119077.75 | 0 | 119077.75
2025-09-15 | 156415 | 122835.025 | 156415 | 122835.025 | 0 | 122835.025
2025-09-16 | 157993.5 | 126592.3 | 157993.5 | 126592.3 | 0 | 126592.3
2025-09-17 | 159572 | 130349.575 | 159572 | 130349.575 | 0 | 130349.575
2025-09-18 | 161150.5 | 134106.85 | 161150.5 | 134106.85 | 0 | 134106.85
2025-09-19 | 162729 | 137864.125 | 162729 | 137864.125 | 0 | 137864.125
2025-09-20 | 164307.5 | 137864.125 | 164307.5 | 137864.125 | 0 | 137864.125
2025-09-21 | 165886 | 137864.125 | 165886 | 137864.125 | 0 | 137864.125
2025-09-22 | 167464.5 | 140095.775 | 167464.5 | 140095.775 | 0 | 140095.775
2025-09-23 | 169043 | 142327.425 | 169043 | 142327.425 | 0 | 142327.425
2025-09-24 | 170621.5 | 144559.075 | 170621.5 | 144559.075 | 0 | 144559.075
2025-09-25 | 172200 | 146790.725 | 172200 | 146790.725 | 0 | 146790.725
2025-09-26 | 173778.5 | 149022.375 | 173778.5 | 149022.375 | 0 | 149022.375
2025-09-27 | 175357 | 149022.375 | 175357 | 149022.375 | 0 | 149022.375
2025-09-28 | 176935.5 | 149022.375 | 176935.5 | 149022.375 | 0 | 149022.375
2025-09-29 | 178514 | 151532.35 | 178514 | 151532.35 | 0 | 151532.35
2025-09-30 | 180092.5 | 154042.325 | 180092.5 | 154042.325 | 0 | 154042.325
2025-10-01 | 181671 | 156552.3 | 181671 | 156552.3 | 0 | 156552.3
2025-10-02 | 183249.5 | 159062.275 | 183249.5 | 159062.275 | 0 | 159062.275
2025-10-03 | 184828 | 161572.25 | 184828 | 161572.25 | 0 | 161572.25
2025-10-04 | 186406.5 | 161572.25 | 186406.5 | 161572.25 | 0 | 161572.25
2025-10-05 | 187985 | 161572.25 | 187985 | 161572.25 | 0 | 161572.25
2025-10-06 | 189563.5 | 162594.425 | 189563.5 | 162594.425 | 0 | 162594.425
2025-10-07 | 191142 | 163616.6 | 191142 | 163616.6 | 0 | 163616.6
2025-10-08 | 192720.5 | 164638.775 | 192720.5 | 164638.775 | 0 | 164638.775
2025-10-09 | 194299 | 165660.95 | 194299 | 165660.95 | 0 | 165660.95
2025-10-10 | 195877.5 | 166683.125 | 195877.5 | 166683.125 | 0 | 166683.125
2025-10-11 | 197456 | 166683.125 | 197456 | 166683.125 | 0 | 166683.125
2025-10-12 | 199034.5 | 166683.125 | 199034.5 | 166683.125 | 0 | 166683.125
2025-10-13 | 200613 | 168710.3 | 200613 | 168710.3 | 0 | 168710.3
2025-10-14 | 202191.5 | 170737.475 | 202191.5 | 170737.475 | 0 | 170737.475
2025-10-15 | 203770 | 172764.65 | 203770 | 172764.65 | 0 | 172764.65
2025-10-16 | 205348.5 | 174791.825 | 205348.5 | 174791.825 | 0 | 174791.825
2025-10-17 | 206927 | 176819 | 206927 | 176819 | 0 | 176819
2025-10-18 | 208505.5 | 176819 | 208505.5 | 176819 | 0 | 176819
2025-10-19 | 210084 | 176819 | 210084 | 176819 | 0 | 176819
2025-10-20 | 211662.5 |  | 211662.5 |  | 0
2025-10-21 | 213241 |  | 213241 |  | 0
2025-10-22 | 214819.5 |  | 214819.5 |  | 0
2025-10-23 | 216398 |  | 216398 |  | 0
2025-10-24 | 217976.5 |  | 217976.5 |  | 0
2025-10-25 | 219555 |  | 219555 |  | 0
2025-10-26 | 221133.5 |  | 221133.5 |  | 0
2025-10-27 | 222712 |  | 222712 |  | 0
2025-10-28 | 224290.5 |  | 224290.5 |  | 0
2025-10-29 | 225869 |  | 225869 |  | 0
2025-10-30 | 227447.5 |  | 227447.5 |  | 0
2025-10-31 | 229026 |  | 229026 |  | 0
2025-11-03 | 230328.4857 |  | 230328.4857 |  | 0
2025-11-04 | 231630.9714 |  | 231630.9714 |  | 0
2025-11-05 | 232933.4571 |  | 232933.4571 |  | 0
2025-11-06 | 234235.9428 |  | 234235.9428 |  | 0
2025-11-07 | 235538.4285 |  | 235538.4285 |  | 0
2025-11-08 | 236840.9142 |  | 236840.9142 |  | 0
2025-11-09 | 238143.3999 |  | 238143.3999 |  | 0
2025-11-10 | 239445.8856 |  | 239445.8856 |  | 0
2025-11-11 | 240748.3713 |  | 240748.3713 |  | 0
2025-11-12 | 242050.857 |  | 242050.857 |  | 0
2025-11-13 | 243353.3427 |  | 243353.3427 |  | 0
2025-11-14 | 244655.8284 |  | 244655.8284 |  | 0
2025-11-15 | 245958.3141 |  | 245958.3141 |  | 0
2025-11-16 | 247260.7998 |  | 247260.7998 |  | 0
2025-11-17 | 248563.2855 |  | 248563.2855 |  | 0
2025-11-18 | 249865.7712 |  | 249865.7712 |  | 0
2025-11-19 | 251168.2569 |  | 251168.2569 |  | 0
2025-11-20 | 252470.7426 |  | 252470.7426 |  | 0
2025-11-21 | 253773.2283 |  | 253773.2283 |  | 0
2025-11-22 | 255075.714 |  | 255075.714 |  | 0
2025-11-23 | 256378.1997 |  | 256378.1997 |  | 0
2025-11-24 | 257680.6854 |  | 257680.6854 |  | 0
2025-11-25 | 258983.1711 |  | 258983.1711 |  | 0
2025-11-26 | 260285.6568 |  | 260285.6568 |  | 0
2025-11-27 | 261588.1425 |  | 261588.1425 |  | 0
2025-11-28 | 262890.6282 |  | 262890.6282 |  | 0
2025-11-29 | 264193.1139 |  | 264193.1139 |  | 0
2025-11-30 | 265495.5996 |  | 265495.5996 |  | 0
2025-12-01 | 266798.0853 |  | 266798.0853 |  | 0
2025-12-02 | 268100.571 |  | 268100.571 |  | 0
2025-12-03 | 269403.0567 |  | 269403.0567 |  | 0
2025-12-04 | 270705.5424 |  | 270705.5424 |  | 0
2025-12-05 | 272008.0281 |  | 272008.0281 |  | 0
2025-12-06 | 273310.5138 |  | 273310.5138 |  | 0
2025-12-07 | 274612.9995 |  | 274612.9995 |  | 0
2025-12-08 | 275915.4852 |  | 275915.4852 |  | 0
2025-12-09 | 277217.9709 |  | 277217.9709 |  | 0
2025-12-10 | 278520.4566 |  | 278520.4566 |  | 0
2025-12-11 | 279822.9423 |  | 279822.9423 |  | 0
2025-12-12 | 281125.428 |  | 281125.428 |  | 0
2025-12-13 | 282427.9137 |  | 282427.9137 |  | 0
2025-12-14 | 283730.3994 |  | 283730.3994 |  | 0
2025-12-15 | 285032.8851 |  | 285032.8851 |  | 0
2025-12-16 | 286335.3708 |  | 286335.3708 |  | 0
2025-12-17 | 287637.8565 |  | 287637.8565 |  | 0
2025-12-18 | 288940.3422 |  | 288940.3422 |  | 0
2025-12-19 | 290242.8279 |  | 290242.8279 |  | 0
2025-12-20 | 291545.3136 |  | 291545.3136 |  | 0
2025-12-21 | 292847.7993 |  | 292847.7993 |  | 0
2025-12-22 | 294150.285 |  | 294150.285 |  | 0
2025-12-23 | 295452.7707 |  | 295452.7707 |  | 0
2025-12-24 | 296755.2564 |  | 296755.2564 |  | 0
2025-12-25 | 298057.7421 |  | 298057.7421 |  | 0
2025-12-26 | 299360.2278 |  | 299360.2278 |  | 0
2025-12-27 | 300662.7135 |  | 300662.7135 |  | 0
2025-12-28 | 301965.1992 |  | 301965.1992 |  | 0
2025-12-29 | 303267.6849 |  | 303267.6849 |  | 0
2025-12-30 | 304570.1706 |  | 304570.1706 |  | 0
2025-12-31 | 305872.6563 |  | 305872.6563 |  | 0
2026-01-01 | 307175.142 |  | 307175.142 |  | 0
2026-01-02 | 308477.6277 |  | 308477.6277 |  | 0
2026-01-03 | 309780.1134 |  | 309780.1134 |  | 0
2026-01-04 | 311082.5991 |  | 311082.5991 |  | 0
2026-01-05 | 312385.0848 |  | 312385.0848 |  | 0
2026-01-06 | 313687.5705 |  | 313687.5705 |  | 0
2026-01-07 | 314990.0562 |  | 314990.0562 |  | 0
2026-01-08 | 316292.5419 |  | 316292.5419 |  | 0
2026-01-09 | 317595.0276 |  | 317595.0276 |  | 0
2026-01-10 | 318897.5133 |  | 318897.5133 |  | 0
2026-01-11 | 320199.999 |  | 320199.999 |  | 0
2026-01-12 | 321502.4847 |  | 321502.4847 |  | 0
2026-01-13 | 322804.9704 |  | 322804.9704 |  | 0
2026-01-14 | 324107.4561 |  | 324107.4561 |  | 0
2026-01-15 | 325409.9418 |  | 325409.9418 |  | 0
2026-01-16 | 326712.4275 |  | 326712.4275 |  | 0
2026-01-17 | 328014.9132 |  | 328014.9132 |  | 0
2026-01-18 | 329317.3989 |  | 329317.3989 |  | 0
2026-01-19 | 330619.8846 |  | 330619.8846 |  | 0
2026-01-20 | 331922.3703 |  | 331922.3703 |  | 0
2026-01-21 | 333224.856 |  | 333224.856 |  | 0
2026-01-22 | 334527.3417 |  | 334527.3417 |  | 0
2026-01-23 | 335829.8274 |  | 335829.8274 |  | 0
2026-01-24 | 337132.3131 |  | 337132.3131 |  | 0
2026-01-25 | 338434.7988 |  | 338434.7988 |  | 0
2026-01-26 | 339737.2845 |  | 339737.2845 |  | 0
2026-01-27 | 341039.7702 |  | 341039.7702 |  | 0
2026-01-28 | 342342.2559 |  | 342342.2559 |  | 0
2026-01-29 | 343644.7416 |  | 343644.7416 |  | 0
2026-01-30 | 344947.2273 |  | 344947.2273 |  | 0
2026-01-31 | 346249.713 |  | 346249.713 |  | 0
2026-02-01 | 347552.1987 |  | 347552.1987 |  | 0
2026-02-02 | 348854.6844 |  | 348854.6844 |  | 0
2026-02-03 | 350157.1701 |  | 350157.1701 |  | 0
2026-02-04 | 351459.6558 |  | 351459.6558 |  | 0
2026-02-05 | 352762.1415 |  | 352762.1415 |  | 0
2026-02-06 | 354064.6272 |  | 354064.6272 |  | 0
2026-02-07 | 355367.1129 |  | 355367.1129 |  | 0
2026-02-08 | 356669.5986 |  | 356669.5986 |  | 0
2026-02-09 | 357972.0843 |  | 357972.0843 |  | 0
2026-02-10 | 359274.57 |  | 359274.57 |  | 0
2026-02-11 | 360577.0557 |  | 360577.0557 |  | 0
2026-02-12 | 361879.5414 |  | 361879.5414 |  | 0
2026-02-13 | 363182.0271 |  | 363182.0271 |  | 0
2026-02-14 | 364484.5128 |  | 364484.5128 |  | 0
2026-02-15 | 365786.9985 |  | 365786.9985 |  | 0
2026-02-16 | 367089.4842 |  | 367089.4842 |  | 0
2026-02-17 | 368391.9699 |  | 368391.9699 |  | 0
2026-02-18 | 369694.4556 |  | 369694.4556 |  | 0
2026-02-19 | 370996.9413 |  | 370996.9413 |  | 0
2026-02-20 | 372299.427 |  | 372299.427 |  | 0
2026-02-21 | 373601.9127 |  | 373601.9127 |  | 0
2026-02-22 | 374904.3984 |  | 374904.3984 |  | 0
2026-02-23 | 376206.8841 |  | 376206.8841 |  | 0
2026-02-24 | 377509.3698 |  | 377509.3698 |  | 0
2026-02-25 | 378811.8555 |  | 378811.8555 |  | 0
2026-02-26 | 380114.3412 |  | 380114.3412 |  | 0
2026-02-27 | 381416.8269 |  | 381416.8269 |  | 0
2026-02-28 | 382719.3126 |  | 382719.3126 |  | 0
2026-03-01 | 384021.7983 |  | 384021.7983 |  | 0
2026-03-02 | 385324.284 |  | 385324.284 |  | 0
2026-03-03 | 386626.7697 |  | 386626.7697 |  | 0
2026-03-04 | 387929.2554 |  | 387929.2554 |  | 0
2026-03-05 | 389231.7411 |  | 389231.7411 |  | 0
2026-03-06 | 390534.2268 |  | 390534.2268 |  | 0
2026-03-07 | 391836.7125 |  | 391836.7125 |  | 0
2026-03-08 | 393139.1982 |  | 393139.1982 |  | 0
2026-03-09 | 394441.6839 |  | 394441.6839 |  | 0
2026-03-10 | 395744.1696 |  | 395744.1696 |  | 0
2026-03-11 | 397046.6553 |  | 397046.6553 |  | 0
2026-03-12 | 398349.141 |  | 398349.141 |  | 0
2026-03-13 | 399651.6267 |  | 399651.6267 |  | 0
2026-03-14 | 400954.1124 |  | 400954.1124 |  | 0
2026-03-15 | 402256.5981 |  | 402256.5981 |  | 0
2026-03-16 | 403559.0838 |  | 403559.0838 |  | 0
2026-03-17 | 404861.5695 |  | 404861.5695 |  | 0
2026-03-18 | 406164.0552 |  | 406164.0552 |  | 0
2026-03-19 | 407466.5409 |  | 407466.5409 |  | 0
2026-03-20 | 408769.0266 |  | 408769.0266 |  | 0
2026-03-21 | 410071.5123 |  | 410071.5123 |  | 0
2026-03-22 | 411373.998 |  | 411373.998 |  | 0
2026-03-23 | 412676.4837 |  | 412676.4837 |  | 0
2026-03-24 | 413978.9694 |  | 413978.9694 |  | 0
2026-03-25 | 415281.4551 |  | 415281.4551 |  | 0
2026-03-26 | 416583.9408 |  | 416583.9408 |  | 0
2026-03-27 | 417886.4265 |  | 417886.4265 |  | 0
2026-03-28 | 419188.9122 |  | 419188.9122 |  | 0
2026-03-29 | 420491.3979 |  | 420491.3979 |  | 0
2026-03-30 | 421793.8836 |  | 421793.8836 |  | 0
2026-03-31 | 423096.3693 |  | 423096.3693 |  | 0
2026-04-01 | 424398.855 |  | 424398.855 |  | 0
2026-04-02 | 425701.3407 |  | 425701.3407 |  | 0
2026-04-03 | 427003.8264 |  | 427003.8264 |  | 0
2026-04-04 | 428306.3121 |  | 428306.3121 |  | 0
2026-04-05 | 429608.7978 |  | 429608.7978 |  | 0
2026-04-06 | 430911.2835 |  | 430911.2835 |  | 0
2026-04-07 | 432213.7692 |  | 432213.7692 |  | 0
2026-04-08 | 433516.2549 |  | 433516.2549 |  | 0
2026-04-09 | 434818.7406 |  | 434818.7406 |  | 0
2026-04-10 | 436121.2263 |  | 436121.2263 |  | 0
2026-04-11 | 437423.712 |  | 437423.712 |  | 0
2026-04-12 | 438726.1977 |  | 438726.1977 |  | 0
2026-04-13 | 440028.6834 |  | 440028.6834 |  | 0
2026-04-14 | 441331.1691 |  | 441331.1691 |  | 0
2026-04-15 | 442633.6548 |  | 442633.6548 |  | 0
2026-04-16 | 443936.1405 |  | 443936.1405 |  | 0
2026-04-17 | 445238.6262 |  | 445238.6262 |  | 0
2026-04-18 | 446541.1119 |  | 446541.1119 |  | 0
2026-04-19 | 447843.5976 |  | 447843.5976 |  | 0
2026-04-20 | 449146.0833 |  | 449146.0833 |  | 0
2026-04-21 | 450448.569 |  | 450448.569 |  | 0
2026-04-22 | 451751.0547 |  | 451751.0547 |  | 0
2026-04-23 | 453053.5404 |  | 453053.5404 |  | 0
2026-04-24 | 454356.0261 |  | 454356.0261 |  | 0
2026-04-25 | 455658.5118 |  | 455658.5118 |  | 0
2026-04-26 | 456960.9975 |  | 456960.9975 |  | 0
2026-04-27 | 458263.4832 |  | 458263.4832 |  | 0
2026-04-28 | 459565.9689 |  | 459565.9689 |  | 0
2026-04-29 | 460868.4546 |  | 460868.4546 |  | 0
2026-04-30 | 462170.9403 |  | 462170.9403 |  | 0
2026-05-01 | 463473.426 |  | 463473.426 |  | 0
2026-05-02 | 464775.9117 |  | 464775.9117 |  | 0
2026-05-03 | 466078.3974 |  | 466078.3974 |  | 0
2026-05-04 | 467380.8831 |  | 467380.8831 |  | 0
2026-05-05 | 468683.3688 |  | 468683.3688 |  | 0
2026-05-06 | 469985.8545 |  | 469985.8545 |  | 0
2026-05-07 | 471288.3402 |  | 471288.3402 |  | 0
2026-05-08 | 472590.8259 |  | 472590.8259 |  | 0
2026-05-09 | 473893.3116 |  | 473893.3116 |  | 0
2026-05-10 | 475195.7973 |  | 475195.7973 |  | 0
2026-05-11 | 476498.283 |  | 476498.283 |  | 0
2026-05-12 | 477800.7687 |  | 477800.7687 |  | 0
2026-05-13 | 479103.2544 |  | 479103.2544 |  | 0
2026-05-14 | 480405.7401 |  | 480405.7401 |  | 0
2026-05-15 | 481708.2258 |  | 481708.2258 |  | 0
2026-05-16 | 483010.7115 |  | 483010.7115 |  | 0
2026-05-17 | 484313.1972 |  | 484313.1972 |  | 0
2026-05-18 | 485615.6829 |  | 485615.6829 |  | 0
2026-05-19 | 486918.1686 |  | 486918.1686 |  | 0
2026-05-20 | 488220.6543 |  | 488220.6543 |  | 0
2026-05-21 | 489523.14 |  | 489523.14 |  | 0
2026-05-22 | 492610.241 |  | 492610.241 |  | 0
2026-05-23 | 495697.3419 |  | 495697.3419 |  | 0
2026-05-24 | 498784.4429 |  | 498784.4429 |  | 0
2026-05-25 | 501871.5439 |  | 501871.5439 |  | 0
2026-05-26 | 504958.6449 |  | 504958.6449 |  | 0
2026-05-27 | 508045.7458 |  | 508045.7458 |  | 0
2026-05-28 | 511132.8468 |  | 511132.8468 |  | 0
2026-05-29 | 514219.9478 |  | 514219.9478 |  | 0
2026-05-30 | 517307.0488 |  | 517307.0488 |  | 0
2026-05-31 | 520394.1497 |  | 520394.1497 |  | 0
2026-06-01 | 523481.2507 |  | 523481.2507 |  | 0
2026-06-02 | 526568.3517 |  | 526568.3517 |  | 0
2026-06-03 | 529655.4527 |  | 529655.4527 |  | 0
2026-06-04 | 532742.5536 |  | 532742.5536 |  | 0
2026-06-05 | 535829.6546 |  | 535829.6546 |  | 0
2026-06-06 | 538916.7556 |  | 538916.7556 |  | 0
2026-06-07 | 542003.8566 |  | 542003.8566 |  | 0
2026-06-08 | 545090.9575 |  | 545090.9575 |  | 0
2026-06-09 | 548178.0585 |  | 548178.0585 |  | 0
2026-06-10 | 551265.1595 |  | 551265.1595 |  | 0
2026-06-11 | 554352.2605 |  | 554352.2605 |  | 0
2026-06-12 | 557439.3614 |  | 557439.3614 |  | 0
2026-06-13 | 558049.8079 |  | 558049.8079 |  | 0
2026-06-14 | 558660.2543 |  | 558660.2543 |  | 0
2026-06-15 | 559270.7007 |  | 559270.7007 |  | 0
2026-06-16 | 559881.1471 |  | 559881.1471 |  | 0
2026-06-17 | 560491.5936 |  | 560491.5936 |  | 0
2026-06-18 | 561102.04 |  | 561102.04 |  | 0
2026-06-19 | 561712.4864 |  | 561712.4864 |  | 0
2026-06-20 | 562322.9329 |  | 562322.9329 |  | 0
2026-06-21 | 562933.3793 |  | 562933.3793 |  | 0
2026-06-22 | 563543.8257 |  | 563543.8257 |  | 0
2026-06-23 | 564154.2721 |  | 564154.2721 |  | 0
2026-06-24 | 564764.7186 |  | 564764.7186 |  | 0
2026-06-25 | 565375.165 |  | 565375.165 |  | 0
2026-06-26 | 565985.6114 |  | 565985.6114 |  | 0
2026-06-27 | 566596.0579 |  | 566596.0579 |  | 0
2026-06-28 | 567206.5043 |  | 567206.5043 |  | 0
2026-06-29 | 567816.9507 |  | 567816.9507 |  | 0
2026-06-30 | 568427.3971 |  | 568427.3971 |  | 0
2026-07-01 | 569037.8436 |  | 569037.8436 |  | 0
2026-07-02 | 569648.29 |  | 569648.29 |  | 0
2026-07-03 | 570258.7364 |  | 570258.7364 |  | 0
2026-07-04 | 570869.1829 |  | 570869.1829 |  | 0
2026-07-05 | 571479.6293 |  | 571479.6293 |  | 0
2026-07-06 | 572090.0757 |  | 572090.0757 |  | 0
2026-07-07 | 572700.5221 |  | 572700.5221 |  | 0
2026-07-08 | 573310.9686 |  | 573310.9686 |  | 0
2026-07-09 | 573921.415 |  | 573921.415 |  | 0
2026-07-10 | 574531.8614 |  | 574531.8614 |  | 0
2026-07-11 | 575142.3079 |  | 575142.3079 |  | 0
2026-07-12 | 575752.7543 |  | 575752.7543 |  | 0
2026-07-13 | 576363.2007 |  | 576363.2007 |  | 0
2026-07-14 | 576973.6471 |  | 576973.6471 |  | 0
2026-07-15 | 577584.0936 |  | 577584.0936 |  | 0
2026-07-16 | 578194.54 |  | 578194.54 |  | 0

## Travel&perdiem (Direct Cost)
Date | Planned Travel&perdiem (Cumulative) | Actual Travel&perdiem (Cumulative) | Planned 5105 · Travel - Airfare (Direct) (Cumulative) | Actual 5105 · Travel - Airfare (Direct) (Cumulative) | Planned 5106 · Travel - Hotel (Direct) (Cumulative) | Actual 5106 · Travel - Hotel (Direct) (Cumulative) | Planned 5107 · Travel - Other (Direct) (Cumulative) | Actual 5107 · Travel - Other (Direct) (Cumulative) | Planned 5108 · Meals & entertainment (Direct) (Cumulative) | Actual 5108 · Meals & entertainment (Direct) (Cumulative) | Planned 5122 · Motor vehicle exp (Direct) (Cumulative) | Actual 5122 · Motor vehicle exp (Direct) (Cumulative) | Planned 5123 · Auto fuel (Direct) (Cumulative) | Actual 5123 · Auto fuel (Direct) (Cumulative)
2025-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 80.6747 | 0 | 13.4458 | 0 | 13.4458 | 0 | 13.4458 | 0 | 13.4458 | 0 | 13.4458 | 0 | 13.4458 | 0
2025-06-02 | 161.3494 | 0 | 26.8916 | 0 | 26.8916 | 0 | 26.8916 | 0 | 26.8916 | 0 | 26.8916 | 0 | 26.8916 | 0
2025-06-03 | 242.0241 | 0 | 40.3373 | 0 | 40.3373 | 0 | 40.3373 | 0 | 40.3373 | 0 | 40.3373 | 0 | 40.3373 | 0
2025-06-04 | 322.6988 | 0 | 53.7831 | 0 | 53.7831 | 0 | 53.7831 | 0 | 53.7831 | 0 | 53.7831 | 0 | 53.7831 | 0
2025-06-05 | 403.3735 | 0 | 67.2289 | 0 | 67.2289 | 0 | 67.2289 | 0 | 67.2289 | 0 | 67.2289 | 0 | 67.2289 | 0
2025-06-06 | 484.0482 | 0 | 80.6747 | 0 | 80.6747 | 0 | 80.6747 | 0 | 80.6747 | 0 | 80.6747 | 0 | 80.6747 | 0
2025-06-07 | 564.7229 | 0 | 94.1205 | 0 | 94.1205 | 0 | 94.1205 | 0 | 94.1205 | 0 | 94.1205 | 0 | 94.1205 | 0
2025-06-08 | 645.3976 | 0 | 107.5663 | 0 | 107.5663 | 0 | 107.5663 | 0 | 107.5663 | 0 | 107.5663 | 0 | 107.5663 | 0
2025-06-09 | 726.0723 | 0 | 121.012 | 0 | 121.012 | 0 | 121.012 | 0 | 121.012 | 0 | 121.012 | 0 | 121.012 | 0
2025-06-10 | 806.747 | 0 | 134.4578 | 0 | 134.4578 | 0 | 134.4578 | 0 | 134.4578 | 0 | 134.4578 | 0 | 134.4578 | 0
2025-06-11 | 887.4217 | 0 | 147.9036 | 0 | 147.9036 | 0 | 147.9036 | 0 | 147.9036 | 0 | 147.9036 | 0 | 147.9036 | 0
2025-06-12 | 968.0964 | 0 | 161.3494 | 0 | 161.3494 | 0 | 161.3494 | 0 | 161.3494 | 0 | 161.3494 | 0 | 161.3494 | 0
2025-06-13 | 1048.7711 | 0 | 174.7952 | 0 | 174.7952 | 0 | 174.7952 | 0 | 174.7952 | 0 | 174.7952 | 0 | 174.7952 | 0
2025-06-14 | 1129.4458 | 0 | 188.241 | 0 | 188.241 | 0 | 188.241 | 0 | 188.241 | 0 | 188.241 | 0 | 188.241 | 0
2025-06-15 | 1210.1205 | 0 | 201.6867 | 0 | 201.6867 | 0 | 201.6867 | 0 | 201.6867 | 0 | 201.6867 | 0 | 201.6867 | 0
2025-06-16 | 1290.7952 | 0 | 215.1325 | 0 | 215.1325 | 0 | 215.1325 | 0 | 215.1325 | 0 | 215.1325 | 0 | 215.1325 | 0
2025-06-17 | 1371.4699 | 0 | 228.5783 | 0 | 228.5783 | 0 | 228.5783 | 0 | 228.5783 | 0 | 228.5783 | 0 | 228.5783 | 0
2025-06-18 | 1452.1446 | 0 | 242.0241 | 0 | 242.0241 | 0 | 242.0241 | 0 | 242.0241 | 0 | 242.0241 | 0 | 242.0241 | 0
2025-06-19 | 1532.8193 | 0 | 255.4699 | 0 | 255.4699 | 0 | 255.4699 | 0 | 255.4699 | 0 | 255.4699 | 0 | 255.4699 | 0
2025-06-20 | 1613.494 | 0 | 268.9157 | 0 | 268.9157 | 0 | 268.9157 | 0 | 268.9157 | 0 | 268.9157 | 0 | 268.9157 | 0
2025-06-21 | 1694.1687 | 0 | 282.3614 | 0 | 282.3614 | 0 | 282.3614 | 0 | 282.3614 | 0 | 282.3614 | 0 | 282.3614 | 0
2025-06-22 | 1774.8434 | 0 | 295.8072 | 0 | 295.8072 | 0 | 295.8072 | 0 | 295.8072 | 0 | 295.8072 | 0 | 295.8072 | 0
2025-06-23 | 1855.5181 | 0 | 309.253 | 0 | 309.253 | 0 | 309.253 | 0 | 309.253 | 0 | 309.253 | 0 | 309.253 | 0
2025-06-24 | 1936.1928 | 679.86 | 322.6988 | 0 | 322.6988 | 0 | 322.6988 | 312.76 | 322.6988 | 0 | 322.6988 | 367.1 | 322.6988 | 0
2025-06-25 | 2016.8675 | 679.86 | 336.1446 | 0 | 336.1446 | 0 | 336.1446 | 312.76 | 336.1446 | 0 | 336.1446 | 367.1 | 336.1446 | 0
2025-06-26 | 2097.5422 | 679.86 | 349.5904 | 0 | 349.5904 | 0 | 349.5904 | 312.76 | 349.5904 | 0 | 349.5904 | 367.1 | 349.5904 | 0
2025-06-27 | 2178.2169 | 679.86 | 363.0361 | 0 | 363.0361 | 0 | 363.0361 | 312.76 | 363.0361 | 0 | 363.0361 | 367.1 | 363.0361 | 0
2025-06-28 | 2258.8916 | 792.13 | 376.4819 | 0 | 376.4819 | 0 | 376.4819 | 425.03 | 376.4819 | 0 | 376.4819 | 367.1 | 376.4819 | 0
2025-06-29 | 2339.5663 | 940.88 | 389.9277 | 0 | 389.9277 | 148.75 | 389.9277 | 425.03 | 389.9277 | 0 | 389.9277 | 367.1 | 389.9277 | 0
2025-06-30 | 2420.241 | 1060.26 | 403.3735 | 0 | 403.3735 | 148.75 | 403.3735 | 425.03 | 403.3735 | 0 | 403.3735 | 367.1 | 403.3735 | 119.38
2025-07-01 | 2500.9157 | 1060.26 | 416.8193 | 0 | 416.8193 | 148.75 | 416.8193 | 425.03 | 416.8193 | 0 | 416.8193 | 367.1 | 416.8193 | 119.38
2025-07-02 | 2581.5904 | 1060.26 | 430.2651 | 0 | 430.2651 | 148.75 | 430.2651 | 425.03 | 430.2651 | 0 | 430.2651 | 367.1 | 430.2651 | 119.38
2025-07-03 | 2662.2651 | 1060.26 | 443.7108 | 0 | 443.7108 | 148.75 | 443.7108 | 425.03 | 443.7108 | 0 | 443.7108 | 367.1 | 443.7108 | 119.38
2025-07-04 | 2742.9398 | 1060.26 | 457.1566 | 0 | 457.1566 | 148.75 | 457.1566 | 425.03 | 457.1566 | 0 | 457.1566 | 367.1 | 457.1566 | 119.38
2025-07-05 | 2823.6145 | 1060.26 | 470.6024 | 0 | 470.6024 | 148.75 | 470.6024 | 425.03 | 470.6024 | 0 | 470.6024 | 367.1 | 470.6024 | 119.38
2025-07-06 | 2904.2892 | 1060.26 | 484.0482 | 0 | 484.0482 | 148.75 | 484.0482 | 425.03 | 484.0482 | 0 | 484.0482 | 367.1 | 484.0482 | 119.38
2025-07-07 | 2984.9639 | 1241.36 | 497.494 | 0 | 497.494 | 148.75 | 497.494 | 425.03 | 497.494 | 0 | 497.494 | 479.66 | 497.494 | 187.92
2025-07-08 | 3065.6386 | 1741.36 | 510.9398 | 0 | 510.9398 | 148.75 | 510.9398 | 425.03 | 510.9398 | 500 | 510.9398 | 479.66 | 510.9398 | 187.92
2025-07-09 | 3146.3133 | 1741.36 | 524.3855 | 0 | 524.3855 | 148.75 | 524.3855 | 425.03 | 524.3855 | 500 | 524.3855 | 479.66 | 524.3855 | 187.92
2025-07-10 | 3226.988 | 1799.25 | 537.8313 | 0 | 537.8313 | 148.75 | 537.8313 | 425.03 | 537.8313 | 500 | 537.8313 | 479.66 | 537.8313 | 245.81
2025-07-11 | 3307.6627 | 2100.37 | 551.2771 | 0 | 551.2771 | 449.87 | 551.2771 | 425.03 | 551.2771 | 500 | 551.2771 | 479.66 | 551.2771 | 245.81
2025-07-12 | 3388.3373 | 2534.49 | 564.7229 | 0 | 564.7229 | 654.71 | 564.7229 | 425.03 | 564.7229 | 500 | 564.7229 | 479.66 | 564.7229 | 475.09
2025-07-13 | 3469.012 | 7516.12 | 578.1687 | 0 | 578.1687 | 5636.34 | 578.1687 | 425.03 | 578.1687 | 500 | 578.1687 | 479.66 | 578.1687 | 475.09
2025-07-14 | 3549.6867 | 8164.67 | 591.6145 | 0 | 591.6145 | 6214.75 | 591.6145 | 425.03 | 591.6145 | 500 | 591.6145 | 479.66 | 591.6145 | 545.23
2025-07-15 | 3630.3614 | 6429.32 | 605.0602 | 0 | 605.0602 | 4479.4 | 605.0602 | 425.03 | 605.0602 | 500 | 605.0602 | 479.66 | 605.0602 | 545.23
2025-07-16 | 3711.0361 | 6779.32 | 618.506 | 0 | 618.506 | 4479.4 | 618.506 | 425.03 | 618.506 | 850 | 618.506 | 479.66 | 618.506 | 545.23
2025-07-17 | 3791.7108 | 7054.51 | 631.9518 | 185.57 | 631.9518 | 4479.4 | 631.9518 | 425.03 | 631.9518 | 850 | 631.9518 | 479.66 | 631.9518 | 634.85
2025-07-18 | 3872.3855 | 9214.51 | 645.3976 | 185.57 | 645.3976 | 4839.4 | 645.3976 | 425.03 | 645.3976 | 2650 | 645.3976 | 479.66 | 645.3976 | 634.85
2025-07-19 | 3953.0602 | 9257.81 | 658.8434 | 228.87 | 658.8434 | 4839.4 | 658.8434 | 425.03 | 658.8434 | 2650 | 658.8434 | 479.66 | 658.8434 | 634.85
2025-07-20 | 4033.7349 | 9257.81 | 672.2892 | 228.87 | 672.2892 | 4839.4 | 672.2892 | 425.03 | 672.2892 | 2650 | 672.2892 | 479.66 | 672.2892 | 634.85
2025-07-21 | 4659.4329 | 10547.81 | 776.5721 | 228.87 | 776.5721 | 6089.4 | 776.5721 | 425.03 | 776.5721 | 2650 | 776.5721 | 479.66 | 776.5721 | 674.85
2025-07-22 | 5285.1308 | 10413.49 | 880.8551 | 43.3 | 880.8551 | 6039.4 | 880.8551 | 425.03 | 880.8551 | 2650 | 880.8551 | 580.91 | 880.8551 | 674.85
2025-07-23 | 5910.8288 | 10233.49 | 985.1381 | 43.3 | 985.1381 | 5859.4 | 985.1381 | 425.03 | 985.1381 | 2650 | 985.1381 | 580.91 | 985.1381 | 674.85
2025-07-24 | 6536.5268 | 10353.38 | 1089.4211 | 43.3 | 1089.4211 | 5859.4 | 1089.4211 | 425.03 | 1089.4211 | 2650 | 1089.4211 | 580.91 | 1089.4211 | 794.74
2025-07-25 | 7162.2247 | 11503.38 | 1193.7041 | 43.3 | 1193.7041 | 5859.4 | 1193.7041 | 425.03 | 1193.7041 | 3800 | 1193.7041 | 580.91 | 1193.7041 | 794.74
2025-07-26 | 7787.9227 | 11503.38 | 1297.9871 | 43.3 | 1297.9871 | 5859.4 | 1297.9871 | 425.03 | 1297.9871 | 3800 | 1297.9871 | 580.91 | 1297.9871 | 794.74
2025-07-27 | 8413.6206 | 11595.82 | 1402.2701 | 43.3 | 1402.2701 | 5859.4 | 1402.2701 | 440.44 | 1402.2701 | 3800 | 1402.2701 | 580.91 | 1402.2701 | 871.77
2025-07-28 | 9039.3186 | 11595.82 | 1506.5531 | 43.3 | 1506.5531 | 5859.4 | 1506.5531 | 440.44 | 1506.5531 | 3800 | 1506.5531 | 580.91 | 1506.5531 | 871.77
2025-07-29 | 9665.0165 | 11655.82 | 1610.8361 | 43.3 | 1610.8361 | 5859.4 | 1610.8361 | 440.44 | 1610.8361 | 3800 | 1610.8361 | 580.91 | 1610.8361 | 931.77
2025-07-30 | 10290.7145 | 11655.82 | 1715.1191 | 43.3 | 1715.1191 | 5859.4 | 1715.1191 | 440.44 | 1715.1191 | 3800 | 1715.1191 | 580.91 | 1715.1191 | 931.77
2025-07-31 | 10916.4124 | 12076.98 | 1819.4021 | 43.3 | 1819.4021 | 6280.56 | 1819.4021 | 440.44 | 1819.4021 | 3800 | 1819.4021 | 580.91 | 1819.4021 | 931.77
2025-08-01 | 11542.1104 | 13439.85 | 1923.6851 | 43.3 | 1923.6851 | 6280.56 | 1923.6851 | 440.44 | 1923.6851 | 4850 | 1923.6851 | 580.91 | 1923.6851 | 931.77
2025-08-02 | 12167.8083 | 14516.45 | 2027.9681 | 43.3 | 2027.9681 | 7357.16 | 2027.9681 | 440.44 | 2027.9681 | 4850 | 2027.9681 | 580.91 | 2027.9681 | 931.77
2025-08-03 | 12793.5063 | 16548 | 2132.2511 | 43.3 | 2132.2511 | 9388.71 | 2132.2511 | 440.44 | 2132.2511 | 4850 | 2132.2511 | 580.91 | 2132.2511 | 931.77
2025-08-04 | 13419.2043 | 16548 | 2236.534 | 43.3 | 2236.534 | 9388.71 | 2236.534 | 440.44 | 2236.534 | 4850 | 2236.534 | 580.91 | 2236.534 | 931.77
2025-08-05 | 14044.9022 | 16548 | 2340.817 | 43.3 | 2340.817 | 9388.71 | 2340.817 | 440.44 | 2340.817 | 4850 | 2340.817 | 580.91 | 2340.817 | 931.77
2025-08-06 | 14670.6002 | 16548 | 2445.1 | 43.3 | 2445.1 | 9388.71 | 2445.1 | 440.44 | 2445.1 | 4850 | 2445.1 | 580.91 | 2445.1 | 931.77
2025-08-07 | 15296.2981 | 16548 | 2549.383 | 43.3 | 2549.383 | 9388.71 | 2549.383 | 440.44 | 2549.383 | 4850 | 2549.383 | 580.91 | 2549.383 | 931.77
2025-08-08 | 15921.9961 | 18298 | 2653.666 | 43.3 | 2653.666 | 9388.71 | 2653.666 | 440.44 | 2653.666 | 6600 | 2653.666 | 580.91 | 2653.666 | 931.77
2025-08-09 | 16547.694 | 18298 | 2757.949 | 43.3 | 2757.949 | 9388.71 | 2757.949 | 440.44 | 2757.949 | 6600 | 2757.949 | 580.91 | 2757.949 | 931.77
2025-08-10 | 17173.392 | 19221.48 | 2862.232 | 428.48 | 2862.232 | 9927.01 | 2862.232 | 440.44 | 2862.232 | 6600 | 2862.232 | 580.91 | 2862.232 | 931.77
2025-08-11 | 17799.0899 | 20067.38 | 2966.515 | 428.48 | 2966.515 | 10772.91 | 2966.515 | 440.44 | 2966.515 | 6600 | 2966.515 | 580.91 | 2966.515 | 931.77
2025-08-12 | 18424.7879 | 20067.38 | 3070.798 | 428.48 | 3070.798 | 10772.91 | 3070.798 | 440.44 | 3070.798 | 6600 | 3070.798 | 580.91 | 3070.798 | 931.77
2025-08-13 | 19050.4859 | 20067.38 | 3175.081 | 428.48 | 3175.081 | 10772.91 | 3175.081 | 440.44 | 3175.081 | 6600 | 3175.081 | 580.91 | 3175.081 | 931.77
2025-08-14 | 19676.1838 | 20067.38 | 3279.364 | 428.48 | 3279.364 | 10772.91 | 3279.364 | 440.44 | 3279.364 | 6600 | 3279.364 | 580.91 | 3279.364 | 931.77
2025-08-15 | 20301.8818 | 21817.38 | 3383.647 | 428.48 | 3383.647 | 10772.91 | 3383.647 | 440.44 | 3383.647 | 8350 | 3383.647 | 580.91 | 3383.647 | 931.77
2025-08-16 | 20927.5797 | 21817.38 | 3487.93 | 428.48 | 3487.93 | 10772.91 | 3487.93 | 440.44 | 3487.93 | 8350 | 3487.93 | 580.91 | 3487.93 | 931.77
2025-08-17 | 21553.2777 | 21817.38 | 3592.2129 | 428.48 | 3592.2129 | 10772.91 | 3592.2129 | 440.44 | 3592.2129 | 8350 | 3592.2129 | 580.91 | 3592.2129 | 931.77
2025-08-18 | 22178.9756 | 21817.38 | 3696.4959 | 428.48 | 3696.4959 | 10772.91 | 3696.4959 | 440.44 | 3696.4959 | 8350 | 3696.4959 | 580.91 | 3696.4959 | 931.77
2025-08-19 | 22804.6736 | 21817.38 | 3800.7789 | 428.48 | 3800.7789 | 10772.91 | 3800.7789 | 440.44 | 3800.7789 | 8350 | 3800.7789 | 580.91 | 3800.7789 | 931.77
2025-08-20 | 23430.3715 | 21817.38 | 3905.0619 | 428.48 | 3905.0619 | 10772.91 | 3905.0619 | 440.44 | 3905.0619 | 8350 | 3905.0619 | 580.91 | 3905.0619 | 931.77
2025-08-21 | 24056.0695 | 21817.38 | 4009.3449 | 428.48 | 4009.3449 | 10772.91 | 4009.3449 | 440.44 | 4009.3449 | 8350 | 4009.3449 | 580.91 | 4009.3449 | 931.77
2025-08-22 | 24681.7674 | 22667.38 | 4113.6279 | 428.48 | 4113.6279 | 10772.91 | 4113.6279 | 440.44 | 4113.6279 | 9200 | 4113.6279 | 580.91 | 4113.6279 | 931.77
2025-08-23 | 25226.7907 | 22667.38 | 4204.4651 | 428.48 | 4204.4651 | 10772.91 | 4204.4651 | 440.44 | 4204.4651 | 9200 | 4204.4651 | 580.91 | 4204.4651 | 931.77
2025-08-24 | 25771.814 | 22667.38 | 4295.3023 | 428.48 | 4295.3023 | 10772.91 | 4295.3023 | 440.44 | 4295.3023 | 9200 | 4295.3023 | 580.91 | 4295.3023 | 931.77
2025-08-25 | 26316.8372 | 22667.38 | 4386.1395 | 428.48 | 4386.1395 | 10772.91 | 4386.1395 | 440.44 | 4386.1395 | 9200 | 4386.1395 | 580.91 | 4386.1395 | 931.77
2025-08-26 | 26861.8605 | 22667.38 | 4476.9767 | 428.48 | 4476.9767 | 10772.91 | 4476.9767 | 440.44 | 4476.9767 | 9200 | 4476.9767 | 580.91 | 4476.9767 | 931.77
2025-08-27 | 27406.8837 | 22667.38 | 4567.814 | 428.48 | 4567.814 | 10772.91 | 4567.814 | 440.44 | 4567.814 | 9200 | 4567.814 | 580.91 | 4567.814 | 931.77
2025-08-28 | 27951.907 | 22667.38 | 4658.6512 | 428.48 | 4658.6512 | 10772.91 | 4658.6512 | 440.44 | 4658.6512 | 9200 | 4658.6512 | 580.91 | 4658.6512 | 931.77
2025-08-29 | 28496.9302 | 23017.38 | 4749.4884 | 428.48 | 4749.4884 | 10772.91 | 4749.4884 | 440.44 | 4749.4884 | 9550 | 4749.4884 | 580.91 | 4749.4884 | 931.77
2025-08-30 | 29041.9535 | 23017.38 | 4840.3256 | 428.48 | 4840.3256 | 10772.91 | 4840.3256 | 440.44 | 4840.3256 | 9550 | 4840.3256 | 580.91 | 4840.3256 | 931.77
2025-08-31 | 29586.9767 | 23017.38 | 4931.1628 | 428.48 | 4931.1628 | 10772.91 | 4931.1628 | 440.44 | 4931.1628 | 9550 | 4931.1628 | 580.91 | 4931.1628 | 931.77
2025-09-01 | 30132 | 23017.38 | 5022 | 428.48 | 5022 | 10772.91 | 5022 | 440.44 | 5022 | 9550 | 5022 | 580.91 | 5022 | 931.77
2025-09-02 | 31052.7 | 23017.38 | 5175.45 | 428.48 | 5175.45 | 10772.91 | 5175.45 | 440.44 | 5175.45 | 9550 | 5175.45 | 580.91 | 5175.45 | 931.77
2025-09-03 | 31973.4 | 23017.38 | 5328.9 | 428.48 | 5328.9 | 10772.91 | 5328.9 | 440.44 | 5328.9 | 9550 | 5328.9 | 580.91 | 5328.9 | 931.77
2025-09-04 | 32894.1 | 23017.38 | 5482.35 | 428.48 | 5482.35 | 10772.91 | 5482.35 | 440.44 | 5482.35 | 9550 | 5482.35 | 580.91 | 5482.35 | 931.77
2025-09-05 | 33814.8 | 23367.38 | 5635.8 | 428.48 | 5635.8 | 10772.91 | 5635.8 | 440.44 | 5635.8 | 9900 | 5635.8 | 580.91 | 5635.8 | 931.77
2025-09-06 | 34735.5 | 23367.38 | 5789.25 | 428.48 | 5789.25 | 10772.91 | 5789.25 | 440.44 | 5789.25 | 9900 | 5789.25 | 580.91 | 5789.25 | 931.77
2025-09-07 | 35656.2 | 23367.38 | 5942.7 | 428.48 | 5942.7 | 10772.91 | 5942.7 | 440.44 | 5942.7 | 9900 | 5942.7 | 580.91 | 5942.7 | 931.77
2025-09-08 | 36576.9 | 23367.38 | 6096.15 | 428.48 | 6096.15 | 10772.91 | 6096.15 | 440.44 | 6096.15 | 9900 | 6096.15 | 580.91 | 6096.15 | 931.77
2025-09-09 | 37497.6 | 23367.38 | 6249.6 | 428.48 | 6249.6 | 10772.91 | 6249.6 | 440.44 | 6249.6 | 9900 | 6249.6 | 580.91 | 6249.6 | 931.77
2025-09-10 | 38418.3 | 23367.38 | 6403.05 | 428.48 | 6403.05 | 10772.91 | 6403.05 | 440.44 | 6403.05 | 9900 | 6403.05 | 580.91 | 6403.05 | 931.77
2025-09-11 | 39339 | 23367.38 | 6556.5 | 428.48 | 6556.5 | 10772.91 | 6556.5 | 440.44 | 6556.5 | 9900 | 6556.5 | 580.91 | 6556.5 | 931.77
2025-09-12 | 40259.7 | 23367.38 | 6709.95 | 428.48 | 6709.95 | 10772.91 | 6709.95 | 440.44 | 6709.95 | 9900 | 6709.95 | 580.91 | 6709.95 | 931.77
2025-09-13 | 41180.4 | 23367.38 | 6863.4 | 428.48 | 6863.4 | 10772.91 | 6863.4 | 440.44 | 6863.4 | 9900 | 6863.4 | 580.91 | 6863.4 | 931.77
2025-09-14 | 42101.1 | 23367.38 | 7016.85 | 428.48 | 7016.85 | 10772.91 | 7016.85 | 440.44 | 7016.85 | 9900 | 7016.85 | 580.91 | 7016.85 | 931.77
2025-09-15 | 43021.8 | 24817.38 | 7170.3 | 428.48 | 7170.3 | 10772.91 | 7170.3 | 440.44 | 7170.3 | 11350 | 7170.3 | 580.91 | 7170.3 | 931.77
2025-09-16 | 43942.5 | 24817.38 | 7323.75 | 428.48 | 7323.75 | 10772.91 | 7323.75 | 440.44 | 7323.75 | 11350 | 7323.75 | 580.91 | 7323.75 | 931.77
2025-09-17 | 44863.2 | 24817.38 | 7477.2 | 428.48 | 7477.2 | 10772.91 | 7477.2 | 440.44 | 7477.2 | 11350 | 7477.2 | 580.91 | 7477.2 | 931.77
2025-09-18 | 45783.9 | 24817.38 | 7630.65 | 428.48 | 7630.65 | 10772.91 | 7630.65 | 440.44 | 7630.65 | 11350 | 7630.65 | 580.91 | 7630.65 | 931.77
2025-09-19 | 46704.6 | 24817.38 | 7784.1 | 428.48 | 7784.1 | 10772.91 | 7784.1 | 440.44 | 7784.1 | 11350 | 7784.1 | 580.91 | 7784.1 | 931.77
2025-09-20 | 47625.3 | 24817.38 | 7937.55 | 428.48 | 7937.55 | 10772.91 | 7937.55 | 440.44 | 7937.55 | 11350 | 7937.55 | 580.91 | 7937.55 | 931.77
2025-09-21 | 48546 | 24817.38 | 8091 | 428.48 | 8091 | 10772.91 | 8091 | 440.44 | 8091 | 11350 | 8091 | 580.91 | 8091 | 931.77
2025-09-22 | 49466.7 | 27567.38 | 8244.45 | 428.48 | 8244.45 | 10772.91 | 8244.45 | 440.44 | 8244.45 | 14100 | 8244.45 | 580.91 | 8244.45 | 931.77
2025-09-23 | 50387.4 | 27567.38 | 8397.9 | 428.48 | 8397.9 | 10772.91 | 8397.9 | 440.44 | 8397.9 | 14100 | 8397.9 | 580.91 | 8397.9 | 931.77
2025-09-24 | 51308.1 | 27567.38 | 8551.35 | 428.48 | 8551.35 | 10772.91 | 8551.35 | 440.44 | 8551.35 | 14100 | 8551.35 | 580.91 | 8551.35 | 931.77
2025-09-25 | 52228.8 | 27567.38 | 8704.8 | 428.48 | 8704.8 | 10772.91 | 8704.8 | 440.44 | 8704.8 | 14100 | 8704.8 | 580.91 | 8704.8 | 931.77
2025-09-26 | 53149.5 | 27567.38 | 8858.25 | 428.48 | 8858.25 | 10772.91 | 8858.25 | 440.44 | 8858.25 | 14100 | 8858.25 | 580.91 | 8858.25 | 931.77
2025-09-27 | 54070.2 | 27567.38 | 9011.7 | 428.48 | 9011.7 | 10772.91 | 9011.7 | 440.44 | 9011.7 | 14100 | 9011.7 | 580.91 | 9011.7 | 931.77
2025-09-28 | 54990.9 | 27567.38 | 9165.15 | 428.48 | 9165.15 | 10772.91 | 9165.15 | 440.44 | 9165.15 | 14100 | 9165.15 | 580.91 | 9165.15 | 931.77
2025-09-29 | 55911.6 | 29317.38 | 9318.6 | 428.48 | 9318.6 | 10772.91 | 9318.6 | 440.44 | 9318.6 | 15850 | 9318.6 | 580.91 | 9318.6 | 931.77
2025-09-30 | 56832.3 | 29317.38 | 9472.05 | 428.48 | 9472.05 | 10772.91 | 9472.05 | 440.44 | 9472.05 | 15850 | 9472.05 | 580.91 | 9472.05 | 931.77
2025-10-01 | 57753 | 29317.38 | 9625.5 | 428.48 | 9625.5 | 10772.91 | 9625.5 | 440.44 | 9625.5 | 15850 | 9625.5 | 580.91 | 9625.5 | 931.77
2025-10-02 | 58673.7 | 29317.38 | 9778.95 | 428.48 | 9778.95 | 10772.91 | 9778.95 | 440.44 | 9778.95 | 15850 | 9778.95 | 580.91 | 9778.95 | 931.77
2025-10-03 | 59594.4 | 31367.38 | 9932.4 | 428.48 | 9932.4 | 10772.91 | 9932.4 | 440.44 | 9932.4 | 17900 | 9932.4 | 580.91 | 9932.4 | 931.77
2025-10-04 | 60515.1 | 31367.38 | 10085.85 | 428.48 | 10085.85 | 10772.91 | 10085.85 | 440.44 | 10085.85 | 17900 | 10085.85 | 580.91 | 10085.85 | 931.77
2025-10-05 | 61435.8 | 31367.38 | 10239.3 | 428.48 | 10239.3 | 10772.91 | 10239.3 | 440.44 | 10239.3 | 17900 | 10239.3 | 580.91 | 10239.3 | 931.77
2025-10-06 | 62356.5 | 31367.38 | 10392.75 | 428.48 | 10392.75 | 10772.91 | 10392.75 | 440.44 | 10392.75 | 17900 | 10392.75 | 580.91 | 10392.75 | 931.77
2025-10-07 | 63277.2 | 31367.38 | 10546.2 | 428.48 | 10546.2 | 10772.91 | 10546.2 | 440.44 | 10546.2 | 17900 | 10546.2 | 580.91 | 10546.2 | 931.77
2025-10-08 | 64197.9 | 31367.38 | 10699.65 | 428.48 | 10699.65 | 10772.91 | 10699.65 | 440.44 | 10699.65 | 17900 | 10699.65 | 580.91 | 10699.65 | 931.77
2025-10-09 | 65118.6 | 31367.38 | 10853.1 | 428.48 | 10853.1 | 10772.91 | 10853.1 | 440.44 | 10853.1 | 17900 | 10853.1 | 580.91 | 10853.1 | 931.77
2025-10-10 | 66039.3 | 31367.38 | 11006.55 | 428.48 | 11006.55 | 10772.91 | 11006.55 | 440.44 | 11006.55 | 17900 | 11006.55 | 580.91 | 11006.55 | 931.77
2025-10-11 | 66960 | 31367.38 | 11160 | 428.48 | 11160 | 10772.91 | 11160 | 440.44 | 11160 | 17900 | 11160 | 580.91 | 11160 | 931.77
2025-10-12 | 67880.7 | 31367.38 | 11313.45 | 428.48 | 11313.45 | 10772.91 | 11313.45 | 440.44 | 11313.45 | 17900 | 11313.45 | 580.91 | 11313.45 | 931.77
2025-10-13 | 68801.4 | 31367.38 | 11466.9 | 428.48 | 11466.9 | 10772.91 | 11466.9 | 440.44 | 11466.9 | 17900 | 11466.9 | 580.91 | 11466.9 | 931.77
2025-10-14 | 69722.1 | 31717.38 | 11620.35 | 428.48 | 11620.35 | 10772.91 | 11620.35 | 440.44 | 11620.35 | 18250 | 11620.35 | 580.91 | 11620.35 | 931.77
2025-10-15 | 70642.8 | 31717.38 | 11773.8 | 428.48 | 11773.8 | 10772.91 | 11773.8 | 440.44 | 11773.8 | 18250 | 11773.8 | 580.91 | 11773.8 | 931.77
2025-10-16 | 71563.5 | 31717.38 | 11927.25 | 428.48 | 11927.25 | 10772.91 | 11927.25 | 440.44 | 11927.25 | 18250 | 11927.25 | 580.91 | 11927.25 | 931.77
2025-10-17 | 72484.2 | 32717.38 | 12080.7 | 428.48 | 12080.7 | 10772.91 | 12080.7 | 440.44 | 12080.7 | 19250 | 12080.7 | 580.91 | 12080.7 | 931.77
2025-10-18 | 73404.9 | 32717.38 | 12234.15 | 428.48 | 12234.15 | 10772.91 | 12234.15 | 440.44 | 12234.15 | 19250 | 12234.15 | 580.91 | 12234.15 | 931.77
2025-10-19 | 74325.6 | 32717.38 | 12387.6 | 428.48 | 12387.6 | 10772.91 | 12387.6 | 440.44 | 12387.6 | 19250 | 12387.6 | 580.91 | 12387.6 | 931.77
2025-10-20 | 75246.3 |  | 12541.05 |  | 12541.05 |  | 12541.05 |  | 12541.05 |  | 12541.05 |  | 12541.05
2025-10-21 | 76167 |  | 12694.5 |  | 12694.5 |  | 12694.5 |  | 12694.5 |  | 12694.5 |  | 12694.5
2025-10-22 | 77087.7 |  | 12847.95 |  | 12847.95 |  | 12847.95 |  | 12847.95 |  | 12847.95 |  | 12847.95
2025-10-23 | 78008.4 |  | 13001.4 |  | 13001.4 |  | 13001.4 |  | 13001.4 |  | 13001.4 |  | 13001.4
2025-10-24 | 78929.1 |  | 13154.85 |  | 13154.85 |  | 13154.85 |  | 13154.85 |  | 13154.85 |  | 13154.85
2025-10-25 | 79849.8 |  | 13308.3 |  | 13308.3 |  | 13308.3 |  | 13308.3 |  | 13308.3 |  | 13308.3
2025-10-26 | 80770.5 |  | 13461.75 |  | 13461.75 |  | 13461.75 |  | 13461.75 |  | 13461.75 |  | 13461.75
2025-10-27 | 81691.2 |  | 13615.2 |  | 13615.2 |  | 13615.2 |  | 13615.2 |  | 13615.2 |  | 13615.2
2025-10-28 | 82611.9 |  | 13768.65 |  | 13768.65 |  | 13768.65 |  | 13768.65 |  | 13768.65 |  | 13768.65
2025-10-29 | 83532.6 |  | 13922.1 |  | 13922.1 |  | 13922.1 |  | 13922.1 |  | 13922.1 |  | 13922.1
2025-10-30 | 84453.3 |  | 14075.55 |  | 14075.55 |  | 14075.55 |  | 14075.55 |  | 14075.55 |  | 14075.55
2025-10-31 | 85374 |  | 14229 |  | 14229 |  | 14229 |  | 14229 |  | 14229 |  | 14229
2025-11-03 | 86038.9798 |  | 14339.83 |  | 14339.83 |  | 14339.83 |  | 14339.83 |  | 14339.83 |  | 14339.83
2025-11-04 | 86703.9595 |  | 14450.6599 |  | 14450.6599 |  | 14450.6599 |  | 14450.6599 |  | 14450.6599 |  | 14450.6599
2025-11-05 | 87368.9393 |  | 14561.4899 |  | 14561.4899 |  | 14561.4899 |  | 14561.4899 |  | 14561.4899 |  | 14561.4899
2025-11-06 | 88033.919 |  | 14672.3198 |  | 14672.3198 |  | 14672.3198 |  | 14672.3198 |  | 14672.3198 |  | 14672.3198
2025-11-07 | 88698.8988 |  | 14783.1498 |  | 14783.1498 |  | 14783.1498 |  | 14783.1498 |  | 14783.1498 |  | 14783.1498
2025-11-08 | 89363.8786 |  | 14893.9798 |  | 14893.9798 |  | 14893.9798 |  | 14893.9798 |  | 14893.9798 |  | 14893.9798
2025-11-09 | 90028.8583 |  | 15004.8097 |  | 15004.8097 |  | 15004.8097 |  | 15004.8097 |  | 15004.8097 |  | 15004.8097
2025-11-10 | 90693.8381 |  | 15115.6397 |  | 15115.6397 |  | 15115.6397 |  | 15115.6397 |  | 15115.6397 |  | 15115.6397
2025-11-11 | 91358.8178 |  | 15226.4696 |  | 15226.4696 |  | 15226.4696 |  | 15226.4696 |  | 15226.4696 |  | 15226.4696
2025-11-12 | 92023.7976 |  | 15337.2996 |  | 15337.2996 |  | 15337.2996 |  | 15337.2996 |  | 15337.2996 |  | 15337.2996
2025-11-13 | 92688.7774 |  | 15448.1296 |  | 15448.1296 |  | 15448.1296 |  | 15448.1296 |  | 15448.1296 |  | 15448.1296
2025-11-14 | 93353.7571 |  | 15558.9595 |  | 15558.9595 |  | 15558.9595 |  | 15558.9595 |  | 15558.9595 |  | 15558.9595
2025-11-15 | 94018.7369 |  | 15669.7895 |  | 15669.7895 |  | 15669.7895 |  | 15669.7895 |  | 15669.7895 |  | 15669.7895
2025-11-16 | 94683.7166 |  | 15780.6194 |  | 15780.6194 |  | 15780.6194 |  | 15780.6194 |  | 15780.6194 |  | 15780.6194
2025-11-17 | 95348.6964 |  | 15891.4494 |  | 15891.4494 |  | 15891.4494 |  | 15891.4494 |  | 15891.4494 |  | 15891.4494
2025-11-18 | 96013.6762 |  | 16002.2794 |  | 16002.2794 |  | 16002.2794 |  | 16002.2794 |  | 16002.2794 |  | 16002.2794
2025-11-19 | 96678.6559 |  | 16113.1093 |  | 16113.1093 |  | 16113.1093 |  | 16113.1093 |  | 16113.1093 |  | 16113.1093
2025-11-20 | 97343.6357 |  | 16223.9393 |  | 16223.9393 |  | 16223.9393 |  | 16223.9393 |  | 16223.9393 |  | 16223.9393
2025-11-21 | 98008.6154 |  | 16334.7692 |  | 16334.7692 |  | 16334.7692 |  | 16334.7692 |  | 16334.7692 |  | 16334.7692
2025-11-22 | 98673.5952 |  | 16445.5992 |  | 16445.5992 |  | 16445.5992 |  | 16445.5992 |  | 16445.5992 |  | 16445.5992
2025-11-23 | 99338.575 |  | 16556.4292 |  | 16556.4292 |  | 16556.4292 |  | 16556.4292 |  | 16556.4292 |  | 16556.4292
2025-11-24 | 100003.5547 |  | 16667.2591 |  | 16667.2591 |  | 16667.2591 |  | 16667.2591 |  | 16667.2591 |  | 16667.2591
2025-11-25 | 100668.5345 |  | 16778.0891 |  | 16778.0891 |  | 16778.0891 |  | 16778.0891 |  | 16778.0891 |  | 16778.0891
2025-11-26 | 101333.5142 |  | 16888.919 |  | 16888.919 |  | 16888.919 |  | 16888.919 |  | 16888.919 |  | 16888.919
2025-11-27 | 101998.494 |  | 16999.749 |  | 16999.749 |  | 16999.749 |  | 16999.749 |  | 16999.749 |  | 16999.749
2025-11-28 | 102663.4738 |  | 17110.579 |  | 17110.579 |  | 17110.579 |  | 17110.579 |  | 17110.579 |  | 17110.579
2025-11-29 | 103328.4535 |  | 17221.4089 |  | 17221.4089 |  | 17221.4089 |  | 17221.4089 |  | 17221.4089 |  | 17221.4089
2025-11-30 | 103993.4333 |  | 17332.2389 |  | 17332.2389 |  | 17332.2389 |  | 17332.2389 |  | 17332.2389 |  | 17332.2389
2025-12-01 | 104658.413 |  | 17443.0688 |  | 17443.0688 |  | 17443.0688 |  | 17443.0688 |  | 17443.0688 |  | 17443.0688
2025-12-02 | 105323.3928 |  | 17553.8988 |  | 17553.8988 |  | 17553.8988 |  | 17553.8988 |  | 17553.8988 |  | 17553.8988
2025-12-03 | 105988.3726 |  | 17664.7288 |  | 17664.7288 |  | 17664.7288 |  | 17664.7288 |  | 17664.7288 |  | 17664.7288
2025-12-04 | 106653.3523 |  | 17775.5587 |  | 17775.5587 |  | 17775.5587 |  | 17775.5587 |  | 17775.5587 |  | 17775.5587
2025-12-05 | 107318.3321 |  | 17886.3887 |  | 17886.3887 |  | 17886.3887 |  | 17886.3887 |  | 17886.3887 |  | 17886.3887
2025-12-06 | 107983.3118 |  | 17997.2186 |  | 17997.2186 |  | 17997.2186 |  | 17997.2186 |  | 17997.2186 |  | 17997.2186
2025-12-07 | 108648.2916 |  | 18108.0486 |  | 18108.0486 |  | 18108.0486 |  | 18108.0486 |  | 18108.0486 |  | 18108.0486
2025-12-08 | 109313.2714 |  | 18218.8786 |  | 18218.8786 |  | 18218.8786 |  | 18218.8786 |  | 18218.8786 |  | 18218.8786
2025-12-09 | 109978.2511 |  | 18329.7085 |  | 18329.7085 |  | 18329.7085 |  | 18329.7085 |  | 18329.7085 |  | 18329.7085
2025-12-10 | 110643.2309 |  | 18440.5385 |  | 18440.5385 |  | 18440.5385 |  | 18440.5385 |  | 18440.5385 |  | 18440.5385
2025-12-11 | 111308.2106 |  | 18551.3684 |  | 18551.3684 |  | 18551.3684 |  | 18551.3684 |  | 18551.3684 |  | 18551.3684
2025-12-12 | 111973.1904 |  | 18662.1984 |  | 18662.1984 |  | 18662.1984 |  | 18662.1984 |  | 18662.1984 |  | 18662.1984
2025-12-13 | 112638.1702 |  | 18773.0284 |  | 18773.0284 |  | 18773.0284 |  | 18773.0284 |  | 18773.0284 |  | 18773.0284
2025-12-14 | 113303.1499 |  | 18883.8583 |  | 18883.8583 |  | 18883.8583 |  | 18883.8583 |  | 18883.8583 |  | 18883.8583
2025-12-15 | 113968.1297 |  | 18994.6883 |  | 18994.6883 |  | 18994.6883 |  | 18994.6883 |  | 18994.6883 |  | 18994.6883
2025-12-16 | 114633.1094 |  | 19105.5182 |  | 19105.5182 |  | 19105.5182 |  | 19105.5182 |  | 19105.5182 |  | 19105.5182
2025-12-17 | 115298.0892 |  | 19216.3482 |  | 19216.3482 |  | 19216.3482 |  | 19216.3482 |  | 19216.3482 |  | 19216.3482
2025-12-18 | 115963.069 |  | 19327.1782 |  | 19327.1782 |  | 19327.1782 |  | 19327.1782 |  | 19327.1782 |  | 19327.1782
2025-12-19 | 116628.0487 |  | 19438.0081 |  | 19438.0081 |  | 19438.0081 |  | 19438.0081 |  | 19438.0081 |  | 19438.0081
2025-12-20 | 117293.0285 |  | 19548.8381 |  | 19548.8381 |  | 19548.8381 |  | 19548.8381 |  | 19548.8381 |  | 19548.8381
2025-12-21 | 117958.0082 |  | 19659.668 |  | 19659.668 |  | 19659.668 |  | 19659.668 |  | 19659.668 |  | 19659.668
2025-12-22 | 118622.988 |  | 19770.498 |  | 19770.498 |  | 19770.498 |  | 19770.498 |  | 19770.498 |  | 19770.498
2025-12-23 | 119287.9678 |  | 19881.328 |  | 19881.328 |  | 19881.328 |  | 19881.328 |  | 19881.328 |  | 19881.328
2025-12-24 | 119952.9475 |  | 19992.1579 |  | 19992.1579 |  | 19992.1579 |  | 19992.1579 |  | 19992.1579 |  | 19992.1579
2025-12-25 | 120617.9273 |  | 20102.9879 |  | 20102.9879 |  | 20102.9879 |  | 20102.9879 |  | 20102.9879 |  | 20102.9879
2025-12-26 | 121282.907 |  | 20213.8178 |  | 20213.8178 |  | 20213.8178 |  | 20213.8178 |  | 20213.8178 |  | 20213.8178
2025-12-27 | 121947.8868 |  | 20324.6478 |  | 20324.6478 |  | 20324.6478 |  | 20324.6478 |  | 20324.6478 |  | 20324.6478
2025-12-28 | 122612.8666 |  | 20435.4778 |  | 20435.4778 |  | 20435.4778 |  | 20435.4778 |  | 20435.4778 |  | 20435.4778
2025-12-29 | 123277.8463 |  | 20546.3077 |  | 20546.3077 |  | 20546.3077 |  | 20546.3077 |  | 20546.3077 |  | 20546.3077
2025-12-30 | 123942.8261 |  | 20657.1377 |  | 20657.1377 |  | 20657.1377 |  | 20657.1377 |  | 20657.1377 |  | 20657.1377
2025-12-31 | 124607.8058 |  | 20767.9676 |  | 20767.9676 |  | 20767.9676 |  | 20767.9676 |  | 20767.9676 |  | 20767.9676
2026-01-01 | 125272.7856 |  | 20878.7976 |  | 20878.7976 |  | 20878.7976 |  | 20878.7976 |  | 20878.7976 |  | 20878.7976
2026-01-02 | 125937.7654 |  | 20989.6276 |  | 20989.6276 |  | 20989.6276 |  | 20989.6276 |  | 20989.6276 |  | 20989.6276
2026-01-03 | 126602.7451 |  | 21100.4575 |  | 21100.4575 |  | 21100.4575 |  | 21100.4575 |  | 21100.4575 |  | 21100.4575
2026-01-04 | 127267.7249 |  | 21211.2875 |  | 21211.2875 |  | 21211.2875 |  | 21211.2875 |  | 21211.2875 |  | 21211.2875
2026-01-05 | 127932.7046 |  | 21322.1174 |  | 21322.1174 |  | 21322.1174 |  | 21322.1174 |  | 21322.1174 |  | 21322.1174
2026-01-06 | 128597.6844 |  | 21432.9474 |  | 21432.9474 |  | 21432.9474 |  | 21432.9474 |  | 21432.9474 |  | 21432.9474
2026-01-07 | 129262.6642 |  | 21543.7774 |  | 21543.7774 |  | 21543.7774 |  | 21543.7774 |  | 21543.7774 |  | 21543.7774
2026-01-08 | 129927.6439 |  | 21654.6073 |  | 21654.6073 |  | 21654.6073 |  | 21654.6073 |  | 21654.6073 |  | 21654.6073
2026-01-09 | 130592.6237 |  | 21765.4373 |  | 21765.4373 |  | 21765.4373 |  | 21765.4373 |  | 21765.4373 |  | 21765.4373
2026-01-10 | 131257.6034 |  | 21876.2672 |  | 21876.2672 |  | 21876.2672 |  | 21876.2672 |  | 21876.2672 |  | 21876.2672
2026-01-11 | 131922.5832 |  | 21987.0972 |  | 21987.0972 |  | 21987.0972 |  | 21987.0972 |  | 21987.0972 |  | 21987.0972
2026-01-12 | 132587.563 |  | 22097.9272 |  | 22097.9272 |  | 22097.9272 |  | 22097.9272 |  | 22097.9272 |  | 22097.9272
2026-01-13 | 133252.5427 |  | 22208.7571 |  | 22208.7571 |  | 22208.7571 |  | 22208.7571 |  | 22208.7571 |  | 22208.7571
2026-01-14 | 133917.5225 |  | 22319.5871 |  | 22319.5871 |  | 22319.5871 |  | 22319.5871 |  | 22319.5871 |  | 22319.5871
2026-01-15 | 134582.5022 |  | 22430.417 |  | 22430.417 |  | 22430.417 |  | 22430.417 |  | 22430.417 |  | 22430.417
2026-01-16 | 135247.482 |  | 22541.247 |  | 22541.247 |  | 22541.247 |  | 22541.247 |  | 22541.247 |  | 22541.247
2026-01-17 | 135912.4618 |  | 22652.077 |  | 22652.077 |  | 22652.077 |  | 22652.077 |  | 22652.077 |  | 22652.077
2026-01-18 | 136577.4415 |  | 22762.9069 |  | 22762.9069 |  | 22762.9069 |  | 22762.9069 |  | 22762.9069 |  | 22762.9069
2026-01-19 | 137242.4213 |  | 22873.7369 |  | 22873.7369 |  | 22873.7369 |  | 22873.7369 |  | 22873.7369 |  | 22873.7369
2026-01-20 | 137907.401 |  | 22984.5668 |  | 22984.5668 |  | 22984.5668 |  | 22984.5668 |  | 22984.5668 |  | 22984.5668
2026-01-21 | 138572.3808 |  | 23095.3968 |  | 23095.3968 |  | 23095.3968 |  | 23095.3968 |  | 23095.3968 |  | 23095.3968
2026-01-22 | 139237.3606 |  | 23206.2268 |  | 23206.2268 |  | 23206.2268 |  | 23206.2268 |  | 23206.2268 |  | 23206.2268
2026-01-23 | 139902.3403 |  | 23317.0567 |  | 23317.0567 |  | 23317.0567 |  | 23317.0567 |  | 23317.0567 |  | 23317.0567
2026-01-24 | 140567.3201 |  | 23427.8867 |  | 23427.8867 |  | 23427.8867 |  | 23427.8867 |  | 23427.8867 |  | 23427.8867
2026-01-25 | 141232.2998 |  | 23538.7166 |  | 23538.7166 |  | 23538.7166 |  | 23538.7166 |  | 23538.7166 |  | 23538.7166
2026-01-26 | 141897.2796 |  | 23649.5466 |  | 23649.5466 |  | 23649.5466 |  | 23649.5466 |  | 23649.5466 |  | 23649.5466
2026-01-27 | 142562.2594 |  | 23760.3766 |  | 23760.3766 |  | 23760.3766 |  | 23760.3766 |  | 23760.3766 |  | 23760.3766
2026-01-28 | 143227.2391 |  | 23871.2065 |  | 23871.2065 |  | 23871.2065 |  | 23871.2065 |  | 23871.2065 |  | 23871.2065
2026-01-29 | 143892.2189 |  | 23982.0365 |  | 23982.0365 |  | 23982.0365 |  | 23982.0365 |  | 23982.0365 |  | 23982.0365
2026-01-30 | 144557.1986 |  | 24092.8664 |  | 24092.8664 |  | 24092.8664 |  | 24092.8664 |  | 24092.8664 |  | 24092.8664
2026-01-31 | 145222.1784 |  | 24203.6964 |  | 24203.6964 |  | 24203.6964 |  | 24203.6964 |  | 24203.6964 |  | 24203.6964
2026-02-01 | 145887.1582 |  | 24314.5264 |  | 24314.5264 |  | 24314.5264 |  | 24314.5264 |  | 24314.5264 |  | 24314.5264
2026-02-02 | 146552.1379 |  | 24425.3563 |  | 24425.3563 |  | 24425.3563 |  | 24425.3563 |  | 24425.3563 |  | 24425.3563
2026-02-03 | 147217.1177 |  | 24536.1863 |  | 24536.1863 |  | 24536.1863 |  | 24536.1863 |  | 24536.1863 |  | 24536.1863
2026-02-04 | 147882.0974 |  | 24647.0162 |  | 24647.0162 |  | 24647.0162 |  | 24647.0162 |  | 24647.0162 |  | 24647.0162
2026-02-05 | 148547.0772 |  | 24757.8462 |  | 24757.8462 |  | 24757.8462 |  | 24757.8462 |  | 24757.8462 |  | 24757.8462
2026-02-06 | 149212.057 |  | 24868.6762 |  | 24868.6762 |  | 24868.6762 |  | 24868.6762 |  | 24868.6762 |  | 24868.6762
2026-02-07 | 149877.0367 |  | 24979.5061 |  | 24979.5061 |  | 24979.5061 |  | 24979.5061 |  | 24979.5061 |  | 24979.5061
2026-02-08 | 150542.0165 |  | 25090.3361 |  | 25090.3361 |  | 25090.3361 |  | 25090.3361 |  | 25090.3361 |  | 25090.3361
2026-02-09 | 151206.9962 |  | 25201.166 |  | 25201.166 |  | 25201.166 |  | 25201.166 |  | 25201.166 |  | 25201.166
2026-02-10 | 151871.976 |  | 25311.996 |  | 25311.996 |  | 25311.996 |  | 25311.996 |  | 25311.996 |  | 25311.996
2026-02-11 | 152536.9558 |  | 25422.826 |  | 25422.826 |  | 25422.826 |  | 25422.826 |  | 25422.826 |  | 25422.826
2026-02-12 | 153201.9355 |  | 25533.6559 |  | 25533.6559 |  | 25533.6559 |  | 25533.6559 |  | 25533.6559 |  | 25533.6559
2026-02-13 | 153866.9153 |  | 25644.4859 |  | 25644.4859 |  | 25644.4859 |  | 25644.4859 |  | 25644.4859 |  | 25644.4859
2026-02-14 | 154531.895 |  | 25755.3158 |  | 25755.3158 |  | 25755.3158 |  | 25755.3158 |  | 25755.3158 |  | 25755.3158
2026-02-15 | 155196.8748 |  | 25866.1458 |  | 25866.1458 |  | 25866.1458 |  | 25866.1458 |  | 25866.1458 |  | 25866.1458
2026-02-16 | 155861.8546 |  | 25976.9758 |  | 25976.9758 |  | 25976.9758 |  | 25976.9758 |  | 25976.9758 |  | 25976.9758
2026-02-17 | 156526.8343 |  | 26087.8057 |  | 26087.8057 |  | 26087.8057 |  | 26087.8057 |  | 26087.8057 |  | 26087.8057
2026-02-18 | 157191.8141 |  | 26198.6357 |  | 26198.6357 |  | 26198.6357 |  | 26198.6357 |  | 26198.6357 |  | 26198.6357
2026-02-19 | 157856.7938 |  | 26309.4656 |  | 26309.4656 |  | 26309.4656 |  | 26309.4656 |  | 26309.4656 |  | 26309.4656
2026-02-20 | 158521.7736 |  | 26420.2956 |  | 26420.2956 |  | 26420.2956 |  | 26420.2956 |  | 26420.2956 |  | 26420.2956
2026-02-21 | 159186.7534 |  | 26531.1256 |  | 26531.1256 |  | 26531.1256 |  | 26531.1256 |  | 26531.1256 |  | 26531.1256
2026-02-22 | 159851.7331 |  | 26641.9555 |  | 26641.9555 |  | 26641.9555 |  | 26641.9555 |  | 26641.9555 |  | 26641.9555
2026-02-23 | 160516.7129 |  | 26752.7855 |  | 26752.7855 |  | 26752.7855 |  | 26752.7855 |  | 26752.7855 |  | 26752.7855
2026-02-24 | 161181.6926 |  | 26863.6154 |  | 26863.6154 |  | 26863.6154 |  | 26863.6154 |  | 26863.6154 |  | 26863.6154
2026-02-25 | 161846.6724 |  | 26974.4454 |  | 26974.4454 |  | 26974.4454 |  | 26974.4454 |  | 26974.4454 |  | 26974.4454
2026-02-26 | 162511.6522 |  | 27085.2754 |  | 27085.2754 |  | 27085.2754 |  | 27085.2754 |  | 27085.2754 |  | 27085.2754
2026-02-27 | 163176.6319 |  | 27196.1053 |  | 27196.1053 |  | 27196.1053 |  | 27196.1053 |  | 27196.1053 |  | 27196.1053
2026-02-28 | 163841.6117 |  | 27306.9353 |  | 27306.9353 |  | 27306.9353 |  | 27306.9353 |  | 27306.9353 |  | 27306.9353
2026-03-01 | 164506.5914 |  | 27417.7652 |  | 27417.7652 |  | 27417.7652 |  | 27417.7652 |  | 27417.7652 |  | 27417.7652
2026-03-02 | 165171.5712 |  | 27528.5952 |  | 27528.5952 |  | 27528.5952 |  | 27528.5952 |  | 27528.5952 |  | 27528.5952
2026-03-03 | 165836.551 |  | 27639.4252 |  | 27639.4252 |  | 27639.4252 |  | 27639.4252 |  | 27639.4252 |  | 27639.4252
2026-03-04 | 166501.5307 |  | 27750.2551 |  | 27750.2551 |  | 27750.2551 |  | 27750.2551 |  | 27750.2551 |  | 27750.2551
2026-03-05 | 167166.5105 |  | 27861.0851 |  | 27861.0851 |  | 27861.0851 |  | 27861.0851 |  | 27861.0851 |  | 27861.0851
2026-03-06 | 167831.4902 |  | 27971.915 |  | 27971.915 |  | 27971.915 |  | 27971.915 |  | 27971.915 |  | 27971.915
2026-03-07 | 168496.47 |  | 28082.745 |  | 28082.745 |  | 28082.745 |  | 28082.745 |  | 28082.745 |  | 28082.745
2026-03-08 | 169161.4498 |  | 28193.575 |  | 28193.575 |  | 28193.575 |  | 28193.575 |  | 28193.575 |  | 28193.575
2026-03-09 | 169826.4295 |  | 28304.4049 |  | 28304.4049 |  | 28304.4049 |  | 28304.4049 |  | 28304.4049 |  | 28304.4049
2026-03-10 | 170491.4093 |  | 28415.2349 |  | 28415.2349 |  | 28415.2349 |  | 28415.2349 |  | 28415.2349 |  | 28415.2349
2026-03-11 | 171156.389 |  | 28526.0648 |  | 28526.0648 |  | 28526.0648 |  | 28526.0648 |  | 28526.0648 |  | 28526.0648
2026-03-12 | 171821.3688 |  | 28636.8948 |  | 28636.8948 |  | 28636.8948 |  | 28636.8948 |  | 28636.8948 |  | 28636.8948
2026-03-13 | 172486.3486 |  | 28747.7248 |  | 28747.7248 |  | 28747.7248 |  | 28747.7248 |  | 28747.7248 |  | 28747.7248
2026-03-14 | 173151.3283 |  | 28858.5547 |  | 28858.5547 |  | 28858.5547 |  | 28858.5547 |  | 28858.5547 |  | 28858.5547
2026-03-15 | 173816.3081 |  | 28969.3847 |  | 28969.3847 |  | 28969.3847 |  | 28969.3847 |  | 28969.3847 |  | 28969.3847
2026-03-16 | 174481.2878 |  | 29080.2146 |  | 29080.2146 |  | 29080.2146 |  | 29080.2146 |  | 29080.2146 |  | 29080.2146
2026-03-17 | 175146.2676 |  | 29191.0446 |  | 29191.0446 |  | 29191.0446 |  | 29191.0446 |  | 29191.0446 |  | 29191.0446
2026-03-18 | 175811.2474 |  | 29301.8746 |  | 29301.8746 |  | 29301.8746 |  | 29301.8746 |  | 29301.8746 |  | 29301.8746
2026-03-19 | 176476.2271 |  | 29412.7045 |  | 29412.7045 |  | 29412.7045 |  | 29412.7045 |  | 29412.7045 |  | 29412.7045
2026-03-20 | 177141.2069 |  | 29523.5345 |  | 29523.5345 |  | 29523.5345 |  | 29523.5345 |  | 29523.5345 |  | 29523.5345
2026-03-21 | 177806.1866 |  | 29634.3644 |  | 29634.3644 |  | 29634.3644 |  | 29634.3644 |  | 29634.3644 |  | 29634.3644
2026-03-22 | 178471.1664 |  | 29745.1944 |  | 29745.1944 |  | 29745.1944 |  | 29745.1944 |  | 29745.1944 |  | 29745.1944
2026-03-23 | 179136.1462 |  | 29856.0244 |  | 29856.0244 |  | 29856.0244 |  | 29856.0244 |  | 29856.0244 |  | 29856.0244
2026-03-24 | 179801.1259 |  | 29966.8543 |  | 29966.8543 |  | 29966.8543 |  | 29966.8543 |  | 29966.8543 |  | 29966.8543
2026-03-25 | 180466.1057 |  | 30077.6843 |  | 30077.6843 |  | 30077.6843 |  | 30077.6843 |  | 30077.6843 |  | 30077.6843
2026-03-26 | 181131.0854 |  | 30188.5142 |  | 30188.5142 |  | 30188.5142 |  | 30188.5142 |  | 30188.5142 |  | 30188.5142
2026-03-27 | 181796.0652 |  | 30299.3442 |  | 30299.3442 |  | 30299.3442 |  | 30299.3442 |  | 30299.3442 |  | 30299.3442
2026-03-28 | 182461.045 |  | 30410.1742 |  | 30410.1742 |  | 30410.1742 |  | 30410.1742 |  | 30410.1742 |  | 30410.1742
2026-03-29 | 183126.0247 |  | 30521.0041 |  | 30521.0041 |  | 30521.0041 |  | 30521.0041 |  | 30521.0041 |  | 30521.0041
2026-03-30 | 183791.0045 |  | 30631.8341 |  | 30631.8341 |  | 30631.8341 |  | 30631.8341 |  | 30631.8341 |  | 30631.8341
2026-03-31 | 184455.9842 |  | 30742.664 |  | 30742.664 |  | 30742.664 |  | 30742.664 |  | 30742.664 |  | 30742.664
2026-04-01 | 185120.964 |  | 30853.494 |  | 30853.494 |  | 30853.494 |  | 30853.494 |  | 30853.494 |  | 30853.494
2026-04-02 | 185785.9438 |  | 30964.324 |  | 30964.324 |  | 30964.324 |  | 30964.324 |  | 30964.324 |  | 30964.324
2026-04-03 | 186450.9235 |  | 31075.1539 |  | 31075.1539 |  | 31075.1539 |  | 31075.1539 |  | 31075.1539 |  | 31075.1539
2026-04-04 | 187115.9033 |  | 31185.9839 |  | 31185.9839 |  | 31185.9839 |  | 31185.9839 |  | 31185.9839 |  | 31185.9839
2026-04-05 | 187780.883 |  | 31296.8138 |  | 31296.8138 |  | 31296.8138 |  | 31296.8138 |  | 31296.8138 |  | 31296.8138
2026-04-06 | 188445.8628 |  | 31407.6438 |  | 31407.6438 |  | 31407.6438 |  | 31407.6438 |  | 31407.6438 |  | 31407.6438
2026-04-07 | 189110.8426 |  | 31518.4738 |  | 31518.4738 |  | 31518.4738 |  | 31518.4738 |  | 31518.4738 |  | 31518.4738
2026-04-08 | 189775.8223 |  | 31629.3037 |  | 31629.3037 |  | 31629.3037 |  | 31629.3037 |  | 31629.3037 |  | 31629.3037
2026-04-09 | 190440.8021 |  | 31740.1337 |  | 31740.1337 |  | 31740.1337 |  | 31740.1337 |  | 31740.1337 |  | 31740.1337
2026-04-10 | 191105.7818 |  | 31850.9636 |  | 31850.9636 |  | 31850.9636 |  | 31850.9636 |  | 31850.9636 |  | 31850.9636
2026-04-11 | 191770.7616 |  | 31961.7936 |  | 31961.7936 |  | 31961.7936 |  | 31961.7936 |  | 31961.7936 |  | 31961.7936
2026-04-12 | 192435.7414 |  | 32072.6236 |  | 32072.6236 |  | 32072.6236 |  | 32072.6236 |  | 32072.6236 |  | 32072.6236
2026-04-13 | 193100.7211 |  | 32183.4535 |  | 32183.4535 |  | 32183.4535 |  | 32183.4535 |  | 32183.4535 |  | 32183.4535
2026-04-14 | 193765.7009 |  | 32294.2835 |  | 32294.2835 |  | 32294.2835 |  | 32294.2835 |  | 32294.2835 |  | 32294.2835
2026-04-15 | 194430.6806 |  | 32405.1134 |  | 32405.1134 |  | 32405.1134 |  | 32405.1134 |  | 32405.1134 |  | 32405.1134
2026-04-16 | 195095.6604 |  | 32515.9434 |  | 32515.9434 |  | 32515.9434 |  | 32515.9434 |  | 32515.9434 |  | 32515.9434
2026-04-17 | 195760.6402 |  | 32626.7734 |  | 32626.7734 |  | 32626.7734 |  | 32626.7734 |  | 32626.7734 |  | 32626.7734
2026-04-18 | 196425.6199 |  | 32737.6033 |  | 32737.6033 |  | 32737.6033 |  | 32737.6033 |  | 32737.6033 |  | 32737.6033
2026-04-19 | 197090.5997 |  | 32848.4333 |  | 32848.4333 |  | 32848.4333 |  | 32848.4333 |  | 32848.4333 |  | 32848.4333
2026-04-20 | 197755.5794 |  | 32959.2632 |  | 32959.2632 |  | 32959.2632 |  | 32959.2632 |  | 32959.2632 |  | 32959.2632
2026-04-21 | 198420.5592 |  | 33070.0932 |  | 33070.0932 |  | 33070.0932 |  | 33070.0932 |  | 33070.0932 |  | 33070.0932
2026-04-22 | 199085.539 |  | 33180.9232 |  | 33180.9232 |  | 33180.9232 |  | 33180.9232 |  | 33180.9232 |  | 33180.9232
2026-04-23 | 199750.5187 |  | 33291.7531 |  | 33291.7531 |  | 33291.7531 |  | 33291.7531 |  | 33291.7531 |  | 33291.7531
2026-04-24 | 200415.4985 |  | 33402.5831 |  | 33402.5831 |  | 33402.5831 |  | 33402.5831 |  | 33402.5831 |  | 33402.5831
2026-04-25 | 201080.4782 |  | 33513.413 |  | 33513.413 |  | 33513.413 |  | 33513.413 |  | 33513.413 |  | 33513.413
2026-04-26 | 201745.458 |  | 33624.243 |  | 33624.243 |  | 33624.243 |  | 33624.243 |  | 33624.243 |  | 33624.243
2026-04-27 | 202410.4378 |  | 33735.073 |  | 33735.073 |  | 33735.073 |  | 33735.073 |  | 33735.073 |  | 33735.073
2026-04-28 | 203075.4175 |  | 33845.9029 |  | 33845.9029 |  | 33845.9029 |  | 33845.9029 |  | 33845.9029 |  | 33845.9029
2026-04-29 | 203740.3973 |  | 33956.7329 |  | 33956.7329 |  | 33956.7329 |  | 33956.7329 |  | 33956.7329 |  | 33956.7329
2026-04-30 | 204405.377 |  | 34067.5628 |  | 34067.5628 |  | 34067.5628 |  | 34067.5628 |  | 34067.5628 |  | 34067.5628
2026-05-01 | 205070.3568 |  | 34178.3928 |  | 34178.3928 |  | 34178.3928 |  | 34178.3928 |  | 34178.3928 |  | 34178.3928
2026-05-02 | 205735.3366 |  | 34289.2228 |  | 34289.2228 |  | 34289.2228 |  | 34289.2228 |  | 34289.2228 |  | 34289.2228
2026-05-03 | 206400.3163 |  | 34400.0527 |  | 34400.0527 |  | 34400.0527 |  | 34400.0527 |  | 34400.0527 |  | 34400.0527
2026-05-04 | 207065.2961 |  | 34510.8827 |  | 34510.8827 |  | 34510.8827 |  | 34510.8827 |  | 34510.8827 |  | 34510.8827
2026-05-05 | 207730.2758 |  | 34621.7126 |  | 34621.7126 |  | 34621.7126 |  | 34621.7126 |  | 34621.7126 |  | 34621.7126
2026-05-06 | 208395.2556 |  | 34732.5426 |  | 34732.5426 |  | 34732.5426 |  | 34732.5426 |  | 34732.5426 |  | 34732.5426
2026-05-07 | 209060.2354 |  | 34843.3726 |  | 34843.3726 |  | 34843.3726 |  | 34843.3726 |  | 34843.3726 |  | 34843.3726
2026-05-08 | 209725.2151 |  | 34954.2025 |  | 34954.2025 |  | 34954.2025 |  | 34954.2025 |  | 34954.2025 |  | 34954.2025
2026-05-09 | 210390.1949 |  | 35065.0325 |  | 35065.0325 |  | 35065.0325 |  | 35065.0325 |  | 35065.0325 |  | 35065.0325
2026-05-10 | 211055.1746 |  | 35175.8624 |  | 35175.8624 |  | 35175.8624 |  | 35175.8624 |  | 35175.8624 |  | 35175.8624
2026-05-11 | 211720.1544 |  | 35286.6924 |  | 35286.6924 |  | 35286.6924 |  | 35286.6924 |  | 35286.6924 |  | 35286.6924
2026-05-12 | 212385.1342 |  | 35397.5224 |  | 35397.5224 |  | 35397.5224 |  | 35397.5224 |  | 35397.5224 |  | 35397.5224
2026-05-13 | 213050.1139 |  | 35508.3523 |  | 35508.3523 |  | 35508.3523 |  | 35508.3523 |  | 35508.3523 |  | 35508.3523
2026-05-14 | 213715.0937 |  | 35619.1823 |  | 35619.1823 |  | 35619.1823 |  | 35619.1823 |  | 35619.1823 |  | 35619.1823
2026-05-15 | 214380.0734 |  | 35730.0122 |  | 35730.0122 |  | 35730.0122 |  | 35730.0122 |  | 35730.0122 |  | 35730.0122
2026-05-16 | 215045.0532 |  | 35840.8422 |  | 35840.8422 |  | 35840.8422 |  | 35840.8422 |  | 35840.8422 |  | 35840.8422
2026-05-17 | 215710.033 |  | 35951.6722 |  | 35951.6722 |  | 35951.6722 |  | 35951.6722 |  | 35951.6722 |  | 35951.6722
2026-05-18 | 216375.0127 |  | 36062.5021 |  | 36062.5021 |  | 36062.5021 |  | 36062.5021 |  | 36062.5021 |  | 36062.5021
2026-05-19 | 217039.9925 |  | 36173.3321 |  | 36173.3321 |  | 36173.3321 |  | 36173.3321 |  | 36173.3321 |  | 36173.3321
2026-05-20 | 217704.9722 |  | 36284.162 |  | 36284.162 |  | 36284.162 |  | 36284.162 |  | 36284.162 |  | 36284.162
2026-05-21 | 218369.952 |  | 36394.992 |  | 36394.992 |  | 36394.992 |  | 36394.992 |  | 36394.992 |  | 36394.992
2026-05-22 | 220104.8247 |  | 36684.1375 |  | 36684.1375 |  | 36684.1375 |  | 36684.1375 |  | 36684.1375 |  | 36684.1375
2026-05-23 | 221839.6975 |  | 36973.2829 |  | 36973.2829 |  | 36973.2829 |  | 36973.2829 |  | 36973.2829 |  | 36973.2829
2026-05-24 | 223574.5702 |  | 37262.4284 |  | 37262.4284 |  | 37262.4284 |  | 37262.4284 |  | 37262.4284 |  | 37262.4284
2026-05-25 | 225309.4429 |  | 37551.5738 |  | 37551.5738 |  | 37551.5738 |  | 37551.5738 |  | 37551.5738 |  | 37551.5738
2026-05-26 | 227044.3156 |  | 37840.7193 |  | 37840.7193 |  | 37840.7193 |  | 37840.7193 |  | 37840.7193 |  | 37840.7193
2026-05-27 | 228779.1884 |  | 38129.8647 |  | 38129.8647 |  | 38129.8647 |  | 38129.8647 |  | 38129.8647 |  | 38129.8647
2026-05-28 | 230514.0611 |  | 38419.0102 |  | 38419.0102 |  | 38419.0102 |  | 38419.0102 |  | 38419.0102 |  | 38419.0102
2026-05-29 | 232248.9338 |  | 38708.1556 |  | 38708.1556 |  | 38708.1556 |  | 38708.1556 |  | 38708.1556 |  | 38708.1556
2026-05-30 | 233983.8065 |  | 38997.3011 |  | 38997.3011 |  | 38997.3011 |  | 38997.3011 |  | 38997.3011 |  | 38997.3011
2026-05-31 | 235718.6793 |  | 39286.4465 |  | 39286.4465 |  | 39286.4465 |  | 39286.4465 |  | 39286.4465 |  | 39286.4465
2026-06-01 | 237453.552 |  | 39575.592 |  | 39575.592 |  | 39575.592 |  | 39575.592 |  | 39575.592 |  | 39575.592
2026-06-02 | 239188.4247 |  | 39864.7375 |  | 39864.7375 |  | 39864.7375 |  | 39864.7375 |  | 39864.7375 |  | 39864.7375
2026-06-03 | 240923.2975 |  | 40153.8829 |  | 40153.8829 |  | 40153.8829 |  | 40153.8829 |  | 40153.8829 |  | 40153.8829
2026-06-04 | 242658.1702 |  | 40443.0284 |  | 40443.0284 |  | 40443.0284 |  | 40443.0284 |  | 40443.0284 |  | 40443.0284
2026-06-05 | 244393.0429 |  | 40732.1738 |  | 40732.1738 |  | 40732.1738 |  | 40732.1738 |  | 40732.1738 |  | 40732.1738
2026-06-06 | 246127.9156 |  | 41021.3193 |  | 41021.3193 |  | 41021.3193 |  | 41021.3193 |  | 41021.3193 |  | 41021.3193
2026-06-07 | 247862.7884 |  | 41310.4647 |  | 41310.4647 |  | 41310.4647 |  | 41310.4647 |  | 41310.4647 |  | 41310.4647
2026-06-08 | 249597.6611 |  | 41599.6102 |  | 41599.6102 |  | 41599.6102 |  | 41599.6102 |  | 41599.6102 |  | 41599.6102
2026-06-09 | 251332.5338 |  | 41888.7556 |  | 41888.7556 |  | 41888.7556 |  | 41888.7556 |  | 41888.7556 |  | 41888.7556
2026-06-10 | 253067.4065 |  | 42177.9011 |  | 42177.9011 |  | 42177.9011 |  | 42177.9011 |  | 42177.9011 |  | 42177.9011
2026-06-11 | 254802.2793 |  | 42467.0465 |  | 42467.0465 |  | 42467.0465 |  | 42467.0465 |  | 42467.0465 |  | 42467.0465
2026-06-12 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-06-13 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-06-14 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-06-15 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-06-16 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-06-17 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-06-18 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-06-19 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-06-20 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-06-21 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-06-22 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-06-23 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-06-24 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-06-25 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-06-26 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-06-27 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-06-28 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-06-29 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-06-30 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-07-01 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-07-02 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-07-03 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-07-04 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-07-05 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-07-06 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-07-07 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-07-08 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-07-09 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-07-10 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-07-11 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-07-12 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-07-13 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-07-14 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-07-15 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192
2026-07-16 | 256537.152 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192 |  | 42756.192

## Parts&materials (Direct Cost)
Date | Planned Parts&materials (Cumulative) | Actual Parts&materials (Cumulative) | Planned 5004 · GTR Cost of Sales - Parts (Cumulative) | Actual 5004 · GTR Cost of Sales - Parts (Cumulative) | Planned 5111 · Parts & material costs (Direct) (Cumulative) | Actual 5111 · Parts & material costs (Direct) (Cumulative) | Planned 5128 · Health & Safety Equip (Direct) (Cumulative) | Actual 5128 · Health & Safety Equip (Direct) (Cumulative)
2025-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-17 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-18 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-19 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-20 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-21 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-22 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-23 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-24 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-25 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-26 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-27 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-28 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-29 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-04-30 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-01 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-02 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-03 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-04 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-05 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-06 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-07 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-08 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-09 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-10 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-11 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-12 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-13 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-14 | 0 | 33.72 | 0 | 0 | 0 | 33.72 | 0 | 0
2025-05-15 | 0 | 6127.24 | 0 | 0 | 0 | 6127.24 | 0 | 0
2025-05-16 | 0 | 6127.24 | 0 | 0 | 0 | 6127.24 | 0 | 0
2025-05-17 | 0 | 6127.24 | 0 | 0 | 0 | 6127.24 | 0 | 0
2025-05-18 | 0 | 6127.24 | 0 | 0 | 0 | 6127.24 | 0 | 0
2025-05-19 | 0 | 6127.24 | 0 | 0 | 0 | 6127.24 | 0 | 0
2025-05-20 | 0 | 7176.96 | 0 | 0 | 0 | 7176.96 | 0 | 0
2025-05-21 | 0 | 7176.96 | 0 | 0 | 0 | 7176.96 | 0 | 0
2025-05-22 | 0 | 7176.96 | 0 | 0 | 0 | 7176.96 | 0 | 0
2025-05-23 | 0 | 7176.96 | 0 | 0 | 0 | 7176.96 | 0 | 0
2025-05-24 | 0 | 7176.96 | 0 | 0 | 0 | 7176.96 | 0 | 0
2025-05-25 | 0 | 7176.96 | 0 | 0 | 0 | 7176.96 | 0 | 0
2025-05-26 | 0 | 7176.96 | 0 | 0 | 0 | 7176.96 | 0 | 0
2025-05-27 | 0 | 7176.96 | 0 | 0 | 0 | 7176.96 | 0 | 0
2025-05-28 | 0 | 7176.96 | 0 | 0 | 0 | 7176.96 | 0 | 0
2025-05-29 | 0 | 7176.96 | 0 | 0 | 0 | 7176.96 | 0 | 0
2025-05-30 | 0 | 7176.96 | 0 | 0 | 0 | 7176.96 | 0 | 0
2025-06-01 | 1261.7398 | 7176.96 | 420.5799 | 0 | 420.5799 | 7176.96 | 420.5799 | 0
2025-06-02 | 2523.4795 | 7176.96 | 841.1598 | 0 | 841.1598 | 7176.96 | 841.1598 | 0
2025-06-03 | 3785.2193 | 7176.96 | 1261.7398 | 0 | 1261.7398 | 7176.96 | 1261.7398 | 0
2025-06-04 | 5046.959 | 7196.88 | 1682.3197 | 0 | 1682.3197 | 7196.88 | 1682.3197 | 0
2025-06-05 | 6308.6988 | 33683.56 | 2102.8996 | 0 | 2102.8996 | 33683.56 | 2102.8996 | 0
2025-06-06 | 7570.4386 | 33683.56 | 2523.4795 | 0 | 2523.4795 | 33683.56 | 2523.4795 | 0
2025-06-07 | 8832.1783 | 33683.56 | 2944.0594 | 0 | 2944.0594 | 33683.56 | 2944.0594 | 0
2025-06-08 | 10093.9181 | 33683.56 | 3364.6394 | 0 | 3364.6394 | 33683.56 | 3364.6394 | 0
2025-06-09 | 11355.6578 | 33683.56 | 3785.2193 | 0 | 3785.2193 | 33683.56 | 3785.2193 | 0
2025-06-10 | 12617.3976 | 33683.56 | 4205.7992 | 0 | 4205.7992 | 33683.56 | 4205.7992 | 0
2025-06-11 | 13879.1373 | 33683.56 | 4626.3791 | 0 | 4626.3791 | 33683.56 | 4626.3791 | 0
2025-06-12 | 15140.8771 | 33683.56 | 5046.959 | 0 | 5046.959 | 33683.56 | 5046.959 | 0
2025-06-13 | 16402.6169 | 33683.56 | 5467.539 | 0 | 5467.539 | 33683.56 | 5467.539 | 0
2025-06-14 | 17664.3566 | 33683.56 | 5888.1189 | 0 | 5888.1189 | 33683.56 | 5888.1189 | 0
2025-06-15 | 18926.0964 | 33683.56 | 6308.6988 | 0 | 6308.6988 | 33683.56 | 6308.6988 | 0
2025-06-16 | 20187.8361 | 33683.56 | 6729.2787 | 0 | 6729.2787 | 33683.56 | 6729.2787 | 0
2025-06-17 | 21449.5759 | 33683.56 | 7149.8586 | 0 | 7149.8586 | 33683.56 | 7149.8586 | 0
2025-06-18 | 22711.3157 | 33683.56 | 7570.4386 | 0 | 7570.4386 | 33683.56 | 7570.4386 | 0
2025-06-19 | 23973.0554 | 33683.56 | 7991.0185 | 0 | 7991.0185 | 33683.56 | 7991.0185 | 0
2025-06-20 | 25234.7952 | 33683.56 | 8411.5984 | 0 | 8411.5984 | 33683.56 | 8411.5984 | 0
2025-06-21 | 26496.5349 | 33683.56 | 8832.1783 | 0 | 8832.1783 | 33683.56 | 8832.1783 | 0
2025-06-22 | 27758.2747 | 33683.56 | 9252.7582 | 0 | 9252.7582 | 33683.56 | 9252.7582 | 0
2025-06-23 | 29020.0145 | 33683.56 | 9673.3382 | 0 | 9673.3382 | 33683.56 | 9673.3382 | 0
2025-06-24 | 30281.7542 | 33930.56 | 10093.9181 | 0 | 10093.9181 | 33930.56 | 10093.9181 | 0
2025-06-25 | 31543.494 | 34318.96 | 10514.498 | 0 | 10514.498 | 34318.96 | 10514.498 | 0
2025-06-26 | 32805.2337 | 34318.96 | 10935.0779 | 0 | 10935.0779 | 34318.96 | 10935.0779 | 0
2025-06-27 | 34066.9735 | 34318.96 | 11355.6578 | 0 | 11355.6578 | 34318.96 | 11355.6578 | 0
2025-06-28 | 35328.7133 | 34318.96 | 11776.2378 | 0 | 11776.2378 | 34318.96 | 11776.2378 | 0
2025-06-29 | 36590.453 | 34318.96 | 12196.8177 | 0 | 12196.8177 | 34318.96 | 12196.8177 | 0
2025-06-30 | 37852.1928 | 34318.96 | 12617.3976 | 0 | 12617.3976 | 34318.96 | 12617.3976 | 0
2025-07-01 | 39113.9325 | 73029.78 | 13037.9775 | 37227.57 | 13037.9775 | 35802.21 | 13037.9775 | 0
2025-07-02 | 40375.6723 | 73029.78 | 13458.5574 | 37227.57 | 13458.5574 | 35802.21 | 13458.5574 | 0
2025-07-03 | 41637.412 | 73112.36 | 13879.1373 | 37227.57 | 13879.1373 | 35884.79 | 13879.1373 | 0
2025-07-04 | 42899.1518 | 73398.98 | 14299.7173 | 37227.57 | 14299.7173 | 36171.41 | 14299.7173 | 0
2025-07-05 | 44160.8916 | 73449.23 | 14720.2972 | 37227.57 | 14720.2972 | 36221.66 | 14720.2972 | 0
2025-07-06 | 45422.6313 | 73449.23 | 15140.8771 | 37227.57 | 15140.8771 | 36221.66 | 15140.8771 | 0
2025-07-07 | 46684.3711 | 73449.23 | 15561.457 | 37227.57 | 15561.457 | 36221.66 | 15561.457 | 0
2025-07-08 | 47946.1108 | 74110.56 | 15982.0369 | 37227.57 | 15982.0369 | 36882.99 | 15982.0369 | 0
2025-07-09 | 49207.8506 | 74110.56 | 16402.6169 | 37227.57 | 16402.6169 | 36882.99 | 16402.6169 | 0
2025-07-10 | 50469.5904 | 74110.56 | 16823.1968 | 37227.57 | 16823.1968 | 36882.99 | 16823.1968 | 0
2025-07-11 | 51731.3301 | 75440.37 | 17243.7767 | 37227.57 | 17243.7767 | 38212.8 | 17243.7767 | 0
2025-07-12 | 52993.0699 | 75440.37 | 17664.3566 | 37227.57 | 17664.3566 | 38212.8 | 17664.3566 | 0
2025-07-13 | 54254.8096 | 75440.37 | 18084.9365 | 37227.57 | 18084.9365 | 38212.8 | 18084.9365 | 0
2025-07-14 | 55516.5494 | 80693.65 | 18505.5165 | 37227.57 | 18505.5165 | 43466.08 | 18505.5165 | 0
2025-07-15 | 56778.2892 | 82115.91 | 18926.0964 | 37227.57 | 18926.0964 | 44888.34 | 18926.0964 | 0
2025-07-16 | 58040.0289 | 82933.46 | 19346.6763 | 37227.57 | 19346.6763 | 45705.89 | 19346.6763 | 0
2025-07-17 | 59301.7687 | 83234.58 | 19767.2562 | 37227.57 | 19767.2562 | 46007.01 | 19767.2562 | 0
2025-07-18 | 60563.5084 | 89166.31 | 20187.8361 | 37227.57 | 20187.8361 | 51938.74 | 20187.8361 | 0
2025-07-19 | 61825.2482 | 89958 | 20608.4161 | 37227.57 | 20608.4161 | 52730.43 | 20608.4161 | 0
2025-07-20 | 63086.988 | 89958 | 21028.996 | 37227.57 | 21028.996 | 52730.43 | 21028.996 | 0
2025-07-21 | 65426.4488 | 89958 | 21808.8163 | 37227.57 | 21808.8163 | 52730.43 | 21808.8163 | 0
2025-07-22 | 67765.9096 | 105360.93 | 22588.6365 | 37227.57 | 22588.6365 | 68133.36 | 22588.6365 | 0
2025-07-23 | 70105.3704 | 108233.85 | 23368.4568 | 37227.57 | 23368.4568 | 71006.28 | 23368.4568 | 0
2025-07-24 | 72444.8312 | 108428.34 | 24148.2771 | 37227.57 | 24148.2771 | 71200.77 | 24148.2771 | 0
2025-07-25 | 74784.292 | 108793.11 | 24928.0973 | 37227.57 | 24928.0973 | 71565.54 | 24928.0973 | 0
2025-07-26 | 77123.7528 | 108809.24 | 25707.9176 | 37227.57 | 25707.9176 | 71581.67 | 25707.9176 | 0
2025-07-27 | 79463.2137 | 108809.24 | 26487.7379 | 37227.57 | 26487.7379 | 71581.67 | 26487.7379 | 0
2025-07-28 | 81802.6745 | 108809.24 | 27267.5582 | 37227.57 | 27267.5582 | 71581.67 | 27267.5582 | 0
2025-07-29 | 84142.1353 | 108809.24 | 28047.3784 | 37227.57 | 28047.3784 | 71581.67 | 28047.3784 | 0
2025-07-30 | 86481.5961 | 110230.3 | 28827.1987 | 37227.57 | 28827.1987 | 73002.73 | 28827.1987 | 0
2025-07-31 | 88821.0569 | 110525.7 | 29607.019 | 37227.57 | 29607.019 | 73002.73 | 29607.019 | 295.4
2025-08-01 | 91160.5177 | 110709.93 | 30386.8392 | 37227.57 | 30386.8392 | 73186.96 | 30386.8392 | 295.4
2025-08-02 | 93499.9786 | 110709.93 | 31166.6595 | 37227.57 | 31166.6595 | 73186.96 | 31166.6595 | 295.4
2025-08-03 | 95839.4394 | 110709.93 | 31946.4798 | 37227.57 | 31946.4798 | 73186.96 | 31946.4798 | 295.4
2025-08-04 | 98178.9002 | 110792.28 | 32726.3001 | 37227.57 | 32726.3001 | 73269.31 | 32726.3001 | 295.4
2025-08-05 | 100518.361 | 110792.28 | 33506.1203 | 37227.57 | 33506.1203 | 73269.31 | 33506.1203 | 295.4
2025-08-06 | 102857.8218 | 110792.28 | 34285.9406 | 37227.57 | 34285.9406 | 73269.31 | 34285.9406 | 295.4
2025-08-07 | 105197.2826 | 110792.28 | 35065.7609 | 37227.57 | 35065.7609 | 73269.31 | 35065.7609 | 295.4
2025-08-08 | 107536.7435 | 110792.28 | 35845.5812 | 37227.57 | 35845.5812 | 73269.31 | 35845.5812 | 295.4
2025-08-09 | 109876.2043 | 110792.28 | 36625.4014 | 37227.57 | 36625.4014 | 73269.31 | 36625.4014 | 295.4
2025-08-10 | 112215.6651 | 110792.28 | 37405.2217 | 37227.57 | 37405.2217 | 73269.31 | 37405.2217 | 295.4
2025-08-11 | 114555.1259 | 110792.28 | 38185.042 | 37227.57 | 38185.042 | 73269.31 | 38185.042 | 295.4
2025-08-12 | 116894.5867 | 110792.28 | 38964.8622 | 37227.57 | 38964.8622 | 73269.31 | 38964.8622 | 295.4
2025-08-13 | 119234.0475 | 110792.28 | 39744.6825 | 37227.57 | 39744.6825 | 73269.31 | 39744.6825 | 295.4
2025-08-14 | 121573.5083 | 110904.23 | 40524.5028 | 37227.57 | 40524.5028 | 73381.26 | 40524.5028 | 295.4
2025-08-15 | 123912.9692 | 110987.22 | 41304.3231 | 37227.57 | 41304.3231 | 73464.25 | 41304.3231 | 295.4
2025-08-16 | 126252.43 | 110987.22 | 42084.1433 | 37227.57 | 42084.1433 | 73464.25 | 42084.1433 | 295.4
2025-08-17 | 128591.8908 | 110987.22 | 42863.9636 | 37227.57 | 42863.9636 | 73464.25 | 42863.9636 | 295.4
2025-08-18 | 130931.3516 | 110987.22 | 43643.7839 | 37227.57 | 43643.7839 | 73464.25 | 43643.7839 | 295.4
2025-08-19 | 133270.8124 | 113546.28 | 44423.6041 | 37227.57 | 44423.6041 | 76023.31 | 44423.6041 | 295.4
2025-08-20 | 135610.2732 | 113546.28 | 45203.4244 | 37227.57 | 45203.4244 | 76023.31 | 45203.4244 | 295.4
2025-08-21 | 137949.7341 | 113546.28 | 45983.2447 | 37227.57 | 45983.2447 | 76023.31 | 45983.2447 | 295.4
2025-08-22 | 140289.1949 | 126479.47 | 46763.065 | 37227.57 | 46763.065 | 88956.5 | 46763.065 | 295.4
2025-08-23 | 141366.9159 | 126479.47 | 47122.3053 | 37227.57 | 47122.3053 | 88956.5 | 47122.3053 | 295.4
2025-08-24 | 142444.637 | 126479.47 | 47481.5457 | 37227.57 | 47481.5457 | 88956.5 | 47481.5457 | 295.4
2025-08-25 | 143522.358 | 127464.71 | 47840.786 | 37227.57 | 47840.786 | 89941.74 | 47840.786 | 295.4
2025-08-26 | 144600.0791 | 127277.85 | 48200.0264 | 37227.57 | 48200.0264 | 89754.88 | 48200.0264 | 295.4
2025-08-27 | 145677.8002 | 127992.98 | 48559.2667 | 37227.57 | 48559.2667 | 90470.01 | 48559.2667 | 295.4
2025-08-28 | 146755.5212 | 127992.98 | 48918.5071 | 37227.57 | 48918.5071 | 90470.01 | 48918.5071 | 295.4
2025-08-29 | 147833.2423 | 128286.53 | 49277.7474 | 37227.57 | 49277.7474 | 90763.56 | 49277.7474 | 295.4
2025-08-30 | 148910.9633 | 128286.53 | 49636.9878 | 37227.57 | 49636.9878 | 90763.56 | 49636.9878 | 295.4
2025-08-31 | 149988.6844 | 128286.53 | 49996.2281 | 37227.57 | 49996.2281 | 90763.56 | 49996.2281 | 295.4
2025-09-01 | 151066.4054 | 128286.53 | 50355.4685 | 37227.57 | 50355.4685 | 90763.56 | 50355.4685 | 295.4
2025-09-02 | 151512.6638 | 128566.7 | 50504.2213 | 37227.57 | 50504.2213 | 91043.73 | 50504.2213 | 295.4
2025-09-03 | 151958.9221 | 132429.51 | 50652.974 | 37227.57 | 50652.974 | 94906.54 | 50652.974 | 295.4
2025-09-04 | 152405.1804 | 132429.51 | 50801.7268 | 37227.57 | 50801.7268 | 94906.54 | 50801.7268 | 295.4
2025-09-05 | 152851.4388 | 132429.51 | 50950.4796 | 37227.57 | 50950.4796 | 94906.54 | 50950.4796 | 295.4
2025-09-06 | 153297.6971 | 132429.51 | 51099.2324 | 37227.57 | 51099.2324 | 94906.54 | 51099.2324 | 295.4
2025-09-07 | 153743.9554 | 132429.51 | 51247.9851 | 37227.57 | 51247.9851 | 94906.54 | 51247.9851 | 295.4
2025-09-08 | 154190.2138 | 132429.51 | 51396.7379 | 37227.57 | 51396.7379 | 94906.54 | 51396.7379 | 295.4
2025-09-09 | 154636.4721 | 132429.51 | 51545.4907 | 37227.57 | 51545.4907 | 94906.54 | 51545.4907 | 295.4
2025-09-10 | 155082.7304 | 132483.11 | 51694.2435 | 37227.57 | 51694.2435 | 94960.14 | 51694.2435 | 295.4
2025-09-11 | 155528.9888 | 132566.1 | 51842.9963 | 37227.57 | 51842.9963 | 95043.13 | 51842.9963 | 295.4
2025-09-12 | 155975.2471 | 132566.1 | 51991.749 | 37227.57 | 51991.749 | 95043.13 | 51991.749 | 295.4
2025-09-13 | 156421.5054 | 132566.1 | 52140.5018 | 37227.57 | 52140.5018 | 95043.13 | 52140.5018 | 295.4
2025-09-14 | 156867.7638 | 132566.1 | 52289.2546 | 37227.57 | 52289.2546 | 95043.13 | 52289.2546 | 295.4
2025-09-15 | 157314.0221 | 132859.65 | 52438.0074 | 37227.57 | 52438.0074 | 95336.68 | 52438.0074 | 295.4
2025-09-16 | 157760.2804 | 132859.65 | 52586.7601 | 37227.57 | 52586.7601 | 95336.68 | 52586.7601 | 295.4
2025-09-17 | 158206.5388 | 132859.65 | 52735.5129 | 37227.57 | 52735.5129 | 95336.68 | 52735.5129 | 295.4
2025-09-18 | 158652.7971 | 132859.65 | 52884.2657 | 37227.57 | 52884.2657 | 95336.68 | 52884.2657 | 295.4
2025-09-19 | 159099.0554 | 132859.65 | 53033.0185 | 37227.57 | 53033.0185 | 95336.68 | 53033.0185 | 295.4
2025-09-20 | 159545.3138 | 132859.65 | 53181.7713 | 37227.57 | 53181.7713 | 95336.68 | 53181.7713 | 295.4
2025-09-21 | 159991.5721 | 132859.65 | 53330.524 | 37227.57 | 53330.524 | 95336.68 | 53330.524 | 295.4
2025-09-22 | 160437.8304 | 132859.65 | 53479.2768 | 37227.57 | 53479.2768 | 95336.68 | 53479.2768 | 295.4
2025-09-23 | 160884.0888 | 133153.2 | 53628.0296 | 37227.57 | 53628.0296 | 95630.23 | 53628.0296 | 295.4
2025-09-24 | 161330.3471 | 133153.2 | 53776.7824 | 37227.57 | 53776.7824 | 95630.23 | 53776.7824 | 295.4
2025-09-25 | 161776.6054 | 133153.2 | 53925.5351 | 37227.57 | 53925.5351 | 95630.23 | 53925.5351 | 295.4
2025-09-26 | 162222.8638 | 133153.2 | 54074.2879 | 37227.57 | 54074.2879 | 95630.23 | 54074.2879 | 295.4
2025-09-27 | 162669.1221 | 133153.2 | 54223.0407 | 37227.57 | 54223.0407 | 95630.23 | 54223.0407 | 295.4
2025-09-28 | 163115.3804 | 133153.2 | 54371.7935 | 37227.57 | 54371.7935 | 95630.23 | 54371.7935 | 295.4
2025-09-29 | 163561.6388 | 133153.2 | 54520.5463 | 37227.57 | 54520.5463 | 95630.23 | 54520.5463 | 295.4
2025-09-30 | 164007.8971 | 133153.2 | 54669.299 | 37227.57 | 54669.299 | 95630.23 | 54669.299 | 295.4
2025-10-01 | 164454.1554 | 133153.2 | 54818.0518 | 37227.57 | 54818.0518 | 95630.23 | 54818.0518 | 295.4
2025-10-02 | 164900.4138 | 133153.2 | 54966.8046 | 37227.57 | 54966.8046 | 95630.23 | 54966.8046 | 295.4
2025-10-03 | 165346.6721 | 133153.2 | 55115.5574 | 37227.57 | 55115.5574 | 95630.23 | 55115.5574 | 295.4
2025-10-04 | 165792.9304 | 133153.2 | 55264.3101 | 37227.57 | 55264.3101 | 95630.23 | 55264.3101 | 295.4
2025-10-05 | 166239.1888 | 133153.2 | 55413.0629 | 37227.57 | 55413.0629 | 95630.23 | 55413.0629 | 295.4
2025-10-06 | 166685.4471 | 133153.2 | 55561.8157 | 37227.57 | 55561.8157 | 95630.23 | 55561.8157 | 295.4
2025-10-07 | 167131.7054 | 133153.2 | 55710.5685 | 37227.57 | 55710.5685 | 95630.23 | 55710.5685 | 295.4
2025-10-08 | 167577.9638 | 133153.2 | 55859.3213 | 37227.57 | 55859.3213 | 95630.23 | 55859.3213 | 295.4
2025-10-09 | 168024.2221 | 133153.2 | 56008.074 | 37227.57 | 56008.074 | 95630.23 | 56008.074 | 295.4
2025-10-10 | 168470.4804 | 133153.2 | 56156.8268 | 37227.57 | 56156.8268 | 95630.23 | 56156.8268 | 295.4
2025-10-11 | 168916.7388 | 133153.2 | 56305.5796 | 37227.57 | 56305.5796 | 95630.23 | 56305.5796 | 295.4
2025-10-12 | 169362.9971 | 133153.2 | 56454.3324 | 37227.57 | 56454.3324 | 95630.23 | 56454.3324 | 295.4
2025-10-13 | 169809.2554 | 133153.2 | 56603.0851 | 37227.57 | 56603.0851 | 95630.23 | 56603.0851 | 295.4
2025-10-14 | 170255.5138 | 133153.2 | 56751.8379 | 37227.57 | 56751.8379 | 95630.23 | 56751.8379 | 295.4
2025-10-15 | 170701.7721 | 133153.2 | 56900.5907 | 37227.57 | 56900.5907 | 95630.23 | 56900.5907 | 295.4
2025-10-16 | 171148.0304 | 133153.2 | 57049.3435 | 37227.57 | 57049.3435 | 95630.23 | 57049.3435 | 295.4
2025-10-17 | 171594.2888 | 133153.2 | 57198.0963 | 37227.57 | 57198.0963 | 95630.23 | 57198.0963 | 295.4
2025-10-18 | 172040.5471 | 133153.2 | 57346.849 | 37227.57 | 57346.849 | 95630.23 | 57346.849 | 295.4
2025-10-19 | 172486.8054 | 133153.2 | 57495.6018 | 37227.57 | 57495.6018 | 95630.23 | 57495.6018 | 295.4
2025-10-20 | 172933.0638 |  | 57644.3546 |  | 57644.3546 |  | 57644.3546
2025-10-21 | 173379.3221 |  | 57793.1074 |  | 57793.1074 |  | 57793.1074
2025-10-22 | 173825.5804 |  | 57941.8601 |  | 57941.8601 |  | 57941.8601
2025-10-23 | 174271.8388 |  | 58090.6129 |  | 58090.6129 |  | 58090.6129
2025-10-24 | 174718.0971 |  | 58239.3657 |  | 58239.3657 |  | 58239.3657
2025-10-25 | 175164.3554 |  | 58388.1185 |  | 58388.1185 |  | 58388.1185
2025-10-26 | 175610.6138 |  | 58536.8713 |  | 58536.8713 |  | 58536.8713
2025-10-27 | 176056.8721 |  | 58685.624 |  | 58685.624 |  | 58685.624
2025-10-28 | 176503.1304 |  | 58834.3768 |  | 58834.3768 |  | 58834.3768
2025-10-29 | 176949.3888 |  | 58983.1296 |  | 58983.1296 |  | 58983.1296
2025-10-30 | 177395.6471 |  | 59131.8824 |  | 59131.8824 |  | 59131.8824
2025-10-31 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-03 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-04 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-05 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-06 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-07 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-08 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-09 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-10 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-11 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-12 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-13 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-14 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-15 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-16 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-17 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-18 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-19 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-20 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-21 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-22 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-23 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-24 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-25 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-26 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-27 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-28 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-29 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-11-30 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-01 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-02 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-03 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-04 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-05 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-06 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-07 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-08 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-09 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-10 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-11 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-12 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-13 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-14 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-15 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-16 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-17 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-18 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-19 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-20 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-21 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-22 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-23 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-24 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-25 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-26 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-27 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-28 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-29 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-30 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2025-12-31 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-01 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-02 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-03 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-04 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-05 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-06 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-07 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-08 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-09 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-10 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-11 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-12 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-13 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-14 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-15 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-16 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-17 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-18 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-19 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-20 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-21 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-22 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-23 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-24 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-25 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-26 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-27 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-28 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-29 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-30 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-01-31 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-01 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-02 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-03 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-04 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-05 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-06 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-07 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-08 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-09 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-10 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-11 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-12 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-13 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-14 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-15 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-16 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-17 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-18 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-19 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-20 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-21 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-22 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-23 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-24 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-25 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-26 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-27 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-02-28 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-01 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-02 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-03 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-04 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-05 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-06 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-07 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-08 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-09 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-10 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-11 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-12 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-13 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-14 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-15 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-16 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-17 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-18 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-19 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-20 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-21 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-22 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-23 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-24 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-25 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-26 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-27 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-28 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-29 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-30 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-03-31 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-01 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-02 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-03 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-04 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-05 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-06 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-07 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-08 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-09 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-10 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-11 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-12 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-13 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-14 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-15 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-16 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-17 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-18 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-19 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-20 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-21 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-22 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-23 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-24 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-25 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-26 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-27 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-28 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-29 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-04-30 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-01 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-02 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-03 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-04 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-05 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-06 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-07 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-08 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-09 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-10 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-11 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-12 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-13 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-14 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-15 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-16 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-17 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-18 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-19 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-20 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-21 | 177841.9054 |  | 59280.6351 |  | 59280.6351 |  | 59280.6351
2026-05-22 | 178064.8178 |  | 59354.9393 |  | 59354.9393 |  | 59354.9393
2026-05-23 | 178287.7301 |  | 59429.2434 |  | 59429.2434 |  | 59429.2434
2026-05-24 | 178510.6425 |  | 59503.5475 |  | 59503.5475 |  | 59503.5475
2026-05-25 | 178733.5548 |  | 59577.8516 |  | 59577.8516 |  | 59577.8516
2026-05-26 | 178956.4671 |  | 59652.1557 |  | 59652.1557 |  | 59652.1557
2026-05-27 | 179179.3795 |  | 59726.4598 |  | 59726.4598 |  | 59726.4598
2026-05-28 | 179402.2918 |  | 59800.7639 |  | 59800.7639 |  | 59800.7639
2026-05-29 | 179625.2042 |  | 59875.0681 |  | 59875.0681 |  | 59875.0681
2026-05-30 | 179848.1165 |  | 59949.3722 |  | 59949.3722 |  | 59949.3722
2026-05-31 | 180071.0288 |  | 60023.6763 |  | 60023.6763 |  | 60023.6763
2026-06-01 | 180293.9412 |  | 60097.9804 |  | 60097.9804 |  | 60097.9804
2026-06-02 | 180516.8535 |  | 60172.2845 |  | 60172.2845 |  | 60172.2845
2026-06-03 | 180739.7659 |  | 60246.5886 |  | 60246.5886 |  | 60246.5886
2026-06-04 | 180962.6782 |  | 60320.8927 |  | 60320.8927 |  | 60320.8927
2026-06-05 | 181185.5906 |  | 60395.1969 |  | 60395.1969 |  | 60395.1969
2026-06-06 | 181408.5029 |  | 60469.501 |  | 60469.501 |  | 60469.501
2026-06-07 | 181631.4152 |  | 60543.8051 |  | 60543.8051 |  | 60543.8051
2026-06-08 | 181854.3276 |  | 60618.1092 |  | 60618.1092 |  | 60618.1092
2026-06-09 | 182077.2399 |  | 60692.4133 |  | 60692.4133 |  | 60692.4133
2026-06-10 | 182300.1523 |  | 60766.7174 |  | 60766.7174 |  | 60766.7174
2026-06-11 | 182523.0646 |  | 60841.0215 |  | 60841.0215 |  | 60841.0215
2026-06-12 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-06-13 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-06-14 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-06-15 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-06-16 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-06-17 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-06-18 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-06-19 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-06-20 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-06-21 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-06-22 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-06-23 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-06-24 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-06-25 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-06-26 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-06-27 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-06-28 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-06-29 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-06-30 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-07-01 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-07-02 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-07-03 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-07-04 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-07-05 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-07-06 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-07-07 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-07-08 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-07-09 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-07-10 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-07-11 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-07-12 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-07-13 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-07-14 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-07-15 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256
2026-07-16 | 182745.9769 |  | 60915.3256 |  | 60915.3256 |  | 60915.3256

## Outsource (Direct Cost)
Date | Planned Outsource (Cumulative) | Actual Outsource (Cumulative) | Planned 5006 · Drilling Expense (Cumulative) | Actual 5006 · Drilling Expense (Cumulative) | Planned 5110 · Temporary labor (Direct) (Cumulative) | Actual 5110 · Temporary labor (Direct) (Cumulative) | Planned 5112 · Carbon & Lab Samplies (Driect) (Cumulative) | Actual 5112 · Carbon & Lab Samplies (Driect) (Cumulative) | Planned 5114 · Rent - Building (Direct) (Cumulative) | Actual 5114 · Rent - Building (Direct) (Cumulative) | Planned 5115 · Rent - Equipment (direct) (Cumulative) | Actual 5115 · Rent - Equipment (direct) (Cumulative) | Planned 5120 · Outside services (Direct) (Cumulative) | Actual 5120 · Outside services (Direct) (Cumulative) | Planned 5121 · Freight & Shipping (Direct) (Cumulative) | Actual 5121 · Freight & Shipping (Direct) (Cumulative) | Planned 5124 · License and permits (Direct) (Cumulative) | Actual 5124 · License and permits (Direct) (Cumulative) | Planned 5129 · Misc expenses (Direct) (Cumulative) | Actual 5129 · Misc expenses (Direct) (Cumulative) | Planned 5132 · Internet fee (Direct) (Cumulative) | Actual 5132 · Internet fee (Direct) (Cumulative) | Planned 6999 · Uncategorized Expenses (Cumulative) | Actual 6999 · Uncategorized Expenses (Cumulative)
2025-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 1405.3373 | 0 | 127.7579 | 0 | 127.7579 | 0 | 127.7579 | 0 | 127.7579 | 0 | 127.7579 | 0 | 127.7579 | 0 | 127.7579 | 0 | 127.7579 | 0 | 127.7579 | 0 | 127.7579 | 0 | 127.7579 | 0
2025-06-02 | 2810.6747 | 0 | 255.5159 | 0 | 255.5159 | 0 | 255.5159 | 0 | 255.5159 | 0 | 255.5159 | 0 | 255.5159 | 0 | 255.5159 | 0 | 255.5159 | 0 | 255.5159 | 0 | 255.5159 | 0 | 255.5159 | 0
2025-06-03 | 4216.012 | 0 | 383.2738 | 0 | 383.2738 | 0 | 383.2738 | 0 | 383.2738 | 0 | 383.2738 | 0 | 383.2738 | 0 | 383.2738 | 0 | 383.2738 | 0 | 383.2738 | 0 | 383.2738 | 0 | 383.2738 | 0
2025-06-04 | 5621.3494 | 0 | 511.0318 | 0 | 511.0318 | 0 | 511.0318 | 0 | 511.0318 | 0 | 511.0318 | 0 | 511.0318 | 0 | 511.0318 | 0 | 511.0318 | 0 | 511.0318 | 0 | 511.0318 | 0 | 511.0318 | 0
2025-06-05 | 7026.6867 | 0 | 638.7897 | 0 | 638.7897 | 0 | 638.7897 | 0 | 638.7897 | 0 | 638.7897 | 0 | 638.7897 | 0 | 638.7897 | 0 | 638.7897 | 0 | 638.7897 | 0 | 638.7897 | 0 | 638.7897 | 0
2025-06-06 | 8432.0241 | 0 | 766.5476 | 0 | 766.5476 | 0 | 766.5476 | 0 | 766.5476 | 0 | 766.5476 | 0 | 766.5476 | 0 | 766.5476 | 0 | 766.5476 | 0 | 766.5476 | 0 | 766.5476 | 0 | 766.5476 | 0
2025-06-07 | 9837.3614 | 0 | 894.3056 | 0 | 894.3056 | 0 | 894.3056 | 0 | 894.3056 | 0 | 894.3056 | 0 | 894.3056 | 0 | 894.3056 | 0 | 894.3056 | 0 | 894.3056 | 0 | 894.3056 | 0 | 894.3056 | 0
2025-06-08 | 11242.6988 | 0 | 1022.0635 | 0 | 1022.0635 | 0 | 1022.0635 | 0 | 1022.0635 | 0 | 1022.0635 | 0 | 1022.0635 | 0 | 1022.0635 | 0 | 1022.0635 | 0 | 1022.0635 | 0 | 1022.0635 | 0 | 1022.0635 | 0
2025-06-09 | 12648.0361 | 0 | 1149.8215 | 0 | 1149.8215 | 0 | 1149.8215 | 0 | 1149.8215 | 0 | 1149.8215 | 0 | 1149.8215 | 0 | 1149.8215 | 0 | 1149.8215 | 0 | 1149.8215 | 0 | 1149.8215 | 0 | 1149.8215 | 0
2025-06-10 | 14053.3735 | 0 | 1277.5794 | 0 | 1277.5794 | 0 | 1277.5794 | 0 | 1277.5794 | 0 | 1277.5794 | 0 | 1277.5794 | 0 | 1277.5794 | 0 | 1277.5794 | 0 | 1277.5794 | 0 | 1277.5794 | 0 | 1277.5794 | 0
2025-06-11 | 15458.7108 | 0 | 1405.3373 | 0 | 1405.3373 | 0 | 1405.3373 | 0 | 1405.3373 | 0 | 1405.3373 | 0 | 1405.3373 | 0 | 1405.3373 | 0 | 1405.3373 | 0 | 1405.3373 | 0 | 1405.3373 | 0 | 1405.3373 | 0
2025-06-12 | 16864.0482 | 0 | 1533.0953 | 0 | 1533.0953 | 0 | 1533.0953 | 0 | 1533.0953 | 0 | 1533.0953 | 0 | 1533.0953 | 0 | 1533.0953 | 0 | 1533.0953 | 0 | 1533.0953 | 0 | 1533.0953 | 0 | 1533.0953 | 0
2025-06-13 | 18269.3855 | 0 | 1660.8532 | 0 | 1660.8532 | 0 | 1660.8532 | 0 | 1660.8532 | 0 | 1660.8532 | 0 | 1660.8532 | 0 | 1660.8532 | 0 | 1660.8532 | 0 | 1660.8532 | 0 | 1660.8532 | 0 | 1660.8532 | 0
2025-06-14 | 19674.7229 | 0 | 1788.6112 | 0 | 1788.6112 | 0 | 1788.6112 | 0 | 1788.6112 | 0 | 1788.6112 | 0 | 1788.6112 | 0 | 1788.6112 | 0 | 1788.6112 | 0 | 1788.6112 | 0 | 1788.6112 | 0 | 1788.6112 | 0
2025-06-15 | 21080.0602 | 0 | 1916.3691 | 0 | 1916.3691 | 0 | 1916.3691 | 0 | 1916.3691 | 0 | 1916.3691 | 0 | 1916.3691 | 0 | 1916.3691 | 0 | 1916.3691 | 0 | 1916.3691 | 0 | 1916.3691 | 0 | 1916.3691 | 0
2025-06-16 | 22485.3976 | 0 | 2044.1271 | 0 | 2044.1271 | 0 | 2044.1271 | 0 | 2044.1271 | 0 | 2044.1271 | 0 | 2044.1271 | 0 | 2044.1271 | 0 | 2044.1271 | 0 | 2044.1271 | 0 | 2044.1271 | 0 | 2044.1271 | 0
2025-06-17 | 23890.7349 | 0 | 2171.885 | 0 | 2171.885 | 0 | 2171.885 | 0 | 2171.885 | 0 | 2171.885 | 0 | 2171.885 | 0 | 2171.885 | 0 | 2171.885 | 0 | 2171.885 | 0 | 2171.885 | 0 | 2171.885 | 0
2025-06-18 | 25296.0723 | 0 | 2299.6429 | 0 | 2299.6429 | 0 | 2299.6429 | 0 | 2299.6429 | 0 | 2299.6429 | 0 | 2299.6429 | 0 | 2299.6429 | 0 | 2299.6429 | 0 | 2299.6429 | 0 | 2299.6429 | 0 | 2299.6429 | 0
2025-06-19 | 26701.4096 | 0 | 2427.4009 | 0 | 2427.4009 | 0 | 2427.4009 | 0 | 2427.4009 | 0 | 2427.4009 | 0 | 2427.4009 | 0 | 2427.4009 | 0 | 2427.4009 | 0 | 2427.4009 | 0 | 2427.4009 | 0 | 2427.4009 | 0
2025-06-20 | 28106.747 | 582.5 | 2555.1588 | 0 | 2555.1588 | 0 | 2555.1588 | 0 | 2555.1588 | 0 | 2555.1588 | 0 | 2555.1588 | 0 | 2555.1588 | 0 | 2555.1588 | 0 | 2555.1588 | 582.5 | 2555.1588 | 0 | 2555.1588 | 0
2025-06-21 | 29512.0843 | 582.5 | 2682.9168 | 0 | 2682.9168 | 0 | 2682.9168 | 0 | 2682.9168 | 0 | 2682.9168 | 0 | 2682.9168 | 0 | 2682.9168 | 0 | 2682.9168 | 0 | 2682.9168 | 582.5 | 2682.9168 | 0 | 2682.9168 | 0
2025-06-22 | 30917.4217 | 582.5 | 2810.6747 | 0 | 2810.6747 | 0 | 2810.6747 | 0 | 2810.6747 | 0 | 2810.6747 | 0 | 2810.6747 | 0 | 2810.6747 | 0 | 2810.6747 | 0 | 2810.6747 | 582.5 | 2810.6747 | 0 | 2810.6747 | 0
2025-06-23 | 32322.759 | 582.5 | 2938.4326 | 0 | 2938.4326 | 0 | 2938.4326 | 0 | 2938.4326 | 0 | 2938.4326 | 0 | 2938.4326 | 0 | 2938.4326 | 0 | 2938.4326 | 0 | 2938.4326 | 582.5 | 2938.4326 | 0 | 2938.4326 | 0
2025-06-24 | 33728.0964 | 582.5 | 3066.1906 | 0 | 3066.1906 | 0 | 3066.1906 | 0 | 3066.1906 | 0 | 3066.1906 | 0 | 3066.1906 | 0 | 3066.1906 | 0 | 3066.1906 | 0 | 3066.1906 | 582.5 | 3066.1906 | 0 | 3066.1906 | 0
2025-06-25 | 35133.4337 | 582.5 | 3193.9485 | 0 | 3193.9485 | 0 | 3193.9485 | 0 | 3193.9485 | 0 | 3193.9485 | 0 | 3193.9485 | 0 | 3193.9485 | 0 | 3193.9485 | 0 | 3193.9485 | 582.5 | 3193.9485 | 0 | 3193.9485 | 0
2025-06-26 | 36538.7711 | 582.5 | 3321.7065 | 0 | 3321.7065 | 0 | 3321.7065 | 0 | 3321.7065 | 0 | 3321.7065 | 0 | 3321.7065 | 0 | 3321.7065 | 0 | 3321.7065 | 0 | 3321.7065 | 582.5 | 3321.7065 | 0 | 3321.7065 | 0
2025-06-27 | 37944.1084 | 582.5 | 3449.4644 | 0 | 3449.4644 | 0 | 3449.4644 | 0 | 3449.4644 | 0 | 3449.4644 | 0 | 3449.4644 | 0 | 3449.4644 | 0 | 3449.4644 | 0 | 3449.4644 | 582.5 | 3449.4644 | 0 | 3449.4644 | 0
2025-06-28 | 39349.4458 | 582.5 | 3577.2223 | 0 | 3577.2223 | 0 | 3577.2223 | 0 | 3577.2223 | 0 | 3577.2223 | 0 | 3577.2223 | 0 | 3577.2223 | 0 | 3577.2223 | 0 | 3577.2223 | 582.5 | 3577.2223 | 0 | 3577.2223 | 0
2025-06-29 | 40754.7831 | 582.5 | 3704.9803 | 0 | 3704.9803 | 0 | 3704.9803 | 0 | 3704.9803 | 0 | 3704.9803 | 0 | 3704.9803 | 0 | 3704.9803 | 0 | 3704.9803 | 0 | 3704.9803 | 582.5 | 3704.9803 | 0 | 3704.9803 | 0
2025-06-30 | 42160.1205 | 582.5 | 3832.7382 | 0 | 3832.7382 | 0 | 3832.7382 | 0 | 3832.7382 | 0 | 3832.7382 | 0 | 3832.7382 | 0 | 3832.7382 | 0 | 3832.7382 | 0 | 3832.7382 | 582.5 | 3832.7382 | 0 | 3832.7382 | 0
2025-07-01 | 43565.4578 | 582.5 | 3960.4962 | 0 | 3960.4962 | 0 | 3960.4962 | 0 | 3960.4962 | 0 | 3960.4962 | 0 | 3960.4962 | 0 | 3960.4962 | 0 | 3960.4962 | 0 | 3960.4962 | 582.5 | 3960.4962 | 0 | 3960.4962 | 0
2025-07-02 | 44970.7952 | 346.65 | 4088.2541 | 0 | 4088.2541 | 0 | 4088.2541 | 0 | 4088.2541 | 0 | 4088.2541 | 0 | 4088.2541 | 0 | 4088.2541 | 0 | 4088.2541 | 0 | 4088.2541 | 237.5 | 4088.2541 | 0 | 4088.2541 | 0
2025-07-03 | 46376.1325 | 346.65 | 4216.012 | 0 | 4216.012 | 0 | 4216.012 | 0 | 4216.012 | 0 | 4216.012 | 0 | 4216.012 | 0 | 4216.012 | 0 | 4216.012 | 0 | 4216.012 | 237.5 | 4216.012 | 0 | 4216.012 | 0
2025-07-04 | 47781.4699 | 796.65 | 4343.77 | 0 | 4343.77 | 0 | 4343.77 | 0 | 4343.77 | 0 | 4343.77 | 0 | 4343.77 | 0 | 4343.77 | 0 | 4343.77 | 0 | 4343.77 | 237.5 | 4343.77 | 0 | 4343.77 | 0
2025-07-05 | 49186.8072 | 796.65 | 4471.5279 | 0 | 4471.5279 | 0 | 4471.5279 | 0 | 4471.5279 | 0 | 4471.5279 | 0 | 4471.5279 | 0 | 4471.5279 | 0 | 4471.5279 | 0 | 4471.5279 | 237.5 | 4471.5279 | 0 | 4471.5279 | 0
2025-07-06 | 50592.1446 | 796.65 | 4599.2859 | 0 | 4599.2859 | 0 | 4599.2859 | 0 | 4599.2859 | 0 | 4599.2859 | 0 | 4599.2859 | 0 | 4599.2859 | 0 | 4599.2859 | 0 | 4599.2859 | 237.5 | 4599.2859 | 0 | 4599.2859 | 0
2025-07-07 | 51997.4819 | 796.65 | 4727.0438 | 0 | 4727.0438 | 0 | 4727.0438 | 0 | 4727.0438 | 0 | 4727.0438 | 0 | 4727.0438 | 0 | 4727.0438 | 0 | 4727.0438 | 0 | 4727.0438 | 237.5 | 4727.0438 | 0 | 4727.0438 | 0
2025-07-08 | 53402.8193 | 796.65 | 4854.8018 | 0 | 4854.8018 | 0 | 4854.8018 | 0 | 4854.8018 | 0 | 4854.8018 | 0 | 4854.8018 | 0 | 4854.8018 | 0 | 4854.8018 | 0 | 4854.8018 | 237.5 | 4854.8018 | 0 | 4854.8018 | 0
2025-07-09 | 54808.1566 | 889.35 | 4982.5597 | 0 | 4982.5597 | 0 | 4982.5597 | 0 | 4982.5597 | 0 | 4982.5597 | 0 | 4982.5597 | 0 | 4982.5597 | 0 | 4982.5597 | 0 | 4982.5597 | 237.5 | 4982.5597 | 0 | 4982.5597 | 0
2025-07-10 | 56213.494 | 889.35 | 5110.3176 | 0 | 5110.3176 | 0 | 5110.3176 | 0 | 5110.3176 | 0 | 5110.3176 | 0 | 5110.3176 | 0 | 5110.3176 | 0 | 5110.3176 | 0 | 5110.3176 | 237.5 | 5110.3176 | 0 | 5110.3176 | 0
2025-07-11 | 57618.8313 | 1147.65 | 5238.0756 | 0 | 5238.0756 | 0 | 5238.0756 | 0 | 5238.0756 | 0 | 5238.0756 | 0 | 5238.0756 | 0 | 5238.0756 | 258.3 | 5238.0756 | 0 | 5238.0756 | 237.5 | 5238.0756 | 0 | 5238.0756 | 0
2025-07-12 | 59024.1687 | 1147.65 | 5365.8335 | 0 | 5365.8335 | 0 | 5365.8335 | 0 | 5365.8335 | 0 | 5365.8335 | 0 | 5365.8335 | 0 | 5365.8335 | 258.3 | 5365.8335 | 0 | 5365.8335 | 237.5 | 5365.8335 | 0 | 5365.8335 | 0
2025-07-13 | 60429.506 | 1313.83 | 5493.5915 | 0 | 5493.5915 | 0 | 5493.5915 | 0 | 5493.5915 | 0 | 5493.5915 | 0 | 5493.5915 | 0 | 5493.5915 | 258.3 | 5493.5915 | 0 | 5493.5915 | 237.5 | 5493.5915 | 0 | 5493.5915 | 0
2025-07-14 | 61834.8434 | 1313.83 | 5621.3494 | 0 | 5621.3494 | 0 | 5621.3494 | 0 | 5621.3494 | 0 | 5621.3494 | 0 | 5621.3494 | 0 | 5621.3494 | 258.3 | 5621.3494 | 0 | 5621.3494 | 237.5 | 5621.3494 | 0 | 5621.3494 | 0
2025-07-15 | 63240.1807 | 1435.78 | 5749.1073 | 0 | 5749.1073 | 0 | 5749.1073 | 0 | 5749.1073 | 0 | 5749.1073 | 121.95 | 5749.1073 | 0 | 5749.1073 | 258.3 | 5749.1073 | 0 | 5749.1073 | 237.5 | 5749.1073 | 0 | 5749.1073 | 0
2025-07-16 | 64645.5181 | 7735.78 | 5876.8653 | 0 | 5876.8653 | 0 | 5876.8653 | 0 | 5876.8653 | 0 | 5876.8653 | 121.95 | 5876.8653 | 0 | 5876.8653 | 6558.3 | 5876.8653 | 0 | 5876.8653 | 237.5 | 5876.8653 | 0 | 5876.8653 | 0
2025-07-17 | 66050.8554 | 7998.27 | 6004.6232 | 0 | 6004.6232 | 0 | 6004.6232 | 0 | 6004.6232 | 0 | 6004.6232 | 121.95 | 6004.6232 | 0 | 6004.6232 | 6558.3 | 6004.6232 | 0 | 6004.6232 | 237.5 | 6004.6232 | 0 | 6004.6232 | 262.49
2025-07-18 | 67456.1928 | 8538.73 | 6132.3812 | 0 | 6132.3812 | 0 | 6132.3812 | 0 | 6132.3812 | 0 | 6132.3812 | 121.95 | 6132.3812 | 0 | 6132.3812 | 7008.3 | 6132.3812 | 0 | 6132.3812 | 237.5 | 6132.3812 | 0 | 6132.3812 | 303.58
2025-07-19 | 68861.5301 | 8538.73 | 6260.1391 | 0 | 6260.1391 | 0 | 6260.1391 | 0 | 6260.1391 | 0 | 6260.1391 | 121.95 | 6260.1391 | 0 | 6260.1391 | 7008.3 | 6260.1391 | 0 | 6260.1391 | 237.5 | 6260.1391 | 0 | 6260.1391 | 303.58
2025-07-20 | 70266.8675 | 8538.73 | 6387.897 | 0 | 6387.897 | 0 | 6387.897 | 0 | 6387.897 | 0 | 6387.897 | 121.95 | 6387.897 | 0 | 6387.897 | 7008.3 | 6387.897 | 0 | 6387.897 | 237.5 | 6387.897 | 0 | 6387.897 | 303.58
2025-07-21 | 80563.492 | 8538.73 | 7323.9538 | 0 | 7323.9538 | 0 | 7323.9538 | 0 | 7323.9538 | 0 | 7323.9538 | 121.95 | 7323.9538 | 0 | 7323.9538 | 7008.3 | 7323.9538 | 0 | 7323.9538 | 237.5 | 7323.9538 | 0 | 7323.9538 | 303.58
2025-07-22 | 90860.1166 | 8538.73 | 8260.0106 | 0 | 8260.0106 | 0 | 8260.0106 | 0 | 8260.0106 | 0 | 8260.0106 | 121.95 | 8260.0106 | 0 | 8260.0106 | 7008.3 | 8260.0106 | 0 | 8260.0106 | 237.5 | 8260.0106 | 0 | 8260.0106 | 303.58
2025-07-23 | 101156.7412 | 8538.73 | 9196.0674 | 0 | 9196.0674 | 0 | 9196.0674 | 0 | 9196.0674 | 0 | 9196.0674 | 121.95 | 9196.0674 | 0 | 9196.0674 | 7008.3 | 9196.0674 | 0 | 9196.0674 | 237.5 | 9196.0674 | 0 | 9196.0674 | 303.58
2025-07-24 | 111453.3657 | 8598.73 | 10132.1242 | 0 | 10132.1242 | 0 | 10132.1242 | 0 | 10132.1242 | 0 | 10132.1242 | 121.95 | 10132.1242 | 0 | 10132.1242 | 7008.3 | 10132.1242 | 0 | 10132.1242 | 237.5 | 10132.1242 | 0 | 10132.1242 | 363.58
2025-07-25 | 121749.9903 | 8598.73 | 11068.1809 | 0 | 11068.1809 | 0 | 11068.1809 | 0 | 11068.1809 | 0 | 11068.1809 | 121.95 | 11068.1809 | 0 | 11068.1809 | 7008.3 | 11068.1809 | 0 | 11068.1809 | 237.5 | 11068.1809 | 0 | 11068.1809 | 363.58
2025-07-26 | 132046.6149 | 8613.35 | 12004.2377 | 0 | 12004.2377 | 0 | 12004.2377 | 0 | 12004.2377 | 0 | 12004.2377 | 121.95 | 12004.2377 | 0 | 12004.2377 | 7008.3 | 12004.2377 | 0 | 12004.2377 | 237.5 | 12004.2377 | 0 | 12004.2377 | 378.2
2025-07-27 | 142343.2394 | 8613.35 | 12940.2945 | 0 | 12940.2945 | 0 | 12940.2945 | 0 | 12940.2945 | 0 | 12940.2945 | 121.95 | 12940.2945 | 0 | 12940.2945 | 7008.3 | 12940.2945 | 0 | 12940.2945 | 237.5 | 12940.2945 | 0 | 12940.2945 | 378.2
2025-07-28 | 152639.864 | 8613.35 | 13876.3513 | 0 | 13876.3513 | 0 | 13876.3513 | 0 | 13876.3513 | 0 | 13876.3513 | 121.95 | 13876.3513 | 0 | 13876.3513 | 7008.3 | 13876.3513 | 0 | 13876.3513 | 237.5 | 13876.3513 | 0 | 13876.3513 | 378.2
2025-07-29 | 162936.4886 | 8613.35 | 14812.4081 | 0 | 14812.4081 | 0 | 14812.4081 | 0 | 14812.4081 | 0 | 14812.4081 | 121.95 | 14812.4081 | 0 | 14812.4081 | 7008.3 | 14812.4081 | 0 | 14812.4081 | 237.5 | 14812.4081 | 0 | 14812.4081 | 378.2
2025-07-30 | 173233.1131 | 14284.53 | 15748.4648 | 0 | 15748.4648 | 0 | 15748.4648 | 0 | 15748.4648 | 0 | 15748.4648 | 5793.13 | 15748.4648 | 0 | 15748.4648 | 7008.3 | 15748.4648 | 0 | 15748.4648 | 237.5 | 15748.4648 | 0 | 15748.4648 | 378.2
2025-07-31 | 183529.7377 | 39929.95 | 16684.5216 | 23367.75 | 16684.5216 | 0 | 16684.5216 | 0 | 16684.5216 | 0 | 16684.5216 | 5793.13 | 16684.5216 | 2277.67 | 16684.5216 | 7008.3 | 16684.5216 | 0 | 16684.5216 | 237.5 | 16684.5216 | 0 | 16684.5216 | 378.2
2025-08-01 | 193826.3623 | 39929.95 | 17620.5784 | 23367.75 | 17620.5784 | 0 | 17620.5784 | 0 | 17620.5784 | 0 | 17620.5784 | 5793.13 | 17620.5784 | 2277.67 | 17620.5784 | 7008.3 | 17620.5784 | 0 | 17620.5784 | 237.5 | 17620.5784 | 0 | 17620.5784 | 378.2
2025-08-02 | 204122.9868 | 39929.95 | 18556.6352 | 23367.75 | 18556.6352 | 0 | 18556.6352 | 0 | 18556.6352 | 0 | 18556.6352 | 5793.13 | 18556.6352 | 2277.67 | 18556.6352 | 7008.3 | 18556.6352 | 0 | 18556.6352 | 237.5 | 18556.6352 | 0 | 18556.6352 | 378.2
2025-08-03 | 214419.6114 | 39929.95 | 19492.6919 | 23367.75 | 19492.6919 | 0 | 19492.6919 | 0 | 19492.6919 | 0 | 19492.6919 | 5793.13 | 19492.6919 | 2277.67 | 19492.6919 | 7008.3 | 19492.6919 | 0 | 19492.6919 | 237.5 | 19492.6919 | 0 | 19492.6919 | 378.2
2025-08-04 | 224716.236 | 39929.95 | 20428.7487 | 23367.75 | 20428.7487 | 0 | 20428.7487 | 0 | 20428.7487 | 0 | 20428.7487 | 5793.13 | 20428.7487 | 2277.67 | 20428.7487 | 7008.3 | 20428.7487 | 0 | 20428.7487 | 237.5 | 20428.7487 | 0 | 20428.7487 | 378.2
2025-08-05 | 235012.8605 | 43034.18 | 21364.8055 | 23367.75 | 21364.8055 | 0 | 21364.8055 | 0 | 21364.8055 | 0 | 21364.8055 | 8897.36 | 21364.8055 | 2277.67 | 21364.8055 | 7008.3 | 21364.8055 | 0 | 21364.8055 | 237.5 | 21364.8055 | 0 | 21364.8055 | 378.2
2025-08-06 | 245309.4851 | 47941.62 | 22300.8623 | 23367.75 | 22300.8623 | 0 | 22300.8623 | 0 | 22300.8623 | 0 | 22300.8623 | 8897.36 | 22300.8623 | 7185.11 | 22300.8623 | 7008.3 | 22300.8623 | 0 | 22300.8623 | 237.5 | 22300.8623 | 0 | 22300.8623 | 378.2
2025-08-07 | 255606.1097 | 47941.62 | 23236.9191 | 23367.75 | 23236.9191 | 0 | 23236.9191 | 0 | 23236.9191 | 0 | 23236.9191 | 8897.36 | 23236.9191 | 7185.11 | 23236.9191 | 7008.3 | 23236.9191 | 0 | 23236.9191 | 237.5 | 23236.9191 | 0 | 23236.9191 | 378.2
2025-08-08 | 265902.7343 | 47941.62 | 24172.9758 | 23367.75 | 24172.9758 | 0 | 24172.9758 | 0 | 24172.9758 | 0 | 24172.9758 | 8897.36 | 24172.9758 | 7185.11 | 24172.9758 | 7008.3 | 24172.9758 | 0 | 24172.9758 | 237.5 | 24172.9758 | 0 | 24172.9758 | 378.2
2025-08-09 | 276199.3588 | 47941.62 | 25109.0326 | 23367.75 | 25109.0326 | 0 | 25109.0326 | 0 | 25109.0326 | 0 | 25109.0326 | 8897.36 | 25109.0326 | 7185.11 | 25109.0326 | 7008.3 | 25109.0326 | 0 | 25109.0326 | 237.5 | 25109.0326 | 0 | 25109.0326 | 378.2
2025-08-10 | 286495.9834 | 47941.62 | 26045.0894 | 23367.75 | 26045.0894 | 0 | 26045.0894 | 0 | 26045.0894 | 0 | 26045.0894 | 8897.36 | 26045.0894 | 7185.11 | 26045.0894 | 7008.3 | 26045.0894 | 0 | 26045.0894 | 237.5 | 26045.0894 | 0 | 26045.0894 | 378.2
2025-08-11 | 296792.608 | 47941.62 | 26981.1462 | 23367.75 | 26981.1462 | 0 | 26981.1462 | 0 | 26981.1462 | 0 | 26981.1462 | 8897.36 | 26981.1462 | 7185.11 | 26981.1462 | 7008.3 | 26981.1462 | 0 | 26981.1462 | 237.5 | 26981.1462 | 0 | 26981.1462 | 378.2
2025-08-12 | 307089.2325 | 49649.24 | 27917.203 | 23367.75 | 27917.203 | 0 | 27917.203 | 0 | 27917.203 | 0 | 27917.203 | 8897.36 | 27917.203 | 8892.73 | 27917.203 | 7008.3 | 27917.203 | 0 | 27917.203 | 237.5 | 27917.203 | 0 | 27917.203 | 378.2
2025-08-13 | 317385.8571 | 49649.24 | 28853.2597 | 23367.75 | 28853.2597 | 0 | 28853.2597 | 0 | 28853.2597 | 0 | 28853.2597 | 8897.36 | 28853.2597 | 8892.73 | 28853.2597 | 7008.3 | 28853.2597 | 0 | 28853.2597 | 237.5 | 28853.2597 | 0 | 28853.2597 | 378.2
2025-08-14 | 327682.4817 | 50949.24 | 29789.3165 | 23367.75 | 29789.3165 | 0 | 29789.3165 | 0 | 29789.3165 | 0 | 29789.3165 | 8897.36 | 29789.3165 | 8892.73 | 29789.3165 | 8308.3 | 29789.3165 | 0 | 29789.3165 | 237.5 | 29789.3165 | 0 | 29789.3165 | 378.2
2025-08-15 | 337979.1062 | 52045.16 | 30725.3733 | 23367.75 | 30725.3733 | 0 | 30725.3733 | 0 | 30725.3733 | 0 | 30725.3733 | 9961.36 | 30725.3733 | 8892.73 | 30725.3733 | 8340.22 | 30725.3733 | 0 | 30725.3733 | 237.5 | 30725.3733 | 0 | 30725.3733 | 378.2
2025-08-16 | 348275.7308 | 52045.16 | 31661.4301 | 23367.75 | 31661.4301 | 0 | 31661.4301 | 0 | 31661.4301 | 0 | 31661.4301 | 9961.36 | 31661.4301 | 8892.73 | 31661.4301 | 8340.22 | 31661.4301 | 0 | 31661.4301 | 237.5 | 31661.4301 | 0 | 31661.4301 | 378.2
2025-08-17 | 358572.3554 | 52045.16 | 32597.4869 | 23367.75 | 32597.4869 | 0 | 32597.4869 | 0 | 32597.4869 | 0 | 32597.4869 | 9961.36 | 32597.4869 | 8892.73 | 32597.4869 | 8340.22 | 32597.4869 | 0 | 32597.4869 | 237.5 | 32597.4869 | 0 | 32597.4869 | 378.2
2025-08-18 | 368868.9799 | 52045.16 | 33533.5436 | 23367.75 | 33533.5436 | 0 | 33533.5436 | 0 | 33533.5436 | 0 | 33533.5436 | 9961.36 | 33533.5436 | 8892.73 | 33533.5436 | 8340.22 | 33533.5436 | 0 | 33533.5436 | 237.5 | 33533.5436 | 0 | 33533.5436 | 378.2
2025-08-19 | 379165.6045 | 52045.16 | 34469.6004 | 23367.75 | 34469.6004 | 0 | 34469.6004 | 0 | 34469.6004 | 0 | 34469.6004 | 9961.36 | 34469.6004 | 8892.73 | 34469.6004 | 8340.22 | 34469.6004 | 0 | 34469.6004 | 237.5 | 34469.6004 | 0 | 34469.6004 | 378.2
2025-08-20 | 389462.2291 | 55851.45 | 35405.6572 | 23367.75 | 35405.6572 | 0 | 35405.6572 | 0 | 35405.6572 | 0 | 35405.6572 | 9961.36 | 35405.6572 | 12699.02 | 35405.6572 | 8340.22 | 35405.6572 | 0 | 35405.6572 | 237.5 | 35405.6572 | 0 | 35405.6572 | 378.2
2025-08-21 | 399758.8536 | 55851.45 | 36341.714 | 23367.75 | 36341.714 | 0 | 36341.714 | 0 | 36341.714 | 0 | 36341.714 | 9961.36 | 36341.714 | 12699.02 | 36341.714 | 8340.22 | 36341.714 | 0 | 36341.714 | 237.5 | 36341.714 | 0 | 36341.714 | 378.2
2025-08-22 | 410055.4782 | 55851.45 | 37277.7707 | 23367.75 | 37277.7707 | 0 | 37277.7707 | 0 | 37277.7707 | 0 | 37277.7707 | 9961.36 | 37277.7707 | 12699.02 | 37277.7707 | 8340.22 | 37277.7707 | 0 | 37277.7707 | 237.5 | 37277.7707 | 0 | 37277.7707 | 378.2
2025-08-23 | 418946.7654 | 55851.45 | 38086.0696 | 23367.75 | 38086.0696 | 0 | 38086.0696 | 0 | 38086.0696 | 0 | 38086.0696 | 9961.36 | 38086.0696 | 12699.02 | 38086.0696 | 8340.22 | 38086.0696 | 0 | 38086.0696 | 237.5 | 38086.0696 | 0 | 38086.0696 | 378.2
2025-08-24 | 427838.0526 | 55851.45 | 38894.3684 | 23367.75 | 38894.3684 | 0 | 38894.3684 | 0 | 38894.3684 | 0 | 38894.3684 | 9961.36 | 38894.3684 | 12699.02 | 38894.3684 | 8340.22 | 38894.3684 | 0 | 38894.3684 | 237.5 | 38894.3684 | 0 | 38894.3684 | 378.2
2025-08-25 | 436729.3398 | 112943.95 | 39702.6673 | 77310.25 | 39702.6673 | 0 | 39702.6673 | 0 | 39702.6673 | 0 | 39702.6673 | 9961.36 | 39702.6673 | 12699.02 | 39702.6673 | 11490.22 | 39702.6673 | 0 | 39702.6673 | 237.5 | 39702.6673 | 0 | 39702.6673 | 378.2
2025-08-26 | 445620.6271 | 112943.95 | 40510.9661 | 77310.25 | 40510.9661 | 0 | 40510.9661 | 0 | 40510.9661 | 0 | 40510.9661 | 9961.36 | 40510.9661 | 12699.02 | 40510.9661 | 11490.22 | 40510.9661 | 0 | 40510.9661 | 237.5 | 40510.9661 | 0 | 40510.9661 | 378.2
2025-08-27 | 454511.9143 | 120623.49 | 41319.2649 | 77310.25 | 41319.2649 | 0 | 41319.2649 | 0 | 41319.2649 | 0 | 41319.2649 | 15062.22 | 41319.2649 | 15277.7 | 41319.2649 | 11490.22 | 41319.2649 | 0 | 41319.2649 | 237.5 | 41319.2649 | 0 | 41319.2649 | 378.2
2025-08-28 | 463403.2015 | 120623.49 | 42127.5638 | 77310.25 | 42127.5638 | 0 | 42127.5638 | 0 | 42127.5638 | 0 | 42127.5638 | 15062.22 | 42127.5638 | 15277.7 | 42127.5638 | 11490.22 | 42127.5638 | 0 | 42127.5638 | 237.5 | 42127.5638 | 0 | 42127.5638 | 378.2
2025-08-29 | 472294.4887 | 123202.17 | 42935.8626 | 77310.25 | 42935.8626 | 0 | 42935.8626 | 0 | 42935.8626 | 0 | 42935.8626 | 15062.22 | 42935.8626 | 17856.38 | 42935.8626 | 11490.22 | 42935.8626 | 0 | 42935.8626 | 237.5 | 42935.8626 | 0 | 42935.8626 | 378.2
2025-08-30 | 481185.7759 | 123202.17 | 43744.1614 | 77310.25 | 43744.1614 | 0 | 43744.1614 | 0 | 43744.1614 | 0 | 43744.1614 | 15062.22 | 43744.1614 | 17856.38 | 43744.1614 | 11490.22 | 43744.1614 | 0 | 43744.1614 | 237.5 | 43744.1614 | 0 | 43744.1614 | 378.2
2025-08-31 | 490077.0632 | 140235.26 | 44552.4603 | 77310.25 | 44552.4603 | 0 | 44552.4603 | 0 | 44552.4603 | 0 | 44552.4603 | 15062.22 | 44552.4603 | 34889.47 | 44552.4603 | 11490.22 | 44552.4603 | 0 | 44552.4603 | 237.5 | 44552.4603 | 0 | 44552.4603 | 378.2
2025-09-01 | 498968.3504 | 140235.26 | 45360.7591 | 77310.25 | 45360.7591 | 0 | 45360.7591 | 0 | 45360.7591 | 0 | 45360.7591 | 15062.22 | 45360.7591 | 34889.47 | 45360.7591 | 11490.22 | 45360.7591 | 0 | 45360.7591 | 237.5 | 45360.7591 | 0 | 45360.7591 | 378.2
2025-09-02 | 499656.3836 | 142908.29 | 45423.3076 | 77310.25 | 45423.3076 | 0 | 45423.3076 | 0 | 45423.3076 | 0 | 45423.3076 | 17735.25 | 45423.3076 | 34889.47 | 45423.3076 | 11490.22 | 45423.3076 | 0 | 45423.3076 | 237.5 | 45423.3076 | 0 | 45423.3076 | 378.2
2025-09-03 | 500344.4169 | 396340.79 | 45485.8561 | 330517.75 | 45485.8561 | 0 | 45485.8561 | 0 | 45485.8561 | 0 | 45485.8561 | 17735.25 | 45485.8561 | 34889.47 | 45485.8561 | 11715.22 | 45485.8561 | 0 | 45485.8561 | 237.5 | 45485.8561 | 0 | 45485.8561 | 378.2
2025-09-04 | 501032.4502 | 396340.79 | 45548.4046 | 330517.75 | 45548.4046 | 0 | 45548.4046 | 0 | 45548.4046 | 0 | 45548.4046 | 17735.25 | 45548.4046 | 34889.47 | 45548.4046 | 11715.22 | 45548.4046 | 0 | 45548.4046 | 237.5 | 45548.4046 | 0 | 45548.4046 | 378.2
2025-09-05 | 501720.4835 | 398895.46 | 45610.953 | 330517.75 | 45610.953 | 0 | 45610.953 | 0 | 45610.953 | 0 | 45610.953 | 17735.25 | 45610.953 | 37444.14 | 45610.953 | 11715.22 | 45610.953 | 0 | 45610.953 | 237.5 | 45610.953 | 0 | 45610.953 | 378.2
2025-09-06 | 502408.5167 | 398895.46 | 45673.5015 | 330517.75 | 45673.5015 | 0 | 45673.5015 | 0 | 45673.5015 | 0 | 45673.5015 | 17735.25 | 45673.5015 | 37444.14 | 45673.5015 | 11715.22 | 45673.5015 | 0 | 45673.5015 | 237.5 | 45673.5015 | 0 | 45673.5015 | 378.2
2025-09-07 | 503096.55 | 398895.46 | 45736.05 | 330517.75 | 45736.05 | 0 | 45736.05 | 0 | 45736.05 | 0 | 45736.05 | 17735.25 | 45736.05 | 37444.14 | 45736.05 | 11715.22 | 45736.05 | 0 | 45736.05 | 237.5 | 45736.05 | 0 | 45736.05 | 378.2
2025-09-08 | 503784.5833 | 401608.92 | 45798.5985 | 330517.75 | 45798.5985 | 0 | 45798.5985 | 0 | 45798.5985 | 0 | 45798.5985 | 17735.25 | 45798.5985 | 40157.6 | 45798.5985 | 11715.22 | 45798.5985 | 0 | 45798.5985 | 237.5 | 45798.5985 | 0 | 45798.5985 | 378.2
2025-09-09 | 504472.6165 | 403737.39 | 45861.147 | 330517.75 | 45861.147 | 0 | 45861.147 | 0 | 45861.147 | 0 | 45861.147 | 17735.25 | 45861.147 | 42286.07 | 45861.147 | 11715.22 | 45861.147 | 0 | 45861.147 | 237.5 | 45861.147 | 0 | 45861.147 | 378.2
2025-09-10 | 505160.6498 | 403737.39 | 45923.6954 | 330517.75 | 45923.6954 | 0 | 45923.6954 | 0 | 45923.6954 | 0 | 45923.6954 | 17735.25 | 45923.6954 | 42286.07 | 45923.6954 | 11715.22 | 45923.6954 | 0 | 45923.6954 | 237.5 | 45923.6954 | 0 | 45923.6954 | 378.2
2025-09-11 | 505848.6831 | 404833.31 | 45986.2439 | 330517.75 | 45986.2439 | 0 | 45986.2439 | 0 | 45986.2439 | 0 | 45986.2439 | 18799.25 | 45986.2439 | 42286.07 | 45986.2439 | 11747.14 | 45986.2439 | 0 | 45986.2439 | 237.5 | 45986.2439 | 0 | 45986.2439 | 378.2
2025-09-12 | 506536.7163 | 404833.31 | 46048.7924 | 330517.75 | 46048.7924 | 0 | 46048.7924 | 0 | 46048.7924 | 0 | 46048.7924 | 18799.25 | 46048.7924 | 42286.07 | 46048.7924 | 11747.14 | 46048.7924 | 0 | 46048.7924 | 237.5 | 46048.7924 | 0 | 46048.7924 | 378.2
2025-09-13 | 507224.7496 | 404833.31 | 46111.3409 | 330517.75 | 46111.3409 | 0 | 46111.3409 | 0 | 46111.3409 | 0 | 46111.3409 | 18799.25 | 46111.3409 | 42286.07 | 46111.3409 | 11747.14 | 46111.3409 | 0 | 46111.3409 | 237.5 | 46111.3409 | 0 | 46111.3409 | 378.2
2025-09-14 | 507912.7829 | 404833.31 | 46173.8894 | 330517.75 | 46173.8894 | 0 | 46173.8894 | 0 | 46173.8894 | 0 | 46173.8894 | 18799.25 | 46173.8894 | 42286.07 | 46173.8894 | 11747.14 | 46173.8894 | 0 | 46173.8894 | 237.5 | 46173.8894 | 0 | 46173.8894 | 378.2
2025-09-15 | 508600.8161 | 409974.69 | 46236.4378 | 330517.75 | 46236.4378 | 0 | 46236.4378 | 0 | 46236.4378 | 0 | 46236.4378 | 18799.25 | 46236.4378 | 47427.45 | 46236.4378 | 11747.14 | 46236.4378 | 0 | 46236.4378 | 237.5 | 46236.4378 | 0 | 46236.4378 | 378.2
2025-09-16 | 509288.8494 | 409974.69 | 46298.9863 | 330517.75 | 46298.9863 | 0 | 46298.9863 | 0 | 46298.9863 | 0 | 46298.9863 | 18799.25 | 46298.9863 | 47427.45 | 46298.9863 | 11747.14 | 46298.9863 | 0 | 46298.9863 | 237.5 | 46298.9863 | 0 | 46298.9863 | 378.2
2025-09-17 | 509976.8827 | 409974.69 | 46361.5348 | 330517.75 | 46361.5348 | 0 | 46361.5348 | 0 | 46361.5348 | 0 | 46361.5348 | 18799.25 | 46361.5348 | 47427.45 | 46361.5348 | 11747.14 | 46361.5348 | 0 | 46361.5348 | 237.5 | 46361.5348 | 0 | 46361.5348 | 378.2
2025-09-18 | 510664.916 | 409974.69 | 46424.0833 | 330517.75 | 46424.0833 | 0 | 46424.0833 | 0 | 46424.0833 | 0 | 46424.0833 | 18799.25 | 46424.0833 | 47427.45 | 46424.0833 | 11747.14 | 46424.0833 | 0 | 46424.0833 | 237.5 | 46424.0833 | 0 | 46424.0833 | 378.2
2025-09-19 | 511352.9492 | 409974.69 | 46486.6317 | 330517.75 | 46486.6317 | 0 | 46486.6317 | 0 | 46486.6317 | 0 | 46486.6317 | 18799.25 | 46486.6317 | 47427.45 | 46486.6317 | 11747.14 | 46486.6317 | 0 | 46486.6317 | 237.5 | 46486.6317 | 0 | 46486.6317 | 378.2
2025-09-20 | 512040.9825 | 409974.69 | 46549.1802 | 330517.75 | 46549.1802 | 0 | 46549.1802 | 0 | 46549.1802 | 0 | 46549.1802 | 18799.25 | 46549.1802 | 47427.45 | 46549.1802 | 11747.14 | 46549.1802 | 0 | 46549.1802 | 237.5 | 46549.1802 | 0 | 46549.1802 | 378.2
2025-09-21 | 512729.0158 | 409974.69 | 46611.7287 | 330517.75 | 46611.7287 | 0 | 46611.7287 | 0 | 46611.7287 | 0 | 46611.7287 | 18799.25 | 46611.7287 | 47427.45 | 46611.7287 | 11747.14 | 46611.7287 | 0 | 46611.7287 | 237.5 | 46611.7287 | 0 | 46611.7287 | 378.2
2025-09-22 | 513417.049 | 409974.69 | 46674.2772 | 330517.75 | 46674.2772 | 0 | 46674.2772 | 0 | 46674.2772 | 0 | 46674.2772 | 18799.25 | 46674.2772 | 47427.45 | 46674.2772 | 11747.14 | 46674.2772 | 0 | 46674.2772 | 237.5 | 46674.2772 | 0 | 46674.2772 | 378.2
2025-09-23 | 514105.0823 | 412553.37 | 46736.8257 | 330517.75 | 46736.8257 | 0 | 46736.8257 | 0 | 46736.8257 | 0 | 46736.8257 | 18799.25 | 46736.8257 | 50006.13 | 46736.8257 | 11747.14 | 46736.8257 | 0 | 46736.8257 | 237.5 | 46736.8257 | 0 | 46736.8257 | 378.2
2025-09-24 | 514793.1156 | 420327.26 | 46799.3741 | 330517.75 | 46799.3741 | 0 | 46799.3741 | 0 | 46799.3741 | 0 | 46799.3741 | 26573.14 | 46799.3741 | 50006.13 | 46799.3741 | 11747.14 | 46799.3741 | 0 | 46799.3741 | 237.5 | 46799.3741 | 0 | 46799.3741 | 378.2
2025-09-25 | 515481.1488 | 430587.92 | 46861.9226 | 330517.75 | 46861.9226 | 0 | 46861.9226 | 0 | 46861.9226 | 0 | 46861.9226 | 26573.14 | 46861.9226 | 60266.79 | 46861.9226 | 11747.14 | 46861.9226 | 0 | 46861.9226 | 237.5 | 46861.9226 | 0 | 46861.9226 | 378.2
2025-09-26 | 516169.1821 | 436285.58 | 46924.4711 | 330517.75 | 46924.4711 | 0 | 46924.4711 | 0 | 46924.4711 | 0 | 46924.4711 | 26573.14 | 46924.4711 | 65964.45 | 46924.4711 | 11747.14 | 46924.4711 | 0 | 46924.4711 | 237.5 | 46924.4711 | 0 | 46924.4711 | 378.2
2025-09-27 | 516857.2154 | 436285.58 | 46987.0196 | 330517.75 | 46987.0196 | 0 | 46987.0196 | 0 | 46987.0196 | 0 | 46987.0196 | 26573.14 | 46987.0196 | 65964.45 | 46987.0196 | 11747.14 | 46987.0196 | 0 | 46987.0196 | 237.5 | 46987.0196 | 0 | 46987.0196 | 378.2
2025-09-28 | 517545.2486 | 436285.58 | 47049.5681 | 330517.75 | 47049.5681 | 0 | 47049.5681 | 0 | 47049.5681 | 0 | 47049.5681 | 26573.14 | 47049.5681 | 65964.45 | 47049.5681 | 11747.14 | 47049.5681 | 0 | 47049.5681 | 237.5 | 47049.5681 | 0 | 47049.5681 | 378.2
2025-09-29 | 518233.2819 | 451104.64 | 47112.1165 | 330517.75 | 47112.1165 | 0 | 47112.1165 | 0 | 47112.1165 | 0 | 47112.1165 | 29251.67 | 47112.1165 | 78091.3 | 47112.1165 | 11760.82 | 47112.1165 | 0 | 47112.1165 | 237.5 | 47112.1165 | 0 | 47112.1165 | 378.2
2025-09-30 | 518921.3152 | 456229.15 | 47174.665 | 330517.75 | 47174.665 | 0 | 47174.665 | 0 | 47174.665 | 0 | 47174.665 | 29251.67 | 47174.665 | 83215.81 | 47174.665 | 11760.82 | 47174.665 | 0 | 47174.665 | 237.5 | 47174.665 | 0 | 47174.665 | 378.2
2025-10-01 | 519609.3485 | 456229.15 | 47237.2135 | 330517.75 | 47237.2135 | 0 | 47237.2135 | 0 | 47237.2135 | 0 | 47237.2135 | 29251.67 | 47237.2135 | 83215.81 | 47237.2135 | 11760.82 | 47237.2135 | 0 | 47237.2135 | 237.5 | 47237.2135 | 0 | 47237.2135 | 378.2
2025-10-02 | 520297.3817 | 456229.15 | 47299.762 | 330517.75 | 47299.762 | 0 | 47299.762 | 0 | 47299.762 | 0 | 47299.762 | 29251.67 | 47299.762 | 83215.81 | 47299.762 | 11760.82 | 47299.762 | 0 | 47299.762 | 237.5 | 47299.762 | 0 | 47299.762 | 378.2
2025-10-03 | 520985.415 | 456229.15 | 47362.3105 | 330517.75 | 47362.3105 | 0 | 47362.3105 | 0 | 47362.3105 | 0 | 47362.3105 | 29251.67 | 47362.3105 | 83215.81 | 47362.3105 | 11760.82 | 47362.3105 | 0 | 47362.3105 | 237.5 | 47362.3105 | 0 | 47362.3105 | 378.2
2025-10-04 | 521673.4483 | 460232.04 | 47424.8589 | 330517.75 | 47424.8589 | 0 | 47424.8589 | 0 | 47424.8589 | 0 | 47424.8589 | 33254.56 | 47424.8589 | 83215.81 | 47424.8589 | 11760.82 | 47424.8589 | 0 | 47424.8589 | 237.5 | 47424.8589 | 0 | 47424.8589 | 378.2
2025-10-05 | 522361.4815 | 460232.04 | 47487.4074 | 330517.75 | 47487.4074 | 0 | 47487.4074 | 0 | 47487.4074 | 0 | 47487.4074 | 33254.56 | 47487.4074 | 83215.81 | 47487.4074 | 11760.82 | 47487.4074 | 0 | 47487.4074 | 237.5 | 47487.4074 | 0 | 47487.4074 | 378.2
2025-10-06 | 523049.5148 | 460232.04 | 47549.9559 | 330517.75 | 47549.9559 | 0 | 47549.9559 | 0 | 47549.9559 | 0 | 47549.9559 | 33254.56 | 47549.9559 | 83215.81 | 47549.9559 | 11760.82 | 47549.9559 | 0 | 47549.9559 | 237.5 | 47549.9559 | 0 | 47549.9559 | 378.2
2025-10-07 | 523737.5481 | 461654.63 | 47612.5044 | 330517.75 | 47612.5044 | 0 | 47612.5044 | 0 | 47612.5044 | 0 | 47612.5044 | 33254.56 | 47612.5044 | 84638.4 | 47612.5044 | 11760.82 | 47612.5044 | 0 | 47612.5044 | 237.5 | 47612.5044 | 0 | 47612.5044 | 378.2
2025-10-08 | 524425.5813 | 461654.63 | 47675.0528 | 330517.75 | 47675.0528 | 0 | 47675.0528 | 0 | 47675.0528 | 0 | 47675.0528 | 33254.56 | 47675.0528 | 84638.4 | 47675.0528 | 11760.82 | 47675.0528 | 0 | 47675.0528 | 237.5 | 47675.0528 | 0 | 47675.0528 | 378.2
2025-10-09 | 525113.6146 | 461654.63 | 47737.6013 | 330517.75 | 47737.6013 | 0 | 47737.6013 | 0 | 47737.6013 | 0 | 47737.6013 | 33254.56 | 47737.6013 | 84638.4 | 47737.6013 | 11760.82 | 47737.6013 | 0 | 47737.6013 | 237.5 | 47737.6013 | 0 | 47737.6013 | 378.2
2025-10-10 | 525801.6479 | 461654.63 | 47800.1498 | 330517.75 | 47800.1498 | 0 | 47800.1498 | 0 | 47800.1498 | 0 | 47800.1498 | 33254.56 | 47800.1498 | 84638.4 | 47800.1498 | 11760.82 | 47800.1498 | 0 | 47800.1498 | 237.5 | 47800.1498 | 0 | 47800.1498 | 378.2
2025-10-11 | 526489.6811 | 461654.63 | 47862.6983 | 330517.75 | 47862.6983 | 0 | 47862.6983 | 0 | 47862.6983 | 0 | 47862.6983 | 33254.56 | 47862.6983 | 84638.4 | 47862.6983 | 11760.82 | 47862.6983 | 0 | 47862.6983 | 237.5 | 47862.6983 | 0 | 47862.6983 | 378.2
2025-10-12 | 527177.7144 | 461654.63 | 47925.2468 | 330517.75 | 47925.2468 | 0 | 47925.2468 | 0 | 47925.2468 | 0 | 47925.2468 | 33254.56 | 47925.2468 | 84638.4 | 47925.2468 | 11760.82 | 47925.2468 | 0 | 47925.2468 | 237.5 | 47925.2468 | 0 | 47925.2468 | 378.2
2025-10-13 | 527865.7477 | 461654.63 | 47987.7952 | 330517.75 | 47987.7952 | 0 | 47987.7952 | 0 | 47987.7952 | 0 | 47987.7952 | 33254.56 | 47987.7952 | 84638.4 | 47987.7952 | 11760.82 | 47987.7952 | 0 | 47987.7952 | 237.5 | 47987.7952 | 0 | 47987.7952 | 378.2
2025-10-14 | 528553.781 | 461654.63 | 48050.3437 | 330517.75 | 48050.3437 | 0 | 48050.3437 | 0 | 48050.3437 | 0 | 48050.3437 | 33254.56 | 48050.3437 | 84638.4 | 48050.3437 | 11760.82 | 48050.3437 | 0 | 48050.3437 | 237.5 | 48050.3437 | 0 | 48050.3437 | 378.2
2025-10-15 | 529241.8142 | 461654.63 | 48112.8922 | 330517.75 | 48112.8922 | 0 | 48112.8922 | 0 | 48112.8922 | 0 | 48112.8922 | 33254.56 | 48112.8922 | 84638.4 | 48112.8922 | 11760.82 | 48112.8922 | 0 | 48112.8922 | 237.5 | 48112.8922 | 0 | 48112.8922 | 378.2
2025-10-16 | 529929.8475 | 461654.63 | 48175.4407 | 330517.75 | 48175.4407 | 0 | 48175.4407 | 0 | 48175.4407 | 0 | 48175.4407 | 33254.56 | 48175.4407 | 84638.4 | 48175.4407 | 11760.82 | 48175.4407 | 0 | 48175.4407 | 237.5 | 48175.4407 | 0 | 48175.4407 | 378.2
2025-10-17 | 530617.8808 | 461654.63 | 48237.9892 | 330517.75 | 48237.9892 | 0 | 48237.9892 | 0 | 48237.9892 | 0 | 48237.9892 | 33254.56 | 48237.9892 | 84638.4 | 48237.9892 | 11760.82 | 48237.9892 | 0 | 48237.9892 | 237.5 | 48237.9892 | 0 | 48237.9892 | 378.2
2025-10-18 | 531305.914 | 461654.63 | 48300.5376 | 330517.75 | 48300.5376 | 0 | 48300.5376 | 0 | 48300.5376 | 0 | 48300.5376 | 33254.56 | 48300.5376 | 84638.4 | 48300.5376 | 11760.82 | 48300.5376 | 0 | 48300.5376 | 237.5 | 48300.5376 | 0 | 48300.5376 | 378.2
2025-10-19 | 531993.9473 | 461654.63 | 48363.0861 | 330517.75 | 48363.0861 | 0 | 48363.0861 | 0 | 48363.0861 | 0 | 48363.0861 | 33254.56 | 48363.0861 | 84638.4 | 48363.0861 | 11760.82 | 48363.0861 | 0 | 48363.0861 | 237.5 | 48363.0861 | 0 | 48363.0861 | 378.2
2025-10-20 | 532681.9806 |  | 48425.6346 |  | 48425.6346 |  | 48425.6346 |  | 48425.6346 |  | 48425.6346 |  | 48425.6346 |  | 48425.6346 |  | 48425.6346 |  | 48425.6346 |  | 48425.6346 |  | 48425.6346
2025-10-21 | 533370.0138 |  | 48488.1831 |  | 48488.1831 |  | 48488.1831 |  | 48488.1831 |  | 48488.1831 |  | 48488.1831 |  | 48488.1831 |  | 48488.1831 |  | 48488.1831 |  | 48488.1831 |  | 48488.1831
2025-10-22 | 534058.0471 |  | 48550.7316 |  | 48550.7316 |  | 48550.7316 |  | 48550.7316 |  | 48550.7316 |  | 48550.7316 |  | 48550.7316 |  | 48550.7316 |  | 48550.7316 |  | 48550.7316 |  | 48550.7316
2025-10-23 | 534746.0804 |  | 48613.28 |  | 48613.28 |  | 48613.28 |  | 48613.28 |  | 48613.28 |  | 48613.28 |  | 48613.28 |  | 48613.28 |  | 48613.28 |  | 48613.28 |  | 48613.28
2025-10-24 | 535434.1136 |  | 48675.8285 |  | 48675.8285 |  | 48675.8285 |  | 48675.8285 |  | 48675.8285 |  | 48675.8285 |  | 48675.8285 |  | 48675.8285 |  | 48675.8285 |  | 48675.8285 |  | 48675.8285
2025-10-25 | 536122.1469 |  | 48738.377 |  | 48738.377 |  | 48738.377 |  | 48738.377 |  | 48738.377 |  | 48738.377 |  | 48738.377 |  | 48738.377 |  | 48738.377 |  | 48738.377 |  | 48738.377
2025-10-26 | 536810.1802 |  | 48800.9255 |  | 48800.9255 |  | 48800.9255 |  | 48800.9255 |  | 48800.9255 |  | 48800.9255 |  | 48800.9255 |  | 48800.9255 |  | 48800.9255 |  | 48800.9255 |  | 48800.9255
2025-10-27 | 537498.2135 |  | 48863.474 |  | 48863.474 |  | 48863.474 |  | 48863.474 |  | 48863.474 |  | 48863.474 |  | 48863.474 |  | 48863.474 |  | 48863.474 |  | 48863.474 |  | 48863.474
2025-10-28 | 538186.2467 |  | 48926.0224 |  | 48926.0224 |  | 48926.0224 |  | 48926.0224 |  | 48926.0224 |  | 48926.0224 |  | 48926.0224 |  | 48926.0224 |  | 48926.0224 |  | 48926.0224 |  | 48926.0224
2025-10-29 | 538874.28 |  | 48988.5709 |  | 48988.5709 |  | 48988.5709 |  | 48988.5709 |  | 48988.5709 |  | 48988.5709 |  | 48988.5709 |  | 48988.5709 |  | 48988.5709 |  | 48988.5709 |  | 48988.5709
2025-10-30 | 539562.3133 |  | 49051.1194 |  | 49051.1194 |  | 49051.1194 |  | 49051.1194 |  | 49051.1194 |  | 49051.1194 |  | 49051.1194 |  | 49051.1194 |  | 49051.1194 |  | 49051.1194 |  | 49051.1194
2025-10-31 | 540250.3465 |  | 49113.6679 |  | 49113.6679 |  | 49113.6679 |  | 49113.6679 |  | 49113.6679 |  | 49113.6679 |  | 49113.6679 |  | 49113.6679 |  | 49113.6679 |  | 49113.6679 |  | 49113.6679
2025-11-03 | 540470.1882 |  | 49133.6535 |  | 49133.6535 |  | 49133.6535 |  | 49133.6535 |  | 49133.6535 |  | 49133.6535 |  | 49133.6535 |  | 49133.6535 |  | 49133.6535 |  | 49133.6535 |  | 49133.6535
2025-11-04 | 540690.0299 |  | 49153.6391 |  | 49153.6391 |  | 49153.6391 |  | 49153.6391 |  | 49153.6391 |  | 49153.6391 |  | 49153.6391 |  | 49153.6391 |  | 49153.6391 |  | 49153.6391 |  | 49153.6391
2025-11-05 | 540909.8715 |  | 49173.6247 |  | 49173.6247 |  | 49173.6247 |  | 49173.6247 |  | 49173.6247 |  | 49173.6247 |  | 49173.6247 |  | 49173.6247 |  | 49173.6247 |  | 49173.6247 |  | 49173.6247
2025-11-06 | 541129.7132 |  | 49193.6103 |  | 49193.6103 |  | 49193.6103 |  | 49193.6103 |  | 49193.6103 |  | 49193.6103 |  | 49193.6103 |  | 49193.6103 |  | 49193.6103 |  | 49193.6103 |  | 49193.6103
2025-11-07 | 541349.5549 |  | 49213.5959 |  | 49213.5959 |  | 49213.5959 |  | 49213.5959 |  | 49213.5959 |  | 49213.5959 |  | 49213.5959 |  | 49213.5959 |  | 49213.5959 |  | 49213.5959 |  | 49213.5959
2025-11-08 | 541569.3965 |  | 49233.5815 |  | 49233.5815 |  | 49233.5815 |  | 49233.5815 |  | 49233.5815 |  | 49233.5815 |  | 49233.5815 |  | 49233.5815 |  | 49233.5815 |  | 49233.5815 |  | 49233.5815
2025-11-09 | 541789.2382 |  | 49253.5671 |  | 49253.5671 |  | 49253.5671 |  | 49253.5671 |  | 49253.5671 |  | 49253.5671 |  | 49253.5671 |  | 49253.5671 |  | 49253.5671 |  | 49253.5671 |  | 49253.5671
2025-11-10 | 542009.0799 |  | 49273.5527 |  | 49273.5527 |  | 49273.5527 |  | 49273.5527 |  | 49273.5527 |  | 49273.5527 |  | 49273.5527 |  | 49273.5527 |  | 49273.5527 |  | 49273.5527 |  | 49273.5527
2025-11-11 | 542228.9215 |  | 49293.5383 |  | 49293.5383 |  | 49293.5383 |  | 49293.5383 |  | 49293.5383 |  | 49293.5383 |  | 49293.5383 |  | 49293.5383 |  | 49293.5383 |  | 49293.5383 |  | 49293.5383
2025-11-12 | 542448.7632 |  | 49313.5239 |  | 49313.5239 |  | 49313.5239 |  | 49313.5239 |  | 49313.5239 |  | 49313.5239 |  | 49313.5239 |  | 49313.5239 |  | 49313.5239 |  | 49313.5239 |  | 49313.5239
2025-11-13 | 542668.6049 |  | 49333.5095 |  | 49333.5095 |  | 49333.5095 |  | 49333.5095 |  | 49333.5095 |  | 49333.5095 |  | 49333.5095 |  | 49333.5095 |  | 49333.5095 |  | 49333.5095 |  | 49333.5095
2025-11-14 | 542888.4465 |  | 49353.4951 |  | 49353.4951 |  | 49353.4951 |  | 49353.4951 |  | 49353.4951 |  | 49353.4951 |  | 49353.4951 |  | 49353.4951 |  | 49353.4951 |  | 49353.4951 |  | 49353.4951
2025-11-15 | 543108.2882 |  | 49373.4807 |  | 49373.4807 |  | 49373.4807 |  | 49373.4807 |  | 49373.4807 |  | 49373.4807 |  | 49373.4807 |  | 49373.4807 |  | 49373.4807 |  | 49373.4807 |  | 49373.4807
2025-11-16 | 543328.1299 |  | 49393.4664 |  | 49393.4664 |  | 49393.4664 |  | 49393.4664 |  | 49393.4664 |  | 49393.4664 |  | 49393.4664 |  | 49393.4664 |  | 49393.4664 |  | 49393.4664 |  | 49393.4664
2025-11-17 | 543547.9715 |  | 49413.452 |  | 49413.452 |  | 49413.452 |  | 49413.452 |  | 49413.452 |  | 49413.452 |  | 49413.452 |  | 49413.452 |  | 49413.452 |  | 49413.452 |  | 49413.452
2025-11-18 | 543767.8132 |  | 49433.4376 |  | 49433.4376 |  | 49433.4376 |  | 49433.4376 |  | 49433.4376 |  | 49433.4376 |  | 49433.4376 |  | 49433.4376 |  | 49433.4376 |  | 49433.4376 |  | 49433.4376
2025-11-19 | 543987.6549 |  | 49453.4232 |  | 49453.4232 |  | 49453.4232 |  | 49453.4232 |  | 49453.4232 |  | 49453.4232 |  | 49453.4232 |  | 49453.4232 |  | 49453.4232 |  | 49453.4232 |  | 49453.4232
2025-11-20 | 544207.4965 |  | 49473.4088 |  | 49473.4088 |  | 49473.4088 |  | 49473.4088 |  | 49473.4088 |  | 49473.4088 |  | 49473.4088 |  | 49473.4088 |  | 49473.4088 |  | 49473.4088 |  | 49473.4088
2025-11-21 | 544427.3382 |  | 49493.3944 |  | 49493.3944 |  | 49493.3944 |  | 49493.3944 |  | 49493.3944 |  | 49493.3944 |  | 49493.3944 |  | 49493.3944 |  | 49493.3944 |  | 49493.3944 |  | 49493.3944
2025-11-22 | 544647.1799 |  | 49513.38 |  | 49513.38 |  | 49513.38 |  | 49513.38 |  | 49513.38 |  | 49513.38 |  | 49513.38 |  | 49513.38 |  | 49513.38 |  | 49513.38 |  | 49513.38
2025-11-23 | 544867.0215 |  | 49533.3656 |  | 49533.3656 |  | 49533.3656 |  | 49533.3656 |  | 49533.3656 |  | 49533.3656 |  | 49533.3656 |  | 49533.3656 |  | 49533.3656 |  | 49533.3656 |  | 49533.3656
2025-11-24 | 545086.8632 |  | 49553.3512 |  | 49553.3512 |  | 49553.3512 |  | 49553.3512 |  | 49553.3512 |  | 49553.3512 |  | 49553.3512 |  | 49553.3512 |  | 49553.3512 |  | 49553.3512 |  | 49553.3512
2025-11-25 | 545306.7049 |  | 49573.3368 |  | 49573.3368 |  | 49573.3368 |  | 49573.3368 |  | 49573.3368 |  | 49573.3368 |  | 49573.3368 |  | 49573.3368 |  | 49573.3368 |  | 49573.3368 |  | 49573.3368
2025-11-26 | 545526.5465 |  | 49593.3224 |  | 49593.3224 |  | 49593.3224 |  | 49593.3224 |  | 49593.3224 |  | 49593.3224 |  | 49593.3224 |  | 49593.3224 |  | 49593.3224 |  | 49593.3224 |  | 49593.3224
2025-11-27 | 545746.3882 |  | 49613.308 |  | 49613.308 |  | 49613.308 |  | 49613.308 |  | 49613.308 |  | 49613.308 |  | 49613.308 |  | 49613.308 |  | 49613.308 |  | 49613.308 |  | 49613.308
2025-11-28 | 545966.2299 |  | 49633.2936 |  | 49633.2936 |  | 49633.2936 |  | 49633.2936 |  | 49633.2936 |  | 49633.2936 |  | 49633.2936 |  | 49633.2936 |  | 49633.2936 |  | 49633.2936 |  | 49633.2936
2025-11-29 | 546186.0715 |  | 49653.2792 |  | 49653.2792 |  | 49653.2792 |  | 49653.2792 |  | 49653.2792 |  | 49653.2792 |  | 49653.2792 |  | 49653.2792 |  | 49653.2792 |  | 49653.2792 |  | 49653.2792
2025-11-30 | 546405.9132 |  | 49673.2648 |  | 49673.2648 |  | 49673.2648 |  | 49673.2648 |  | 49673.2648 |  | 49673.2648 |  | 49673.2648 |  | 49673.2648 |  | 49673.2648 |  | 49673.2648 |  | 49673.2648
2025-12-01 | 546625.7549 |  | 49693.2504 |  | 49693.2504 |  | 49693.2504 |  | 49693.2504 |  | 49693.2504 |  | 49693.2504 |  | 49693.2504 |  | 49693.2504 |  | 49693.2504 |  | 49693.2504 |  | 49693.2504
2025-12-02 | 546845.5965 |  | 49713.236 |  | 49713.236 |  | 49713.236 |  | 49713.236 |  | 49713.236 |  | 49713.236 |  | 49713.236 |  | 49713.236 |  | 49713.236 |  | 49713.236 |  | 49713.236
2025-12-03 | 547065.4382 |  | 49733.2217 |  | 49733.2217 |  | 49733.2217 |  | 49733.2217 |  | 49733.2217 |  | 49733.2217 |  | 49733.2217 |  | 49733.2217 |  | 49733.2217 |  | 49733.2217 |  | 49733.2217
2025-12-04 | 547285.2799 |  | 49753.2073 |  | 49753.2073 |  | 49753.2073 |  | 49753.2073 |  | 49753.2073 |  | 49753.2073 |  | 49753.2073 |  | 49753.2073 |  | 49753.2073 |  | 49753.2073 |  | 49753.2073
2025-12-05 | 547505.1215 |  | 49773.1929 |  | 49773.1929 |  | 49773.1929 |  | 49773.1929 |  | 49773.1929 |  | 49773.1929 |  | 49773.1929 |  | 49773.1929 |  | 49773.1929 |  | 49773.1929 |  | 49773.1929
2025-12-06 | 547724.9632 |  | 49793.1785 |  | 49793.1785 |  | 49793.1785 |  | 49793.1785 |  | 49793.1785 |  | 49793.1785 |  | 49793.1785 |  | 49793.1785 |  | 49793.1785 |  | 49793.1785 |  | 49793.1785
2025-12-07 | 547944.8049 |  | 49813.1641 |  | 49813.1641 |  | 49813.1641 |  | 49813.1641 |  | 49813.1641 |  | 49813.1641 |  | 49813.1641 |  | 49813.1641 |  | 49813.1641 |  | 49813.1641 |  | 49813.1641
2025-12-08 | 548164.6465 |  | 49833.1497 |  | 49833.1497 |  | 49833.1497 |  | 49833.1497 |  | 49833.1497 |  | 49833.1497 |  | 49833.1497 |  | 49833.1497 |  | 49833.1497 |  | 49833.1497 |  | 49833.1497
2025-12-09 | 548384.4882 |  | 49853.1353 |  | 49853.1353 |  | 49853.1353 |  | 49853.1353 |  | 49853.1353 |  | 49853.1353 |  | 49853.1353 |  | 49853.1353 |  | 49853.1353 |  | 49853.1353 |  | 49853.1353
2025-12-10 | 548604.3299 |  | 49873.1209 |  | 49873.1209 |  | 49873.1209 |  | 49873.1209 |  | 49873.1209 |  | 49873.1209 |  | 49873.1209 |  | 49873.1209 |  | 49873.1209 |  | 49873.1209 |  | 49873.1209
2025-12-11 | 548824.1715 |  | 49893.1065 |  | 49893.1065 |  | 49893.1065 |  | 49893.1065 |  | 49893.1065 |  | 49893.1065 |  | 49893.1065 |  | 49893.1065 |  | 49893.1065 |  | 49893.1065 |  | 49893.1065
2025-12-12 | 549044.0132 |  | 49913.0921 |  | 49913.0921 |  | 49913.0921 |  | 49913.0921 |  | 49913.0921 |  | 49913.0921 |  | 49913.0921 |  | 49913.0921 |  | 49913.0921 |  | 49913.0921 |  | 49913.0921
2025-12-13 | 549263.8549 |  | 49933.0777 |  | 49933.0777 |  | 49933.0777 |  | 49933.0777 |  | 49933.0777 |  | 49933.0777 |  | 49933.0777 |  | 49933.0777 |  | 49933.0777 |  | 49933.0777 |  | 49933.0777
2025-12-14 | 549483.6965 |  | 49953.0633 |  | 49953.0633 |  | 49953.0633 |  | 49953.0633 |  | 49953.0633 |  | 49953.0633 |  | 49953.0633 |  | 49953.0633 |  | 49953.0633 |  | 49953.0633 |  | 49953.0633
2025-12-15 | 549703.5382 |  | 49973.0489 |  | 49973.0489 |  | 49973.0489 |  | 49973.0489 |  | 49973.0489 |  | 49973.0489 |  | 49973.0489 |  | 49973.0489 |  | 49973.0489 |  | 49973.0489 |  | 49973.0489
2025-12-16 | 549923.3799 |  | 49993.0345 |  | 49993.0345 |  | 49993.0345 |  | 49993.0345 |  | 49993.0345 |  | 49993.0345 |  | 49993.0345 |  | 49993.0345 |  | 49993.0345 |  | 49993.0345 |  | 49993.0345
2025-12-17 | 550143.2215 |  | 50013.0201 |  | 50013.0201 |  | 50013.0201 |  | 50013.0201 |  | 50013.0201 |  | 50013.0201 |  | 50013.0201 |  | 50013.0201 |  | 50013.0201 |  | 50013.0201 |  | 50013.0201
2025-12-18 | 550363.0632 |  | 50033.0057 |  | 50033.0057 |  | 50033.0057 |  | 50033.0057 |  | 50033.0057 |  | 50033.0057 |  | 50033.0057 |  | 50033.0057 |  | 50033.0057 |  | 50033.0057 |  | 50033.0057
2025-12-19 | 550582.9049 |  | 50052.9914 |  | 50052.9914 |  | 50052.9914 |  | 50052.9914 |  | 50052.9914 |  | 50052.9914 |  | 50052.9914 |  | 50052.9914 |  | 50052.9914 |  | 50052.9914 |  | 50052.9914
2025-12-20 | 550802.7465 |  | 50072.977 |  | 50072.977 |  | 50072.977 |  | 50072.977 |  | 50072.977 |  | 50072.977 |  | 50072.977 |  | 50072.977 |  | 50072.977 |  | 50072.977 |  | 50072.977
2025-12-21 | 551022.5882 |  | 50092.9626 |  | 50092.9626 |  | 50092.9626 |  | 50092.9626 |  | 50092.9626 |  | 50092.9626 |  | 50092.9626 |  | 50092.9626 |  | 50092.9626 |  | 50092.9626 |  | 50092.9626
2025-12-22 | 551242.4299 |  | 50112.9482 |  | 50112.9482 |  | 50112.9482 |  | 50112.9482 |  | 50112.9482 |  | 50112.9482 |  | 50112.9482 |  | 50112.9482 |  | 50112.9482 |  | 50112.9482 |  | 50112.9482
2025-12-23 | 551462.2715 |  | 50132.9338 |  | 50132.9338 |  | 50132.9338 |  | 50132.9338 |  | 50132.9338 |  | 50132.9338 |  | 50132.9338 |  | 50132.9338 |  | 50132.9338 |  | 50132.9338 |  | 50132.9338
2025-12-24 | 551682.1132 |  | 50152.9194 |  | 50152.9194 |  | 50152.9194 |  | 50152.9194 |  | 50152.9194 |  | 50152.9194 |  | 50152.9194 |  | 50152.9194 |  | 50152.9194 |  | 50152.9194 |  | 50152.9194
2025-12-25 | 551901.9549 |  | 50172.905 |  | 50172.905 |  | 50172.905 |  | 50172.905 |  | 50172.905 |  | 50172.905 |  | 50172.905 |  | 50172.905 |  | 50172.905 |  | 50172.905 |  | 50172.905
2025-12-26 | 552121.7965 |  | 50192.8906 |  | 50192.8906 |  | 50192.8906 |  | 50192.8906 |  | 50192.8906 |  | 50192.8906 |  | 50192.8906 |  | 50192.8906 |  | 50192.8906 |  | 50192.8906 |  | 50192.8906
2025-12-27 | 552341.6382 |  | 50212.8762 |  | 50212.8762 |  | 50212.8762 |  | 50212.8762 |  | 50212.8762 |  | 50212.8762 |  | 50212.8762 |  | 50212.8762 |  | 50212.8762 |  | 50212.8762 |  | 50212.8762
2025-12-28 | 552561.4799 |  | 50232.8618 |  | 50232.8618 |  | 50232.8618 |  | 50232.8618 |  | 50232.8618 |  | 50232.8618 |  | 50232.8618 |  | 50232.8618 |  | 50232.8618 |  | 50232.8618 |  | 50232.8618
2025-12-29 | 552781.3215 |  | 50252.8474 |  | 50252.8474 |  | 50252.8474 |  | 50252.8474 |  | 50252.8474 |  | 50252.8474 |  | 50252.8474 |  | 50252.8474 |  | 50252.8474 |  | 50252.8474 |  | 50252.8474
2025-12-30 | 553001.1632 |  | 50272.833 |  | 50272.833 |  | 50272.833 |  | 50272.833 |  | 50272.833 |  | 50272.833 |  | 50272.833 |  | 50272.833 |  | 50272.833 |  | 50272.833 |  | 50272.833
2025-12-31 | 553221.0049 |  | 50292.8186 |  | 50292.8186 |  | 50292.8186 |  | 50292.8186 |  | 50292.8186 |  | 50292.8186 |  | 50292.8186 |  | 50292.8186 |  | 50292.8186 |  | 50292.8186 |  | 50292.8186
2026-01-01 | 553440.8465 |  | 50312.8042 |  | 50312.8042 |  | 50312.8042 |  | 50312.8042 |  | 50312.8042 |  | 50312.8042 |  | 50312.8042 |  | 50312.8042 |  | 50312.8042 |  | 50312.8042 |  | 50312.8042
2026-01-02 | 553660.6882 |  | 50332.7898 |  | 50332.7898 |  | 50332.7898 |  | 50332.7898 |  | 50332.7898 |  | 50332.7898 |  | 50332.7898 |  | 50332.7898 |  | 50332.7898 |  | 50332.7898 |  | 50332.7898
2026-01-03 | 553880.5299 |  | 50352.7754 |  | 50352.7754 |  | 50352.7754 |  | 50352.7754 |  | 50352.7754 |  | 50352.7754 |  | 50352.7754 |  | 50352.7754 |  | 50352.7754 |  | 50352.7754 |  | 50352.7754
2026-01-04 | 554100.3715 |  | 50372.761 |  | 50372.761 |  | 50372.761 |  | 50372.761 |  | 50372.761 |  | 50372.761 |  | 50372.761 |  | 50372.761 |  | 50372.761 |  | 50372.761 |  | 50372.761
2026-01-05 | 554320.2132 |  | 50392.7467 |  | 50392.7467 |  | 50392.7467 |  | 50392.7467 |  | 50392.7467 |  | 50392.7467 |  | 50392.7467 |  | 50392.7467 |  | 50392.7467 |  | 50392.7467 |  | 50392.7467
2026-01-06 | 554540.0549 |  | 50412.7323 |  | 50412.7323 |  | 50412.7323 |  | 50412.7323 |  | 50412.7323 |  | 50412.7323 |  | 50412.7323 |  | 50412.7323 |  | 50412.7323 |  | 50412.7323 |  | 50412.7323
2026-01-07 | 554759.8965 |  | 50432.7179 |  | 50432.7179 |  | 50432.7179 |  | 50432.7179 |  | 50432.7179 |  | 50432.7179 |  | 50432.7179 |  | 50432.7179 |  | 50432.7179 |  | 50432.7179 |  | 50432.7179
2026-01-08 | 554979.7382 |  | 50452.7035 |  | 50452.7035 |  | 50452.7035 |  | 50452.7035 |  | 50452.7035 |  | 50452.7035 |  | 50452.7035 |  | 50452.7035 |  | 50452.7035 |  | 50452.7035 |  | 50452.7035
2026-01-09 | 555199.5799 |  | 50472.6891 |  | 50472.6891 |  | 50472.6891 |  | 50472.6891 |  | 50472.6891 |  | 50472.6891 |  | 50472.6891 |  | 50472.6891 |  | 50472.6891 |  | 50472.6891 |  | 50472.6891
2026-01-10 | 555419.4215 |  | 50492.6747 |  | 50492.6747 |  | 50492.6747 |  | 50492.6747 |  | 50492.6747 |  | 50492.6747 |  | 50492.6747 |  | 50492.6747 |  | 50492.6747 |  | 50492.6747 |  | 50492.6747
2026-01-11 | 555639.2632 |  | 50512.6603 |  | 50512.6603 |  | 50512.6603 |  | 50512.6603 |  | 50512.6603 |  | 50512.6603 |  | 50512.6603 |  | 50512.6603 |  | 50512.6603 |  | 50512.6603 |  | 50512.6603
2026-01-12 | 555859.1049 |  | 50532.6459 |  | 50532.6459 |  | 50532.6459 |  | 50532.6459 |  | 50532.6459 |  | 50532.6459 |  | 50532.6459 |  | 50532.6459 |  | 50532.6459 |  | 50532.6459 |  | 50532.6459
2026-01-13 | 556078.9465 |  | 50552.6315 |  | 50552.6315 |  | 50552.6315 |  | 50552.6315 |  | 50552.6315 |  | 50552.6315 |  | 50552.6315 |  | 50552.6315 |  | 50552.6315 |  | 50552.6315 |  | 50552.6315
2026-01-14 | 556298.7882 |  | 50572.6171 |  | 50572.6171 |  | 50572.6171 |  | 50572.6171 |  | 50572.6171 |  | 50572.6171 |  | 50572.6171 |  | 50572.6171 |  | 50572.6171 |  | 50572.6171 |  | 50572.6171
2026-01-15 | 556518.6299 |  | 50592.6027 |  | 50592.6027 |  | 50592.6027 |  | 50592.6027 |  | 50592.6027 |  | 50592.6027 |  | 50592.6027 |  | 50592.6027 |  | 50592.6027 |  | 50592.6027 |  | 50592.6027
2026-01-16 | 556738.4715 |  | 50612.5883 |  | 50612.5883 |  | 50612.5883 |  | 50612.5883 |  | 50612.5883 |  | 50612.5883 |  | 50612.5883 |  | 50612.5883 |  | 50612.5883 |  | 50612.5883 |  | 50612.5883
2026-01-17 | 556958.3132 |  | 50632.5739 |  | 50632.5739 |  | 50632.5739 |  | 50632.5739 |  | 50632.5739 |  | 50632.5739 |  | 50632.5739 |  | 50632.5739 |  | 50632.5739 |  | 50632.5739 |  | 50632.5739
2026-01-18 | 557178.1549 |  | 50652.5595 |  | 50652.5595 |  | 50652.5595 |  | 50652.5595 |  | 50652.5595 |  | 50652.5595 |  | 50652.5595 |  | 50652.5595 |  | 50652.5595 |  | 50652.5595 |  | 50652.5595
2026-01-19 | 557397.9965 |  | 50672.5451 |  | 50672.5451 |  | 50672.5451 |  | 50672.5451 |  | 50672.5451 |  | 50672.5451 |  | 50672.5451 |  | 50672.5451 |  | 50672.5451 |  | 50672.5451 |  | 50672.5451
2026-01-20 | 557617.8382 |  | 50692.5307 |  | 50692.5307 |  | 50692.5307 |  | 50692.5307 |  | 50692.5307 |  | 50692.5307 |  | 50692.5307 |  | 50692.5307 |  | 50692.5307 |  | 50692.5307 |  | 50692.5307
2026-01-21 | 557837.6799 |  | 50712.5164 |  | 50712.5164 |  | 50712.5164 |  | 50712.5164 |  | 50712.5164 |  | 50712.5164 |  | 50712.5164 |  | 50712.5164 |  | 50712.5164 |  | 50712.5164 |  | 50712.5164
2026-01-22 | 558057.5215 |  | 50732.502 |  | 50732.502 |  | 50732.502 |  | 50732.502 |  | 50732.502 |  | 50732.502 |  | 50732.502 |  | 50732.502 |  | 50732.502 |  | 50732.502 |  | 50732.502
2026-01-23 | 558277.3632 |  | 50752.4876 |  | 50752.4876 |  | 50752.4876 |  | 50752.4876 |  | 50752.4876 |  | 50752.4876 |  | 50752.4876 |  | 50752.4876 |  | 50752.4876 |  | 50752.4876 |  | 50752.4876
2026-01-24 | 558497.2049 |  | 50772.4732 |  | 50772.4732 |  | 50772.4732 |  | 50772.4732 |  | 50772.4732 |  | 50772.4732 |  | 50772.4732 |  | 50772.4732 |  | 50772.4732 |  | 50772.4732 |  | 50772.4732
2026-01-25 | 558717.0465 |  | 50792.4588 |  | 50792.4588 |  | 50792.4588 |  | 50792.4588 |  | 50792.4588 |  | 50792.4588 |  | 50792.4588 |  | 50792.4588 |  | 50792.4588 |  | 50792.4588 |  | 50792.4588
2026-01-26 | 558936.8882 |  | 50812.4444 |  | 50812.4444 |  | 50812.4444 |  | 50812.4444 |  | 50812.4444 |  | 50812.4444 |  | 50812.4444 |  | 50812.4444 |  | 50812.4444 |  | 50812.4444 |  | 50812.4444
2026-01-27 | 559156.7299 |  | 50832.43 |  | 50832.43 |  | 50832.43 |  | 50832.43 |  | 50832.43 |  | 50832.43 |  | 50832.43 |  | 50832.43 |  | 50832.43 |  | 50832.43 |  | 50832.43
2026-01-28 | 559376.5715 |  | 50852.4156 |  | 50852.4156 |  | 50852.4156 |  | 50852.4156 |  | 50852.4156 |  | 50852.4156 |  | 50852.4156 |  | 50852.4156 |  | 50852.4156 |  | 50852.4156 |  | 50852.4156
2026-01-29 | 559596.4132 |  | 50872.4012 |  | 50872.4012 |  | 50872.4012 |  | 50872.4012 |  | 50872.4012 |  | 50872.4012 |  | 50872.4012 |  | 50872.4012 |  | 50872.4012 |  | 50872.4012 |  | 50872.4012
2026-01-30 | 559816.2549 |  | 50892.3868 |  | 50892.3868 |  | 50892.3868 |  | 50892.3868 |  | 50892.3868 |  | 50892.3868 |  | 50892.3868 |  | 50892.3868 |  | 50892.3868 |  | 50892.3868 |  | 50892.3868
2026-01-31 | 560036.0965 |  | 50912.3724 |  | 50912.3724 |  | 50912.3724 |  | 50912.3724 |  | 50912.3724 |  | 50912.3724 |  | 50912.3724 |  | 50912.3724 |  | 50912.3724 |  | 50912.3724 |  | 50912.3724
2026-02-01 | 560255.9382 |  | 50932.358 |  | 50932.358 |  | 50932.358 |  | 50932.358 |  | 50932.358 |  | 50932.358 |  | 50932.358 |  | 50932.358 |  | 50932.358 |  | 50932.358 |  | 50932.358
2026-02-02 | 560475.7799 |  | 50952.3436 |  | 50952.3436 |  | 50952.3436 |  | 50952.3436 |  | 50952.3436 |  | 50952.3436 |  | 50952.3436 |  | 50952.3436 |  | 50952.3436 |  | 50952.3436 |  | 50952.3436
2026-02-03 | 560695.6215 |  | 50972.3292 |  | 50972.3292 |  | 50972.3292 |  | 50972.3292 |  | 50972.3292 |  | 50972.3292 |  | 50972.3292 |  | 50972.3292 |  | 50972.3292 |  | 50972.3292 |  | 50972.3292
2026-02-04 | 560915.4632 |  | 50992.3148 |  | 50992.3148 |  | 50992.3148 |  | 50992.3148 |  | 50992.3148 |  | 50992.3148 |  | 50992.3148 |  | 50992.3148 |  | 50992.3148 |  | 50992.3148 |  | 50992.3148
2026-02-05 | 561135.3049 |  | 51012.3004 |  | 51012.3004 |  | 51012.3004 |  | 51012.3004 |  | 51012.3004 |  | 51012.3004 |  | 51012.3004 |  | 51012.3004 |  | 51012.3004 |  | 51012.3004 |  | 51012.3004
2026-02-06 | 561355.1465 |  | 51032.286 |  | 51032.286 |  | 51032.286 |  | 51032.286 |  | 51032.286 |  | 51032.286 |  | 51032.286 |  | 51032.286 |  | 51032.286 |  | 51032.286 |  | 51032.286
2026-02-07 | 561574.9882 |  | 51052.2717 |  | 51052.2717 |  | 51052.2717 |  | 51052.2717 |  | 51052.2717 |  | 51052.2717 |  | 51052.2717 |  | 51052.2717 |  | 51052.2717 |  | 51052.2717 |  | 51052.2717
2026-02-08 | 561794.8299 |  | 51072.2573 |  | 51072.2573 |  | 51072.2573 |  | 51072.2573 |  | 51072.2573 |  | 51072.2573 |  | 51072.2573 |  | 51072.2573 |  | 51072.2573 |  | 51072.2573 |  | 51072.2573
2026-02-09 | 562014.6715 |  | 51092.2429 |  | 51092.2429 |  | 51092.2429 |  | 51092.2429 |  | 51092.2429 |  | 51092.2429 |  | 51092.2429 |  | 51092.2429 |  | 51092.2429 |  | 51092.2429 |  | 51092.2429
2026-02-10 | 562234.5132 |  | 51112.2285 |  | 51112.2285 |  | 51112.2285 |  | 51112.2285 |  | 51112.2285 |  | 51112.2285 |  | 51112.2285 |  | 51112.2285 |  | 51112.2285 |  | 51112.2285 |  | 51112.2285
2026-02-11 | 562454.3549 |  | 51132.2141 |  | 51132.2141 |  | 51132.2141 |  | 51132.2141 |  | 51132.2141 |  | 51132.2141 |  | 51132.2141 |  | 51132.2141 |  | 51132.2141 |  | 51132.2141 |  | 51132.2141
2026-02-12 | 562674.1965 |  | 51152.1997 |  | 51152.1997 |  | 51152.1997 |  | 51152.1997 |  | 51152.1997 |  | 51152.1997 |  | 51152.1997 |  | 51152.1997 |  | 51152.1997 |  | 51152.1997 |  | 51152.1997
2026-02-13 | 562894.0382 |  | 51172.1853 |  | 51172.1853 |  | 51172.1853 |  | 51172.1853 |  | 51172.1853 |  | 51172.1853 |  | 51172.1853 |  | 51172.1853 |  | 51172.1853 |  | 51172.1853 |  | 51172.1853
2026-02-14 | 563113.8799 |  | 51192.1709 |  | 51192.1709 |  | 51192.1709 |  | 51192.1709 |  | 51192.1709 |  | 51192.1709 |  | 51192.1709 |  | 51192.1709 |  | 51192.1709 |  | 51192.1709 |  | 51192.1709
2026-02-15 | 563333.7215 |  | 51212.1565 |  | 51212.1565 |  | 51212.1565 |  | 51212.1565 |  | 51212.1565 |  | 51212.1565 |  | 51212.1565 |  | 51212.1565 |  | 51212.1565 |  | 51212.1565 |  | 51212.1565
2026-02-16 | 563553.5632 |  | 51232.1421 |  | 51232.1421 |  | 51232.1421 |  | 51232.1421 |  | 51232.1421 |  | 51232.1421 |  | 51232.1421 |  | 51232.1421 |  | 51232.1421 |  | 51232.1421 |  | 51232.1421
2026-02-17 | 563773.4049 |  | 51252.1277 |  | 51252.1277 |  | 51252.1277 |  | 51252.1277 |  | 51252.1277 |  | 51252.1277 |  | 51252.1277 |  | 51252.1277 |  | 51252.1277 |  | 51252.1277 |  | 51252.1277
2026-02-18 | 563993.2465 |  | 51272.1133 |  | 51272.1133 |  | 51272.1133 |  | 51272.1133 |  | 51272.1133 |  | 51272.1133 |  | 51272.1133 |  | 51272.1133 |  | 51272.1133 |  | 51272.1133 |  | 51272.1133
2026-02-19 | 564213.0882 |  | 51292.0989 |  | 51292.0989 |  | 51292.0989 |  | 51292.0989 |  | 51292.0989 |  | 51292.0989 |  | 51292.0989 |  | 51292.0989 |  | 51292.0989 |  | 51292.0989 |  | 51292.0989
2026-02-20 | 564432.9299 |  | 51312.0845 |  | 51312.0845 |  | 51312.0845 |  | 51312.0845 |  | 51312.0845 |  | 51312.0845 |  | 51312.0845 |  | 51312.0845 |  | 51312.0845 |  | 51312.0845 |  | 51312.0845
2026-02-21 | 564652.7715 |  | 51332.0701 |  | 51332.0701 |  | 51332.0701 |  | 51332.0701 |  | 51332.0701 |  | 51332.0701 |  | 51332.0701 |  | 51332.0701 |  | 51332.0701 |  | 51332.0701 |  | 51332.0701
2026-02-22 | 564872.6132 |  | 51352.0557 |  | 51352.0557 |  | 51352.0557 |  | 51352.0557 |  | 51352.0557 |  | 51352.0557 |  | 51352.0557 |  | 51352.0557 |  | 51352.0557 |  | 51352.0557 |  | 51352.0557
2026-02-23 | 565092.4549 |  | 51372.0414 |  | 51372.0414 |  | 51372.0414 |  | 51372.0414 |  | 51372.0414 |  | 51372.0414 |  | 51372.0414 |  | 51372.0414 |  | 51372.0414 |  | 51372.0414 |  | 51372.0414
2026-02-24 | 565312.2965 |  | 51392.027 |  | 51392.027 |  | 51392.027 |  | 51392.027 |  | 51392.027 |  | 51392.027 |  | 51392.027 |  | 51392.027 |  | 51392.027 |  | 51392.027 |  | 51392.027
2026-02-25 | 565532.1382 |  | 51412.0126 |  | 51412.0126 |  | 51412.0126 |  | 51412.0126 |  | 51412.0126 |  | 51412.0126 |  | 51412.0126 |  | 51412.0126 |  | 51412.0126 |  | 51412.0126 |  | 51412.0126
2026-02-26 | 565751.9799 |  | 51431.9982 |  | 51431.9982 |  | 51431.9982 |  | 51431.9982 |  | 51431.9982 |  | 51431.9982 |  | 51431.9982 |  | 51431.9982 |  | 51431.9982 |  | 51431.9982 |  | 51431.9982
2026-02-27 | 565971.8215 |  | 51451.9838 |  | 51451.9838 |  | 51451.9838 |  | 51451.9838 |  | 51451.9838 |  | 51451.9838 |  | 51451.9838 |  | 51451.9838 |  | 51451.9838 |  | 51451.9838 |  | 51451.9838
2026-02-28 | 566191.6632 |  | 51471.9694 |  | 51471.9694 |  | 51471.9694 |  | 51471.9694 |  | 51471.9694 |  | 51471.9694 |  | 51471.9694 |  | 51471.9694 |  | 51471.9694 |  | 51471.9694 |  | 51471.9694
2026-03-01 | 566411.5049 |  | 51491.955 |  | 51491.955 |  | 51491.955 |  | 51491.955 |  | 51491.955 |  | 51491.955 |  | 51491.955 |  | 51491.955 |  | 51491.955 |  | 51491.955 |  | 51491.955
2026-03-02 | 566631.3465 |  | 51511.9406 |  | 51511.9406 |  | 51511.9406 |  | 51511.9406 |  | 51511.9406 |  | 51511.9406 |  | 51511.9406 |  | 51511.9406 |  | 51511.9406 |  | 51511.9406 |  | 51511.9406
2026-03-03 | 566851.1882 |  | 51531.9262 |  | 51531.9262 |  | 51531.9262 |  | 51531.9262 |  | 51531.9262 |  | 51531.9262 |  | 51531.9262 |  | 51531.9262 |  | 51531.9262 |  | 51531.9262 |  | 51531.9262
2026-03-04 | 567071.0299 |  | 51551.9118 |  | 51551.9118 |  | 51551.9118 |  | 51551.9118 |  | 51551.9118 |  | 51551.9118 |  | 51551.9118 |  | 51551.9118 |  | 51551.9118 |  | 51551.9118 |  | 51551.9118
2026-03-05 | 567290.8715 |  | 51571.8974 |  | 51571.8974 |  | 51571.8974 |  | 51571.8974 |  | 51571.8974 |  | 51571.8974 |  | 51571.8974 |  | 51571.8974 |  | 51571.8974 |  | 51571.8974 |  | 51571.8974
2026-03-06 | 567510.7132 |  | 51591.883 |  | 51591.883 |  | 51591.883 |  | 51591.883 |  | 51591.883 |  | 51591.883 |  | 51591.883 |  | 51591.883 |  | 51591.883 |  | 51591.883 |  | 51591.883
2026-03-07 | 567730.5549 |  | 51611.8686 |  | 51611.8686 |  | 51611.8686 |  | 51611.8686 |  | 51611.8686 |  | 51611.8686 |  | 51611.8686 |  | 51611.8686 |  | 51611.8686 |  | 51611.8686 |  | 51611.8686
2026-03-08 | 567950.3965 |  | 51631.8542 |  | 51631.8542 |  | 51631.8542 |  | 51631.8542 |  | 51631.8542 |  | 51631.8542 |  | 51631.8542 |  | 51631.8542 |  | 51631.8542 |  | 51631.8542 |  | 51631.8542
2026-03-09 | 568170.2382 |  | 51651.8398 |  | 51651.8398 |  | 51651.8398 |  | 51651.8398 |  | 51651.8398 |  | 51651.8398 |  | 51651.8398 |  | 51651.8398 |  | 51651.8398 |  | 51651.8398 |  | 51651.8398
2026-03-10 | 568390.0799 |  | 51671.8254 |  | 51671.8254 |  | 51671.8254 |  | 51671.8254 |  | 51671.8254 |  | 51671.8254 |  | 51671.8254 |  | 51671.8254 |  | 51671.8254 |  | 51671.8254 |  | 51671.8254
2026-03-11 | 568609.9215 |  | 51691.811 |  | 51691.811 |  | 51691.811 |  | 51691.811 |  | 51691.811 |  | 51691.811 |  | 51691.811 |  | 51691.811 |  | 51691.811 |  | 51691.811 |  | 51691.811
2026-03-12 | 568829.7632 |  | 51711.7967 |  | 51711.7967 |  | 51711.7967 |  | 51711.7967 |  | 51711.7967 |  | 51711.7967 |  | 51711.7967 |  | 51711.7967 |  | 51711.7967 |  | 51711.7967 |  | 51711.7967
2026-03-13 | 569049.6049 |  | 51731.7823 |  | 51731.7823 |  | 51731.7823 |  | 51731.7823 |  | 51731.7823 |  | 51731.7823 |  | 51731.7823 |  | 51731.7823 |  | 51731.7823 |  | 51731.7823 |  | 51731.7823
2026-03-14 | 569269.4465 |  | 51751.7679 |  | 51751.7679 |  | 51751.7679 |  | 51751.7679 |  | 51751.7679 |  | 51751.7679 |  | 51751.7679 |  | 51751.7679 |  | 51751.7679 |  | 51751.7679 |  | 51751.7679
2026-03-15 | 569489.2882 |  | 51771.7535 |  | 51771.7535 |  | 51771.7535 |  | 51771.7535 |  | 51771.7535 |  | 51771.7535 |  | 51771.7535 |  | 51771.7535 |  | 51771.7535 |  | 51771.7535 |  | 51771.7535
2026-03-16 | 569709.1299 |  | 51791.7391 |  | 51791.7391 |  | 51791.7391 |  | 51791.7391 |  | 51791.7391 |  | 51791.7391 |  | 51791.7391 |  | 51791.7391 |  | 51791.7391 |  | 51791.7391 |  | 51791.7391
2026-03-17 | 569928.9715 |  | 51811.7247 |  | 51811.7247 |  | 51811.7247 |  | 51811.7247 |  | 51811.7247 |  | 51811.7247 |  | 51811.7247 |  | 51811.7247 |  | 51811.7247 |  | 51811.7247 |  | 51811.7247
2026-03-18 | 570148.8132 |  | 51831.7103 |  | 51831.7103 |  | 51831.7103 |  | 51831.7103 |  | 51831.7103 |  | 51831.7103 |  | 51831.7103 |  | 51831.7103 |  | 51831.7103 |  | 51831.7103 |  | 51831.7103
2026-03-19 | 570368.6549 |  | 51851.6959 |  | 51851.6959 |  | 51851.6959 |  | 51851.6959 |  | 51851.6959 |  | 51851.6959 |  | 51851.6959 |  | 51851.6959 |  | 51851.6959 |  | 51851.6959 |  | 51851.6959
2026-03-20 | 570588.4965 |  | 51871.6815 |  | 51871.6815 |  | 51871.6815 |  | 51871.6815 |  | 51871.6815 |  | 51871.6815 |  | 51871.6815 |  | 51871.6815 |  | 51871.6815 |  | 51871.6815 |  | 51871.6815
2026-03-21 | 570808.3382 |  | 51891.6671 |  | 51891.6671 |  | 51891.6671 |  | 51891.6671 |  | 51891.6671 |  | 51891.6671 |  | 51891.6671 |  | 51891.6671 |  | 51891.6671 |  | 51891.6671 |  | 51891.6671
2026-03-22 | 571028.1799 |  | 51911.6527 |  | 51911.6527 |  | 51911.6527 |  | 51911.6527 |  | 51911.6527 |  | 51911.6527 |  | 51911.6527 |  | 51911.6527 |  | 51911.6527 |  | 51911.6527 |  | 51911.6527
2026-03-23 | 571248.0215 |  | 51931.6383 |  | 51931.6383 |  | 51931.6383 |  | 51931.6383 |  | 51931.6383 |  | 51931.6383 |  | 51931.6383 |  | 51931.6383 |  | 51931.6383 |  | 51931.6383 |  | 51931.6383
2026-03-24 | 571467.8632 |  | 51951.6239 |  | 51951.6239 |  | 51951.6239 |  | 51951.6239 |  | 51951.6239 |  | 51951.6239 |  | 51951.6239 |  | 51951.6239 |  | 51951.6239 |  | 51951.6239 |  | 51951.6239
2026-03-25 | 571687.7049 |  | 51971.6095 |  | 51971.6095 |  | 51971.6095 |  | 51971.6095 |  | 51971.6095 |  | 51971.6095 |  | 51971.6095 |  | 51971.6095 |  | 51971.6095 |  | 51971.6095 |  | 51971.6095
2026-03-26 | 571907.5465 |  | 51991.5951 |  | 51991.5951 |  | 51991.5951 |  | 51991.5951 |  | 51991.5951 |  | 51991.5951 |  | 51991.5951 |  | 51991.5951 |  | 51991.5951 |  | 51991.5951 |  | 51991.5951
2026-03-27 | 572127.3882 |  | 52011.5807 |  | 52011.5807 |  | 52011.5807 |  | 52011.5807 |  | 52011.5807 |  | 52011.5807 |  | 52011.5807 |  | 52011.5807 |  | 52011.5807 |  | 52011.5807 |  | 52011.5807
2026-03-28 | 572347.2299 |  | 52031.5664 |  | 52031.5664 |  | 52031.5664 |  | 52031.5664 |  | 52031.5664 |  | 52031.5664 |  | 52031.5664 |  | 52031.5664 |  | 52031.5664 |  | 52031.5664 |  | 52031.5664
2026-03-29 | 572567.0715 |  | 52051.552 |  | 52051.552 |  | 52051.552 |  | 52051.552 |  | 52051.552 |  | 52051.552 |  | 52051.552 |  | 52051.552 |  | 52051.552 |  | 52051.552 |  | 52051.552
2026-03-30 | 572786.9132 |  | 52071.5376 |  | 52071.5376 |  | 52071.5376 |  | 52071.5376 |  | 52071.5376 |  | 52071.5376 |  | 52071.5376 |  | 52071.5376 |  | 52071.5376 |  | 52071.5376 |  | 52071.5376
2026-03-31 | 573006.7549 |  | 52091.5232 |  | 52091.5232 |  | 52091.5232 |  | 52091.5232 |  | 52091.5232 |  | 52091.5232 |  | 52091.5232 |  | 52091.5232 |  | 52091.5232 |  | 52091.5232 |  | 52091.5232
2026-04-01 | 573226.5965 |  | 52111.5088 |  | 52111.5088 |  | 52111.5088 |  | 52111.5088 |  | 52111.5088 |  | 52111.5088 |  | 52111.5088 |  | 52111.5088 |  | 52111.5088 |  | 52111.5088 |  | 52111.5088
2026-04-02 | 573446.4382 |  | 52131.4944 |  | 52131.4944 |  | 52131.4944 |  | 52131.4944 |  | 52131.4944 |  | 52131.4944 |  | 52131.4944 |  | 52131.4944 |  | 52131.4944 |  | 52131.4944 |  | 52131.4944
2026-04-03 | 573666.2799 |  | 52151.48 |  | 52151.48 |  | 52151.48 |  | 52151.48 |  | 52151.48 |  | 52151.48 |  | 52151.48 |  | 52151.48 |  | 52151.48 |  | 52151.48 |  | 52151.48
2026-04-04 | 573886.1215 |  | 52171.4656 |  | 52171.4656 |  | 52171.4656 |  | 52171.4656 |  | 52171.4656 |  | 52171.4656 |  | 52171.4656 |  | 52171.4656 |  | 52171.4656 |  | 52171.4656 |  | 52171.4656
2026-04-05 | 574105.9632 |  | 52191.4512 |  | 52191.4512 |  | 52191.4512 |  | 52191.4512 |  | 52191.4512 |  | 52191.4512 |  | 52191.4512 |  | 52191.4512 |  | 52191.4512 |  | 52191.4512 |  | 52191.4512
2026-04-06 | 574325.8049 |  | 52211.4368 |  | 52211.4368 |  | 52211.4368 |  | 52211.4368 |  | 52211.4368 |  | 52211.4368 |  | 52211.4368 |  | 52211.4368 |  | 52211.4368 |  | 52211.4368 |  | 52211.4368
2026-04-07 | 574545.6465 |  | 52231.4224 |  | 52231.4224 |  | 52231.4224 |  | 52231.4224 |  | 52231.4224 |  | 52231.4224 |  | 52231.4224 |  | 52231.4224 |  | 52231.4224 |  | 52231.4224 |  | 52231.4224
2026-04-08 | 574765.4882 |  | 52251.408 |  | 52251.408 |  | 52251.408 |  | 52251.408 |  | 52251.408 |  | 52251.408 |  | 52251.408 |  | 52251.408 |  | 52251.408 |  | 52251.408 |  | 52251.408
2026-04-09 | 574985.3299 |  | 52271.3936 |  | 52271.3936 |  | 52271.3936 |  | 52271.3936 |  | 52271.3936 |  | 52271.3936 |  | 52271.3936 |  | 52271.3936 |  | 52271.3936 |  | 52271.3936 |  | 52271.3936
2026-04-10 | 575205.1715 |  | 52291.3792 |  | 52291.3792 |  | 52291.3792 |  | 52291.3792 |  | 52291.3792 |  | 52291.3792 |  | 52291.3792 |  | 52291.3792 |  | 52291.3792 |  | 52291.3792 |  | 52291.3792
2026-04-11 | 575425.0132 |  | 52311.3648 |  | 52311.3648 |  | 52311.3648 |  | 52311.3648 |  | 52311.3648 |  | 52311.3648 |  | 52311.3648 |  | 52311.3648 |  | 52311.3648 |  | 52311.3648 |  | 52311.3648
2026-04-12 | 575644.8549 |  | 52331.3504 |  | 52331.3504 |  | 52331.3504 |  | 52331.3504 |  | 52331.3504 |  | 52331.3504 |  | 52331.3504 |  | 52331.3504 |  | 52331.3504 |  | 52331.3504 |  | 52331.3504
2026-04-13 | 575864.6965 |  | 52351.336 |  | 52351.336 |  | 52351.336 |  | 52351.336 |  | 52351.336 |  | 52351.336 |  | 52351.336 |  | 52351.336 |  | 52351.336 |  | 52351.336 |  | 52351.336
2026-04-14 | 576084.5382 |  | 52371.3217 |  | 52371.3217 |  | 52371.3217 |  | 52371.3217 |  | 52371.3217 |  | 52371.3217 |  | 52371.3217 |  | 52371.3217 |  | 52371.3217 |  | 52371.3217 |  | 52371.3217
2026-04-15 | 576304.3799 |  | 52391.3073 |  | 52391.3073 |  | 52391.3073 |  | 52391.3073 |  | 52391.3073 |  | 52391.3073 |  | 52391.3073 |  | 52391.3073 |  | 52391.3073 |  | 52391.3073 |  | 52391.3073
2026-04-16 | 576524.2215 |  | 52411.2929 |  | 52411.2929 |  | 52411.2929 |  | 52411.2929 |  | 52411.2929 |  | 52411.2929 |  | 52411.2929 |  | 52411.2929 |  | 52411.2929 |  | 52411.2929 |  | 52411.2929
2026-04-17 | 576744.0632 |  | 52431.2785 |  | 52431.2785 |  | 52431.2785 |  | 52431.2785 |  | 52431.2785 |  | 52431.2785 |  | 52431.2785 |  | 52431.2785 |  | 52431.2785 |  | 52431.2785 |  | 52431.2785
2026-04-18 | 576963.9049 |  | 52451.2641 |  | 52451.2641 |  | 52451.2641 |  | 52451.2641 |  | 52451.2641 |  | 52451.2641 |  | 52451.2641 |  | 52451.2641 |  | 52451.2641 |  | 52451.2641 |  | 52451.2641
2026-04-19 | 577183.7465 |  | 52471.2497 |  | 52471.2497 |  | 52471.2497 |  | 52471.2497 |  | 52471.2497 |  | 52471.2497 |  | 52471.2497 |  | 52471.2497 |  | 52471.2497 |  | 52471.2497 |  | 52471.2497
2026-04-20 | 577403.5882 |  | 52491.2353 |  | 52491.2353 |  | 52491.2353 |  | 52491.2353 |  | 52491.2353 |  | 52491.2353 |  | 52491.2353 |  | 52491.2353 |  | 52491.2353 |  | 52491.2353 |  | 52491.2353
2026-04-21 | 577623.4299 |  | 52511.2209 |  | 52511.2209 |  | 52511.2209 |  | 52511.2209 |  | 52511.2209 |  | 52511.2209 |  | 52511.2209 |  | 52511.2209 |  | 52511.2209 |  | 52511.2209 |  | 52511.2209
2026-04-22 | 577843.2715 |  | 52531.2065 |  | 52531.2065 |  | 52531.2065 |  | 52531.2065 |  | 52531.2065 |  | 52531.2065 |  | 52531.2065 |  | 52531.2065 |  | 52531.2065 |  | 52531.2065 |  | 52531.2065
2026-04-23 | 578063.1132 |  | 52551.1921 |  | 52551.1921 |  | 52551.1921 |  | 52551.1921 |  | 52551.1921 |  | 52551.1921 |  | 52551.1921 |  | 52551.1921 |  | 52551.1921 |  | 52551.1921 |  | 52551.1921
2026-04-24 | 578282.9549 |  | 52571.1777 |  | 52571.1777 |  | 52571.1777 |  | 52571.1777 |  | 52571.1777 |  | 52571.1777 |  | 52571.1777 |  | 52571.1777 |  | 52571.1777 |  | 52571.1777 |  | 52571.1777
2026-04-25 | 578502.7965 |  | 52591.1633 |  | 52591.1633 |  | 52591.1633 |  | 52591.1633 |  | 52591.1633 |  | 52591.1633 |  | 52591.1633 |  | 52591.1633 |  | 52591.1633 |  | 52591.1633 |  | 52591.1633
2026-04-26 | 578722.6382 |  | 52611.1489 |  | 52611.1489 |  | 52611.1489 |  | 52611.1489 |  | 52611.1489 |  | 52611.1489 |  | 52611.1489 |  | 52611.1489 |  | 52611.1489 |  | 52611.1489 |  | 52611.1489
2026-04-27 | 578942.4799 |  | 52631.1345 |  | 52631.1345 |  | 52631.1345 |  | 52631.1345 |  | 52631.1345 |  | 52631.1345 |  | 52631.1345 |  | 52631.1345 |  | 52631.1345 |  | 52631.1345 |  | 52631.1345
2026-04-28 | 579162.3215 |  | 52651.1201 |  | 52651.1201 |  | 52651.1201 |  | 52651.1201 |  | 52651.1201 |  | 52651.1201 |  | 52651.1201 |  | 52651.1201 |  | 52651.1201 |  | 52651.1201 |  | 52651.1201
2026-04-29 | 579382.1632 |  | 52671.1057 |  | 52671.1057 |  | 52671.1057 |  | 52671.1057 |  | 52671.1057 |  | 52671.1057 |  | 52671.1057 |  | 52671.1057 |  | 52671.1057 |  | 52671.1057 |  | 52671.1057
2026-04-30 | 579602.0049 |  | 52691.0914 |  | 52691.0914 |  | 52691.0914 |  | 52691.0914 |  | 52691.0914 |  | 52691.0914 |  | 52691.0914 |  | 52691.0914 |  | 52691.0914 |  | 52691.0914 |  | 52691.0914
2026-05-01 | 579821.8465 |  | 52711.077 |  | 52711.077 |  | 52711.077 |  | 52711.077 |  | 52711.077 |  | 52711.077 |  | 52711.077 |  | 52711.077 |  | 52711.077 |  | 52711.077 |  | 52711.077
2026-05-02 | 580041.6882 |  | 52731.0626 |  | 52731.0626 |  | 52731.0626 |  | 52731.0626 |  | 52731.0626 |  | 52731.0626 |  | 52731.0626 |  | 52731.0626 |  | 52731.0626 |  | 52731.0626 |  | 52731.0626
2026-05-03 | 580261.5299 |  | 52751.0482 |  | 52751.0482 |  | 52751.0482 |  | 52751.0482 |  | 52751.0482 |  | 52751.0482 |  | 52751.0482 |  | 52751.0482 |  | 52751.0482 |  | 52751.0482 |  | 52751.0482
2026-05-04 | 580481.3715 |  | 52771.0338 |  | 52771.0338 |  | 52771.0338 |  | 52771.0338 |  | 52771.0338 |  | 52771.0338 |  | 52771.0338 |  | 52771.0338 |  | 52771.0338 |  | 52771.0338 |  | 52771.0338
2026-05-05 | 580701.2132 |  | 52791.0194 |  | 52791.0194 |  | 52791.0194 |  | 52791.0194 |  | 52791.0194 |  | 52791.0194 |  | 52791.0194 |  | 52791.0194 |  | 52791.0194 |  | 52791.0194 |  | 52791.0194
2026-05-06 | 580921.0549 |  | 52811.005 |  | 52811.005 |  | 52811.005 |  | 52811.005 |  | 52811.005 |  | 52811.005 |  | 52811.005 |  | 52811.005 |  | 52811.005 |  | 52811.005 |  | 52811.005
2026-05-07 | 581140.8965 |  | 52830.9906 |  | 52830.9906 |  | 52830.9906 |  | 52830.9906 |  | 52830.9906 |  | 52830.9906 |  | 52830.9906 |  | 52830.9906 |  | 52830.9906 |  | 52830.9906 |  | 52830.9906
2026-05-08 | 581360.7382 |  | 52850.9762 |  | 52850.9762 |  | 52850.9762 |  | 52850.9762 |  | 52850.9762 |  | 52850.9762 |  | 52850.9762 |  | 52850.9762 |  | 52850.9762 |  | 52850.9762 |  | 52850.9762
2026-05-09 | 581580.5799 |  | 52870.9618 |  | 52870.9618 |  | 52870.9618 |  | 52870.9618 |  | 52870.9618 |  | 52870.9618 |  | 52870.9618 |  | 52870.9618 |  | 52870.9618 |  | 52870.9618 |  | 52870.9618
2026-05-10 | 581800.4215 |  | 52890.9474 |  | 52890.9474 |  | 52890.9474 |  | 52890.9474 |  | 52890.9474 |  | 52890.9474 |  | 52890.9474 |  | 52890.9474 |  | 52890.9474 |  | 52890.9474 |  | 52890.9474
2026-05-11 | 582020.2632 |  | 52910.933 |  | 52910.933 |  | 52910.933 |  | 52910.933 |  | 52910.933 |  | 52910.933 |  | 52910.933 |  | 52910.933 |  | 52910.933 |  | 52910.933 |  | 52910.933
2026-05-12 | 582240.1049 |  | 52930.9186 |  | 52930.9186 |  | 52930.9186 |  | 52930.9186 |  | 52930.9186 |  | 52930.9186 |  | 52930.9186 |  | 52930.9186 |  | 52930.9186 |  | 52930.9186 |  | 52930.9186
2026-05-13 | 582459.9465 |  | 52950.9042 |  | 52950.9042 |  | 52950.9042 |  | 52950.9042 |  | 52950.9042 |  | 52950.9042 |  | 52950.9042 |  | 52950.9042 |  | 52950.9042 |  | 52950.9042 |  | 52950.9042
2026-05-14 | 582679.7882 |  | 52970.8898 |  | 52970.8898 |  | 52970.8898 |  | 52970.8898 |  | 52970.8898 |  | 52970.8898 |  | 52970.8898 |  | 52970.8898 |  | 52970.8898 |  | 52970.8898 |  | 52970.8898
2026-05-15 | 582899.6299 |  | 52990.8754 |  | 52990.8754 |  | 52990.8754 |  | 52990.8754 |  | 52990.8754 |  | 52990.8754 |  | 52990.8754 |  | 52990.8754 |  | 52990.8754 |  | 52990.8754 |  | 52990.8754
2026-05-16 | 583119.4715 |  | 53010.861 |  | 53010.861 |  | 53010.861 |  | 53010.861 |  | 53010.861 |  | 53010.861 |  | 53010.861 |  | 53010.861 |  | 53010.861 |  | 53010.861 |  | 53010.861
2026-05-17 | 583339.3132 |  | 53030.8467 |  | 53030.8467 |  | 53030.8467 |  | 53030.8467 |  | 53030.8467 |  | 53030.8467 |  | 53030.8467 |  | 53030.8467 |  | 53030.8467 |  | 53030.8467 |  | 53030.8467
2026-05-18 | 583559.1549 |  | 53050.8323 |  | 53050.8323 |  | 53050.8323 |  | 53050.8323 |  | 53050.8323 |  | 53050.8323 |  | 53050.8323 |  | 53050.8323 |  | 53050.8323 |  | 53050.8323 |  | 53050.8323
2026-05-19 | 583778.9965 |  | 53070.8179 |  | 53070.8179 |  | 53070.8179 |  | 53070.8179 |  | 53070.8179 |  | 53070.8179 |  | 53070.8179 |  | 53070.8179 |  | 53070.8179 |  | 53070.8179 |  | 53070.8179
2026-05-20 | 583998.8382 |  | 53090.8035 |  | 53090.8035 |  | 53090.8035 |  | 53090.8035 |  | 53090.8035 |  | 53090.8035 |  | 53090.8035 |  | 53090.8035 |  | 53090.8035 |  | 53090.8035 |  | 53090.8035
2026-05-21 | 584218.6799 |  | 53110.7891 |  | 53110.7891 |  | 53110.7891 |  | 53110.7891 |  | 53110.7891 |  | 53110.7891 |  | 53110.7891 |  | 53110.7891 |  | 53110.7891 |  | 53110.7891 |  | 53110.7891
2026-05-22 | 588395.3882 |  | 53490.4898 |  | 53490.4898 |  | 53490.4898 |  | 53490.4898 |  | 53490.4898 |  | 53490.4898 |  | 53490.4898 |  | 53490.4898 |  | 53490.4898 |  | 53490.4898 |  | 53490.4898
2026-05-23 | 592572.0965 |  | 53870.1906 |  | 53870.1906 |  | 53870.1906 |  | 53870.1906 |  | 53870.1906 |  | 53870.1906 |  | 53870.1906 |  | 53870.1906 |  | 53870.1906 |  | 53870.1906 |  | 53870.1906
2026-05-24 | 596748.8049 |  | 54249.8914 |  | 54249.8914 |  | 54249.8914 |  | 54249.8914 |  | 54249.8914 |  | 54249.8914 |  | 54249.8914 |  | 54249.8914 |  | 54249.8914 |  | 54249.8914 |  | 54249.8914
2026-05-25 | 600925.5132 |  | 54629.5921 |  | 54629.5921 |  | 54629.5921 |  | 54629.5921 |  | 54629.5921 |  | 54629.5921 |  | 54629.5921 |  | 54629.5921 |  | 54629.5921 |  | 54629.5921 |  | 54629.5921
2026-05-26 | 605102.2215 |  | 55009.2929 |  | 55009.2929 |  | 55009.2929 |  | 55009.2929 |  | 55009.2929 |  | 55009.2929 |  | 55009.2929 |  | 55009.2929 |  | 55009.2929 |  | 55009.2929 |  | 55009.2929
2026-05-27 | 609278.9299 |  | 55388.9936 |  | 55388.9936 |  | 55388.9936 |  | 55388.9936 |  | 55388.9936 |  | 55388.9936 |  | 55388.9936 |  | 55388.9936 |  | 55388.9936 |  | 55388.9936 |  | 55388.9936
2026-05-28 | 613455.6382 |  | 55768.6944 |  | 55768.6944 |  | 55768.6944 |  | 55768.6944 |  | 55768.6944 |  | 55768.6944 |  | 55768.6944 |  | 55768.6944 |  | 55768.6944 |  | 55768.6944 |  | 55768.6944
2026-05-29 | 617632.3465 |  | 56148.3951 |  | 56148.3951 |  | 56148.3951 |  | 56148.3951 |  | 56148.3951 |  | 56148.3951 |  | 56148.3951 |  | 56148.3951 |  | 56148.3951 |  | 56148.3951 |  | 56148.3951
2026-05-30 | 621809.0549 |  | 56528.0959 |  | 56528.0959 |  | 56528.0959 |  | 56528.0959 |  | 56528.0959 |  | 56528.0959 |  | 56528.0959 |  | 56528.0959 |  | 56528.0959 |  | 56528.0959 |  | 56528.0959
2026-05-31 | 625985.7632 |  | 56907.7967 |  | 56907.7967 |  | 56907.7967 |  | 56907.7967 |  | 56907.7967 |  | 56907.7967 |  | 56907.7967 |  | 56907.7967 |  | 56907.7967 |  | 56907.7967 |  | 56907.7967
2026-06-01 | 630162.4715 |  | 57287.4974 |  | 57287.4974 |  | 57287.4974 |  | 57287.4974 |  | 57287.4974 |  | 57287.4974 |  | 57287.4974 |  | 57287.4974 |  | 57287.4974 |  | 57287.4974 |  | 57287.4974
2026-06-02 | 634339.1799 |  | 57667.1982 |  | 57667.1982 |  | 57667.1982 |  | 57667.1982 |  | 57667.1982 |  | 57667.1982 |  | 57667.1982 |  | 57667.1982 |  | 57667.1982 |  | 57667.1982 |  | 57667.1982
2026-06-03 | 638515.8882 |  | 58046.8989 |  | 58046.8989 |  | 58046.8989 |  | 58046.8989 |  | 58046.8989 |  | 58046.8989 |  | 58046.8989 |  | 58046.8989 |  | 58046.8989 |  | 58046.8989 |  | 58046.8989
2026-06-04 | 642692.5965 |  | 58426.5997 |  | 58426.5997 |  | 58426.5997 |  | 58426.5997 |  | 58426.5997 |  | 58426.5997 |  | 58426.5997 |  | 58426.5997 |  | 58426.5997 |  | 58426.5997 |  | 58426.5997
2026-06-05 | 646869.3049 |  | 58806.3004 |  | 58806.3004 |  | 58806.3004 |  | 58806.3004 |  | 58806.3004 |  | 58806.3004 |  | 58806.3004 |  | 58806.3004 |  | 58806.3004 |  | 58806.3004 |  | 58806.3004
2026-06-06 | 651046.0132 |  | 59186.0012 |  | 59186.0012 |  | 59186.0012 |  | 59186.0012 |  | 59186.0012 |  | 59186.0012 |  | 59186.0012 |  | 59186.0012 |  | 59186.0012 |  | 59186.0012 |  | 59186.0012
2026-06-07 | 655222.7215 |  | 59565.702 |  | 59565.702 |  | 59565.702 |  | 59565.702 |  | 59565.702 |  | 59565.702 |  | 59565.702 |  | 59565.702 |  | 59565.702 |  | 59565.702 |  | 59565.702
2026-06-08 | 659399.4299 |  | 59945.4027 |  | 59945.4027 |  | 59945.4027 |  | 59945.4027 |  | 59945.4027 |  | 59945.4027 |  | 59945.4027 |  | 59945.4027 |  | 59945.4027 |  | 59945.4027 |  | 59945.4027
2026-06-09 | 663576.1382 |  | 60325.1035 |  | 60325.1035 |  | 60325.1035 |  | 60325.1035 |  | 60325.1035 |  | 60325.1035 |  | 60325.1035 |  | 60325.1035 |  | 60325.1035 |  | 60325.1035 |  | 60325.1035
2026-06-10 | 667752.8465 |  | 60704.8042 |  | 60704.8042 |  | 60704.8042 |  | 60704.8042 |  | 60704.8042 |  | 60704.8042 |  | 60704.8042 |  | 60704.8042 |  | 60704.8042 |  | 60704.8042 |  | 60704.8042
2026-06-11 | 671929.5549 |  | 61084.505 |  | 61084.505 |  | 61084.505 |  | 61084.505 |  | 61084.505 |  | 61084.505 |  | 61084.505 |  | 61084.505 |  | 61084.505 |  | 61084.505 |  | 61084.505
2026-06-12 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-06-13 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-06-14 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-06-15 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-06-16 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-06-17 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-06-18 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-06-19 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-06-20 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-06-21 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-06-22 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-06-23 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-06-24 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-06-25 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-06-26 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-06-27 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-06-28 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-06-29 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-06-30 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-07-01 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-07-02 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-07-03 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-07-04 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-07-05 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-07-06 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-07-07 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-07-08 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-07-09 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-07-10 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-07-11 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-07-12 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-07-13 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-07-14 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-07-15 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057
2026-07-16 | 676106.2632 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057 |  | 61464.2057

## Equipment Cost
Date | Planned Equipment (Cumulative) | Actual Equipment (Cumulative) | Planned 1805 · Equipment - Forklift (Cumulative) | Actual 1805 · Equipment - Forklift (Cumulative) | Planned 1818 · Equipment - BCU (Cumulative) | Actual 1818 · Equipment - BCU (Cumulative) | Planned 1819 · Equipment - TPMB (Cumulative) | Actual 1819 · Equipment - TPMB (Cumulative) | Planned 1820 · Equipment & Tools (Cumulative) | Actual 1820 · Equipment & Tools (Cumulative) | Planned 1821 · Equipment - C3 (Cumulative) | Actual 1821 · Equipment - C3 (Cumulative) | Planned 1822 · Equipment - C2 (Cumulative) | Actual 1822 · Equipment - C2 (Cumulative) | Planned 1823 · Equipment - TCU Basic (Cumulative) | Actual 1823 · Equipment - TCU Basic (Cumulative) | Planned 1824 · Equipment - TCU PLC (Cumulative) | Actual 1824 · Equipment - TCU PLC (Cumulative) | Planned 1825 · Equipment - Blower Skids (Cumulative) | Actual 1825 · Equipment - Blower Skids (Cumulative) | Planned 1826 · Equipment - Well Heads (Cumulative) | Actual 1826 · Equipment - Well Heads (Cumulative) | Planned 1827 · Equipment - Thermal Wells (Cumulative) | Actual 1827 · Equipment - Thermal Wells (Cumulative) | Planned 1829 · Equipment - Water Treatment Sys (Cumulative) | Actual 1829 · Equipment - Water Treatment Sys (Cumulative) | Planned 1830 · Equipment - Vapor Extraction (Cumulative) | Actual 1830 · Equipment - Vapor Extraction (Cumulative) | Planned 1831 · Equipment - GTR/C3 Components (Cumulative) | Actual 1831 · Equipment - GTR/C3 Components (Cumulative) | Planned 1832 · Equip - Control/Dist panels (Cumulative) | Actual 1832 · Equip - Control/Dist panels (Cumulative) | Planned 1833 · Equipment - Office & computer (Cumulative) | Actual 1833 · Equipment - Office & computer (Cumulative) | Planned 5113 · Repairs & maint (Direct) (Cumulative) | Actual 5113 · Repairs & maint (Direct) (Cumulative)
2025-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 1441.4843 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0 | 84.7932 | 0
2025-06-02 | 2882.9687 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0 | 169.5864 | 0
2025-06-03 | 4324.453 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0 | 254.3796 | 0
2025-06-04 | 5765.9373 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0 | 339.1728 | 0
2025-06-05 | 7207.4217 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0 | 423.966 | 0
2025-06-06 | 8648.906 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0 | 508.7592 | 0
2025-06-07 | 10090.3904 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0 | 593.5524 | 0
2025-06-08 | 11531.8747 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0 | 678.3456 | 0
2025-06-09 | 12973.359 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0 | 763.1388 | 0
2025-06-10 | 14414.8434 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0 | 847.932 | 0
2025-06-11 | 15856.3277 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0 | 932.7252 | 0
2025-06-12 | 17297.812 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0 | 1017.5184 | 0
2025-06-13 | 18739.2964 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0 | 1102.3116 | 0
2025-06-14 | 20180.7807 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0 | 1187.1047 | 0
2025-06-15 | 21622.2651 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0 | 1271.8979 | 0
2025-06-16 | 23063.7494 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0 | 1356.6911 | 0
2025-06-17 | 24505.2337 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0 | 1441.4843 | 0
2025-06-18 | 25946.7181 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0 | 1526.2775 | 0
2025-06-19 | 27388.2024 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0 | 1611.0707 | 0
2025-06-20 | 28829.6867 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0 | 1695.8639 | 0
2025-06-21 | 30271.1711 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0 | 1780.6571 | 0
2025-06-22 | 31712.6554 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0 | 1865.4503 | 0
2025-06-23 | 33154.1398 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0 | 1950.2435 | 0
2025-06-24 | 34595.6241 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0 | 2035.0367 | 0
2025-06-25 | 36037.1084 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0 | 2119.8299 | 0
2025-06-26 | 37478.5928 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0 | 2204.6231 | 0
2025-06-27 | 38920.0771 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0 | 2289.4163 | 0
2025-06-28 | 40361.5614 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0 | 2374.2095 | 0
2025-06-29 | 41803.0458 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0 | 2459.0027 | 0
2025-06-30 | 43244.5301 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0 | 2543.7959 | 0
2025-07-01 | 44686.0145 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0 | 2628.5891 | 0
2025-07-02 | 46127.4988 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0 | 2713.3823 | 0
2025-07-03 | 47568.9831 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0 | 2798.1755 | 0
2025-07-04 | 49010.4675 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0 | 2882.9687 | 0
2025-07-05 | 50451.9518 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0 | 2967.7619 | 0
2025-07-06 | 51893.4361 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0 | 3052.5551 | 0
2025-07-07 | 53334.9205 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0 | 3137.3483 | 0
2025-07-08 | 54776.4048 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0 | 3222.1415 | 0
2025-07-09 | 56217.8892 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0 | 3306.9347 | 0
2025-07-10 | 57659.3735 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0 | 3391.7279 | 0
2025-07-11 | 59100.8578 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0 | 3476.521 | 0
2025-07-12 | 60542.3422 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0 | 3561.3142 | 0
2025-07-13 | 61983.8265 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0 | 3646.1074 | 0
2025-07-14 | 63425.3108 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0 | 3730.9006 | 0
2025-07-15 | 64866.7952 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0 | 3815.6938 | 0
2025-07-16 | 66308.2795 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0 | 3900.487 | 0
2025-07-17 | 67749.7639 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0 | 3985.2802 | 0
2025-07-18 | 69191.2482 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0 | 4070.0734 | 0
2025-07-19 | 70632.7325 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0 | 4154.8666 | 0
2025-07-20 | 72074.2169 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0 | 4239.6598 | 0
2025-07-21 | 73515.7012 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0 | 4324.453 | 0
2025-07-22 | 74957.1855 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0 | 4409.2462 | 0
2025-07-23 | 76398.6699 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0 | 4494.0394 | 0
2025-07-24 | 77840.1542 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0 | 4578.8326 | 0
2025-07-25 | 79281.6386 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0 | 4663.6258 | 0
2025-07-26 | 80723.1229 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0 | 4748.419 | 0
2025-07-27 | 82164.6072 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0 | 4833.2122 | 0
2025-07-28 | 83606.0916 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0 | 4918.0054 | 0
2025-07-29 | 85047.5759 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0 | 5002.7986 | 0
2025-07-30 | 86489.0602 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0 | 5087.5918 | 0
2025-07-31 | 87930.5446 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0 | 5172.385 | 0
2025-08-01 | 89372.0289 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0 | 5257.1782 | 0
2025-08-02 | 90813.5133 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0 | 5341.9714 | 0
2025-08-03 | 92254.9976 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0 | 5426.7646 | 0
2025-08-04 | 93696.4819 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0 | 5511.5578 | 0
2025-08-05 | 95137.9663 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0 | 5596.351 | 0
2025-08-06 | 96579.4506 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0 | 5681.1442 | 0
2025-08-07 | 98020.9349 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0 | 5765.9373 | 0
2025-08-08 | 99462.4193 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0 | 5850.7305 | 0
2025-08-09 | 100903.9036 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0 | 5935.5237 | 0
2025-08-10 | 102345.388 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0 | 6020.3169 | 0
2025-08-11 | 103786.8723 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0 | 6105.1101 | 0
2025-08-12 | 105228.3566 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0 | 6189.9033 | 0
2025-08-13 | 106669.841 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0 | 6274.6965 | 0
2025-08-14 | 108111.3253 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0 | 6359.4897 | 0
2025-08-15 | 109552.8096 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0 | 6444.2829 | 0
2025-08-16 | 110994.294 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0 | 6529.0761 | 0
2025-08-17 | 112435.7783 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0 | 6613.8693 | 0
2025-08-18 | 113877.2627 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0 | 6698.6625 | 0
2025-08-19 | 115318.747 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0 | 6783.4557 | 0
2025-08-20 | 116760.2313 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0 | 6868.2489 | 0
2025-08-21 | 118201.7157 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0 | 6953.0421 | 0
2025-08-22 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-08-23 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-08-24 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-08-25 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-08-26 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-08-27 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-08-28 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-08-29 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-08-30 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-08-31 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-01 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-02 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-03 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-04 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-05 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-06 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-07 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-08 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-09 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-10 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-11 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-12 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-13 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-14 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-15 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-16 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-17 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-18 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-19 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-20 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-21 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-22 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-23 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-24 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-25 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-26 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-27 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-28 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-29 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-09-30 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-01 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-02 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-03 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-04 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-05 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-06 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-07 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-08 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-09 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-10 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-11 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-12 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-13 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-14 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-15 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-16 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-17 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-18 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-19 | 119643.2 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0 | 7037.8353 | 0
2025-10-20 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-10-21 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-10-22 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-10-23 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-10-24 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-10-25 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-10-26 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-10-27 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-10-28 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-10-29 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-10-30 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-10-31 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-03 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-04 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-05 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-06 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-07 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-08 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-09 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-10 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-11 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-12 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-13 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-14 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-15 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-16 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-17 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-18 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-19 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-20 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-21 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-22 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-23 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-24 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-25 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-26 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-27 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-28 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-29 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-11-30 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-01 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-02 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-03 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-04 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-05 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-06 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-07 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-08 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-09 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-10 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-11 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-12 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-13 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-14 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-15 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-16 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-17 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-18 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-19 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-20 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-21 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-22 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-23 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-24 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-25 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-26 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-27 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-28 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-29 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-30 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2025-12-31 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-01 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-02 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-03 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-04 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-05 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-06 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-07 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-08 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-09 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-10 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-11 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-12 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-13 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-14 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-15 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-16 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-17 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-18 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-19 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-20 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-21 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-22 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-23 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-24 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-25 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-26 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-27 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-28 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-29 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-30 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-01-31 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-01 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-02 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-03 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-04 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-05 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-06 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-07 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-08 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-09 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-10 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-11 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-12 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-13 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-14 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-15 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-16 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-17 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-18 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-19 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-20 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-21 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-22 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-23 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-24 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-25 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-26 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-27 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-02-28 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-01 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-02 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-03 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-04 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-05 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-06 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-07 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-08 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-09 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-10 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-11 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-12 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-13 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-14 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-15 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-16 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-17 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-18 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-19 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-20 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-21 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-22 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-23 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-24 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-25 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-26 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-27 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-28 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-29 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-30 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-03-31 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-01 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-02 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-03 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-04 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-05 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-06 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-07 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-08 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-09 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-10 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-11 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-12 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-13 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-14 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-15 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-16 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-17 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-18 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-19 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-20 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-21 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-22 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-23 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-24 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-25 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-26 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-27 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-28 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-29 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-04-30 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-01 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-02 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-03 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-04 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-05 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-06 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-07 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-08 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-09 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-10 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-11 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-12 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-13 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-14 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-15 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-16 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-17 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-18 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-19 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-20 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-21 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-22 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-23 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-24 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-25 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-26 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-27 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-28 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-29 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-30 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-05-31 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-01 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-02 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-03 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-04 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-05 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-06 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-07 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-08 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-09 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-10 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-11 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-12 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-13 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-14 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-15 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-16 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-17 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-18 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-19 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-20 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-21 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-22 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-23 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-24 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-25 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-26 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-27 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-28 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-29 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-06-30 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-01 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-02 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-03 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-04 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-05 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-06 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-07 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-08 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-09 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-10 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-11 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-12 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-13 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-14 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-15 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353
2026-07-16 | 119643.2 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353 |  | 7037.8353

## Labor-by months
Month | Actual Geo Total (Monthly) | Actual On Site Personal (Monthly) | Actual Remote Personal (Monthly) | Planned GEO total personal (Monthly) | Planned on site personal (Monthly) | Planned remote personal (Monthly) | Planned Technician I (Monthly) | Actual Technician I (Monthly) | Planned Technician II (Monthly) | Actual Technician II (Monthly) | Planned Welder (Monthly) | Actual Welder (Monthly) | Planned Engineer/supervisor (Monthly) | Actual Engineer/supervisor (Monthly) | Planned Manager/senior Engineer (Monthly) | Actual Manager/senior Engineer (Monthly) | Planned Remote mid engineer (Monthly) | Actual Remote mid engineer (Monthly) | Planned Remote senior (Monthly) | Actual Remote senior (Monthly) | Assigned Task ID
April 25 | 25 | 0 | 25 | 68.75 | 0 | 68.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.5 | 0 | 15.25 | 0 | 100
May 25 | 6 | 0 | 6 | 68.75 | 0 | 68.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.5 | 0 | 15.25 | 0 | 100
June 25 | 14 | 4 | 10 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200
July 25 | 54 | 52 | 2 | 34.086 | 27.9892 | 6.0968 | 0 | 0 | 10.1613 | 0 | 3.8333 | 0 | 13.9946 | 0 | 0 | 0 | 5.0806 | 0 | 1.0161 | 0 | 300
August 25 | 78 | 74 | 4 | 66.9785 | 52.7527 | 14.2258 | 0 | 0 | 23.7097 | 0 | 2.6667 | 0 | 26.3763 | 0 | 0 | 0 | 11.8548 | 0 | 2.371 | 0 | 300
September 25 | 106.625 | 92 | 14.625 | 74.5264 | 59.5308 | 14.9956 | 14.3182 | 0 | 15.4472 | 0 | 21.4773 | 0 | 22.6063 | 0 | 7.1591 | 0 | 12.0191 | 0 | 2.9765 | 0 | 400
October 25 | 31.125 | 30 | 1.125 | 78.4091 | 62.7273 | 15.6818 | 15.6818 | 0 | 15.6818 | 0 | 23.5227 | 0 | 23.5227 | 0 | 7.8409 | 0 | 12.5455 | 0 | 3.1364 | 0 | 400
November 25 | 0 | 0 | 0 | 52.9732 | 33.3732 | 19.6 | 16.674 | 0 | 16.674 | 0 | 0 | 0 | 16.6992 | 0 | 5.5664 | 0 | 14 | 0 | 5.6 | 0 | 500
December 25 | 0 | 0 | 0 | 58.6489 | 36.9489 | 21.7 | 18.4605 | 0 | 18.4605 | 0 | 0 | 0 | 18.4884 | 0 | 6.1628 | 0 | 15.5 | 0 | 6.2 | 0 | 500
January 26 | 0 | 0 | 0 | 58.6489 | 36.9489 | 21.7 | 18.4605 | 0 | 18.4605 | 0 | 0 | 0 | 18.4884 | 0 | 6.1628 | 0 | 15.5 | 0 | 6.2 | 0 | 500
February 26 | 0 | 0 | 0 | 52.9732 | 33.3732 | 19.6 | 16.674 | 0 | 16.674 | 0 | 0 | 0 | 16.6992 | 0 | 5.5664 | 0 | 14 | 0 | 5.6 | 0 | 500
March 26 | 0 | 0 | 0 | 58.6489 | 36.9489 | 21.7 | 18.4605 | 0 | 18.4605 | 0 | 0 | 0 | 18.4884 | 0 | 6.1628 | 0 | 15.5 | 0 | 6.2 | 0 | 500
April 26 | 0 | 0 | 0 | 56.757 | 35.757 | 21 | 17.865 | 0 | 17.865 | 0 | 0 | 0 | 17.892 | 0 | 5.964 | 0 | 15 | 0 | 6 | 0 | 500
May 26 | 0 | 0 | 0 | 77.4249 | 52.7799 | 24.645 | 24.5055 | 0 | 24.5055 | 0 | 6 | 0 | 22.2744 | 0 | 7.1748 | 0 | 17.97 | 0 | 6.675 | 0 | 700
June 26 | 0 | 0 | 0 | 82.715 | 46.25 | 36.465 | 20 | 0 | 20 | 0 | 10 | 0 | 16.25 | 0 | 5 | 0 | 27.39 | 0 | 9.075 | 0 | 700
July 26 | 0 | 0 | 0 | 19.89 | 0 | 19.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.94 | 0 | 4.95 | 0 | 700

## Deleted Duplicates
Date | Account | Amount | Type | Num | Memo | Split | Source_File | Category
No duplicates found

## Labor-by days
Date | Actual Geo Total (Daily) | Actual On Site Personal (Daily) | Actual Remote Personal (Daily) | Planned GEO total personal (Daily) | Planned on site personal (Daily) | Planned remote personal (Daily) | Assigned Task ID | Planned Remote senior (Daily) | Actual Remote senior (Daily) | Planned Remote mid engineer (Daily) | Actual Remote mid engineer (Daily) | Planned Engineer/supervisor (Daily) | Actual Engineer/supervisor (Daily) | Planned Technician II (Daily) | Actual Technician II (Daily) | Planned Welder (Daily) | Actual Welder (Daily) | Planned Technician I (Daily) | Actual Technician I (Daily) | Planned Manager/senior Engineer (Daily) | Actual Manager/senior Engineer (Daily)
2025-04-01 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-02 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-03 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-04 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-05 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-06 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-07 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-08 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-09 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-10 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-11 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-12 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-13 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-14 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-15 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-16 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-17 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-18 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-19 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-20 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-21 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-22 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-23 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-24 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-25 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-26 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-27 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-28 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-29 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-04-30 | 0.83333 | 0 | 0.83333 | 2.2917 | 0 | 2.2917 | 100 | 0.50833 | 0 | 1.7833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-01 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-02 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-03 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-04 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-05 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-06 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-07 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-08 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-09 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-10 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-11 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-12 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-13 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-14 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-15 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-16 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-17 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-18 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-19 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-20 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-21 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-22 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-23 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-24 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-25 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-26 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-27 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-28 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-29 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-30 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-05-31 | 0.19355 | 0 | 0.19355 | 2.2177 | 0 | 2.2177 | 100 | 0.49194 | 0 | 1.7258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2025-06-01 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-02 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-03 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-04 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-05 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-06 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-07 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-08 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-09 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-10 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-11 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-12 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-13 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-14 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-15 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-16 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-17 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-18 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-19 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-20 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-21 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-22 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-23 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-24 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-25 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-26 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-27 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-28 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-29 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-06-30 | 0.46667 | 0.13333 | 0.33333 | 0.23333 | 0.23333 | 0 | 200 | 0 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0.11667 | 0 | 0 | 0 | 0 | 0
2025-07-01 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-02 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-03 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-04 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-05 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-06 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-07 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-08 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-09 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-10 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-11 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-12 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-13 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-14 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-15 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-16 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-17 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-18 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-19 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-20 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-21 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-22 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-23 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-24 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-25 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-26 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-27 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-28 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-29 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-30 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-07-31 | 1.7419 | 1.6774 | 0.064516 | 1.0995 | 0.90288 | 0.19667 | 300 | 0.032778 | 0 | 0.16389 | 0 | 0.45144 | 0 | 0.32778 | 0 | 0.12366 | 0 | 0 | 0 | 0 | 0
2025-08-01 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-02 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-03 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-04 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-05 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-06 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-07 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-08 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-09 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-10 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-11 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-12 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-13 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-14 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-15 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-16 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-17 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-18 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-19 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-20 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-21 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-22 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-23 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-24 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-25 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-26 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-27 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-28 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-29 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-30 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-08-31 | 2.5161 | 2.3871 | 0.12903 | 2.1606 | 1.7017 | 0.4589 | 300 | 0.076483 | 0 | 0.38241 | 0 | 0.85085 | 0 | 0.76483 | 0 | 0.086022 | 0 | 0 | 0 | 0 | 0
2025-09-01 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-02 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-03 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-04 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-05 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-06 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-07 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-08 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-09 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-10 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-11 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-12 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-13 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-14 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-15 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-16 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-17 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-18 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-19 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-20 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-21 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-22 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-23 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-24 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-25 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-26 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-27 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-28 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-29 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-09-30 | 3.5542 | 3.0667 | 0.4875 | 2.4842 | 1.9844 | 0.49985 | 400 | 0.099218 | 0 | 0.40064 | 0 | 0.75354 | 0 | 0.51491 | 0 | 0.71591 | 0 | 0.47727 | 0 | 0.23864 | 0
2025-10-01 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-02 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-03 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-04 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-05 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-06 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-07 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-08 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-09 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-10 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-11 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-12 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-13 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-14 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-15 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-16 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-17 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-18 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-19 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-20 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-21 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-22 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-23 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-24 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-25 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-26 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-27 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-28 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-29 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-30 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-10-31 | 1.004 | 0.96774 | 0.03629 | 2.5293 | 2.0235 | 0.50587 | 400 | 0.10117 | 0 | 0.40469 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.7588 | 0 | 0.50587 | 0 | 0.25293 | 0
2025-11-01 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-02 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-03 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-04 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-05 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-06 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-07 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-08 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-09 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-10 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-11 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-12 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-13 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-14 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-15 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-16 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-17 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-18 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-19 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-20 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-21 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-22 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-23 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-24 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-25 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-26 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-27 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-28 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-29 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-11-30 | 0 | 0 | 0 | 1.7658 | 1.1124 | 0.65333 | 500 | 0.18667 | 0 | 0.46667 | 0 | 0.55664 | 0 | 0.5558 | 0 | 0 | 0 | 0.5558 | 0 | 0.18555 | 0
2025-12-01 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-02 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-03 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-04 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-05 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-06 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-07 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-08 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-09 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-10 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-11 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-12 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-13 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-14 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-15 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-16 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-17 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-18 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-19 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-20 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-21 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-22 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-23 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-24 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-25 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-26 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-27 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-28 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-29 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-30 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2025-12-31 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-01 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-02 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-03 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-04 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-05 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-06 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-07 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-08 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-09 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-10 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-11 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-12 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-13 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-14 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-15 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-16 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-17 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-18 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-19 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-20 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-21 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-22 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-23 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-24 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-25 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-26 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-27 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-28 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-29 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-30 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-01-31 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-01 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-02 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-03 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-04 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-05 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-06 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-07 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-08 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-09 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-10 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-11 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-12 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-13 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-14 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-15 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-16 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-17 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-18 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-19 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-20 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-21 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-22 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-23 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-24 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-25 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-26 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-27 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-02-28 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-01 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-02 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-03 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-04 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-05 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-06 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-07 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-08 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-09 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-10 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-11 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-12 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-13 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-14 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-15 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-16 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-17 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-18 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-19 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-20 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-21 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-22 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-23 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-24 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-25 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-26 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-27 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-28 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-29 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-30 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-03-31 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-01 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-02 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-03 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-04 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-05 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-06 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-07 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-08 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-09 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-10 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-11 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-12 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-13 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-14 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-15 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-16 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-17 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-18 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-19 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-20 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-21 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-22 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-23 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-24 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-25 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-26 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-27 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-28 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-29 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-04-30 | 0 | 0 | 0 | 1.8919 | 1.1919 | 0.7 | 500 | 0.2 | 0 | 0.5 | 0 | 0.5964 | 0 | 0.5955 | 0 | 0 | 0 | 0.5955 | 0 | 0.1988 | 0
2026-05-01 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-02 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-03 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-04 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-05 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-06 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-07 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-08 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-09 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-10 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-11 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-12 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-13 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-14 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-15 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-16 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-17 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-18 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-19 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-20 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-21 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-22 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-23 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-24 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-25 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-26 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-27 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-28 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-29 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-30 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-05-31 | 0 | 0 | 0 | 2.4976 | 1.7026 | 0.795 | 700 | 0.21532 | 0 | 0.57968 | 0 | 0.71853 | 0 | 0.7905 | 0 | 0.19355 | 0 | 0.7905 | 0 | 0.23145 | 0
2026-06-01 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-02 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-03 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-04 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-05 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-06 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-07 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-08 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-09 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-10 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-11 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-12 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-13 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-14 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-15 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-16 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-17 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-18 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-19 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-20 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-21 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-22 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-23 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-24 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-25 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-26 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-27 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-28 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-29 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-06-30 | 0 | 0 | 0 | 2.7572 | 1.5417 | 1.2155 | 700 | 0.3025 | 0 | 0.913 | 0 | 0.54167 | 0 | 0.66667 | 0 | 0.33333 | 0 | 0.66667 | 0 | 0.16667 | 0
2026-07-01 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-02 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-03 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-04 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-05 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-06 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-07 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-08 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-09 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-10 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-11 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-12 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-13 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-14 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-15 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-16 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-17 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-18 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-19 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-20 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-21 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-22 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-23 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-24 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-25 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-26 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-27 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-28 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-29 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-30 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2026-07-31 | 0 | 0 | 0 | 0.64161 | 0 | 0.64161 | 700 | 0.15968 | 0 | 0.48194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0